## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | ITC 07 - R15 Kerb and Gutters Rev 1 | itp | ITC 07 - R15 Kerb and Gutters Rev 1 |  | c9461529-4844-4043-b2b6-6e3734d33f85
| section | Lot Information
| checkpoint | Lot Information complete
dfd64e0a-4aeb-522b-8d46-e8abe3db0bf2 | textbox | Lot Opened On
30c725a1-6904-5691-b2d6-f89b1c51b97f | textbox | Date of Works
b563ba21-f8e0-5ab4-8c34-3ee5c388af49 | textbox | Lot Type
8ef1b341-0c95-58f6-b165-ae68c79663fb | textbox | Start Chainage
74161b4e-d2c9-5552-8859-12124a6d7894 | textbox | End Chainage
258e17b3-e16d-5420-90e6-49c3d9a1f843 | textbox | Offset
a202e987-0275-529c-8b71-a0298a0f550b | textbox | Control Line
| section | 1. Preliminary Works
| checkpoint | 1.1 - IFC Drawings are Current
4a6c234e-09ed-5967-bc81-51bcebcc84b4 | note | Document Reference / Applicable Standard - Pavement IFC Drawings
50a567a2-bc60-5e91-bcaa-e37539552fc6 | note | Acceptance Criteria - Use of latest revision of approved Issued for Construction (IFC) Drawings. Any changes in design, RFI was raised and approved:
f4556580-9e3c-5c15-a198-83bdbb757f45 | textbox | RFI
c553bcf2-d49c-51b6-ae06-56f00f197d3a | note | Frequency/ Process Held - Once / Prior to Construction
f8c3c712-5ad4-54b9-960d-7eb38312f586 | note | Inspection - ACPL - S
7056747e-541d-5446-a2b0-f0c68038462a | note | Inspection - Client - S
7e080222-1448-5e27-9ac1-00448a7d1ad2 | note | Verifying Records - Pavements IFC Drawing
| checkpoint | 1.2 - Underlying lot conforming
fe0e47f9-a652-58b2-91c1-541a6c4521c5 | note | Document Reference / Applicable Standard - Survey Report
afe89d81-4042-57a8-8189-692800a4c97b | note | Acceptance Criteria - Underlying/Preceding lot is conforming prior to commencement including survey levels of underlying lot and K&C Subgrade
613ec8a3-781d-5216-aae6-181b132b8d02 | note | Frequency/ Process Held - Once / Prior to Construction
8f40f743-c396-5166-8758-3f33854c2876 | note | Inspection - ACPL - S
0c2ef9df-1e23-5625-a34a-cf5e85139b5f | note | Inspection - Client - S
8eb7aeff-d504-57f3-90f8-f1d0f066e034 | note | Verifying Records - Test Results / Survey Report
| checkpoint | 1.3 - Concrete Mix Design
c29b13fe-b038-5df5-aecc-a4bd79dc7e62 | note | Document Reference / Applicable Standard - R53 Cl 2.4.1, R53 Annexure, R53/E, R15 Cl 2.2
35c531e2-97c1-5692-ae61-61175501a431 | note | Acceptance Criteria - Concrete Mix Design approved by client
07195412-93d3-5840-9c57-733d6ed47d40 | note | 25mpa – 15 – 25mm slump – max. nom aggregate 10mm
479504f0-bbac-5101-95fe-6c5f61a87c82 | note | Frequency/ Process Held - Once / prior to construction
6cd37821-1649-59e7-b7d7-40cb0e49bdfd | note | Inspection - ACPL - H
bf4fccb9-bf19-5502-a8b8-92dbcec0453c | note | Inspection - Client - H
354a453c-f023-5868-ba7d-afc003797fd0 | note | Verifying Records - Concrete Mix Design
| signoff | AUTHORITY HOLDPOINT
| section | 2. Construction
| checkpoint | 2.1 - Survey Set out
274805de-01ee-520c-89a7-cc7cdae0cd4d | note | Document Reference / Applicable Standard - QMP
ebc32581-0cce-5cf1-a107-62fd67decf4e | note | Acceptance Criteria - Survey set out as per design drawings
e2c17161-6a78-57cf-8fc5-33c7b78962dc | note | Frequency/ Process Held - Once / Prior to Placement
06ca5209-c246-564d-8e08-18dd0b938a7f | note | Inspection - ACPL - S
caa627b0-526a-579b-b107-07d94244f93e | note | Inspection - Client - S
d56e7a50-9454-52be-a516-51baef7a771f | note | Verifying Records - Set out Report
| checkpoint | 2.2 - Placement of Concrete
29c1ef7c-f552-5725-9ae8-19e4a24e5b32 | note | Document Reference / Applicable Standard - R53 Cl 3.3.1
e0e06adb-7922-530f-b43a-a331fad813f5 | note | Acceptance Criteria - Provide 2 working days’ notice to client of expected completion of preparation and expected commencement date and time of concrete placement
0e936203-e9ea-520f-8131-3332f6dbf639 | note | Frequency/ Process Held - Once / Prior to Placement
21d7eaac-4a86-585e-be89-a95a5c7a3eb1 | note | Inspection - ACPL - H
54e39d9c-683c-5d36-a440-9f591623d905 | note | Inspection - Client - H
af504707-a7d4-593b-bead-22ef09bdca12 | note | Verifying Records - HP Submission
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Concrete Sampling
c254e55e-3459-51a1-bd5c-7e27d3577b59 | note | Document Reference / Applicable Standard - R53 Cl 4.1 AS1379
0860afb4-ec95-5b8f-a364-8e55b37ab436 | note | Acceptance Criteria - Slump:
222f0212-4bf9-529e-826c-f5c05a5389a1 | note | ○ Perform slump tests on each strength sample
bbcf5878-b60d-57fd-a2d7-6095387a5548 | note | Strength:
39508643-f57d-56bf-b2d9-dacc7de3ceac | note | ○ Each grade at a plant shall be sampled at a frequency of at least one sample per 100 m3 of that grade produced except that, for Grade 20 concrete when 15 or more samples per month are obtained, the frequency may be reduced.
506fd688-56b0-5629-94ea-be1c48b1c889 | note | Frequency/ Process Held - Prior to Placement
d88662fc-0e1c-5ffc-a51c-face379abc4d | note | Inspection - ACPL - S
0dc543fb-7f38-5fea-be67-c712652cbf95 | note | Inspection - Client - S
57279ba6-03c6-528a-933d-c75b55e6e02c | note | Verifying Records - Slump Results Strength Results
| checkpoint | 2.4 - Concrete and Air Temp
b70098bb-0ef1-5d7d-a90b-f49afe322eca | note | Document Reference / Applicable Standard - R53 Cl 3.3.2
5f9eb58e-42d0-58b0-877d-2acdb765cb50 | note | Acceptance Criteria - Do not place concrete during rain or when air temperature in the shade is below 5oC or above 35oC
d5a67c36-4966-5785-a38f-5ea95413544e | note | Frequency/ Process Held - Prior to pouring each load
fea54f42-6a37-525b-8825-55142d4db072 | note | Inspection - ACPL - S
32ac706a-5e36-547f-9718-e82d06c5bfad | note | Inspection - Client - S
6ef6de0f-f69f-52b1-8353-0892215c6ff4 | note | Verifying Records - Pour Record
| checkpoint | 2.5 - Joints
34bc3f7a-8267-5999-86b9-dec4ff49dcae | note | Document Reference / Applicable Standard - R15 Cl 2.6, R15 cl 3.8
93e61b91-1672-5d73-8635-dbe7fcfe7470 | note | Acceptance Criteria - Joint sealant must be silicone sealant conforming to Specification TfNSW R83. Form and prepare joints in conformity to AS 2876.
d8351fcc-56d3-541d-abee-3cb0f075c80f | note | Shrinkage Control Joints: Spaced every 2.3 to 3m. Constructed by guillotining extruded work. Min 50% of the area of the section shall be cut. Resultant slot to be tooled to a depth of not less than 20mm to provide a groove of not less than 5mm in width.
75796663-a5f3-5c55-99c8-9d2a8d7818ae | note | Construction Joints: For Machine placed concrete, the last section of poorly formed or compacted concrete is to be removed while still plastic. Approx. 300mm. Leave suitable square face. Immediately prior to placing further concrete, the contact face shall be covered by a thin coat of cement water paste of creamy consistency. A Construction joint shall not be used to replace a shrinkage control joint.
1fe0c95b-6387-5ef0-a26f-11c757e5f87e | note | Frequency/ Process Held - Once / prior to placement of concrete
976aa66f-1eca-5e22-8a08-2538caeb41d2 | note | Inspection - ACPL - S
68bc4fc5-2edb-51cd-a5fa-c4552f60adc3 | note | Inspection - Client - S
370e3070-6dd9-5af9-967c-b977b6fcab99 | note | Verifying Records - Checklist
| checkpoint | 2.6 - Curing
b5987455-32fa-5ff6-83dc-55f820695823 | note | Document Reference / Applicable Standard - R53 Cl 3.4.3
1b61aad3-5754-5f45-b34a-e5939aaf691f | note | Acceptance Criteria - Apply curing compound to unform surfaces immediately after the surface is firm and free of bleed water
20822334-856a-5edc-8dc0-4ea94ea3ed4d | note | Apply curing compound at the rate specified by the manufacturer
6fc786eb-0944-525b-a780-826425b8fccd | note | Apply two coats when necessary to ensure complete and uniform coverage. The time between the first and second coat must be in accordance with the manufacturer’s recommendation.
e5957196-29dd-5a09-95ab-9109e9de2f7a | note | During application, implement measures to prevent the curing compound drifting away from the target concrete surface and deposited on adjacent surfaces.
13fbb02e-a938-56de-8715-37b0847d2cee | note | Maintain the curing membrane intact until at least seven days have elapsed after concrete placement
960f565b-ec94-5f93-9a71-221f2e035c02 | note | Frequency/ Process Held - Once / prior to placement of concrete
409f2938-2952-5dac-b35f-4597791451f2 | note | Inspection - ACPL - H
affdabf1-69d7-5c95-8bab-42753357f8aa | note | Inspection - Client - H
61296dfa-bf5b-580b-a4b5-16c3f1845858 | note | Verifying Records - Checklist
| checkpoint | 2.7 - Concrete Finish
e26a1ad9-d714-59de-a465-4c150fb8de30 | note | Document Reference / Applicable Standard - R15 Cl 3.9
346c8949-34a8-5b5f-8bc7-bc2666197a97 | note | Acceptance Criteria - Unless otherwise shown in the drawings, provide a steel float finish to channel inverts and faces of kerb and broomed finish to vehicular crossing and ramps. Brooming must be transverse to the direction of travel.
54afeddc-c243-5cbc-b4ac-f656a06fcae9 | note | Protect the concrete surface from rain during and after surface finishing and until final set.
1ee40a28-e66b-53d8-ad21-d88e1993503c | note | Frequency/ Process Held - Once / Prior to Survey
d31e8e53-7c39-5e5a-a0a0-78f89f2ddf0c | note | Inspection - ACPL - S
56aaf9e3-dbe3-55a8-8b99-2107991a22d2 | note | Inspection - Client - S
b61fd801-ad11-56db-a1f8-0ee0e4bc7cd6 | note | Verifying Records - Visual Inspection Project Quality Plan
| section | 3. Conformity
| checkpoint | 3.1 - Conformity
74917ff9-90a7-5d8a-aacc-d1a7deb50ad0 | note | Document Reference / Applicable Standard - R15 Cl 4
7bd26f0b-caaf-56b2-bc90-f5b841ccccd0 | note | Acceptance Criteria - All finished surfaces must conform to the lines, levels, grades, thicknesses and cross sections shown on the Drawings within the specified tolerances.
d9a456d6-3935-5a36-84dc-958edb8483bd | note | The tolerances stated in AS 2876 for irregularities in the bedding layer, level of the bedding layer, horizontal alignment, level, deviation from a 3 m straightedge, deviation on vertical curves, and profile dimensions also apply, except that the level of the constructed channel lip must not vary by more than 0 mm above or 10 mm below the adjoining pavement surface at any point.
bebe405c-4652-5baf-b552-50f65080fd6a | note | Frequency of conformity testing as per Annexure R15/L:
8a750f55-48eb-504a-9ab8-f7dd4a92dc5b | note | Frequency/ Process Held - During concrete delivery
cedcc87c-1a84-5ea8-85f1-51edb7589cc9 | note | Inspection - ACPL - S
9b3dbd3f-4d74-55d6-8242-feaf41a6ed7e | note | Inspection - Client - S
be97b71b-4ee2-5828-889e-f1c9a041de80 | note | Verifying Records - Concrete Docket Survey Report, Concrete Pour Record
| section | Review by Quality Manager / Project Engineer
| checkpoint-no-value | Review by Quality Manager / Project Engineer
9c47b30a-8b92-5460-9896-96603fb463a0 | button | Any non-conformances? | YES, NO
dd9185a1-6cfd-531f-82fe-864ab52a2604 | textbox | No's:
8d9def4f-1878-5b31-b9bb-03ea5dad4aa1 | button | Closed Out | YES, NO
6c98138e-80d0-55a6-8d9d-fe6909733ea9 | button | All work has been satisfactorily completed. | YES, NO
570674ec-2d5f-510e-83fe-123f9ad2e7bd | textbox | Name:
| signoff | Add signature
| section | Lot Verification
| checkpoint | Lot Verification complete
f5698ff0-b0d2-59a0-a4de-2be79d2bd0a4 | textbox | Lot Verified By:
7abdc1a6-c793-5602-8642-8508e6d8e440 | textbox | Lot Closed Date:
ef3360df-d190-5bad-b281-d56945a85c9c | button | Submitted to Client | Yes, No, N/A
9c06d55f-659f-5803-82cf-b8e0365cf79a | button | Reviewed by Client | Yes, No, N/A
5a32483d-f093-5e79-8fbe-b881ea2568f8 | textbox | Submission Comments:
| section-nested-checklists | NCR