## Project Structure
Folder Structure |  |  |  |  | Checklists
Pre-Con Inspection |  |  |  |  | Pre-Con Inspection
Site QA
Ground
FCU-G-1
|  |  | Rough-In |  | ITP-115 - Mechanical - Rough-In
|  |  | Fit-Off |  | ITP-115 - Mechanical - Fit-Off
|  | FCU-G-2 |  | as above
|  | Level Sign Off |  |  | ITP-115 - Mechanical - Final Sign Off
Level 1
|  | FCU-G-1.1 |  | as above
|  | FCU-G-1.2 |  | as above
|  | FCU-G-1.3 |  | as above
|  | FCU-G-1.4 |  | as above
|  | FCU-G-1.5 |  | as above
|  | FCU-G-1.6 |  | as above
|  | FCU-4.2 |  | as above
|  | Level Sign Off |  |  | ITP-115 - Mechanical - Final Sign Off
Roof
|  | CU-G-1 |  | as above
|  | CU-G-2 |  | as above
|  | CU-G-1.1 |  | as above
|  | CU-G-1.2 |  | as above
|  | CU-G-1.3 |  | as above
|  | CU-G-1.4 |  | as above
|  | CU-G-1.5 |  | as above
|  | CU-G-1.6 |  | as above
|  | Level Sign Off |  |  | ITP-115 - Mechanical - Final Sign Off

## Checklists
type | name | values
checklist-flat | Pre-Con Inspection
checkpoint | Sub Review
checkpoint | Safety Induction
checkpoint | Drawings Approved
checkpoint | Site Inspection
checklist-flat | ITP-115 - Mechanical - Rough-In
checkpoint | Check Materials
checkpoint | Install FCUs
checkpoint | Install Fans
checkpoint | Install Pipework
checkpoint | Install Cabling, Controls, etc.
checkpoint | Install Flexible Ducts
checkpoint | Install Drains and test
checkpoint | Fire Boxes/Collars/Dampers Installed. Attach photos
checkpoint | Install Rigid Duct and seal
checkpoint | Install Louvre Box
checkpoint | Access Panels Marked
checkpoint | Pressure Testing
checkpoint | Confirm Model No
checkpoint | Confirm Serial No.
checklist-flat | ITP-115 - Mechanical - Fit-Off
checkpoint | Check Pressure
checkpoint | Install Condensers
checkpoint | Terminate Drain
checkpoint | Terminate Power and Controller
checkpoint | Install Grilles
checkpoint | Pressure test
checkpoint | Vacuum system
checkpoint | Access To Equipment Checked
checkpoint | Commission
checkpoint | Confirm Model No
checkpoint | Confirm Serial No.
checklist-flat | ITP-115 - Mechanical - Final Sign Off
checkpoint | Subcontractor Sign-Off (attach signature)
checkpoint | Head Contractor Sign-Off (attach signature)
checkpoint | Client Sign-Off (attach signature)