## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-005 - Rehabilitation Works - Site 1 | itp |  |  |  |  | ITP-005 - Rehabilitation Works - Site 1 Rev0
section | 1 - Preliminaries and Submissions
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Before commencement of activity
label | ACCEPTANCE CRITERIA: Check correct documentation is being utilized
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Current revision of drawing
label | RECORD OF CONFORMITY: Current revision of drawing
label | *HP
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
checkpoint | 1.2 - Ensure Safety, Traffic, Quality & Environmental management measures are in place
label | FREQUENCY: Prior to commencement of activity.
label | ACCEPTANCE CRITERIA: Safety plan, traffic management plan and environmental management plan
label | REFERENCE DOCUMENTS: PSP, TMP, EMP
label | INSPECTION/TEST METHOD: Ensure all measures in place as per plan
label | RECORD OF CONFORMITY: Inspection
label | HP
label | RESPONSIBILITY: Fulton Hogan/Client
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Stockpiling
label | FREQUENCY: Prior to removing material
label | ACCEPTANCE CRITERIA: Confirmation of stockpile location approved by superintendent.
label | REFERENCE DOCUMENTS: FH Scope document, EMP
label | INSPECTION/TEST METHOD: Approval
label | RECORD OF CONFORMITY: ITP
label | WP
label | RESPONSIBILITY: Client/ Fulton Hogan
date | Date Completed:
checkpoint | 1.4 - Identification of services
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Any existence of underground services to be located and proven
label | REFERENCE DOCUMENTS: BYDA Section 100.8
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: ITP
label | HP
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Project management Plan Completed
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: PMP Completed
label | REFERENCE DOCUMENTS: PMP checklist completed
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: ITP
label | HP
label | RESPONSIBILITY: Fulton Hogan/Client
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Site set out
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Site inspection
label | REFERENCE DOCUMENTS: Scope document Drawing 796684
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: ITP
label | HP
label | RESPONSIBILITY: Client/ Fulton Hogan
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Ground breaking
label | FREQUENCY: Prior to excavation
label | ACCEPTANCE CRITERIA: Works to be reviewed and agreed by Superintendent
label | REFERENCE DOCUMENTS: Hold Point release for Commenceme nt of Works Letter
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: ITP
label | HP
label | RESPONSIBILITY: Client
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.8 - Landowner Agreement with property owner
label | FREQUENCY: Prior to breaking ground
label | ACCEPTANCE CRITERIA: Letter to be signed
label | REFERENCE DOCUMENTS: Signed landowner agreement
label | INSPECTION/TEST METHOD: Hold point
label | RECORD OF CONFORMITY: ITP
label | HP*
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
checkpoint | 1.9 - Environmental controls
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Environmental controls installed and maintained as per EMP
label | REFERENCE DOCUMENTS: EMP
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: ITP
label | HP*
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
section | 2 - Drainage/Rock Fill/Type A select fill
checkpoint | 2.01 - Control of water through site
label | FREQUENCY: Prior to excavation of toe
label | ACCEPTANCE CRITERIA: Diversion to be agreed by Superintendent
label | REFERENCE DOCUMENTS: Environmental Management plan
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: ITP
label | IP
label | RESPONSIBILITY: Client and Fulton Hogan
date | Date Completed:
checkpoint | 2.02 - Rock Fill Material
label | FREQUENCY: Prior to placement
label | ACCEPTANCE CRITERIA: Rock fill to be suitable and size and approved
label | REFERENCE DOCUMENTS: Scope document Drawing 796684
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: ITP
label | WP
label | RESPONSIBILITY: Fulton Hogan/Client
date | Date Completed:
checkpoint | 2.03 - Site Benching/ Staging
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Site benching confirmed with site supervisor
label | ○ Meets the bench sloping of 1:1
label | ○ Rock needs to be installed in stages to ensure that the structure will not be compromise in flood
label | REFERENCE DOCUMENTS: Scope document
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: ITP
label | IP
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
checkpoint | 2.04 - Base of Excavation
label | FREQUENCY: Post benching access
label | ACCEPTANCE CRITERIA: Geotextile layer at excavated surface and on top of rock
label | REFERENCE DOCUMENTS: Section 200.10
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: ITP
label | IP
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
checkpoint | 2.05 - Base for Toe rock and machine
label | FREQUENCY: Once ramp and benching is completed
label | ACCEPTANCE CRITERIA: Solid base visually confirmed
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: ITP
label | IP
label | RESPONSIBILITY: DTP
date | Date Completed:
checkpoint | 2.06 - Base Rock Placement
label | FREQUENCY: During the placement of the toe rock
label | ACCEPTANCE CRITERIA: Solid base, Maximum particle sizes 500mm
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: ITP
label | IP
label | RESPONSIBILITY: Client/ Fulton Hogan
date | Date Completed:
checkpoint | 2.07 - Treatment for works between the bridge abutment
label | FREQUENCY: At the completion of the rockwork
label | ACCEPTANCE CRITERIA: Agreement on the scope to repair above the rock beaching
label | REFERENCE DOCUMENTS: Drawing 796684
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: ITP
label | Hold Point
label | RESPONSIBILITY: Client
date | Date Completed:
checkpoint | 2.08 - Demobilisation
label | FREQUENCY: At the completion of works
label | ACCEPTANCE CRITERIA: Stockpiles and temporary works are removed.
label | ○ Minor defects are agreed with client
label | REFERENCE DOCUMENTS: NA
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: ITP
label | Hold Point
label | RESPONSIBILITY: Client
date | Date Completed:
checkpoint | Final Inspection
note | This is to verify that the final inspection has been carried out in accordance with the Fulton Hogan’s Quality Procedures and Project Quality Strategy and the product is hereby certified to conform with the contract specifications:
textbox | Print Name:
textbox | Position:
date | Date:
checklist | ITP-005 - Rehabilitation Works - Site 2 | itp |  |  |  |  | ITP-005 - Rehabilitation Works - Site 2 Rev0
section | 1 - Preliminaries and Submissions
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Before commencement of activity
label | ACCEPTANCE CRITERIA: Check correct documentation is being utilized
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Current revision of drawing
label | RECORD OF CONFORMITY: Current revision of drawing
label | *HP
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
checkpoint | 1.2 - Ensure Safety, Traffic, Quality & Environmental management measures are in place
label | FREQUENCY: Prior to commencement of activity.
label | ACCEPTANCE CRITERIA: Safety plan, traffic management plan and environmental management plan
label | REFERENCE DOCUMENTS: PSP, TMP, EMP
label | INSPECTION/TEST METHOD: Ensure all measures in place as per plan
label | RECORD OF CONFORMITY: Inspection
label | HP
label | RESPONSIBILITY: Fulton Hogan/Client
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Stockpiling
label | FREQUENCY: Prior to removing material
label | ACCEPTANCE CRITERIA: Confirmation of stockpile location approved by superintendent.
label | REFERENCE DOCUMENTS: FH Scope document, EMP
label | INSPECTION/TEST METHOD: Approval
label | RECORD OF CONFORMITY: ITP
label | WP
label | RESPONSIBILITY: Client/ Fulton Hogan
date | Date Completed:
checkpoint | 1.4 - Identification of services
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Any existence of underground services to be located and proven
label | REFERENCE DOCUMENTS: BYDA Section 100.8
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: ITP
label | HP
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Project management Plan Completed
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: PMP Completed
label | REFERENCE DOCUMENTS: PMP checklist completed
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: ITP
label | HP
label | RESPONSIBILITY: Fulton Hogan/Client
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Site set out
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Site inspection
label | REFERENCE DOCUMENTS: Scope document Drawing 796684
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: ITP
label | HP
label | RESPONSIBILITY: Client/ Fulton Hogan
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Ground breaking
label | FREQUENCY: Prior to excavation
label | ACCEPTANCE CRITERIA: Works to be reviewed and agreed by Superintendent
label | REFERENCE DOCUMENTS: Hold Point release for Commenceme nt of Works Letter
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: ITP
label | HP
label | RESPONSIBILITY: Client
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.8 - Landowner Agreement with property owner
label | FREQUENCY: Prior to breaking ground
label | ACCEPTANCE CRITERIA: Letter to be signed
label | REFERENCE DOCUMENTS: Signed landowner agreement
label | INSPECTION/TEST METHOD: Hold point
label | RECORD OF CONFORMITY: ITP
label | HP*
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
checkpoint | 1.9 - Environmental controls
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Environmental controls installed and maintained as per EMP
label | REFERENCE DOCUMENTS: EMP
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: ITP
label | HP*
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
section | 2 - Drainage/Rock Fill/Type A select fill
checkpoint | 2.1 - Control of water through site
label | FREQUENCY: Prior to excavation of toe
label | ACCEPTANCE CRITERIA: Diversion to be agreed by Superintendent
label | REFERENCE DOCUMENTS: Environmental Management plan
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: ITP
label | IP
label | RESPONSIBILITY: Client and Fulton Hogan
date | Date Completed:
checkpoint | 2.2 - Rock Fill Material
label | FREQUENCY: Prior to placement
label | ACCEPTANCE CRITERIA: Rock fill to be suitable and size and approved
label | REFERENCE DOCUMENTS: Scope document Drawing 796684
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: ITP
label | WP
label | RESPONSIBILITY: Fulton Hogan/Client
date | Date Completed:
checkpoint | 2.3 - Site Benching/ Staging
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Site benching confirmed with site supervisor
label | ○ Meets the bench sloping of 1:1
label | ○ Rock needs to be installed in stages to ensure that the structure will not be compromise in flood
label | REFERENCE DOCUMENTS: Scope document
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: ITP
label | IP
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
checkpoint | 2.4 - Base of Excavation
label | FREQUENCY: Post benching access
label | ACCEPTANCE CRITERIA: Geotextile layer at excavated surface and on top of rock
label | REFERENCE DOCUMENTS: Section 200.10
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: ITP
label | IP
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
checkpoint | 2.5 - Base for Toe rock and machine
label | FREQUENCY: Once ramp and benching is completed
label | ACCEPTANCE CRITERIA: Solid base visually confirmed
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: ITP
label | IP
label | RESPONSIBILITY: DTP
date | Date Completed:
checkpoint | 2.6 - Base Rock Placement
label | FREQUENCY: During the placement of the toe rock
label | ACCEPTANCE CRITERIA: Solid base, Maximum particle sizes 500mm
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: ITP
label | IP
label | RESPONSIBILITY: Client/ Fulton Hogan
date | Date Completed:
checkpoint | 2.7 - Treatment for works between the bridge abutment
label | FREQUENCY: At the completion of the rockwork
label | ACCEPTANCE CRITERIA: Agreement on the scope to repair above the rock beaching
label | REFERENCE DOCUMENTS: Drawing 796684
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: ITP
label | Hold Point
label | RESPONSIBILITY: Client
date | Date Completed:
checkpoint | 2.8 - Demobilisation
label | FREQUENCY: At the completion of works
label | ACCEPTANCE CRITERIA: Stockpiles and temporary works are removed.
label | ○ Minor defects are agreed with client
label | REFERENCE DOCUMENTS: NA
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: ITP
label | Hold Point
label | RESPONSIBILITY: Client
date | Date Completed:
section | 3 - Wire Rope Safety Barrier (WRSB) Retensioning
checkpoint | 3.1 - Retensioning of WRSB
label | FREQUENCY: At the completion of barrier work
label | ACCEPTANCE CRITERIA: All 4 x Wire Ropes are within acceptable tolerance as per manufacturers specification
label | REFERENCE DOCUMENTS: Manufacturers specification
label | RECORD OF CONFORMITY: ITP
label | RESPONSIBILITY: Fulton Hogan/Client
date | Date Completed:
checkpoint | Final Inspection
note | This is to verify that the final inspection has been carried out in accordance with the Fulton Hogan’s Quality Procedures and Project Quality Strategy and the product is hereby certified to conform with the contract specifications:
textbox | Print Name:
textbox | Position:
date | Date: