## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
73d8f2e1-5e24-469f-a500-9c738f392843 | checklist | ITC: 5 - Inground Conduit Installation (UPDATED) |  | ITC: 5 - Inground Conduit Installation (UPDATED)
ae5b7970-7d5c-4c36-8106-9e7e376510de | section | Inground Conduit Installation
33779d1b-92dd-4b1f-bc59-a355571acbce | checkpoint | Correct location to drawing
| textbox | Drawing Number:
| textbox | Revision:
02d87056-df72-4496-a9d9-df76a4722c57 | checkpoint | Correct size and type
| textbox | Conduit size & type required:
| textbox | Conduit size & type installed:
843a6385-61c4-47b2-bd0b-6ddad25999eb | checkpoint | Correct spacing in slabs
| textbox | Spacing required:
| textbox | Spacing measured:
825588ce-5e35-4e42-adb3-9f36340075f9 | checkpoint | Correct alignment
91a50086-3977-4ff0-8ebc-d429e805c502 | checkpoint | Clear to other services
7f8a6d6f-c349-4255-9778-f139def2a2ad | checkpoint | Correct depth underground
| textbox | Depth required:
| textbox | Depth measured:
b00bb701-41fd-43e0-aafb-35943f5266c0 | checkpoint | Correctly marked (tape or other)
| textbox | Tape/cover used:
| tickbox | Photo of marking tape/cover used
b720b61d-fa92-4525-b9a2-da7aff36347f | checkpoint | Correct fixing and safe
| textbox | Fixing used:
| tickbox | Photo of fixing used
| signoff | HOLD POINT - SIGN OFF BY WATPAC & HEYDAY
| section | Trench Backfill
bd48bea3-dce7-429c-8261-2e870d4dffdf | checkpoint | Correct backfill and surfaces
| textbox | Backfill used:
| tickbox | Photo of backfill
ca7ef0a8-37c0-4c9a-a31d-41975816ca96 | checkpoint | Sufficient photo evidence uploaded
| note | Attach Photos:
| tickbox | Before install
| tickbox | During install
| tickbox | Pre backfill
| tickbox | Finish
5a174fae-ea93-45ef-b3d2-19fa6233a452 | signoff | Heyday sign off