## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
f54b02ed-398f-4a83-933f-a25cfe735af1 | checklist | Curtain Wall Facade System Checklist | itp | Curtain Wall Facade System Checklist
4f814008-8f50-43d7-86b5-adb6915438ee | section | Pre-Install
132e28f8-6448-4538-abd5-cadd396a8246 | checkpoint | 1. Check Cast-In is acceptable
ad672558-a039-4352-9f89-84e542e1a481 | checkpoint | 2. Check Structure opening pockets and soffit is correct and within design tolerance
79ce3858-87e9-40a8-98ba-0e3284cd7ad9 | checkpoint | 3. Brackets are torqued (photos), Check the T bolts and Nuts are tightened.
b709648f-c1f1-4a86-9d6c-fd994caf35c6 | checkpoint | 4. Check bracket installed as per design (Bracket fixed to panel), if applicable, preferred to be checked by second person
64dceb8c-8a2c-48a8-befa-f0263ce2a383 | checkpoint | 5. Gutter plate and sleeve installed
7b39c417-d703-4b6e-bf19-e68efd83bb21 | checkpoint | 6. Check panels are correct size/type for the planning to be installed location. All nessecary items are in place.
0092ef75-0ed0-4f04-947f-8a5fa86b8720 | checkpoint | 7. Engage panel Sleeve across panel joint
668be8ad-d0c3-447b-b1dd-cc9fc18f25f3 | checkpoint | 8. Check façade pane is in good condition (photos), no damaged or defected. Any defect finding should be recorded. Document the rectification plan either repair or replace.
9e03e6e9-48fd-4083-9f38-5e85392f5ef5 | checkpoint | 9. Glass cleaned ready for install
7ad43619-774f-43d8-b167-0fa058dae132 | checkpoint | 10. Apply the Safety glass stamp where is required but missed.
7b9d685d-fd84-4b05-9b83-b93610bace2b | checkpoint | 11. The horizontal bead is positioned centrally.
8dc9c8ca-08ab-4a4c-b6bc-22d4e2323023 | checkpoint | 12. The vertical bead is position at the right angle.
07fa59c4-df8c-4fb6-b92e-556398d9e1ff | checkpoint | 13. No color differences or protrusions on either side of the bead.
078f9ac5-97f8-4984-94f3-2c4aa116f087 | section | Install
0259a69d-df68-4eeb-9410-d49590d9221f | checkpoint | 1. Panel in good caulking condition
090d1cc0-dbb3-4ed0-a61f-7cb2c18b0ba4 | checkpoint | 2. Protection tape in good condition
05d90c5c-2808-40e2-9e18-a37d85029e4d | checkpoint | 3. No defects/scratch/dents/distortion/crack
1f38a298-bed7-48fd-90df-213cb293dcec | checkpoint | 4. Panel installed and fixed in position as specified. Panels installed within tolerance (+/-1.5mm in plan, +/-1.5mm in elevation)
db3107e3-f231-477f-9b2c-7ce6c841248a | checkpoint | 5. Ensure bracket to panel hook locking screw installed (SS screw)
e45b66dd-7f8f-4eca-8187-35c3d43b2500 | checkpoint | 6. All Gaskets are installed and caulked neatly.
f6b153bf-8d55-4d61-8013-ea3d0943684d | checkpoint | 7. Gaps between concrete slab edge and façade panel insulation filled.
6860adf4-2019-4e78-b04c-8bbd6e4c18c1 | checkpoint | 8. Smoke flashing installed and sealed as per design. Overlap of sheeting and corretly caulked as per specifications
12a1c58a-357e-472f-8b2f-a8412cb969e3 | checkpoint | 9. Check Panel and Expressed fin is aligning properly at the base of the façade.
0af98c27-38b5-49be-a893-181f977f216f | checkpoint | 10. Record panel ID on the floor plans or elevation
059520cc-5648-4f0e-99b6-946f7740ebb2 | section | Post-Install
b1416707-b25a-46d8-be2c-9929b6727999 | checkpoint | 1. Remove external protection and for gasket caulk only
9e5cadd9-87f1-49e1-ab6e-e0f5d410241d | checkpoint | 2.Check the curtain wall is in good condition. Address any defect issues and findings
4a3ff196-34fa-448a-9410-4cee9404b7a6 | checkpoint | 3. Scratches or damaged powder-coated surfaces are repaired, and the repaired areas have a uniform color after repainting.
6f462c11-0560-406b-aa17-a80735733bfa | checkpoint | 4. Record defect panel on inspection report including panel ID. Mark the defect panel on the back of the panel
749d3a71-61e0-4221-8cee-9c6c43dd1f55 | checkpoint | 5. Record un-installed panel and any un-installed item on the report. Clearly markup the items and ownership of left over items and place them into the safe place for future use.
b18219b4-5239-4876-aaba-018d99ceb183 | checkpoint | 6. Conduct Water test to stackhead (leave for 24hrs) as per inhabit required testing or minimum testing requirments
051c8f0d-13f8-4987-b869-ee280f5a52b4 | checkpoint | 7. Installer (Keystone) Sign off
104c1e86-c903-46b4-8f63-05734829b64f | checkpoint | 8. Lingyun QC Sign off
d780b09f-0944-4712-9e36-31a43cc7904a | checkpoint | 9. Site supervisor Sign off
3f41f82d-53b4-433f-ab87-c1dbbc24e75a | checklist | Window Wall Facade System Checklist | itp | Window Wall Facade System Checklist
78ec56ef-3c25-452c-aa07-d56fb8611f69 | section | Pre-Install
f4a03e29-e07c-4559-b0cf-510a3aff4991 | checkpoint | 1. Subsill and subhead in postion
ed9a146f-8321-4d84-b96f-e7169eae9462 | checkpoint | 2. Expansion bolts are fixed and nuts are tightened
8f2f45ef-fa59-4ecc-b11a-bcab0af29d2c | checkpoint | 3. Gaps between concrete and subsill subhead are sealed properly
6724c42e-e0e4-45cb-91e9-74ac48d7d085 | checkpoint | 4. Gutter plate and sleeve installed
5feb1dc7-ed96-4642-a1ae-8b69f52c4a23 | checkpoint | 5. Check panels are correct size/type for the planning to be installed location. All nessecary items are in place.
8697070c-2d0c-4e82-835c-244f919803eb | checkpoint | 6. Check façade pane is in good condition
b4ecf950-2e3f-41bd-b3aa-33349ef8a669 | checkpoint | 7. Glass cleaned ready for install
7f862dba-4448-4b92-ab42-fa6248152b1e | checkpoint | 8. The horizontal bead is positioned centrally.
e6d1f965-62e3-4717-a91a-11aa8508b71e | checkpoint | 9. The vertical bead is position at the right angle.
c11648d6-8d22-49af-bca6-c5f92bac5195 | checkpoint | 10. No color differences or protrusions on either side of the bead.
b32b0e36-87cb-4b63-a8a7-d491a07fcac7 | checkpoint | 11. Apply the Safety glass stamp where is required but missed.
ad0d4c8f-9a97-418f-b386-3b8fcc5d1fd5 | section | Install
94860248-daaa-46b7-8fa0-883e6cc8711c | checkpoint | 1. Panel in good caulking condition
61fd3cd4-9468-417c-b1f8-79b7b6211624 | checkpoint | 2. Protection tape in good condition
2718c3c9-e6b1-4a64-82be-d6adf4a46a06 | checkpoint | 3. No defects/scratch/dents/distortion/crack
889d5dd8-a39e-43c5-8f5f-b2fb902abda9 | checkpoint | 4. Panel installed and fixed in position as specified. Panels installed within tolerance (+/-1.5mm in plan, +/-1.5mm in elevation)
7482a6c9-6756-40f3-bdca-c75123e994a2 | checkpoint | 5. All Gaskets are installed and caulked neatly.
1d02227e-c24e-433b-858b-e9575e0d670d | checkpoint | 6. Smoke flashing installed and sealed as per design. Overlap of sheeting and corretly caulked as per specifications
1381c2d0-6b47-456c-9a74-cb6d1c4e51dd | checkpoint | 7. Gaps between concrete and subsill subhead are sealed properly
4e4e35e8-21fb-4a76-a36e-8d9cd34ffe9c | checkpoint | 8. Record panel ID on the floor plans or elevation
c4a61dc0-5d76-411b-a23f-49c92992c8d7 | section | Post-Install
39b7d183-ff80-43f9-8877-f34a2a3d5c57 | checkpoint | 1. Remove external protection and for gasket caulk only
27edac64-b875-4d23-bffe-dc442e2da12c | checkpoint | 2. Check the curtain wall is in good condition. Address any defect issues and findings
a2d91d7f-df0d-45a8-8da3-a4ffd543ce3f | checkpoint | 3. Scratches or damaged powder-coated surfaces are repaired, and the repaired areas have a uniform color after repainting.
230e4ceb-2d20-42f7-8945-81a4ffe34ea5 | checkpoint | 4. Record defect panel on inspection report including panel ID. Mark the defect panel on the back of the panel
0beda702-c8d9-4838-91e9-fb684853b11d | checkpoint | 5. Record un-installed panel and any un-installed item on the report. Clearly markup the items and ownership of left over items and place them into the safe place for future use.