## Sheet1
Chadstone Shopping Centre Multi Cat Window Wall Façade System ITP Checklist TEMPLATE
Pre-Install | 1. Subsill and subhead in postion
2. Expansion bolts are fixed and nuts are tightened
3. Gaps between concrete and subsill subhead are sealed properly
4. Gutter plate and sleeve installed
5. Check panels are correct size/type for the planning to be installed location. All nessecary items are in place.
6. Check façade pane is in good condition
7. Glass cleaned ready for install
8. The horizontal bead is positioned centrally.
9. The vertical bead is position at the right angle.
10. No color differences or protrusions on either side of the bead.
11. Apply the Safety glass stamp where is required but missed.
Install | 1. Panel in good caulking condition
2. Protection tape in good condition
3. No defects/scratch/dents/distortion/crack
4. Panel installed and fixed in position as specified. Panels installed within tolerance (+/-1.5mm in plan, +/-1.5mm in elevation)
5. All Gaskets are installed and caulked neatly.
6. Smoke flashing installed and sealed as per design. Overlap of sheeting and corretly caulked as per specifications
7. Gaps between concrete and subsill subhead are sealed properly
8. Record panel ID on the floor plans or elevation
Post-Install | 1. Remove external protection and for gasket caulk only
2. check the curtain wall is in good condition. Address any defect issues and findings
3. Scratches or damaged powder-coated surfaces are repaired, and the repaired areas have a uniform color after repainting.
4. Record defect panel on inspection report including panel ID. Mark the defect panel on the back of the panel
5. Record un-installed panel and any un-installed item on the report. Clearly markup the items and ownership of left over items and place them into the safe place for future use.