## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
907cf460-3738-56c7-bc2b-bad65ed50b25 | checklist | QA - KOROK - internal |  | Speedwall
c969dc9b-cfe1-5729-9c39-4acc7d14aa8f | checkpoint | Installer details entered
2980c297-fb78-5e44-801e-7896cccae74f | textbox | Installer:
1f0333fc-94d0-5c1c-906c-7c825e051158 | checkpoint | drawings for site measure listed below
1f0333fc-94d0-5c1c-906c-7c825e051158 | checkpoint | Main contractor handed over area for install (written confirmation stating that previous trades work has been completed and QA done)
b9bd15bf-23f5-5ae0-8fc1-5582b2075134 | checkpoint | Material being used is correct for area (ssize and density of panels)
b9bd15bf-23f5-5ae0-8fc1-5582b2075134 | checkpoint | Area ready for Speedwall install
9fc29f3c-1ed7-5cd2-ada0-f0449cbb4dd4 | checkpoint | General photos, comments and observations during install
e19415f8-5c74-5215-9254-ad3c428cc787 | checkpoint | Bottom track correctly installed (size, location and fixings)
89f3cafd-20f4-5138-8155-7032fe8780a7 | checkpoint | Top track correctly installed (size, location and fixings)
92a4893d-7d5c-5f50-b211-379346a3a1f2 | checkpoint | 20mm minimum gap at head
c8a1197e-6e96-54fc-a1bc-75ec2dd4a68c | checkpoint | Install C track Fixings @ 400crs with M6.5 x 32 Mushroom head spikes into concrete
5d6c85a8-80ee-5c9c-be84-146c5fb96b46 | checkpoint | Fixings Hilti X-ENP-19 L15MX fixings 400crs in into steel
cb22199a-e317-5b76-9bfb-cd0c1e296429 | checkpoint | 10 x 16 fixings on C-Track to (horizontal panel - vertical C-Track 250crs, horizontal C-Track 400crs) (vertical panel - vertical C-Track 400crs, horizontal C-Track 250crs)
d9fd160d-acb0-5f36-b530-1b066fa4b84a | checkpoint | Fire sealant installed correctly and photographed , description of sealant entered below
a6468365-b8e0-5541-8191-3ee761599e67 | checkpoint | All joints sealed correctly as per specification
43462357-f051-5ffe-abf5-b061e38ea929 | checkpoint | Speedwall installed straight and level
5aef0f4c-b421-5e45-94c0-027e235744b2 | checkpoint | Openings installed for services as per drawings
7c54c3ad-0923-5797-a0ba-6b4e3e9668bf | signoff | Request for signoff
QA - KOROK - External
c969dc9b-cfe1-5729-9c39-4acc7d14aa8f | checkpoint | Installer details entered
2980c297-fb78-5e44-801e-7896cccae74f | textbox | Installer:
1f0333fc-94d0-5c1c-906c-7c825e051158 | checkpoint | drawings for site measure listed below
1f0333fc-94d0-5c1c-906c-7c825e051158 | checkpoint | Main contractor handed over area for install (written confirmation stating that previous trades work has been completed and QA done)
b9bd15bf-23f5-5ae0-8fc1-5582b2075134 | checkpoint | Material being used is correct for area (ssize and density of panels)
b9bd15bf-23f5-5ae0-8fc1-5582b2075134 | checkpoint | Area ready for Speedwall install
9fc29f3c-1ed7-5cd2-ada0-f0449cbb4dd4 | checkpoint | General photos, comments and observations during install
e19415f8-5c74-5215-9254-ad3c428cc787 | checkpoint | Steel Angles installed as per Beca Drawings 20240118-ST-K028
Bottom Steel Flashing installed correctly over steal angle as per Y3420031
89f3cafd-20f4-5138-8155-7032fe8780a7 | checkpoint | Top track correctly installed - 80mm w x 90mm D 1.55BMT as per Y300006 and Y3420031
92a4893d-7d5c-5f50-b211-379346a3a1f2 | checkpoint | 25mm gap at head as per Y3420031
c8a1197e-6e96-54fc-a1bc-75ec2dd4a68c | checkpoint | C track Fixings @ 400crs with Pair of Hilti X-ENP MX fastners
5d6c85a8-80ee-5c9c-be84-146c5fb96b46 | checkpoint | Sikaflex 400 Sealant used in C track and panels as per Y3420033
V776-18 x 4.8mm Foam attached to male end of panels as per Y3-420033
cb22199a-e317-5b76-9bfb-cd0c1e296429 | checkpoint | 10 Gauge x 16 screws at 250mm crs max on rear of panels as per Y3-420033
d9fd160d-acb0-5f36-b530-1b066fa4b84a | checkpoint | 14g x 115mm long Steetite Screws two per panel with 19mm washer each installed as per Y3-420031
a6468365-b8e0-5541-8191-3ee761599e67 | checkpoint | All joints sealed correctly as per specification
43462357-f051-5ffe-abf5-b061e38ea929 | checkpoint | Speedwall installed straight and level
5aef0f4c-b421-5e45-94c0-027e235744b2 | checkpoint | Aluminuim Flashing 2.0mm installed as per Y3-420031
7c54c3ad-0923-5797-a0ba-6b4e3e9668bf | signoff | Request for signoff