## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
d28d4da7-8422-501b-bc44-1f0f42b1f64a | checklist | Bollard Checklist |  | Bollard Checklist
c969dc9b-cfe1-5729-9c39-4acc7d14aa8f | checkpoint | Installer details entered
8722ed7a-e3e6-5f48-be63-c0df41318ae0 | textbox | Installer:
8312b122-cb6c-543d-ace7-3de3024dc441 | checkpoint | All relevant drawings and revision numbers checked and attached
b43149e0-822e-5b81-93e8-93b2d73202d4 | checkpoint | Bollard Type
79bfa553-7726-5603-9dd9-3d1610b3fb55 | checkpoint | Product delivered free from defects - warping, twisting, distortion, damaged section, pitting
707a3ef1-b445-53ad-a8f7-eae60ee5f60b | checkpoint | Welded connections continuous, even, clean, and free of blow holes or other irregularities.
3dc1fe52-77c6-5d43-a7e2-5e403a7d3505 | checkpoint | Correct fixings being used – concrete anchor / bolts / washers
80fddfe6-5497-59d0-8ccb-9d51d88d4e1d | checkpoint | Base plates fully and evenly support.
ad62ff04-b110-57c2-adfd-8d959447165b | checkpoint | Base plates are installed at correct centres
f47003a8-1307-596b-9ba3-774e49bb5cb6 | checkpoint | Bollards are in correct height
7a0f949b-c596-58b1-bc49-c53b8bd68628 | checkpoint | All M.S. Pipes / Posts and connecting members installed plumb, level and true to line.
d3180f37-3fdc-5923-9b59-2cf6aa0f4f14 | checkpoint | Report sent to client.
c62ebec7-adf4-58cc-8c64-84e686527735 | checklist | CLT Checklist |  | CLT Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
8312b122-cb6c-543d-ace7-3de3024dc441 | checkpoint | All relevant drawings and revision numbers checked and attached
4acb94d5-5aa2-54b9-8d61-9c5c51f88d91 | checkpoint | Inspect the panels on receipt at the delivery site &amp; approved (photograph any damage)
94ecd8e8-6e51-504a-b962-33a24d3ad4cb | checkpoint | Blocking connections installed correctly with correct fixings/hardware
c762675d-9b56-544d-8cf5-1b38e82cdf3b | checkpoint | Panels installed level and with correct overhang.
8673ec5a-9929-5290-9cdb-16c66309bbce | checkpoint | Panels installed at correct centres with correct fixing.
fc98e52e-432e-5b5a-8480-35b9b474ff8f | checkpoint | Area complete and all housekeeping undertaken.
90206465-a69b-5c3f-87ff-0c4062135bbe | checkpoint | General photos of area.
d3180f37-3fdc-5923-9b59-2cf6aa0f4f14 | checkpoint | Report sent to client.
ab73c138-854c-4e6f-a4b4-cd2c8596434f | checkpoint | Drill and expoxy as per spec/drawings
a447b823-d80f-45fd-b772-6997820ef593 | checkpoint | Moisture content
7c06a0ec-e2da-5d0b-a1ff-04a3d2558c0b | checklist | COC |  | COC
c969dc9b-cfe1-5729-9c39-4acc7d14aa8f | checkpoint | Installer details entered
7dfe4d04-4678-51ef-aaaf-be7d24491475 | textbox | Installer:
71e35204-27d7-570a-9ea3-b730e52c8473 | checkpoint | Upload COC here and press PASS
bd2c6a4f-e387-4e77-93ef-0e19cdf46363 | checklist | Doors Checklist |  | Doors
c969dc9b-cfe1-5729-9c39-4acc7d14aa8f | checkpoint | Installer details entered
4f8fa5a2-6d8a-557a-ab23-a089d4af8638 | textbox | Installer:
e82604c7-51d3-4d75-8260-ebdfda7f67d1 | checkpoint | Installer details input
a46c7a0f-b814-4aa7-b691-4ecd3ef80ee3 | checkpoint | All relevant drawings and revision numbers checked and attached
817a0cd8-53b0-4740-a0ae-24ece219a933 | checkpoint | Door opening checked and correct
7e76d0d7-6c87-4af0-b252-194592b770d2 | checkpoint | Direction of door correct
af105858-17d0-424d-834c-51bcc279ab78 | checkpoint | Number of screws and hardware location correct
b70a7bc9-9003-4f9b-97fd-afa5fedc29eb | checkpoint | Door hinges installed in place with correct screws
eeaddeb8-8a13-4f3d-98de-c39c90ed0cfd | checkpoint | Floor clearance correct
47fec660-9dba-449a-81cc-a9eae362f4bc | checkpoint | Undercoat on door surface
c79c2bbf-37c3-406c-9405-308181a8a249 | checkpoint | Fireseal around door installed as per spec
fe9a8af7-30e3-4330-9ad7-2d8ee5fafa20 | checkpoint | Door is fully operational after installation
e71e5850-202f-4f39-9cbb-8d2504cc01ed | checkpoint | Door jambs are plumn and level
dbaa0fab-022f-4ed0-a0ed-a7079ad74608 | checkpoint | Door gap around door leaf within tolerance
a1f58017-b428-4574-b2b5-7e392a3fe884 | checkpoint | Door report sent through to client
c2914621-3153-5796-a4ef-b094c26fb2bb | checklist | Ecoply Sheet Fixing |  | Ecoply Sheet Fixing
c969dc9b-cfe1-5729-9c39-4acc7d14aa8f | checkpoint | Installer details entered
1952eb9e-82b2-5198-bf7d-e01fad390396 | textbox | Installer:
7305eb87-01bf-5413-8167-7bc69789f497 | checkpoint | Ecoply pre cladding/RAB board to be kept dry and under cover
930fb872-01c1-5a57-8398-dc4d54f7f4f2 | checkpoint | Ecoply Pre-cladding/RAB board installed in accordance with Ecoply barrier installation manual
4fc305ea-a01e-5c99-941f-310da69ca6f5 | checkpoint | Tape installed over Ecoply pre-cladding/RaB board vertical joints, corners and openings in accordance with Ecoply Barrier installation manual
92e9c041-fc94-5b59-9963-455078110c3d | checkpoint | uPVC horizontal flashing used at all horizontal joints
551324e1-0cb2-5fba-952a-dc0ce80b19b2 | checkpoint | Fixings: Type - Stainless Steel/Galv correct spacing
49a00b42-9da4-566b-a9ae-c7c559b645d7 | textbox | size
41a76a9c-7a14-5667-90eb-1c9ed6f345bd | checkpoint | The panels overhang the bottom plate on a concrete slab by a maximum of 40mm as per installation manual
032774a0-bb89-509b-b253-35dd8455388b | checkpoint | Penetrations through Ecoply pre-cladding/Rab board sealed properly using flexible flashing tape as per E2/AS1
cb7772a3-9c21-554c-adf3-ee63b4868ee0 | checkpoint | Correct paint product and applied correctly to Ecoply (internal only)
8bb476b2-a58d-59dc-8e3b-d00314a14823 | checkpoint | Repair small damages, if any.
84b0945a-c27b-59c3-8dd2-a707432f13a8 | checkpoint | Report sent to client
4d31ddb8-0771-53bc-b67f-d689347af1a6 | checklist | Fencing Checklist |  | Fencing Checklist
c969dc9b-cfe1-5729-9c39-4acc7d14aa8f | checkpoint | Installer details entered
b0d836aa-5769-5f73-abd7-96fcdd5affb7 | textbox | Installer:
8312b122-cb6c-543d-ace7-3de3024dc441 | checkpoint | All relevant drawings and revision numbers checked and attached
79bfa553-7726-5603-9dd9-3d1610b3fb55 | checkpoint | Product delivered free from defects - warping, twisting, distortion, damaged section, pitting
68690d07-31f3-5ef0-9e63-c08dfcf0f917 | checkpoint | Correct fixings being used – Hex / Self Tapping Screws
38bcf7a1-ca60-5939-8b73-ed262caa46c8 | checkpoint | All horizontal galvanized M.S. Pipes installed level
5b62f062-37cf-5333-ad7e-ee742bc71b97 | checkpoint | All horizontal galvanized M.S. Pipes installed at correct centres.
d3180f37-3fdc-5923-9b59-2cf6aa0f4f14 | checkpoint | Report sent to client.
cd98646b-5085-58a1-b2d1-826cc8f927a3 | checklist | Floor framing and plywood flooring |  | Floor framing and plywood flooring
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
c969dc9b-cfe1-5729-9c39-4acc7d14aa8f | checkpoint | Installer details entered
d1b7f6ec-2284-5e36-820e-dfd1e0b1c54e | textbox | Installer:
100ab6ba-1485-5e6a-9e29-6ed7ac12ea0b | checkpoint | All relevant drawings checked and attached.
7b7912b7-714b-4ce8-a405-ecebd3736b56 | checkpoint | Builders work checked
2ca9b4b0-d4ff-581a-83e1-b9c550a13c1d | checkpoint | Joists installed at correct centers
719b1b7e-b697-51b3-9f6c-0b2b62e41906 | checkpoint | Bolts sprecified and installed at correct centers
ad6a8135-fc07-5707-95b5-1d19a628c4b4 | checkpoint | Correct number of hardware (joist hangers ect) according to drawings
b88609b3-fa2f-5df1-bad9-e9f42dd22c30 | checkpoint | Floor framing finished, straight, level and within tolerance.
5e6a346a-e665-5d9e-b632-0629587f09c5 | checkpoint | General photos and notes
6159a80a-4282-5e88-8da3-62453962ab6c | checkpoint | Correct plywood used for plywood flooring.25mm thick and tongue and groove
19841b87-7467-5ed9-a4c2-c75b8cfef005 | checkpoint | 2mm expansion gap allowed around sheet
bfecc87c-5c21-5ce7-8d2f-46e40bd3b604 | checkpoint | Sheet edges are set 20mm from steel edges around perimeter with exception of seismic gaps where sheets are fixed flush.
9f7b9294-edef-5d14-be5f-d9a426e3c320 | checkpoint | Sheets set out correctly as per s2.207
fbfc3f84-b96a-5006-8af0-c8b7fc346e15 | checkpoint | Plywood flooring fixed in accordance to s2.601
d3180f37-3fdc-5923-9b59-2cf6aa0f4f14 | checkpoint | Report sent to client.
a5924ab4-c56f-5375-aa66-5d5f481980d0 | signoff | Request signoff if required
e9c57fb4-89e6-59a7-ba04-bf322548a5b3 | checklist | Gutter Checklist |  | Gutter Checklist
7c1d9a05-aa6a-5213-a718-264be8a071ea | checkpoint-no-value | Installer details
165bd8bf-c77f-505c-97a5-7fc3af3149fa | textbox | Installer:
1b134538-af62-50ca-85a6-637c48962c45 | checkpoint-no-value | Gutter details
f37166c3-1f63-5c3e-ba6a-f2b6d0a04a93 | textbox | Details:
dbaf603f-b8f1-5392-87fe-5d47f6376b7d | checkpoint | GUTTER STEEL STRUCTURE INSTALLED TO CORRECT HEIGHT AND STRAIGHT
9026fd37-1297-5db8-8308-1eaa8e7f1763 | checkpoint | TIMBER TREATMENT STATED BELOW
6ab74aed-f40c-54f4-b806-295044846f75 | checkpoint | TIMBER STRINGER INSTALLED TO CORRECT FALL AND FIXED
fd1a940d-25bb-5183-b495-237b554041e7 | checkpoint | TIMBER CROSS MEMBER INSTALL AT CORRECT CENTERS
63d734ec-e55c-5c7f-b916-c445bf083ac0 | checkpoint | DPC INSTALLED WHERE REQUIRED
09797d86-4edb-5c99-9420-cfc5ce0437e8 | checkpoint | GUTTER WIDTH CORRECT AND STATED BELOW
f4fb1a19-3896-5106-934c-52bdc7194a34 | checkpoint | GUTTER FALLS AND HEIGHT CORRECT AND STATED BELOW
6c39c961-5533-5af4-9548-dbe818a6968b | checkpoint | AREA DEFECTS CHECKED AND REMEDIATED BEFORE MOVING ON TO NEXT AREA
a6096512-a669-5cc5-9537-ee765ebea9c8 | checkpoint | REPORT SENT TO CLIENT
a6e68c22-8142-50d5-b567-d44f4ed4312b | checklist | Plywood Wall Lining |  | Wall Lining
c222ec1a-01a6-5c05-8579-d29f1c4728a9 | checkpoint | All pre installation checks completed and approval given to line
6577c470-bbb0-547e-a8ed-00fc17a2250c | textbox | Drawing no. and revision
8037e47c-7135-584d-817a-d688a2a16d4a | checkpoint | Correct lining (Checked and approved) - area specifics checked
36fbd127-2984-5c19-8df6-9f9d3b9d8487 | checkpoint | Substrate accepted and approval given to start wall lining
84bf8fec-4f84-57fc-b54a-bddd75e2114b | checkpoint | Correct fixings used and installed at correct centers
69a60b8c-dc00-5e09-9cd6-d59b3118a37a | checkpoint | Any bracing elements completed to design specification
9fc29f3c-1ed7-5cd2-ada0-f0449cbb4dd4 | checkpoint | General photos, comments and observations during install
44317bab-c147-54ac-b840-e3247f21977b | checkpoint | All lining completed, checked and approved as per specification
601c1c7f-5742-56c9-ac43-d229412cd20f | checkpoint | Report sent through to client
23d077e4-7271-4988-bef3-4d7c277d0f8a | checklist | QA - Concrete Pour Checklist |  | Concrete Pour for Area:
27dbe8e4-9923-543a-b498-39e9a9f72747 | section | Installer Details
c969dc9b-cfe1-5729-9c39-4acc7d14aa8f | checkpoint | Installer details entered
143c80c4-2c6d-56fb-97a6-18b8358dd3a9 | textbox | Installer:
df4cade4-644d-4cb6-9752-f71d7f156859 | section | Pour Details
9b8a82b3-6f1d-4c1e-ae02-4d47b9a834a9 | checkpoint | Pour details entered
228a87c2-c4fc-528b-b148-3367e32e6a9a | textbox | Area to be poured (grid lines, location):
5278331b-f876-56b0-85a3-4f9d2523931f | textbox | Drawing numbers and revisions
19ca0f3c-08f4-567f-b8cd-17309dbb4f9d | textbox | Date of pour
246a43ae-7357-488f-a2e4-463daca0f66f | section | Formwork and embedded items
34ed4b21-b2be-4ac1-b184-3ac4e79ba423 | checkpoint | Grids and RLs clearly marked for reference
61905e2c-0473-4694-ac3c-7558a936315a | checkpoint | Formwork - location, heights, falls and dimensions checked and accurate
ef39c091-3f3e-4ef7-849f-41b7a5b5d180 | checkpoint | Formwork sufficiently fixed and braced
0a49f692-f700-4c0d-a47a-c55573db8a61 | checkpoint | Any rebates / nibs / cast in items are correctly positioned, sized and appropriately fixed in place.
a9d46929-2553-504b-89ee-ea45651168f6 | tickbox | Hold down bolts checked and correct
c4b20aca-f494-507f-96cc-5b8fc468a3a6 | tickbox | Precast panel starters checked and correct
fcd662d3-12a4-4337-8051-fe61a08d853d | checkpoint | Service penetrations formed correctly and locations checked/correct
efc13c0b-7170-48ab-b46f-9ff59f5dcae7 | checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork, etc.)
5624e7c6-9103-472f-b8fc-18ee5b10f73d | checkpoint | Any control joints / stop ends installed accurately and correctly braced
83af4a1a-d94b-4c9b-a120-cd29f7977336 | checkpoint | DPM & Connection to other waterproofing completed
bd517ae6-a1dc-40bd-95dc-35e34f907ed0 | checkpoint | Any additional formwork photos and observations
32b2f5e8-6222-4cb5-90cd-dbbc8498d23a | checkpoint | All formwork elements completed and ready for concrete pour (excess debris removed)
cacb6b94-fb04-4c99-a20b-578889895330 | checkpoint | Concrete ordered - correct mix and strength
c3b1317d-0675-5bdc-aa34-9d48fe0a420b | textbox | Mix
90d654b6-13b4-542d-aef5-d614ff03b318 | textbox | Strength:
1af2a3c5-1784-5877-8dce-7411582b80f8 | textbox | Summary of Proposed cement mix date and revision checked:
ba0a9a35-7c96-53b5-a723-22111870db39 | textbox | Structrual services specifications number and revision checked:
f8c51566-8dc7-4f6c-a029-fcf6e0c52929 | checkpoint | Slump test/Spread test (only applicable for special mix)
3bb14464-1db2-4ff6-8e62-82bd7b3c9872 | section | Placement Method
df416dea-2706-4be6-a677-f6ac6161bf3d | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
0728475c-9ce0-509e-82b8-999e2610e96d | textbox | Who is placing the concrete
3588b4ef-300f-4e91-a241-5ceaac8a2b8a | checkpoint | Height and falls checked / confirmed before placement
729f57b3-0f92-4754-b3dd-afc38289e172 | checkpoint | Cover correct to specification
9e29c331-0aff-4152-a158-39d82f97d5b9 | checkpoint | All concrete checked and correct on arrival (mix and strength)
5e74aef3-cfbc-5431-a8c3-4326f5b12008 | tickbox | All concrete dockets attached
a578d2f7-5cd7-49bd-ab9b-1c61e2813b57 | checkpoint | General photos and observations of concrete placement attached
5d9b8c07-01a8-4125-ae26-3de5809c5699 | checkpoint | Heights and falls checked / confirmed after placement
88e5e337-c4c0-445e-9b65-faeeae31d236 | checkpoint | Any curing compound applied correctly
f350ca97-55f7-4e54-8748-8eba97a339a5 | checkpoint | Concrete placement completed - specified level of finish achieved
4e41cbd5-2a55-4329-8247-aa41b525a966 | checkpoint | Area left clean and tidy
3747f9de-59e4-4013-9c1c-801413e24739 | section | Post Pour Checks / Signoff
0ea2d8e3-fe67-4139-9306-2f8289155a15 | checkpoint | Any remedial work completed
8dda0684-8f10-4073-8d0c-f2436754203a | checkpoint | Concrete Pour completed - all final checks and documentation completed and attached
42a0ba64-df64-4a58-b333-444359a90c29 | checkpoint | Report sent through to client
a7337640-045b-5e4b-bd6f-6efa182fb8d9 | checklist | QA - External Timber Framing |  | QA - External Timber Framing
c969dc9b-cfe1-5729-9c39-4acc7d14aa8f | checkpoint | Installer details entered
86f2a7ee-71d7-5545-8ac8-6cbc1fcadc81 | textbox | Installer:
6dd2bb6c-5de5-595e-a3f3-343244748b3d | checkpoint | Correct product & fixings delivered, reviewed and approved as per specification
2823ca50-a0b5-5250-9b41-484a6c37967c | checkpoint | Dimensions / locations of walls checked and correct
23b606b1-ecd7-5a29-a4fb-7c328cfcf18f | checkpoint | DPM installed where required
c835a7cb-0af9-5e30-8da5-deac857fa693 | checkpoint | All frames are square & plumb
b3037941-13a3-5240-bf71-8feb3b0b6c2f | checkpoint | External framing is installed at correct centres
acf94367-1ee5-5043-b9bf-022e99fd2d09 | textbox | Input centres
dba23fe1-a474-584a-bae5-34ac680fd0e4 | checkpoint | All openings are in correct location and correct size
cf6ab710-4cb1-5e8d-94bf-a5b5b70bf548 | textbox | Drawing / detail reference
6c8085d0-fa34-5daa-90ea-27a4ccfb1d8d | checklist | QA - GIB Lining |  | QA - GIB Lining
c969dc9b-cfe1-5729-9c39-4acc7d14aa8f | checkpoint | Installer details entered
2be37291-8ad2-5f1e-ad44-bc955bbcfea7 | textbox | Installer:
c222ec1a-01a6-5c05-8579-d29f1c4728a9 | checkpoint | All pre installation checks completed and approval given to line
1f0333fc-94d0-5c1c-906c-7c825e051158 | checkpoint | All relevant drawings and revision numbers checked and attached/commented
c81d1f71-7057-5268-9871-e2b5662b7c8d | textbox | Drawing no. and revision
0bfba9fd-7ae6-5229-84d0-0b894f5383f8 | checkpoint | Correct lining checked and approved and area specifics checked
66a48527-2b97-5cbd-9569-d1f1c8294da1 | checkpoint | Substrate accepted and approval given to start gib lining
12ca808c-05a6-527b-809a-ec11e1660ecf | checkpoint | Correct fixings used and installed at correct centres
69a60b8c-dc00-5e09-9cd6-d59b3118a37a | checkpoint | Any bracing elements completed to design specification
9fc29f3c-1ed7-5cd2-ada0-f0449cbb4dd4 | checkpoint | General photos, comments and observations during install
655bfc0d-3e94-57d0-b30b-97c9423168d5 | checkpoint | All lining completed correctly within specified tolerance, checked and approved
8e7ac91d-428b-5fa4-a7ec-ff01482d54d8 | checkpoint | GIB Lining report sent through to client
9c185639-2e8f-5d1e-83e8-761ae2e1dd6c | checklist | QA - Gib Weatherline |  | QA - Gib Weatherline
c969dc9b-cfe1-5729-9c39-4acc7d14aa8f | checkpoint | Installer details entered
ddcbcddf-ca5d-5dab-8297-fe11c9c4ec67 | textbox | Installer:
2afc9ee7-a635-5a19-9c4c-3552086850e0 | checkpoint | Framing set out adequate to support all sheet edges. Stud and nog spacing complies with GIB Weatherline® technical literature i.e. studs must be at a maximum of 400mm or GIB Weatherline® technical literature i.e. studs must be at a maximum of 400mm or
4586fd12-3422-577d-aca2-1c1f246b1e79 | checkpoint | Framing straightness. Nogs flush with studs, studs flush with top/bottom plates and no protruding fixings.
f40c0dd0-a804-5139-ac9f-d52da8dfef7b | checkpoint | Prior to installation GIB Weatherline® sheets to be kept dry
d33a4ea5-e203-5d9c-9254-ebf0091b4b87 | checkpoint | Correct fixings used and installed at correct centres according to GIB Weatherline® technical literature
01b6a0a8-4583-59ff-9971-3aec3062bca1 | checkpoint | Sheets overhang the bottom plate on a concrete slab by a minimum of 15mm as per GIB Weatherline® technical literature.
c4a093b8-4514-52de-ae6f-75afef73cfab | checkpoint | GIB Weatherline® Tape installed to vertical/ horizontal sheet joints, corners, and openings in accordance with GIB Weatherline® technical literature.
b37a70a1-f6a5-5e27-98ba-24a831bcb568 | checkpoint | Building service penetrations through GIB Weatherline® sheets sealed using Proclima Kaflex or Roflex penetration seal grommets. Proclima installation instructions to be followed.
6f85c4bc-069a-5b7e-ab09-dff43796468a | checkpoint | GIB Weatherline® flashing and sill tapes to be applied on doors and windows as per GIB Weatherline® technical literature.
14096036-d4b0-53b9-bb66-bc6672780c65 | checkpoint | GIB Weatherline® report sent to client
d5a5296c-d213-4aec-b91b-b9af5eb601fe | checklist | QA - Insulation |  | QA - Insulation
f968a904-e261-42b1-b417-051c4db0d222 | checkpoint | Green Star details entered
c5776c13-f1fb-5a57-8c29-378401c4c261 | button | Is this task Green Star related? | Yes, No, N/A
ccd105fb-c657-53d0-a4c3-9bc75803f3f5 | button | Have you contacted/informed Hawkins Green Star representative? | Yes, No, N/A
06ae0034-7efc-474f-95e2-d860388adfc0 | checkpoint | All relevant drawings and revision numbers checked and attached
b86046e4-08d5-5482-b8a1-1a3cddb11d9c | textbox | Area prepared and ready for Insulation install
0c174c29-279f-4a73-9af1-0f02992f908a | checkpoint | Product checked on arrival and correct as per specification
7fbd87d4-f69c-4026-8da7-a8e6c59a1718 | checkpoint | General photos, comments and observations during install
bcc47340-ed65-4f62-9ad7-3fdf34f7f5fd | checkpoint | Ensure work is completed as per specification
17c6ecc8-25bf-5ca6-ab6c-9ee276517ae9 | tickbox | Insulation pre lining works completed, checked and approved
afd791e8-45a1-4789-97bd-abf7b7fc8b84 | checkpoint | Insulation report sent through to client
50c7c8a0-f142-4a4d-ae54-684661e2695a | checklist | QA - KOROK - External |  | QA - KOROK - External
671205c1-9a61-4a3b-a37d-f0a3d756b6de | section | Details
d2862990-221d-4e44-ac76-a76853c4e27a | checkpoint | Installer details entered
208514da-d56a-5c94-bb9e-8a2a16be798a | textbox | Installer:
c479bdbe-6dd1-4dd0-ae06-834b800271f1 | checkpoint | drawings for site measure listed below
f4bc03ee-02ea-4753-a1b9-c1022722aaa7 | checkpoint | Main contractor handed over area for install (written confirmation stating that previous trades work has been completed and QA done)
0f79c542-eb2c-475b-b82d-b6616c70b613 | checkpoint | Material being used is correct for area (size and density of panels)
12bc88ad-4657-44d5-8a9c-8b7f347f80fc | checkpoint | Area ready for Speedwall install
d8858e9b-5efb-48e9-8db8-61af9b7bf03d | checkpoint | General photos, comments and observations during install
fec93457-2488-44e0-9e2a-ac3420d5a134 | checkpoint | Bottom track correctly installed (size, location and fixings)
02f6addb-16cc-4c03-b940-981af6c8ebb8 | checkpoint | Top track correctly installed (size, location and fixings)
561f2bf1-9d3d-4c62-88f7-5c8ccef58ccd | checkpoint | 20mm minimum gap at head
812664f7-3d33-4168-92ce-061e1a11bb10 | checkpoint | Install C track Fixings @ 400crs with M6.5 x 32 Mushroom head spikes into concrete
1e03a705-d55d-4318-b6d3-cbdf563ccde7 | checkpoint | Fixings Hilti X-ENP-19 L15MX fixings 400crs in into steel
c3ffce92-af8c-4d0d-b063-f515dc4f136b | checkpoint | 10 x 16 fixings on C-Track to (horizontal panel - vertical C-Track 250crs, horizontal C-Track 400crs) (vertical panel - vertical C-Track 400crs, horizontal C-Track 250crs)
1fe159c1-5553-486a-b825-1c529d20bd53 | checkpoint | Fire sealant installed correctly and photographed , description of sealant entered below
f5f1aa3d-2858-4f36-81dc-7982454a40d6 | checkpoint | All joints sealed correctly as per specification
d45e3706-633d-458c-b26e-b783277ded5d | checkpoint | Speedwall installed straight and level
0fa74706-2dc7-4a06-896d-224af0730e43 | checkpoint | Openings installed for services as per drawings
cee200ce-4c76-46f9-a76c-38c7584f5b66 | signoff | Request for signoff
3a11c13f-099c-41d7-b80b-ebde41df7c1f | checklist | QA - KOROK - internal |  | QA - KOROK - internal
b2fe62ed-1c4c-4094-a6ee-35e48035e90e | section | Details
265671dc-3e44-4cc5-8c94-eeb87e2cb230 | checkpoint | Installer details entered
66cd56da-7c58-582e-aa32-2b68c5ec2881 | textbox | Installer:
e3a08023-da23-4209-bea5-48e02521dc46 | checkpoint | drawings for site measure listed below
acdb79db-c6c4-4af3-9f66-27e9b723a36c | checkpoint | Main contractor handed over area for install (written confirmation stating that previous trades work has been completed and QA done)
4cb36b0e-4ba2-44aa-825d-a97b84fc6bcf | checkpoint | Material being used is correct for area (size and density of panels)
d366a93c-7cc9-4312-9e2e-f2e2fd503147 | checkpoint | Area ready for Speedwall install
726ee906-6d9f-4567-b580-fefb1fe48d08 | checkpoint | General photos, comments and observations during install
a31324cb-f5c4-400e-b5ab-de2fa2399511 | checkpoint | Bottom track correctly installed (size, location and fixings)
f4d7f758-f1e8-4e62-b1da-8e81ae5950d6 | checkpoint | Top track correctly installed (size, location and fixings)
7cf024fc-44c5-4de9-8c88-0c89b842274d | checkpoint | 20mm minimum gap at head
46d4b58c-602e-448f-93a5-d4cd5d45df0f | checkpoint | Install C track Fixings @ 400crs with M6.5 x 32 Mushroom head spikes into concrete
48f7e126-ada6-468d-abcd-ffd16ce2e3be | checkpoint | Fixings Hilti X-ENP-19 L15MX fixings 400crs in into steel
17d7ca2f-3355-44e1-a1f3-edd306c5bb63 | checkpoint | 10 x 16 fixings on C-Track to (horizontal panel - vertical C-Track 250crs, horizontal C-Track 400crs) (vertical panel - vertical C-Track 400crs, horizontal C-Track 250crs)
9edc5a7d-c04d-4b8a-a087-dc090348b336 | checkpoint | Fire sealant installed correctly and photographed , description of sealant entered below
af006982-8d61-4b46-abbc-78bb07f1e438 | checkpoint | All joints sealed correctly as per specification
00de2873-e176-4cbc-a129-bdd05e42cff3 | checkpoint | Speedwall installed straight and level
a52d8b85-cfe0-409a-9957-37dec20d7b05 | checkpoint | Openings installed for services as per drawings
a3066ca2-54f7-4d43-945d-4bbe7e5dce5e | signoff | Request for signoff
e22a9e44-1e1b-55f6-8fd6-556346735b05 | checklist | QA - RAB |  | QA - RAB
c969dc9b-cfe1-5729-9c39-4acc7d14aa8f | checkpoint | Installer details entered
8b53168c-2dcd-5be2-8a24-f66330afe917 | textbox | Installer:
2e6ff214-96e7-5718-a09b-fcf0b38fe53b | checkpoint | Plans / specs followed
4f9841d1-3333-5f69-a7a1-e7c930467818 | checkpoint | Flashings in place
2d955f73-adc9-50b2-b27e-63ab00ef9a9c | checkpoint | Sheet neatly cut and 1-2mm gaps at join
55dc53b3-14f4-566a-a6bd-7baf65e311ea | checkpoint | Correct nails / nailing pattern
b0a9d4c8-73da-5a9e-82b7-79f7059b6f86 | checkpoint | All nails flat and not puncturing board
d101ae18-4a5d-50d9-9632-448ede1661c0 | checkpoint | Taped / Sealed
b8c177c2-c595-5912-8ab5-a57fc689f246 | checkpoint | Area RAB complete
498ec7f7-d706-5c8e-a8da-8e00f8a0ba55 | checkpoint | RAB Report sent to client
fed86e41-f748-4cb4-b068-45eca710e65e | checklist | QA - Reinforcing Checklist |  | QA - Reinforcing Checklist
c969dc9b-cfe1-5729-9c39-4acc7d14aa8f | checkpoint | Installer details entered
6e1fd02d-1132-511e-a6c9-d4e2dbfcb7c9 | textbox | Installer:
6cae73c2-8276-4b64-ae9f-db115dc31453 | checkpoint | Work area ready
9e3e979a-df02-4d42-ac72-4b221075a18e | checkpoint | Latest drawings available, checked and referenced
ddb0273e-8ee6-40ca-9272-c2c972d67616 | checkpoint | Correct product delivered, reviewed & approved
a5297cbb-1c49-4b82-b268-747681654a62 | checkpoint | Correct size & type installed as per design
3421e0ea-a8d0-477b-9fe6-6f076d30558d | checkpoint | Reinforcing spacing and location correct
90a60116-394b-480c-add5-3ee4b222fd23 | checkpoint | Specified covers checked/correct
159dfce6-944f-4c1f-906b-6361336a4164 | checkpoint | Laps correct per size of bar
1d9d18ed-6b9b-4b1d-8a4a-9946bec2ca7a | checkpoint | Any starter bars are installed correctly (location, size and spacing)
dff05549-9f1c-4c18-91ba-23dc776baf86 | checkpoint | All bars fixed appropriately
4bfdee4b-a22f-42a2-8f0a-d0087c889781 | checkpoint | Couplers installed at correct height
9b70bb15-e2e5-430d-aeb4-7bd8e8554401 | checkpoint | Cast in plates installed correctly
2bd61297-9fae-4e8c-8b82-552909972dbf | checkpoint | Any additional items considered, installed & completed e.g. trimmer bars, reid bar couplers, foot plates, drag bars
16c5cfee-b82d-4fd4-92a6-1e21c761c482 | checkpoint | All excess reinforcing and debris removed - clean & tidy
548c029f-60c3-4aea-abc9-b40a7f1888ca | checkpoint | Reinforcing install completed, send to client
5d3c4555-9e06-55c5-bc66-33745c0e5309 | checklist | QA - Roof Framing |  | QA - Roof Framing
c969dc9b-cfe1-5729-9c39-4acc7d14aa8f | checkpoint | Installer details entered
7cd2b28d-af8d-5d30-a5da-bb7ea3388908 | textbox | Installer:
7af59523-dade-5cd1-8e64-653a2f96c3cd | checkpoint | All relevant drawings and revision numbers checked and attached/referenced
d5293322-bd81-58b4-838b-59f748c377cc | checkpoint | Correct spacing between noggins/purlins in its corresponding area
486bd043-0618-5e0e-9c97-9041304a4a38 | checkpoint | Correct number of hardware and specifications according to manufacturer's detail/drawing
c843157d-21d2-5b0c-ba8d-dac10d7aba93 | checkpoint | Screws are aligned straight, in correct position and all defect free?
5e6a346a-e665-5d9e-b632-0629587f09c5 | checkpoint | General photos and notes
f3d85a05-89a1-5bac-8e51-320baaa17f15 | checkpoint | Straight, flush, levelled and plumb within an acceptable tolerance.
601c1c7f-5742-56c9-ac43-d229412cd20f | checkpoint | Report sent through to client
907cf460-3738-56c7-bc2b-bad65ed50b25 | checklist | QA - Speedwall |  | Speedwall
c969dc9b-cfe1-5729-9c39-4acc7d14aa8f | checkpoint | Installer details entered
2980c297-fb78-5e44-801e-7896cccae74f | textbox | Installer:
1f0333fc-94d0-5c1c-906c-7c825e051158 | checkpoint | All relevant drawings and revision numbers checked and attached/commented
b9bd15bf-23f5-5ae0-8fc1-5582b2075134 | checkpoint | Area ready for Speedwall install
9fc29f3c-1ed7-5cd2-ada0-f0449cbb4dd4 | checkpoint | General photos, comments and observations during install
e19415f8-5c74-5215-9254-ad3c428cc787 | checkpoint | Bottom track correctly installed (size, location and fixings)
89f3cafd-20f4-5138-8155-7032fe8780a7 | checkpoint | Top track correctly installed (size, location and fixings)
92a4893d-7d5c-5f50-b211-379346a3a1f2 | checkpoint | 20mm minimum gap at head
c8a1197e-6e96-54fc-a1bc-75ec2dd4a68c | checkpoint | Install C track Fixings @ 400crs with M6.5 x 32 Mushroom head spikes into concrete
5d6c85a8-80ee-5c9c-be84-146c5fb96b46 | checkpoint | Fixings Hilti X-ENP-19 L15MX fixings 400crs in into steel
cb22199a-e317-5b76-9bfb-cd0c1e296429 | checkpoint | 10 x 16 fixings on C-Track to (horizontal panel - vertical C-Track 250crs, horizontal C-Track 400crs) (vertical panel - vertical C-Track 400crs, horizontal C-Track 250crs)
d9fd160d-acb0-5f36-b530-1b066fa4b84a | checkpoint | Fire sealant installed correctly and photographed
a6468365-b8e0-5541-8191-3ee761599e67 | checkpoint | All joints sealed correctly as per specification
43462357-f051-5ffe-abf5-b061e38ea929 | checkpoint | Speedwall installed straight and level
5aef0f4c-b421-5e45-94c0-027e235744b2 | checkpoint | Openings installed for services as per drawings
7c54c3ad-0923-5797-a0ba-6b4e3e9668bf | signoff | Request for signoff
12410951-ae50-535b-9fca-e0853d6c049a | checklist | QA - Structural Steel |  | QA - Structural Steel
c969dc9b-cfe1-5729-9c39-4acc7d14aa8f | checkpoint | Installer details entered
265e1cf2-2df5-58da-9b28-13056906672c | textbox | Installer:
0dde767a-6817-5c4c-8ed1-589e5565eaa5 | checkpoint | All relevant drawings and revision numbers checked and attached.
ccadaffb-2985-5db0-8e0f-5dbb13751777 | checkpoint | Product delivered free from defects - warping, twisting, distortion, damaged section, pitting.
707a3ef1-b445-53ad-a8f7-eae60ee5f60b | checkpoint | Welded connections continuous, even, clean, and free of blow holes or other irregularities.
65e7287e-7d71-5af6-89f0-66a5ead9eb4d | checkpoint | Primer and galvanizing applied intact and without blemishes.
80fddfe6-5497-59d0-8ccb-9d51d88d4e1d | checkpoint | Base plates fully and evenly support.
a88ebd7e-d476-51da-947f-16b2ebeba297 | checkpoint | Connecting bolts, washers, and nuts tight and clean of dirt/rust.
19a982db-b9a8-55d6-b195-253130d66e54 | checkpoint | All framing and connecting members installed plumb, level and true to line.
d3180f37-3fdc-5923-9b59-2cf6aa0f4f14 | checkpoint | Report sent to client.
65d4ea71-5f08-5cc0-b906-354bdba1f80d | checklist | QA - Villaboard Install |  | QA - Villaboard Install
c969dc9b-cfe1-5729-9c39-4acc7d14aa8f | checkpoint | Installer details entered
cf45e9dc-2849-5c7f-92ef-498ea17e62ba | textbox | Installer:
12ca808c-05a6-527b-809a-ec11e1660ecf | checkpoint | Correct fixings used and installed at correct centres
69a60b8c-dc00-5e09-9cd6-d59b3118a37a | checkpoint | Any bracing elements completed to design specification
44317bab-c147-54ac-b840-e3247f21977b | checkpoint | All lining completed, checked and approved as per specification
e771785f-174c-5494-a4d1-aabe77657993 | checkpoint | Correct stopping product and applied correctly to Villaboard walls to L4 finish
08c16340-87ff-5a7d-8406-e99fccc6c1ff | checkpoint | Adequate drying time between applications & no visible bubbling
c9df6ce9-0cc8-577d-8346-5e0f8ac6451e | checkpoint | All sanding completed as required
674e4273-11a4-5147-acc8-66ac11e0785b | checkpoint | Soffit Framing and Villaboard completed correctly within specified tolerance, checked and approved
b3ca54b9-ad1d-55ae-8969-cc658585da58 | checkpoint | Villaboard report sent through to client
60857c5a-e931-5f20-91e2-7f75503a2463 | checklist | SYS - Bollard Checklist |  | Bollard Checklist
8312b122-cb6c-543d-ace7-3de3024dc441 | checkpoint | All relevant drawings and revision numbers checked and attached
b43149e0-822e-5b81-93e8-93b2d73202d4 | checkpoint | Bollard Type
79bfa553-7726-5603-9dd9-3d1610b3fb55 | checkpoint | Product delivered free from defects - warping, twisting, distortion, damaged section, pitting
707a3ef1-b445-53ad-a8f7-eae60ee5f60b | checkpoint | Welded connections continuous, even, clean, and free of blow holes or other irregularities.
3dc1fe52-77c6-5d43-a7e2-5e403a7d3505 | checkpoint | Correct fixings being used – concrete anchor / bolts / washers
80fddfe6-5497-59d0-8ccb-9d51d88d4e1d | checkpoint | Base plates fully and evenly support.
ad62ff04-b110-57c2-adfd-8d959447165b | checkpoint | Base plates are installed at correct centres
f47003a8-1307-596b-9ba3-774e49bb5cb6 | checkpoint | Bollards are in correct height
7a0f949b-c596-58b1-bc49-c53b8bd68628 | checkpoint | All M.S. Pipes / Posts and connecting members installed plumb, level and true to line.
d3180f37-3fdc-5923-9b59-2cf6aa0f4f14 | checkpoint | Report sent to client.
c852f4a4-5705-4ccd-b0c6-e92e069d5d1f | checklist | SYS - Doors Checklist - v1 |  | SYS - Doors Checklist - v1
e82604c7-51d3-4d75-8260-ebdfda7f67d1 | checkpoint | Installer details input
a46c7a0f-b814-4aa7-b691-4ecd3ef80ee3 | checkpoint | All relevant drawings and revision numbers checked and attached
817a0cd8-53b0-4740-a0ae-24ece219a933 | checkpoint | Door opening checked and correct
7e76d0d7-6c87-4af0-b252-194592b770d2 | checkpoint | Direction of door correct
af105858-17d0-424d-834c-51bcc279ab78 | checkpoint | Number of screws and hardware location correct
b70a7bc9-9003-4f9b-97fd-afa5fedc29eb | checkpoint | Door hinges installed in place with correct screws
eeaddeb8-8a13-4f3d-98de-c39c90ed0cfd | checkpoint | Floor clearance correct
47fec660-9dba-449a-81cc-a9eae362f4bc | checkpoint | Undercoat on door surface
c79c2bbf-37c3-406c-9405-308181a8a249 | checkpoint | Fireseal around door installed as per spec
fe9a8af7-30e3-4330-9ad7-2d8ee5fafa20 | checkpoint | Door is fully operational after installation
e71e5850-202f-4f39-9cbb-8d2504cc01ed | checkpoint | Door jambs are plumn and level
dbaa0fab-022f-4ed0-a0ed-a7079ad74608 | checkpoint | Door gap around door leaf within tolerance
a1f58017-b428-4574-b2b5-7e392a3fe884 | checkpoint | Door report sent through to client
503bbe75-8ec4-587a-a53f-798830455026 | checklist | SYS - Ecoply Sheet Fixing |  | Ecoply Sheet Fixing
7305eb87-01bf-5413-8167-7bc69789f497 | checkpoint | Ecoply pre cladding/RAB board to be kept dry and under cover
930fb872-01c1-5a57-8398-dc4d54f7f4f2 | checkpoint | Ecoply Pre-cladding/RAB board installed in accordance with Ecoply barrier installation manual
4fc305ea-a01e-5c99-941f-310da69ca6f5 | checkpoint | Tape installed over Ecoply pre-cladding/RaB board vertical joints, corners and openings in accordance with Ecoply Barrier installation manual
92e9c041-fc94-5b59-9963-455078110c3d | checkpoint | uPVC horizontal flashing used at all horizontal joints
551324e1-0cb2-5fba-952a-dc0ce80b19b2 | checkpoint | Fixings: Type - Stainless Steel/Galv correct spacing
173d7aea-cd21-5586-9fc5-c8b0f180ca0b | textbox | size
41a76a9c-7a14-5667-90eb-1c9ed6f345bd | checkpoint | The panels overhang the bottom plate on a concrete slab by a maximum of 40mm as per installation manual
032774a0-bb89-509b-b253-35dd8455388b | checkpoint | Penetrations through Ecoply pre-cladding/Rab board sealed properly using flexible flashing tape as per E2/AS1
0aed60f6-3005-510e-9004-f026f7a76854 | checkpoint | Fix Covertek 403 underlay with printed side facing the exterior
9f515a35-24dc-535d-bccc-c612b22ebb57 | checkpoint | Fix securely to the frame, with staples at 300 mm centres horizontally and vertically
1b627326-3e3c-5f65-822b-20d4e3533914 | checkpoint | Minimum of 150mm lap is required at joins.
436435bd-4e93-5828-b4a9-c7628944d99a | checkpoint | All vertical laps must be made over studs.
cb7772a3-9c21-554c-adf3-ee63b4868ee0 | checkpoint | Correct paint product and applied correctly to Ecoply (internal only)
8bb476b2-a58d-59dc-8e3b-d00314a14823 | checkpoint | Repair small damages, if any.
84b0945a-c27b-59c3-8dd2-a707432f13a8 | checkpoint | Report sent to client
8d3acab2-02e4-5b13-930e-7ae658dbaba0 | checklist | SYS - Ecoply Sheet Fixing - L2 parapet |  | Ecoply Sheet Fixing - L2 parapet
7305eb87-01bf-5413-8167-7bc69789f497 | checkpoint | Ecoply pre cladding/RAB board to be kept dry and under cover
930fb872-01c1-5a57-8398-dc4d54f7f4f2 | checkpoint | Ecoply Pre-cladding/RAB board installed in accordance with Ecoply barrier installation manual
4fc305ea-a01e-5c99-941f-310da69ca6f5 | checkpoint | Tape installed over Ecoply pre-cladding/RaB board vertical joints, corners and openings in accordance with Ecoply Barrier installation manual
92e9c041-fc94-5b59-9963-455078110c3d | checkpoint | uPVC horizontal flashing used at all horizontal joints
551324e1-0cb2-5fba-952a-dc0ce80b19b2 | checkpoint | Fixings: Type - Stainless Steel/Galv correct spacing
49a00b42-9da4-566b-a9ae-c7c559b645d7 | textbox | size
41a76a9c-7a14-5667-90eb-1c9ed6f345bd | checkpoint | The panels overhang the bottom plate on a concrete slab by a maximum of 40mm as per installation manual
032774a0-bb89-509b-b253-35dd8455388b | checkpoint | Penetrations through Ecoply pre-cladding/Rab board sealed properly using flexible flashing tape as per E2/AS1
cb7772a3-9c21-554c-adf3-ee63b4868ee0 | checkpoint | Correct paint product and applied correctly to Ecoply (internal only)
8bb476b2-a58d-59dc-8e3b-d00314a14823 | checkpoint | Repair small damages, if any.
84b0945a-c27b-59c3-8dd2-a707432f13a8 | checkpoint | Report sent to client
720d4e25-2f8c-520d-afd4-ecd118f20e15 | checklist | SYS - Fencing Checklist |  | Fencing Checklist
8312b122-cb6c-543d-ace7-3de3024dc441 | checkpoint | All relevant drawings and revision numbers checked and attached
79bfa553-7726-5603-9dd9-3d1610b3fb55 | checkpoint | Product delivered free from defects - warping, twisting, distortion, damaged section, pitting
68690d07-31f3-5ef0-9e63-c08dfcf0f917 | checkpoint | Correct fixings being used – Hex / Self Tapping Screws
38bcf7a1-ca60-5939-8b73-ed262caa46c8 | checkpoint | All horizontal galvanized M.S. Pipes installed level
5b62f062-37cf-5333-ad7e-ee742bc71b97 | checkpoint | All horizontal galvanized M.S. Pipes installed at correct centres.
d3180f37-3fdc-5923-9b59-2cf6aa0f4f14 | checkpoint | Report sent to client.
f326506e-51ad-5390-a411-2d6e6b73a04b | checklist | SYS - Floor framing and plywood flooring |  | Floor framing and plywood flooring
100ab6ba-1485-5e6a-9e29-6ed7ac12ea0b | checkpoint | All relevant drawings checked and attached.
2ca9b4b0-d4ff-581a-83e1-b9c550a13c1d | checkpoint | Joists installed at correct centers
719b1b7e-b697-51b3-9f6c-0b2b62e41906 | checkpoint | Bolts sprecified and installed at correct centers
ad6a8135-fc07-5707-95b5-1d19a628c4b4 | checkpoint | Correct number of hardware (joist hangers ect) according to drawings
b88609b3-fa2f-5df1-bad9-e9f42dd22c30 | checkpoint | Floor framing finished, straight, level and within tolerance.
5e6a346a-e665-5d9e-b632-0629587f09c5 | checkpoint | General photos and notes
6159a80a-4282-5e88-8da3-62453962ab6c | checkpoint | Correct plywood used for plywood flooring.25mm thick and tongue and groove
19841b87-7467-5ed9-a4c2-c75b8cfef005 | checkpoint | 2mm expansion gap allowed around sheet
bfecc87c-5c21-5ce7-8d2f-46e40bd3b604 | checkpoint | Sheet edges are set 20mm from steel edges around perimeter with exception of seismic gaps where sheets are fixed flush.
9f7b9294-edef-5d14-be5f-d9a426e3c320 | checkpoint | Sheets set out correctly as per s2.207
fbfc3f84-b96a-5006-8af0-c8b7fc346e15 | checkpoint | Plywood flooring fixed in accordance to s2.601
d3180f37-3fdc-5923-9b59-2cf6aa0f4f14 | checkpoint | Report sent to client.
a5924ab4-c56f-5375-aa66-5d5f481980d0 | signoff | Request signoff if required
2dc772e3-f8a2-40bc-ae25-1f0e32937a07 | checklist | SYS - GIB Lining - fyreline ground floor |  | GIB Lining - fyreline ground floor
9fd0eeea-01a3-4f99-82dc-ab12ab5aa8d7 | checkpoint | All relevant drawings and revision numbers checked and attached/commented
2272a0be-2d68-4156-9a17-adc2fb45e459 | checkpoint | Area ready for GIB install
e5b864fc-0f23-4733-a923-ccd0ecd2b567 | checkpoint | Insulation installed
7aa46461-3f38-411b-b593-0358b52de006 | checkpoint | General photos, comments and observations during install
adbf1d5b-dbb7-48f3-9bde-2fc35f8709bf | checkpoint | Correct lining checked and approved and area specifics checked
fd676076-01b2-4643-925e-08062a26c5ef | checkpoint | Correct fixings used and installed at correct centres
db368c12-fac9-425f-8612-60cf52b3890e | checkpoint | Any bracing elements completed to design specification
89d10454-7595-4845-8868-a3a439a8f3c2 | checkpoint | GIB Lining completed correctly within specified tolerance, checked and approved
6a81160f-3a7a-4e36-883b-7441d5bfe6ea | checkpoint | GIB Lining report sent through to client
ee5e864b-002c-5d34-b0d4-a5dc17342a02 | checklist | SYS - GIB Weatherline |  | GIB Weatherline
78519a83-0595-567f-9540-ac0fefc2ea12 | checkpoint | All relevant drawings and revision numbers checked and attached / commented.
c0938725-286e-5073-ba53-fd66f529ade8 | checkpoint | Substrate accepted and approval given to start lining.
7354f4b3-f19c-5770-af08-79aecf99a904 | checkpoint | Correct fixings used and installed at correct centres.
5bb91015-446c-5b82-aa02-91c61e94c50e | checkpoint | Panels overhang the bottom plate on a concrete slab by 15mm minimum as per Gib Weatherline installation manual.
bec06e0f-cf88-5cc3-8b66-840b20a0b69d | checkpoint | Correct tape installed over vertical / horizontal joints, corners and openings in accordance with Gib Weatherline installation manual.
b0149de6-4b82-5419-8454-9c17e16cbf80 | checkpoint | General photos, comments and observations during installation.
af21b727-cd20-53c3-9c6d-577e91add033 | checkpoint | All lining completed correctly within a specified tolerance, checked and approved.
02422d9e-2363-5937-b835-5ae02872075b | checkpoint | Gib lining report sent to client
f77d47f2-b172-5d18-81e6-df3d40cdd6a4 | signoff | ( RAISE REMEDIAL / REQUEST FOR SIGNOFF)
41af5bcb-75a0-4375-be62-857b14a56234 | checklist | SYS - QA - Concrete Pour Checklist - v1 |  | SYS - QA - Concrete Pour Checklist - v1
df4cade4-644d-4cb6-9752-f71d7f156859 | section | Pour Details
9b8a82b3-6f1d-4c1e-ae02-4d47b9a834a9 | checkpoint | Pour details entered
228a87c2-c4fc-528b-b148-3367e32e6a9a | textbox | Area to be poured (grid lines, location):
5278331b-f876-56b0-85a3-4f9d2523931f | textbox | Drawing numbers and revisions
19ca0f3c-08f4-567f-b8cd-17309dbb4f9d | textbox | Date of pour
246a43ae-7357-488f-a2e4-463daca0f66f | section | Formwork and embedded items
34ed4b21-b2be-4ac1-b184-3ac4e79ba423 | checkpoint | Grids and RLs clearly marked for reference
61905e2c-0473-4694-ac3c-7558a936315a | checkpoint | Formwork - location, heights, falls and dimensions checked and accurate
ef39c091-3f3e-4ef7-849f-41b7a5b5d180 | checkpoint | Formwork sufficiently fixed and braced
0a49f692-f700-4c0d-a47a-c55573db8a61 | checkpoint | Any rebates / nibs / cast in items are correctly positioned, sized and appropriately fixed in place.
a9d46929-2553-504b-89ee-ea45651168f6 | tickbox | Hold down bolts checked and correct
c4b20aca-f494-507f-96cc-5b8fc468a3a6 | tickbox | Precast panel starters checked and correct
fcd662d3-12a4-4337-8051-fe61a08d853d | checkpoint | Service penetrations formed correctly and locations checked/correct
efc13c0b-7170-48ab-b46f-9ff59f5dcae7 | checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork, etc.)
5624e7c6-9103-472f-b8fc-18ee5b10f73d | checkpoint | Any control joints / stop ends installed accurately and correctly braced
83af4a1a-d94b-4c9b-a120-cd29f7977336 | checkpoint | DPM & Connection to other waterproofing completed
bd517ae6-a1dc-40bd-95dc-35e34f907ed0 | checkpoint | Any additional formwork photos and observations
32b2f5e8-6222-4cb5-90cd-dbbc8498d23a | checkpoint | All formwork elements completed and ready for concrete pour (excess debris removed)
cacb6b94-fb04-4c99-a20b-578889895330 | checkpoint | Concrete ordered - correct mix and strength
c3b1317d-0675-5bdc-aa34-9d48fe0a420b | textbox | Mix
90d654b6-13b4-542d-aef5-d614ff03b318 | textbox | Strength:
1af2a3c5-1784-5877-8dce-7411582b80f8 | textbox | Summary of Proposed cement mix date and revision checked:
ba0a9a35-7c96-53b5-a723-22111870db39 | textbox | Structrual services specifications number and revision checked:
f8c51566-8dc7-4f6c-a029-fcf6e0c52929 | checkpoint | Slump test/Spread test (only applicable for special mix)
3bb14464-1db2-4ff6-8e62-82bd7b3c9872 | section | Placement Method
df416dea-2706-4be6-a677-f6ac6161bf3d | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
0728475c-9ce0-509e-82b8-999e2610e96d | textbox | Who is placing the concrete
3588b4ef-300f-4e91-a241-5ceaac8a2b8a | checkpoint | Height and falls checked / confirmed before placement
729f57b3-0f92-4754-b3dd-afc38289e172 | checkpoint | Cover correct to specification
9e29c331-0aff-4152-a158-39d82f97d5b9 | checkpoint | All concrete checked and correct on arrival (mix and strength)
5e74aef3-cfbc-5431-a8c3-4326f5b12008 | tickbox | All concrete dockets attached
a578d2f7-5cd7-49bd-ab9b-1c61e2813b57 | checkpoint | General photos and observations of concrete placement attached
5d9b8c07-01a8-4125-ae26-3de5809c5699 | checkpoint | Heights and falls checked / confirmed after placement
88e5e337-c4c0-445e-9b65-faeeae31d236 | checkpoint | Any curing compound applied correctly
f350ca97-55f7-4e54-8748-8eba97a339a5 | checkpoint | Concrete placement completed - specified level of finish achieved
4e41cbd5-2a55-4329-8247-aa41b525a966 | checkpoint | Area left clean and tidy
3747f9de-59e4-4013-9c1c-801413e24739 | section | Post Pour Checks / Signoff
0ea2d8e3-fe67-4139-9306-2f8289155a15 | checkpoint | Any remedial work completed
8dda0684-8f10-4073-8d0c-f2436754203a | checkpoint | Concrete Pour completed - all final checks and documentation completed and attached
42a0ba64-df64-4a58-b333-444359a90c29 | checkpoint | Report sent through to client
ffa89b60-156f-5db9-835f-988a82f693a6 | checklist | SYS - QA - External Timber Framing |  | QA - External Timber Framing
6dd2bb6c-5de5-595e-a3f3-343244748b3d | checkpoint | Correct product & fixings delivered, reviewed and approved as per specification
2823ca50-a0b5-5250-9b41-484a6c37967c | checkpoint | Dimensions / locations of walls checked and correct
23b606b1-ecd7-5a29-a4fb-7c328cfcf18f | checkpoint | DPM installed where required
c835a7cb-0af9-5e30-8da5-deac857fa693 | checkpoint | All frames are square & plumb
b3037941-13a3-5240-bf71-8feb3b0b6c2f | checkpoint | External framing is installed at correct centres
acf94367-1ee5-5043-b9bf-022e99fd2d09 | textbox | Input centres
dba23fe1-a474-584a-bae5-34ac680fd0e4 | checkpoint | All openings are in correct location and correct size
cf6ab710-4cb1-5e8d-94bf-a5b5b70bf548 | textbox | Drawing / detail reference
f8eb382a-14bd-5b0a-8b77-d008d513081b | checklist | SYS - QA - GIB Lining |  | QA - GIB Lining
c222ec1a-01a6-5c05-8579-d29f1c4728a9 | checkpoint | All pre installation checks completed and approval given to line
1f0333fc-94d0-5c1c-906c-7c825e051158 | checkpoint | All relevant drawings and revision numbers checked and attached/commented
c81d1f71-7057-5268-9871-e2b5662b7c8d | textbox | Drawing no. and revision
0bfba9fd-7ae6-5229-84d0-0b894f5383f8 | checkpoint | Correct lining checked and approved and area specifics checked
66a48527-2b97-5cbd-9569-d1f1c8294da1 | checkpoint | Substrate accepted and approval given to start gib lining
12ca808c-05a6-527b-809a-ec11e1660ecf | checkpoint | Correct fixings used and installed at correct centres
69a60b8c-dc00-5e09-9cd6-d59b3118a37a | checkpoint | Any bracing elements completed to design specification
9fc29f3c-1ed7-5cd2-ada0-f0449cbb4dd4 | checkpoint | General photos, comments and observations during install
655bfc0d-3e94-57d0-b30b-97c9423168d5 | checkpoint | All lining completed correctly within specified tolerance, checked and approved
8e7ac91d-428b-5fa4-a7ec-ff01482d54d8 | checkpoint | GIB Lining report sent through to client
08633bb4-a473-59c2-97f2-72d1bf2844dc | checklist | SYS - QA - Gib Weatherline |  | QA - Gib Weatherline
2afc9ee7-a635-5a19-9c4c-3552086850e0 | checkpoint | Framing set out adequate to support all sheet edges. Stud and nog spacing complies with GIB Weatherline® technical literature i.e. studs must be at a maximum of 400mm or GIB Weatherline® technical literature i.e. studs must be at a maximum of 400mm or
4586fd12-3422-577d-aca2-1c1f246b1e79 | checkpoint | Framing straightness. Nogs flush with studs, studs flush with top/bottom plates and no protruding fixings.
f40c0dd0-a804-5139-ac9f-d52da8dfef7b | checkpoint | Prior to installation GIB Weatherline® sheets to be kept dry
d33a4ea5-e203-5d9c-9254-ebf0091b4b87 | checkpoint | Correct fixings used and installed at correct centres according to GIB Weatherline® technical literature
01b6a0a8-4583-59ff-9971-3aec3062bca1 | checkpoint | Sheets overhang the bottom plate on a concrete slab by a minimum of 15mm as per GIB Weatherline® technical literature.
c4a093b8-4514-52de-ae6f-75afef73cfab | checkpoint | GIB Weatherline® Tape installed to vertical/ horizontal sheet joints, corners, and openings in accordance with GIB Weatherline® technical literature.
b37a70a1-f6a5-5e27-98ba-24a831bcb568 | checkpoint | Building service penetrations through GIB Weatherline® sheets sealed using Proclima Kaflex or Roflex penetration seal grommets. Proclima installation instructions to be followed.
6f85c4bc-069a-5b7e-ab09-dff43796468a | checkpoint | GIB Weatherline® flashing and sill tapes to be applied on doors and windows as per GIB Weatherline® technical literature.
14096036-d4b0-53b9-bb66-bc6672780c65 | checkpoint | GIB Weatherline® report sent to client
0719481d-83ab-44d1-ba9d-0fdc15f6806a | checklist | SYS - QA - Reinforcing Checklist - v1 |  | SYS - QA - Reinforcing Checklist - v1
6cae73c2-8276-4b64-ae9f-db115dc31453 | checkpoint | Work area ready
9e3e979a-df02-4d42-ac72-4b221075a18e | checkpoint | Latest drawings available, checked and referenced
ddb0273e-8ee6-40ca-9272-c2c972d67616 | checkpoint | Correct product delivered, reviewed & approved
a5297cbb-1c49-4b82-b268-747681654a62 | checkpoint | Correct size & type installed as per design
3421e0ea-a8d0-477b-9fe6-6f076d30558d | checkpoint | Reinforcing spacing and location correct
90a60116-394b-480c-add5-3ee4b222fd23 | checkpoint | Specified covers checked/correct
159dfce6-944f-4c1f-906b-6361336a4164 | checkpoint | Laps correct per size of bar
1d9d18ed-6b9b-4b1d-8a4a-9946bec2ca7a | checkpoint | Any starter bars are installed correctly (location, size and spacing)
dff05549-9f1c-4c18-91ba-23dc776baf86 | checkpoint | All bars fixed appropriately
4bfdee4b-a22f-42a2-8f0a-d0087c889781 | checkpoint | Couplers installed at correct height
9b70bb15-e2e5-430d-aeb4-7bd8e8554401 | checkpoint | Cast in plates installed correctly
2bd61297-9fae-4e8c-8b82-552909972dbf | checkpoint | Any additional items considered, installed & completed e.g. trimmer bars, reid bar couplers, foot plates, drag bars
16c5cfee-b82d-4fd4-92a6-1e21c761c482 | checkpoint | All excess reinforcing and debris removed - clean & tidy
548c029f-60c3-4aea-abc9-b40a7f1888ca | checkpoint | Reinforcing install completed, send to client
d50d513a-398b-50b9-989d-a49be65f759f | checklist | SYS - QA - Roof Framing |  | QA - Roof Framing
7af59523-dade-5cd1-8e64-653a2f96c3cd | checkpoint | All relevant drawings and revision numbers checked and attached/referenced
d5293322-bd81-58b4-838b-59f748c377cc | checkpoint | Correct spacing between noggins/purlins in its corresponding area
486bd043-0618-5e0e-9c97-9041304a4a38 | checkpoint | Correct number of hardware and specifications according to manufacturer's detail/drawing
c843157d-21d2-5b0c-ba8d-dac10d7aba93 | checkpoint | Screws are aligned straight, in correct position and all defect free?
5e6a346a-e665-5d9e-b632-0629587f09c5 | checkpoint | General photos and notes
f3d85a05-89a1-5bac-8e51-320baaa17f15 | checkpoint | Straight, flush, levelled and plumb within an acceptable tolerance.
601c1c7f-5742-56c9-ac43-d229412cd20f | checkpoint | Report sent through to client
b119d0d5-ebc1-5ed2-95c7-57ad96470a0d | checklist | SYS - QA - Structural Steel |  | QA - Structural Steel
0dde767a-6817-5c4c-8ed1-589e5565eaa5 | checkpoint | All relevant drawings and revision numbers checked and attached.
ccadaffb-2985-5db0-8e0f-5dbb13751777 | checkpoint | Product delivered free from defects - warping, twisting, distortion, damaged section, pitting.
707a3ef1-b445-53ad-a8f7-eae60ee5f60b | checkpoint | Welded connections continuous, even, clean, and free of blow holes or other irregularities.
65e7287e-7d71-5af6-89f0-66a5ead9eb4d | checkpoint | Primer and galvanizing applied intact and without blemishes.
80fddfe6-5497-59d0-8ccb-9d51d88d4e1d | checkpoint | Base plates fully and evenly support.
a88ebd7e-d476-51da-947f-16b2ebeba297 | checkpoint | Connecting bolts, washers, and nuts tight and clean of dirt/rust.
19a982db-b9a8-55d6-b195-253130d66e54 | checkpoint | All framing and connecting members installed plumb, level and true to line.
d3180f37-3fdc-5923-9b59-2cf6aa0f4f14 | checkpoint | Report sent to client.
98e65d17-42ba-514f-becb-fa7d3a20144d | checklist | SYS - QA - Villaboard Install |  | QA - Villaboard Install
12ca808c-05a6-527b-809a-ec11e1660ecf | checkpoint | Correct fixings used and installed at correct centres
69a60b8c-dc00-5e09-9cd6-d59b3118a37a | checkpoint | Any bracing elements completed to design specification
44317bab-c147-54ac-b840-e3247f21977b | checkpoint | All lining completed, checked and approved as per specification
e771785f-174c-5494-a4d1-aabe77657993 | checkpoint | Correct stopping product and applied correctly to Villaboard walls to L4 finish
08c16340-87ff-5a7d-8406-e99fccc6c1ff | checkpoint | Adequate drying time between applications & no visible bubbling
c9df6ce9-0cc8-577d-8346-5e0f8ac6451e | checkpoint | All sanding completed as required
674e4273-11a4-5147-acc8-66ac11e0785b | checkpoint | Soffit Framing and Villaboard completed correctly within specified tolerance, checked and approved
b3ca54b9-ad1d-55ae-8969-cc658585da58 | checkpoint | Villaboard report sent through to client
349c3ab2-48fa-511c-ac3e-92af54465346 | checklist | SYS - Speedwall |  | Speedwall
1f0333fc-94d0-5c1c-906c-7c825e051158 | checkpoint | All relevant drawings and revision numbers checked and attached/commented
b9bd15bf-23f5-5ae0-8fc1-5582b2075134 | checkpoint | Area ready for Speedwall install
9fc29f3c-1ed7-5cd2-ada0-f0449cbb4dd4 | checkpoint | General photos, comments and observations during install
e19415f8-5c74-5215-9254-ad3c428cc787 | checkpoint | Bottom track correctly installed (size, location and fixings)
89f3cafd-20f4-5138-8155-7032fe8780a7 | checkpoint | Top track correctly installed (size, location and fixings)
92a4893d-7d5c-5f50-b211-379346a3a1f2 | checkpoint | 20mm minimum gap at head
c8a1197e-6e96-54fc-a1bc-75ec2dd4a68c | checkpoint | Install C track Fixings @ 400crs with M6.5 x 32 Mushroom head spikes into concrete
5d6c85a8-80ee-5c9c-be84-146c5fb96b46 | checkpoint | Fixings Hilti X-ENP-19 L15MX fixings 400crs in into steel
cb22199a-e317-5b76-9bfb-cd0c1e296429 | checkpoint | 10 x 16 fixings on C-Track to (horizontal panel - vertical C-Track 250crs, horizontal C-Track 400crs) (vertical panel - vertical C-Track 400crs, horizontal C-Track 250crs)
d9fd160d-acb0-5f36-b530-1b066fa4b84a | checkpoint | Fire sealant installed correctly and photographed
a6468365-b8e0-5541-8191-3ee761599e67 | checkpoint | All joints sealed correctly as per specification
43462357-f051-5ffe-abf5-b061e38ea929 | checkpoint | Speedwall installed straight and level
5aef0f4c-b421-5e45-94c0-027e235744b2 | checkpoint | Openings installed for services as per drawings
7c54c3ad-0923-5797-a0ba-6b4e3e9668bf | signoff | Request for signoff
d22504ab-d4e5-5080-a024-657acb70e05e | checklist | SYS - Vaproshield Installation Checklist |  | Vaproshield Installation Checklist
38c77a82-95ed-538a-a6db-cb0e8074828f | checkpoint | Wrapshield rolls stored upright
174654c8-1932-5832-b437-f29ee6b79d7f | checkpoint | RAB clean, free of contaminations and dry to touch
e9f4bcb3-63d8-5aaf-8250-e35c1c8106ca | checkpoint | Lower courses lapped under the upper courses with a minimum 80mm lap joints
da58d7fb-a1d9-5ece-8f7d-bf1c3d8aefdb | checkpoint | 150mm lap joint at internal and external corners
12fdbd33-40b5-5d1e-9d7b-cfc1f48cf209 | checkpoint | All service penetrations covered with liquid flashing
b3a6e57e-fedd-555d-8cf2-d25a316e0f16 | checkpoint | 25 mm liquid flashing to all steel and concrete connections
d6eef339-63a4-5f9c-8b7d-4c2684c866fe | checkpoint | All penetrations and damage to Vaproshield repaired
930df3ca-dcdc-5d4a-b319-6542c29c3152 | checklist | SYS - Wall Framing Checks |  | Wall Framing Checks
8312b122-cb6c-543d-ace7-3de3024dc441 | checkpoint | All relevant drawings and revision numbers checked and attached
f6eaf419-f935-5abe-b2a4-52fa4e846ca0 | checkpoint | Drawing no. and revision
dcf3131a-8331-548e-af70-165d8c036ff0 | checkpoint | DPC installed, checked and correct as per specification
84f5cfe0-bfce-5214-b206-a846697a73d6 | checkpoint | Wall locations checked, correct and approved as per latest revised drawing
2ebc7f43-dc9c-5a26-b423-322a10a4d769 | checkpoint | Fixings and hold down bolts checked and correct
000c9e43-9335-56a7-b4e7-50f130a722e8 | checkpoint | All openings (doors / windows etc) checked, correct and approved
e86919dc-e2da-599d-8414-dc534dee21fb | checkpoint | Deflection heads type installed and correct
1fcf02e1-837f-55b6-be4c-dbbfe1630e6e | checkpoint | Wall type checked (straight and plumb) and within tolerance
589d739e-d04d-598a-9fb3-a97731c5e599 | checkpoint | All relevant nogs (service and special/fixtures) installed, checked and correct
ac1e3cca-6d74-5398-bc37-4b72360841d4 | checkpoint | All other nogs checked and approved
660b28f4-eab5-5c7c-b1ba-1c993a7281e6 | checkpoint | Moisture reading checked, recorded and acceptable
0e3e78f5-9269-518d-b0ae-91bdf25dab7c | checkpoint | All wall framing checks completed & Inspections carried out
b068e46a-6887-5af8-a627-6417bed76f2e | checkpoint | Relevant inspections completed and attached
84b0945a-c27b-59c3-8dd2-a707432f13a8 | checkpoint | Report sent to client
0ad560ec-84c4-56d9-b946-455ef5a6c731 | checklist | Vaproshield Installation Checklist |  | Vaproshield Installation Checklist
c969dc9b-cfe1-5729-9c39-4acc7d14aa8f | checkpoint | Installer details entered
705cb3c2-1ebe-588d-bc2d-7256716ed7d6 | textbox | Installer:
38c77a82-95ed-538a-a6db-cb0e8074828f | checkpoint | Wrapshield rolls stored upright
174654c8-1932-5832-b437-f29ee6b79d7f | checkpoint | RAB clean, free of contaminations and dry to touch
e9f4bcb3-63d8-5aaf-8250-e35c1c8106ca | checkpoint | Lower courses lapped under the upper courses with a minimum 80mm lap joints
da58d7fb-a1d9-5ece-8f7d-bf1c3d8aefdb | checkpoint | 150mm lap joint at internal and external corners
12fdbd33-40b5-5d1e-9d7b-cfc1f48cf209 | checkpoint | All service penetrations covered with liquid flashing
b3a6e57e-fedd-555d-8cf2-d25a316e0f16 | checkpoint | 25 mm liquid flashing to all steel and concrete connections
d6eef339-63a4-5f9c-8b7d-4c2684c866fe | checkpoint | All penetrations and damage to Vaproshield repaired
3b89fdf8-c930-5310-9376-18ee1d91d691 | checklist | Wall Framing Checks |  | Wall Framing Checks
c969dc9b-cfe1-5729-9c39-4acc7d14aa8f | checkpoint | Installer details entered
6ad98517-adbb-5cc9-95be-73a8ca7cdd73 | textbox | Installer:
8312b122-cb6c-543d-ace7-3de3024dc441 | checkpoint | All relevant drawings and revision numbers checked and attached
f6eaf419-f935-5abe-b2a4-52fa4e846ca0 | checkpoint | Drawing no. and revision
dcf3131a-8331-548e-af70-165d8c036ff0 | checkpoint | DPC installed, checked and correct as per specification
84f5cfe0-bfce-5214-b206-a846697a73d6 | checkpoint | Wall locations checked, correct and approved as per latest revised drawing
2ebc7f43-dc9c-5a26-b423-322a10a4d769 | checkpoint | Fixings and hold down bolts checked and correct
000c9e43-9335-56a7-b4e7-50f130a722e8 | checkpoint | All openings (doors / windows etc) checked, correct and approved
e86919dc-e2da-599d-8414-dc534dee21fb | checkpoint | Deflection heads type installed and correct
1fcf02e1-837f-55b6-be4c-dbbfe1630e6e | checkpoint | Wall type checked (straight and plumb) and within tolerance
589d739e-d04d-598a-9fb3-a97731c5e599 | checkpoint | All relevant nogs (service and special/fixtures) installed, checked and correct
ac1e3cca-6d74-5398-bc37-4b72360841d4 | checkpoint | All other nogs checked and approved
660b28f4-eab5-5c7c-b1ba-1c993a7281e6 | checkpoint | Moisture reading checked, recorded and acceptable
0e3e78f5-9269-518d-b0ae-91bdf25dab7c | checkpoint | All wall framing checks completed & Inspections carried out
b068e46a-6887-5af8-a627-6417bed76f2e | checkpoint | Relevant inspections completed and attached
84b0945a-c27b-59c3-8dd2-a707432f13a8 | checkpoint | Report sent to client