## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
50c7c8a0-f142-4a4d-ae54-684661e2695a | checklist | QA - KOROK - internal |  | QA - KOROK - internal
| section | Details
| checkpoint | Installer details entered
| textbox | Installer:
| checkpoint | drawings for site measure listed below
| checkpoint | Main contractor handed over area for install (written confirmation stating that previous trades work has been completed and QA done)
| checkpoint | Material being used is correct for area (size and density of panels)
| checkpoint | Area ready for Speedwall install
| checkpoint | General photos, comments and observations during install
| checkpoint | Bottom track correctly installed (size, location and fixings)
| checkpoint | Top track correctly installed (size, location and fixings)
| checkpoint | 20mm minimum gap at head
| checkpoint | Install C track Fixings @ 400crs with M6.5 x 32 Mushroom head spikes into concrete
| checkpoint | Fixings Hilti X-ENP-19 L15MX fixings 400crs in into steel
| checkpoint | 10 x 16 fixings on C-Track to (horizontal panel - vertical C-Track 250crs, horizontal C-Track 400crs) (vertical panel - vertical C-Track 400crs, horizontal C-Track 250crs)
| checkpoint | Fire sealant installed correctly and photographed , description of sealant entered below
| checkpoint | All joints sealed correctly as per specification
| checkpoint | Speedwall installed straight and level
| checkpoint | Openings installed for services as per drawings
| signoff | Request for signoff
3a11c13f-099c-41d7-b80b-ebde41df7c1f | checklist | QA - KOROK - External |  | QA - KOROK - External
| section | Details
| checkpoint | Installer details entered
| textbox | Installer:
| checkpoint | drawings for site measure listed below
| checkpoint | Main contractor handed over area for install (written confirmation stating that previous trades work has been completed and QA done)
| checkpoint | Material being used is correct for area (size and density of panels)
| checkpoint | Area ready for Speedwall install
| checkpoint | General photos, comments and observations during install
| checkpoint | Steel Angles installed as per Beca Drawings 20240118-ST-K028
| checkpoint | Bottom Steel Flashing installed correctly over steal angle as per Y3420031
| checkpoint | Top track correctly installed - 80mm w x 90mm D 1.55BMT as per Y300006 and Y3420031
| checkpoint | 25mm gap at head as per Y3420031
| checkpoint | C track Fixings @ 400crs with Pair of Hilti X-ENP MX fastners
| checkpoint | Sikaflex 400 Sealant used in C track and panels as per Y3420033
| checkpoint | V776-18 x 4.8mm Foam attached to male end of panels as per Y3-420033
| checkpoint | 10 Gauge x 16 screws at 250mm crs max on rear of panels as per Y3-420033
| checkpoint | 14g x 115mm long Steetite Screws two per panel with 19mm washer each installed as per Y3-420031
| checkpoint | All joints sealed correctly as per specification
| checkpoint | Speedwall installed straight and level
| checkpoint | Aluminuim Flashing 2.0mm installed as per Y3-420031
| signoff | Request for signoff