## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
51a12ec0-5226-4c6b-8497-16296f16e1ad | checklist | 00. PRELIMINARY ACTIVITIES |  | 00. PRELIMINARY ACTIVITIES
| section | PRODUCTION PLANNING REQUIREMENTS FOR EACH PRECAST UNIT TYPE
| checkpoint | Contractor's Construction / Installation Programme
| tickbox | Verify Production Lot System / Precast Unit identification accepted by Contractor
| tickbox | Verify programme details are current
| tickbox | Verify programme dates are achievable
| tickbox | Verify Casting Programme finalised
| checkpoint | Production Area
| tickbox | Verify work area identified including storage of raw materials
| tickbox | Easy access for concrete agitator trucks / craneage / forklift
| tickbox | Curing facilities available
| checkpoint | Storage Area
| tickbox | Adequate area for potential long term storage
| tickbox | Bearing capacity of storage area will meet loading of precast units
| tickbox | Unit Layout plan developed
| tickbox | Adequate area for craneage operation and access by heavy haulage
| section | Plant / Equipment / Procurements
| checkpoint | Verify moulding received and dimensions checked
| tickbox | Curing facility available as required
| tickbox | Jigs / working platform (rebar) available as required
| tickbox | Verify Curing Methodology signed off
| tickbox | Verify Curing System functional
| checkpoint | Verify Stressing System / bed signed off by member of MIAustE as required
| checkpoint | Craneage available as required
| checkpoint | Procurements
| tickbox | Verify Reinforcement ordered and delivery commenced
| tickbox | Verify concrete order process agreed with concrete supplier
| tickbox | Verify Strand / Couplers ordered and delivery commenced
| tickbox | Verify Contractor Supplied Product ordered and delivery commenced
| tickbox | Verify cast-in items ordered and delivery commenced
| tickbox | Verify lifting systems in precast unit signed off
| tickbox | Verify lifting equipment available and signed off by Authority as required
| tickbox | Verify production consumables ordered and delivery commenced
| textbox | specify others
da870fe2-3e5c-4737-8241-32c9c13b46d0 | checklist | 01. MDR COMMON BOOK |  | [object Object]
| section | A - PERMACAST CERTIFICATE OF CONFORMANCE
| checkpoint | A1 - Certificate of Conformance for all Precast Concrete Items
| checkpoint | A2 - Permacast ISO 9001 Certification
| section | B - PERMACAST'S DOCUMENTATION (approved and signed off)
| checkpoint | B1 - Register for Quality Plan, Inspection & Test Plans, Work Method Statements, Manufacturer's Data Reports
| checkpoint | B2 - Project Quality Management Plan and Work Method Statement
| checkpoint | B3 - Inspection & Test Plans (Approved copies)
| section | C - DRAWINGS - IFC and SHOP
| checkpoint | C1 - Register of IFC drawings
| checkpoint | C2 - Register of Shop Drawings
| checkpoint | C3 - Register of Lifting Designs
| section | D - CHANGE MANAGEMENT
| checkpoint | D1 - Technical Query Register
| checkpoint | D2 - Completed Technical Queries
| checkpoint | D3 - Non-Conformance Register
| checkpoint | D4 - Closed Out Non-Conformance Reports
| checkpoint | D5 - Defects Register
| checkpoint | D6 - Defects to be carried through to Defects Liability Period
| section | E - CONCRETE
| checkpoint | E1 - Concrete Supplier: ISO 9001 Certificate
| checkpoint | E2 - Aggregate Supplier: ISO 9001 Certificate
| checkpoint | E3 - Concrete Mix Designs
| checkpoint | E4 - CMRS Cement Certificate
| checkpoint | E5 - Concrete Aggregate Reports
| section | F - REINFORCEMENT
| checkpoint | F1 - Reinforcement Supplier: ISO 9001 Certificate
| checkpoint | F2 - ACRS Certificate
| checkpoint | F3 - Register of Mill Certificates
| checkpoint | F4 - Mill Certificates
| section | G - STRESSING (if applicable)
| checkpoint | G1 - Strand Supplier: ISO 9001 Certificate
| checkpoint | G2 - Register of Stressing Coils
| checkpoint | G3 - Mill Certificates
| checkpoint | G4 - Stressing Calculations
| section | H - CAST IN ITEMS
| checkpoint | H1 - Cast-in Items Compliance Records
| section | I - REINFORCEMENT WELDING (if applicable)
| checkpoint | I1 - Weld Procedure Specifications / WPQR
| checkpoint | I2 - Welder Qualification Register
| checkpoint | I3 - Welder Qualifications
| section | J - CALIBRATION OF INSPECTION, MEASURING AND TEST EQUIPMENT
| checkpoint | J1 - Register of NATA Laboratories Used for the Precast Project
| checkpoint | J2 - In-house Concrete Crusher Calibration Certificate
| checkpoint | J3 - Calibration of Jacks / Gauges (if applicable)
| checkpoint | J4 - Other Calibration Records
| section | K - DELIVERY OF PRECAST UNITS
| checkpoint | K1 - Register of Permacast IRC Certificates
| checkpoint | K2 - Permacast IRC Certificates
| checkpoint | K3 - Register of Permacast Conformance Certificates
| checkpoint | K4 - Permacast Conformance Certificates
| checkpoint | K5 - Register of Deliveries
| checkpoint | K6 - Delivery Dockets
| section | L - AUDITS
| checkpoint | L1 - Register of Audits
| checkpoint | L2 - Audit Reports