## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Fire door installation |  |  |  |  | Yes | POST - S - Fire door installation | 00cb5c42-5772-4d6f-8124-ced0d6fa552d
checkpoint-status |  |  | checkpoint | Door Number(s) / Location checked and accurate
checkpoint-status |  |  | checkpoint | Floor clearance - Adequate for proposed floor coverings
checkpoint-status |  |  | checkpoint | Services/Mechanisms & FRR/Acoustic requirements considered & applied (where applicable)
checkpoint-status |  |  | checkpoint | Fixings - Consider Jamb/Hinges, all installed & secure (Size & type)
checkpoint-status |  |  | checkpoint | Door leaf to jamb gaps parallel & correct (Consider paint thickness(s))
checkpoint-status |  |  | checkpoint | Door opening as required & is plumb
checkpoint-status |  |  | checkpoint | Door tags installed
checkpoint-status |  |  | checkpoint | All doors installed, damage free & completed correctly to specification in respective area(s)
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Flashing installation |  |  |  |  | Yes | FC - S - Flashing installation | 05b10e2a-a69a-4624-a72c-936b8d495d3f
checkpoint-status |  |  | checkpoint | Head flashing installed with sealant at windows and doors (STO system)
checkpoint-status |  |  | checkpoint | Rainshield installed between joinery and lintel (brick)
checkpoint-status |  |  | checkpoint | DPC and WANZ bar installed at the bottom of the joinery (see fixing) as per manufacturer's spec
checkpoint-status |  |  | checkpoint | Aluminium window jamb side flashings are installed
checkpoint-status |  |  | checkpoint | All flashing installed at windows and doors to specification & within tolerance in respective area(s)
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Timber Framing |  |  |  |  | Yes | ST - S - Timber Framing | 36040a3d-6503-449d-9b45-46706c029cc9
checkpoint-status |  |  | checkpoint | Dimensions / locations checked and accurate
checkpoint-status |  |  | checkpoint | All frames are square / Frames are plumb and level
checkpoint-status |  |  | checkpoint | Fixings are correct
checkpoint-status |  |  | checkpoint | Installed in correct level, plumb, correct pitch and braced
checkpoint-status |  |  | checkpoint | Any bracing requirements installed
checkpoint-status |  |  | checkpoint | All framing completed correctly within tolerance in respective area
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Insulation |  |  |  |  | Yes | PRE - S - Insulation | 472327a1-ed98-4e93-8333-8d13dba46a86
checkpoint-status |  |  | checkpoint | All materials checked & aligning with consented design & specifications prior to install
checkpoint-status |  |  | checkpoint | Correct product & R value as per specification
checkpoint-status |  |  | checkpoint | All Insulation completed correctly to specification & within tolerance in respective area(s)
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Gutters |  |  |  |  | Yes | FC - S - Gutters | 4777c329-2ec0-452d-8a4c-bb17b312351d
checkpoint-status |  |  | checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint-status |  |  | checkpoint | Framing Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint-status |  |  | checkpoint | All frames have been installed square, straight and plumb
checkpoint-status |  |  | checkpoint | DPC installed (if required) correctly
checkpoint-status |  |  | checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint-status |  |  | checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint-status |  |  | checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Skirting/ Architraves & Trims |  |  |  |  | Yes | POST - S - Skirting/ Architraves & Trims | 5e0bd451-5aea-4cd7-8a40-58f077adc064
checkpoint-status |  |  | checkpoint | Architraves/ skirtings & trims are the correct size and profile
checkpoint-status |  |  | checkpoint | Skirting boards have been properly scribed, sanded, glued and mitred
checkpoint-status |  |  | checkpoint | Architraves/skirtings & trims have been installed with consistent even margins
checkpoint-status |  |  | checkpoint | Skirting/Architraves & trim work completed - specified level of finish achieved
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Tapes and VaproShield |  |  |  |  | Yes | FC - R - Tapes and VaproShield | 7383ea86-1611-43b5-a3e8-f804b559cf3c
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Sign Off
checkpoint-status |  |  | checkpoint | Tapes/VaproShield works completed and acceptable
checklist-flat |  |  | checklist | Internal door installation |  |  |  |  | Yes | POST - S - Internal door installation | 9e8a240c-f7ea-4d10-9c4c-3aa7981ad722
checkpoint-status |  |  | checkpoint | Door Number(s) / Location checked and accurate
checkpoint-status |  |  | checkpoint | Floor clearance - Adequate for proposed floor coverings
checkpoint-status |  |  | checkpoint | Fixings - Consider Jamb/Hinges/Door Packer, all installed & secure (Size & type)
checkpoint-status |  |  | checkpoint | Door leaf to jamb gaps parallel & correct (Consider paint thickness(s))
checkpoint-status |  |  | checkpoint | Door opening as required & is plumb
checkpoint-status |  |  | checkpoint | All doors installed, damage free & completed correctly to specification in respective area(s)
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | Nogs |  |  |  |  | Yes | PRE - S - Nogs | a06dce66-903f-44ea-bddf-38b3019e92d7
checkpoint-group |  |  | section | Service Nogs Toilet
checkpoint-status |  |  | checkpoint | Wall Vanity nogs installed
checkpoint-status |  |  | checkpoint | Handrail and Toilet roll holder Nogs installed
checkpoint-group |  |  | section | Bathroom
checkpoint-status |  |  | checkpoint | Mirror cabinet nogs installed
checkpoint-status |  |  | checkpoint | Wall Vanity nogs installed
checkpoint-status |  |  | checkpoint | Toilet: Handrail nogs Installed
checkpoint-status |  |  | checkpoint | Shower: Handrails nogs (3 areas) installed
checkpoint-status |  |  | checkpoint | Wall Mounted Heater nog installed
checkpoint-status |  |  | checkpoint | Towel rail nogs installed
checkpoint-status |  |  | checkpoint | Shower head nog installed
checkpoint-status |  |  | checkpoint | Shower mixer nog installed
checkpoint-group |  |  | section | Laundry
checkpoint-status |  |  | checkpoint | Dryer nogs installed
checkpoint-status |  |  | checkpoint | Cupboard nogs installed
checkpoint-group |  |  | section | Service Nogs General
checkpoint-status |  |  | checkpoint | Nogs / Service Nogs installed correctly as per plan
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Windows, Sliders and Sealants |  |  |  |  | Yes | FC - S - Windows, Sliders and Sealants | b476e960-5008-411d-b16b-433dc7546e7c
checkpoint-status |  |  | checkpoint | Fixings and clearance around opening min 6mm & max 18mm and PEF rod/air seal are within acceptable tolerance level
checkpoint-status |  |  | checkpoint | Check taping around, before installing the windows and sliders
checkpoint-status |  |  | checkpoint | Packers to be correctly used and set back to allow continuous air seal
checkpoint-status |  |  | checkpoint | Jambs level and straight for finishing lines on the side
checkpoint-status |  |  | checkpoint | Door and window jambs flush to GIB Board
checkpoint-status |  |  | checkpoint | Check air seal is provided at the rear of the window reveal
checkpoint-status |  |  | checkpoint | All joints detailed as per attached Detail Document
checkpoint-status |  |  | checkpoint | All framing completed correctly within tolerance in respective area
checkpoint-status |  |  | checkpoint | Sill support fixing bars installed for all joinery within acceptable tolerance level
checkpoint-status |  |  | checkpoint | All windows, sliders and sealant installation completed to specification & within tolerance in respective area(s)
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Exterior Timber Framing |  |  |  |  | Yes | FC - S - Exterior Timber Framing | ca73ba22-e116-43d7-baa4-062a5c4f8296
checkpoint-status |  |  | checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint-status |  |  | checkpoint | Framing Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint-status |  |  | checkpoint | All frames have been installed square, straight and plumb
checkpoint-status |  |  | checkpoint | DPC installed (if required) correctly
checkpoint-status |  |  | checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint-status |  |  | checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint-status |  |  | checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | RAB |  |  |  |  | Yes | FC - S - RAB | e8fab537-449f-4499-9e6b-50a4da9846e7
checkpoint-status |  |  | checkpoint | Fixing and spacings checked in accordance with manufacturers specs
checkpoint-status |  |  | checkpoint | White MS sealant for air seals between RAB board and concrete horizontal and vertical joints
checkpoint-status |  |  | checkpoint | 3M taping around windows and external corners and vertical joints and horizontal flashing checked
checkpoint-status |  |  | checkpoint | Vaproshield to interfloor installed after vertical taping
checkpoint-status |  |  | checkpoint | Bracing checked and accurate
checkpoint-status |  |  | checkpoint | Penetrations and punctures sealed with flashing tape
checkpoint-status |  |  | checkpoint | Sealing joints over internal and external joints
checkpoint-status |  |  | checkpoint | Batten on RAB Board for cladding fixings
checkpoint-status |  |  | checkpoint | All RAB board installation completed to specification & within tolerance in respective area(s)
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | CST - S - Completion Documents | eeead6bb-e984-459e-88b2-699f7c3dc92a
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
boolean | da61c635-5ffd-5584-9806-de264908a6b7 |  | tickbox | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | 349fa2ad-bb35-5727-9c24-43f9e09b51ab |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Lintels |  |  |  |  | Yes | FC - R - Lintels | fc2d441f-cbc0-4b25-9903-f6e61b214b68
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Sign Off
checkpoint-status |  |  | checkpoint | Lintels completed and acceptable