## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Pre-commencement checks |  |  |  |  | Yes | Pre-commencement checks | 2ae34005-6a22-4665-8470-228b2e3cbe85
checkpoint-status |  |  | checkpoint | Quality Management Plan Completed, Agreed & Attached
checkpoint-status |  |  | checkpoint | Inspection & Test Plan Completed, Agreed & Attached
checkpoint-status |  |  | checkpoint | Relevant Breakdown & Checklists Setup on Conqa & Reviewed by Main Contractor
checkpoint-status |  |  | checkpoint | Conqa Setup & Project Team Trained & Given Access
checkpoint-status |  |  | checkpoint | Review Access Granted to Main Contractor & Relevant Parties
checkpoint-status |  |  | checkpoint | Matrix/insights Setup (if required)
checklist-flat |  |  | checklist | Handover Checklist |  |  |  |  | Yes | Handover Checklist | f76de213-5d1f-4adf-85c9-996c83a53c2f
checkpoint-status |  |  | checkpoint | PS3 - BCO10328723
checkpoint-status |  |  | checkpoint | Product Warranty
checkpoint-status |  |  | checkpoint | Record of Building
checklist-flat |  |  | checklist | FC - S - Fascia/Gutter |  |  |  |  | Yes | FC - S - Fascia/Gutter | ff69cd15-90be-4b33-a206-eea8097c45f7
checkpoint-status |  |  | checkpoint | Size checked and accurate
checkpoint-status |  |  | checkpoint | Fixings installed (2-4 photos attached)
checkpoint-status |  |  | checkpoint | Installation and size of downpipes checked
checkpoint-status |  |  | checkpoint | Installation of downpipe rainwater heads checked
checkpoint-status |  |  | checkpoint | Rainwater heads checked and accurate (2-4 photos attached)
checkpoint-status |  |  | checkpoint | Paint - specified level of finish achieved
checkpoint-status |  |  | checkpoint | Fascia installation completed (2-4 photos attached)
holdpoint |  |  | signoff | Request sign off
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS