## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Timber Architraves & Skirtings & Jamb liners |  |  |  |  | Yes | Internal Checklists - Timber Architraves & Skirtings & Jamb liners | 1f297ae3-372b-43a4-9d51-0221c19f6ba6
checkpoint-status |  |  | checkpoint | Type of skirtings as per drawings
checkpoint-status |  |  | checkpoint | Type of architraves installed as per drawings
checkpoint-status |  |  | checkpoint | Have all the architraves/skirtings been installed with consistent even margin?
checkpoint-status |  |  | checkpoint | Jamb liners installed
checklist-flat |  |  | checklist | External Framing ( Post Weatherline ) |  |  |  |  | Yes | External Framing ( Post Weatherline ) | 25166602-22a4-48ca-b367-c3f940e58d5b
checkpoint-status |  |  | checkpoint | Plywood strip installed to take steel brick edge angle
checkpoint-status |  |  | checkpoint | Wrap shield installed into window openings with liquid flash
checkpoint-status |  |  | checkpoint | Wrap shield installed to face of weatherline / interstory installed if req
checkpoint-status |  |  | checkpoint | Soffit framing and linings to balconies
checkpoint-status |  |  | checkpoint | Additional nogs for exterior face ( that will be installed from interior )
checkpoint-status |  |  | checkpoint | Rotheblass or Simpson brackets installed as per S1-03
checklist-flat |  |  | checklist | External Framing v2 |  |  |  |  | Yes | External Framing v2 | 4e38857e-a818-462f-81e6-7b22276d9e5c
checkpoint-status |  |  | checkpoint | General info/comments recorded
checkpoint-status |  |  | checkpoint | Walls in correct location off grid
checkpoint-status |  |  | checkpoint | Walls built within building tolerances.
checkpoint-status |  |  | checkpoint | DPC under bottom plate against concrete
checkpoint-status |  |  | checkpoint | M16 threaded rods/epoxy installed at correct centres
checkpoint-status |  |  | checkpoint | Timber framing installed at correct centres and size of timber as per drawings
checkpoint-status |  |  | checkpoint | Amount of timber studs per wall type installed and at wall junctions.
checkpoint-status |  |  | checkpoint | All external openings ( doors and windows ) checks, correct openings and approved
checkpoint-status |  |  | checkpoint | Building Hardware installed on exterior face, i.e. tylok plates
checkpoint-status |  |  | checkpoint | Correct lintel sizes installed as per dwgs S1-03 / S8-10
checkpoint-status |  |  | checkpoint | Plywood strip installed to take steel brick edge angle
checkpoint-status |  |  | checkpoint | Wrap shield installed into window openings with liquid flash
checkpoint-status |  |  | checkpoint | Wrap shield installed to face of weatherline / interstory installed if req
checkpoint-status |  |  | checkpoint | Soffit framing and linings to balconies
checkpoint-status |  |  | checkpoint | Additional nogs for exterior face ( that will be installed from interior )
checkpoint-status |  |  | checkpoint | Rotheblass or Simpson brackets installed as per S1-03
checklist-flat |  |  | checklist | External Framing ( Pre Weatherline ) |  |  |  |  | Yes | External Framing ( Pre Weatherline ) | 5398631e-843e-4d85-8a85-f6c34cffecf2
checkpoint-status |  |  | checkpoint | General info/comments recorded
checkpoint-status |  |  | checkpoint | Walls in correct location off grid
checkpoint-status |  |  | checkpoint | Walls built within building tolerances.
checkpoint-status |  |  | checkpoint | DPC under bottom plate against concrete
checkpoint-status |  |  | checkpoint | M16 threaded rods/epoxy installed at correct centres
checkpoint-status |  |  | checkpoint | Timber framing installed at correct centres and size of timber as per drwgs
checkpoint-status |  |  | checkpoint | Amount of timber studs per wall type installed and at wall junctions.
checkpoint-status |  |  | checkpoint | All external openings ( doors and windows ) checks, correct openings and approved
checkpoint-status |  |  | checkpoint | Building Hardware installed on exterior face, i.e. tylok plates
checkpoint-status |  |  | checkpoint | Correct lintel sizes installed as per dwgs S1-03 / S8-10
checklist-flat |  |  | checklist | Timber Architraves & Skirtings & Jamb liners |  |  |  |  | Yes | Timber Architraves & Skirtings & Jamb liners | 8ba7a5f1-5364-4ea0-bfa4-577290da1662
checkpoint-status |  |  | checkpoint | Type of skirtings as per drawings
checkpoint-status |  |  | checkpoint | Type of architraves installed as per drawings
checkpoint-status |  |  | checkpoint | Have all the architraves/skirtings been installed with consistent even margin?
checkpoint-status |  |  | checkpoint | Jamb liners installed
checklist-flat |  |  | checklist | Interior Framing |  |  |  |  | Yes | Internal Checklists - Interior Framing | 996d42fa-61ad-4a89-8674-3805119d561d
checkpoint-status |  |  | checkpoint | Structural Steel QA received and correct
checkpoint-status |  |  | checkpoint | General information recorded
text | 91a7b2c8-282b-586c-8ea5-cd0a6ca55a00 |  | textbox | installed as per wall type
text | 9e9df509-6af4-5f76-8183-437937d4b303 |  | textbox | Correct timber size/treatment installed
checkpoint-status |  |  | checkpoint | DPC installed, checked and correct as per specification
checkpoint-status |  |  | checkpoint | Wall locations checked, correct and approved as per latest revised drawing
checkpoint-status |  |  | checkpoint | Fixings and hold down bolts checked and correct as per structural dwgs
checkpoint-status |  |  | checkpoint | All openings (doors / windows etc) checked - Refer door supplier shop drawings
boolean | 4b2b2591-3d1e-5616-9977-5cc9c2780965 |  | tickbox | Track locks installed
checkpoint-status |  |  | checkpoint | Wall checked (straight and plumb) and within tolerance
checkpoint-status |  |  | checkpoint | Spax screws installed as per structural design
checkpoint-status |  |  | checkpoint | Bracing elements installed as per S1-03
checkpoint-status |  |  | checkpoint | Gib quiet ties installed
checkpoint-status |  |  | checkpoint | All relevant nogs (service and special/fixtures) installed, checked and correct
boolean | fa87182d-d6bb-518b-93c0-3404c6016640 |  | tickbox | Service nogs checked and approved
boolean | 40a60a36-215f-5429-ab4e-ab2a23afc132 |  | tickbox | All other nogs checked and approved
checkpoint-status |  |  | checkpoint | All Wall framing checks completed & Inspections carried out
checklist-sectioned |  |  | checklist | External Framing v1 |  |  |  |  | Yes | External Framing v1 | a17b81df-97c1-4035-9124-ce30b666e104
checkpoint-group |  |  | section | Pre Weatherline
checkpoint-status |  |  | checkpoint | General info/comments recorded
checkpoint-status |  |  | checkpoint | Walls in correct location off grid
checkpoint-status |  |  | checkpoint | Walls built within building tolerances.
checkpoint-status |  |  | checkpoint | DPC under bottom plate against concrete
checkpoint-status |  |  | checkpoint | M16 threaded rods/epoxy installed at correct centres
checkpoint-status |  |  | checkpoint | Timber framing installed at correct centres and size of timber as per drawings
checkpoint-status |  |  | checkpoint | Amount of timber studs per wall type installed and at wall junctions.
checkpoint-status |  |  | checkpoint | All external openings ( doors and windows ) checks, correct openings and approved
checkpoint-status |  |  | checkpoint | Building Hardware installed on exterior face, i.e. tylok plates
checkpoint-status |  |  | checkpoint | Correct lintel sizes installed as per dwgs S1-03 / S8-10
checkpoint-group |  |  | section | Post Weatherline
checkpoint-status |  |  | checkpoint | Plywood strip installed to take steel brick edge angle
checkpoint-status |  |  | checkpoint | Wrap shield installed into window openings with liquid flash
checkpoint-status |  |  | checkpoint | Wrap shield installed to face of weatherline / interstory installed if req
checkpoint-status |  |  | checkpoint | Soffit framing and linings to balconies
checkpoint-status |  |  | checkpoint | Additional nogs for exterior face ( that will be installed from interior )
checkpoint-status |  |  | checkpoint | Rotheblass or Simpson brackets installed as per S1-03
checklist-flat |  |  | checklist | Doors |  |  |  |  | Yes | Doors | bbd12195-77c1-4b48-a7c9-4dd4e421a61c
checkpoint-status |  |  | checkpoint | Door opening checked and correct
checkpoint-status |  |  | checkpoint | Floor clearance correct
checkpoint-status |  |  | checkpoint | Fireseal around door installed as per spec if needed
checkpoint-status |  |  | checkpoint | Door jambs are plumb and level
checklist-flat |  |  | checklist | Doors |  |  |  |  | Yes | Internal Checklists - Doors | d74edfac-a565-44d2-9e20-1f0944cbe189
checkpoint-status |  |  | checkpoint | Check opening is correct and plumb
checkpoint-status |  |  | checkpoint | Doors installed within tolerances
checkpoint-status |  |  | checkpoint | Fire seal installed if fire door
checkpoint-status |  |  | checkpoint | Floor gap is correct
checklist-flat |  |  | checklist | Interior Framing |  |  |  |  | Yes | Interior Framing | dc47df2b-4a53-481c-aeca-56496857d7d4
checkpoint-status |  |  | checkpoint | Structural Steel QA received and correct
checkpoint-status |  |  | checkpoint | General information recorded
text | 31b7f60d-fc8a-5da9-8fb8-3291b15f1d9d |  | textbox | installed as per wall type
text | 0ea36e13-aad9-5bca-bb04-97870647001b |  | textbox | Correct timber size/treatment installed
checkpoint-status |  |  | checkpoint | DPC installed, checked and correct as per specification
checkpoint-status |  |  | checkpoint | Wall locations checked, correct and approved as per latest revised drawing
checkpoint-status |  |  | checkpoint | Fixings and hold down bolts checked and correct as per structural dwgs
checkpoint-status |  |  | checkpoint | All openings (doors / windows etc) checked - Refer door supplier shop drawings
boolean | 3b70b1e1-b5c9-5726-83cc-be70639f3378 |  | tickbox | Deflection heads type installed and correct / Track locks
checkpoint-status |  |  | checkpoint | Wall checked (straight and plumb) and within tolerance
checkpoint-status |  |  | checkpoint | Bracing elements installed as per S1-03
checkpoint-status |  |  | checkpoint | Gib quiet ties installed
checkpoint-status |  |  | checkpoint | All relevant nogs (service and special/fixtures) installed, checked and correct
boolean | c43b6bff-0d5d-5e7e-925b-68db833fbd89 |  | tickbox | Service nogs checked and approved
boolean | 2f5a2373-7bb1-520d-b347-4ba3e67ca96f |  | tickbox | All other nogs checked and approved
checkpoint-status |  |  | checkpoint | All Wall framing checks completed & Inspections carried out