## General
Modify template as required prior to use, e.g. to accommodate project or customer specific requirements, then delete this instructional text when complete.
SECTION 1 – GENERAL DETAILS
Project Name: | Seacliff Wastewater Treatment and Disposal Upgrade |  |  |  |  | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | 561469 |  |  |  |  | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Dunedin City Council |  |  |  |  | B | Report by Breach | CM | Construction Manager
Contract Number: | 9776 |  |  |  |  | C | Check | CR | Cust. Representative
Area/ Sub-System: |  |  | Lot ID Number: |  |  | D | Dimension Inspection | IP | Inspection Personnel
[6 empty] | E | Examine | MC | Material Controller
ITP Number: | 1 |  | Version: | 1 |  | H | Hold Point | OP | Operations Manager
ITP Description: | Culverts |  |  |  |  | I | Inspection | PM | Project Manager
Discipline: | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor
Specification: | Seacliff Watewater Treatment Plant Upgrade |  |  |  |  | O | Operation | QE | Quality Engineer
[6 empty] | R | Review | QM | QA Manager
Drawings: | 310103025-01-001-C101 to C103, C110 to C112 and C152 to C153 |  |  |  |  | S | Subcontractor | SP | Supervisor
[6 empty] | V | Visual Verification | ST | Superintendent
Prepared By: (Name) | Sebastian Charlin |  | Date: | 2023-10-30 |  | W | Witness Point | SV | Surveyor
Quality Specified: | [7 empty] | WS | Welding Supervisor
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key) | Signature
3.1 | Review all Drawings and Documents | Review all drawings and documentation provided to the Contractor. | Prior to the commencement of Works it must be ensure that all necessary documentation has been provided. | ITP | Prior to the commencement of Works | Visual | R | PM/QE
3.2 | Setting Out Levels and Alignment | All setting out shall be performed by or under the control of a licensed surveyor, who shall certify the accuracy of key dimensions of the as constructed works. Specs 1000: 3.2.4 | Levels and allignment Set Out matches marks shown on the Drawings, 2D data and linework provided or agreed with the Engineer | Compliance surveys or spot checks | Prior to the commencement of Works | Visual, Instrumental | H | SP/QE/SV
3.3 | Service location and Hydro Vacumming | Physically locate the services inside and close to the alignment area and levels depth. Specs 1131: 15.2.1 | All services identified in B4UDig, plans and mark outs has been physically located | Plans Mark out, photos | Prior to the commencement of Works | Visual | H | CR
3.4 | Pipes Delivery | Pipes and pipe fittings shall be of the material, pipe class and joint type nominated on the Drawings. Specs 1131: 14.1 and Drawings C152 - C153 | The charasteritics of the pipes delivered to site match the corresponding drawings details or approved equivalent | Delivery docket, Supplier certificate, Photo | Prior to the commencement of Works | Visual | C | QE/CR
3.5 | Drainage Pipes Delivery | Drainage pipes shall be slotted smooth bore PVC or PE pipes, or corrugated polyethylene subsoil drainage pipes in accordance with NZTA F/5 for light duty applications or NZTA F2 for heay-duty applications. Specs 1131: 14.8 | The charasteritics of the pipes delivered to site match the specifications and the duty requirments or approved equivalent | Delivery docket, Supplier certificate, Photo | Prior to the commencement of Works | Visual | C | QE/CR
3.6 | Subsoil drain bedding | Material used for bedding, duct surround and haunching shall be selected granular, non cohesive, free draining material with grading between 0.6mm and 19mm. Maximum Dry Density (MDD) and Optimum Water Content (OWC) of the aggregate must be provided. Specs 1131: 14.8 | Visual Inspection, Engineer approval | Delivery Docket, Laboratory test results | Prior to the commencement of Works | Visual, Lab Test | H | QE/SP/MC
3.7 | Pipe Bedding Agregate | Pipe bedding should be AP20 and in accordance with AS/NZS 2566.2. Maximum Dry Density (MDD) and Optimum Water Content (OWC) of the aggregate must be provided. Specs 1131: 14.9.1 | Visual Inspection, Engineer approval | Delivery Docket, Laboratory test results | Prior to the commencement of Works | Visual, Lab Test | H | QE/SP/MC
3.8 | Drainage Aggregate | Drainage aggregate shall be 19 mm uniformly graded, clean, durable aggregate having a crushing resistance of not less than 100 kN when tested in accordance with NZS 4407. Material used for backfilling the trench above any geotextile wrapping shall be free draining granular material. Specs 1131: 14.9.2 | Visual Inspection | Delivery docket, Supplier certificate, Photo | Prior to the commencement of Works | Visual | C | QE/SP/MC
3.9 | Backfill Aggregate | Backfill aggregate should be GAP 65. Samples of backfill material should be tested in accordence of NZS 4402 to determine the MDD at OMC. The solid density of aggregate should be tested in accordance with NZS 4407. Specs 1131: 16.1.1 | Visual Inspection, Engineer approval | Delivery Docket, Laboratory test results | Prior to the commencement of Works | Visual, Lab Test | H | QE/SP/MC
3.10 | Concrete Manhole | Precast concrete manholes shall comply with NZS 3106. Specs 1131: 14.5 | Manhole charasteritics Match NZS 3106 | Delivery docket, Supplier certificate, Photo | Prior to the commencement of Works | Visual | C | QE/SP/MC
3.11 | Wingwalls | Precast wingwalls as specified in Drawings or equivalent approved. Drawings C122 - C123 | Procured precast wingwall comply with specifications | Delivery docket, Photo, Engineer approval | Prior to the commencement of Works | Visual | C | QE/SP/MC
3.12 | Geotextile | Geotextile underlay bidim A37 or similar approved material. Drawings C122 - C123 | Procured Geotextile comply with specifications | Delivery docket, Photo, Engineer approval | Prior to the commencement of Works | Visual | C | QE/SP/MC
3.13 | Backfill Trail Compaction Testing | Prior to commencement of fill compaction. Trial compaction plateau test should be conducted under presense of Engineer or principal. Methodology to be confirmed in advance generally in accordance with TNZ B/02 specification. Specs 1131: 16.1.1, 16.1.2, 16.1.4. | Compaction Value ≥ Specification Value | Nuclear Density Meter (NDM) Results Sheet, or Clegg Hamer test records | Prior to the commencement of Works. | On site Test | H | QE/CR

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key) | Signature
4.1 | Site Clearance | The material obtained from site celarance must be dumped at an approved location outside the Site. Specs 1100: 5.1 | Location approved by the Engineer | Dumping Docket | After site clearance | Document Check | C | QE/SP/CR
4.2 | Trees Removal | No tree shall be cut down until the Engineer has given written authorisation for such work to commence. Specs 1100: 6.2 | Engineer Approval | Engineer Writen Authorisation | Before remove any tree | Client Consultation | H | CR
4.3 | Removal of Topsoil | Topsoil shall be stockpiled in areas approved by the Engineer for this purpose. stockpiling operations must ensure the maximum utilisation of each area. Specs 1110: 9.4, TNZ F/1 Clause 4 | Engineer Approval | Engineer Writen Authorisation | Before Topsoil Removal | Client Consultation | C | CR
4.4 | Hazardous Waste and Contaminated soils | Contaminated soils (Type H materials) encountered shall be treated and/or disposed off site in accordance with statutory requirements. Specs 1110: 9.3 | Dumping site approval for contamiantion type | Dumping Docket | If constaminated soils are found | Document Check | C | QE/SP/CR
4.5 | Trench Excavation | Trenches for flexible pipes shall be excavated within tollerances in table from Specs 1131: 15.2.5 unless otherwise stated. | Trench width and pipe clearance to walls comply with requirements | Installation Check Sheet | During trench excavation | Visual, Measurement Check | C | QE/SP
4.6 | Pipe Bedding and Haunching | Bedding and Haunching for flexible pipes should be in accordance with AS/NZS 2556.2 and have minimum embedment zone as shown in tabke from Specs 1131: 15.2.8.2 | Bedding and haunching high and with comply width requirements | Installation Check Sheet | During bedding and haunching installation | Visual, Measurement Check | C | QE/SP
4.7 | Pipe Line and Level | Pipes shall be laid true to the design line and level within the tolerances specified in Specs 1131: 15.9. Invert levels shall take precedence over depths. Specs 1131: 15.3.12 | Pipe levels are within the tolerance and according to the drawings, 2D data and linework provided or agreed with the Engineer | Grade Check sheet | During pipe installation | Visual, Instrumental | C | SP/QE/SV
4.8 | PE Pipe Installation | Buried PE pipes shall be installed in accordance with AS/NZS 2033 and AS/NZA 2566.2, as applicable. Specs 1131: 15.3.2.2 | PE Pipe Joints and Intallation comply with standard and specifications | Pipe welds QA records, welding checksheets and machine printouts, destructive tests results (if required) | Per weld, and during pipe installation | Visual, Document Check, Lab test (if required) | C | QE/SP
4.9 | PVC Pipe Installation | Buried PVC pipes shall be installed in accordance with AS/NZS 2032 and AS/NZS 2566.2, as applicable. Fusible PVC pipes shall be welded and installed in accordance with the pipe manufacturers recommendations. Specs 1131: 15.3.1. | PVC Pipes Joints and Intallation comply with standard and specifications | Methodology, Pipe welds QA records, welding checksheets and machine printouts, destructive tests results (if required) | Per joint or weld, and during pipe installation | Visual, Document Check, Lab test (if required) | C | QE/SP
4.10 | Precast Concrete Pipe Installation | Joints between precast pipe units shall be self-centering and shall be sealed with butyl mastic or similar approved to form a watertight joint. Concrete pipes shall be installed in accordance with AS/NZS 3725. Specs 1131: 15.3.6 | Precast concrete pipes Joints and Intallation comply with standard and specifications | Methodology. QA records | Per joint, and during pipe installation | Visual | C | QE/SP
4.11 | Aggregate Compaction | Compaction shall be as stated in Specs 1131: 15.4.4. For concrete pipes the verification testing of compaction shall use a method recommended in table 3 of the CPAA Technical Note on Installing Concrete Pipe and approved by the Engineer. Specs 1131: 15.3.6 | Compaction Value ≥ Specification Value | Depending of Pipe material or Aggregate: CBR Checksheet, Nuclear Density Meter (NDM) Results Sheet, Clegg Hamer test records | Every 50m of trench (not confirmed) or specified by Engineer | On site Test | H | QE/CR
4.12 | Backfill Compaction | Selected fill within 0.8m depth from finished surface shall be AP 65. Subgrade and subbase shall be compacted in layers no greater than 200 mm thick unless otherwise agreed with the Engineer. Under carriageway basecourse shall be compacted in layers no greater than 150mm thick unless otherwise aggred with the engineer. Specs 1131: 15.4.3.2, 15.4.3.3 | Dry Density ≥ 95% MDD (Under Carriageway). Dry Density ≥ 90% MDD (Outside Carriageway) | Nuclear Density Meter (NDM) Results Sheet or Clegg Hamer test records | Every 20m of trench, each layer (Under Carriageway) Every 50m of trench, each layer (Outside Carriageway) | On site Test | H | QE/CR
4.13 | Cutting pipes | Where pipes need to be cut to form non-stardard lengths, pipes shall be cut by a method which complies with manufacturers recommendations and provides a clean square profile. Specs 1131: 15.3.7 | Pipe cutted up to the specifications | Methodology, Photos | During pipe installation | Visual | C | QE/SP
4.14 | Manhole Benching | Benching concrete shall have a crushing strength of 20MPa at 28 days. Semi-circular channels and fittings shall be placed in possition simultaneously with concrete benching and be embedded in true to grade level and line. All benching and sloping surfaces on manhole floor shall be rendered in 20mm thick 1:3 mortar and finished with steel trowel and rounded at corners. Specs 1131: 15.5 | Benching built up to the specifications | Methodology, Delivery Dockey, Photos | During benching contruction | Visual | C | QE/SP
4.15 | Subsoil Drains Installation | Drains shall be constructed, geotextile layed and backfill carried out in accordance with TNZ Specification F/6. Specs 1131: 15.7 | Benching built up to the specifications | Methodology, TNZ Specifications F/6 and F/7, Photos, QA records | During Drains Installation | Visual | C | QE/SP
4.16 | Topsoiling and grassing | Topsoil shall be used to dress areas disturbed by the contrat works to a minimum thickness of 100mm. Grass seed shall be sown evenly over the prepared topsoil area. Specs 1131: 15.8.6 | Topsoil installed and grass seed spread in the specified rate and mixture. | QA records, Photos | After compaction of final layer of backfill | Visual | C | QE/SP
4.17 | Rock Riprap Instllation | Rock riprap shall comply with the dimensions and specifications shown in drawings. Drawings C123, C 152 - C155 | Rock rip rap intalling according dimensions and specifications shown in cross sections of project drawings | Installation Check Sheet, QA records, Photos | During rock riprap installation | Visual, Measurement Check | C | QE/SP

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key) | Signature
5.1 | As-built Drawings | Two hard copies and one electronic copy of As-built drawings shall be prepared in draft and final versions following Schedule 1D in NZS4404:2010. Specs 1000: 3.9.2 | Engineer Approval | QA records | At completion | - | H | QE/CR
5.2 | Gravity Pipes Testing | Stormwater pipes shall be by visual inspection for pipe diameters greater than 750mm and by water testing for diameters up to 750mm. Testing shall be in the presence of the engineer. Specs 1131: 16.2.1 | Engineer Approval | Test Records | For every section of pipe installed (24hr prior notice to the engineer before test) | Test | H | QE/CR
5.3 | Manholes | Manholes should be tested seperately to pipeline for water tightness up to lower rim of manhole cover frame. Testing shall be in the presence of the engineer. Specs 1131: 16.2.2.5 | A maximum drop in water level over 30 min should not exceed 2mL/hr/mm of diameter/meter height of the manhole. Engineer Approval | Test Records | For every manhole installed (24hr prior notice to the engineer before test) | Test | H | QE/CR
5.4 | CCTV Inspection | All pipelines shall pass a CCTV instpection. All pipelines shall be free of debris and flushed 24hrs prior to inspection. Specs 1131: 16.2.3 | A pipeline will fail its inspection if: - The pipe is horizontally misaligned or deformed by more than 5 % of the pipe diameter. - The pipe has visible dips or ponding of water. - The pipe has visible defects, such as open or displaced joints, defective or protruding laterals, cracked barrels or similar defects. - There is evidence of infiltration at joints or laterals. | CCTV footage and log sheets | At every section of pipe installed. | Visual | H | QE/CR
5.5 | Surplus Materials and Refuse Disposal | All surplus, redundant and faulty materials must be removed from the Site and dispose of them in a safe and legal manner. Any demolition material or rubbish coming from the execution of the project must be removed as well. Specs 1000: 3.13.2 | - | - | At completion | Visual | C | QE/SP/CR
5.6 | Cleaning | Completed items of construction about to be placed in service or occupied for their intended use must be properly and thoroughly cleaned of all foreign matter and other debris. Specs 1000: 3.13.3 | - | - | At completion | Visual | C | QE/SP/CR
SECTION 6 – COMMENTS
|  |  | Customer Release Granted: | ☐ Yes | ☐ No | Date:
Certificate Number: