## General
Modify template as required prior to use, e.g. to accommodate project or customer specific requirements, then delete this instructional text when complete.
SECTION 1 – GENERAL DETAILS
Project Name: | Seacliff Wastewater Treatment and Disposal Upgrade |  |  |  |  | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | 561469 |  |  |  |  | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Dunedin City Council |  |  |  |  | B | Report by Breach | CM | Construction Manager
Contract Number: | 9776 |  |  |  |  | C | Check | CR | Cust. Representative
Area/ Sub-System: |  |  | Lot ID Number: |  |  | D | Dimension Inspection | IP | Inspection Personnel
[6 empty] | E | Examine | MC | Material Controller
ITP Number: | 10 |  | Version: | 1 |  | H | Hold Point | OP | Operations Manager
ITP Description: | Footpaths and Steps |  |  |  |  | I | Inspection | PM | Project Manager
Discipline: | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor
Specification: | Seacliff Watewater Treatment Plant Upgrade |  |  |  |  | O | Operation | QE | Quality Engineer
[6 empty] | R | Review | QM | QA Manager
Drawings: | 310103025-01-001-C101 to C113 and C151 |  |  |  |  | S | Subcontractor | SP | Supervisor
[6 empty] | V | Visual Verification | ST | Superintendent
Prepared By: (Name) | Sebastian Charlin |  | Date: | 2023-11-03 |  | W | Witness Point | SV | Surveyor
Quality Specified: | [7 empty] | WS | Welding Supervisor
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key) | Signature
3.1 | Review all Drawings and Documents | Review all drawings and documentation provided to the Contractor. | Prior to the commencement of Works it must be ensure that all necessary documentation has been provided. | ITP | Prior to the commencement of Works | Visual | R | PM/QE
3.2 | Design Approval | Footpaths and steps are provisional items and shall only be constructed if approved by the Engineer. Specs 1230: 27 | Engineer's Approval | Engineer Writen Approval | Prior to the commencement of construction of any footpath or steps | - | H | QE/CR
3.3 | Setting Out Levels and Alignment | All setting out shall be performed by or under the control of a licensed surveyor, who shall certify the accuracy of key dimensions of the as constructed works. Specs 1000: 3.2.4 | Levels and allignment Set Out matches marks shown on the Drawings, 2D data and linework provided or agreed with the Engineer | Compliance surveys or spot checks | Prior to the commencement of Works | Visual, Instrumental | H | SP/QE/SV
3.4 | Service location and Hydro Vacumming | Physically locate the services inside and close to the alignment area and levels depth. Specs 1131: 15.2.1 | All services identified in B4UDig, plans and mark outs has been physically located | Plans Mark out, photos | Prior to the commencement of Works | Visual | H | CR
3.5 | Use of Local Material | Borrow pits are generally a hole dug in the ground from which material is removed and used on the track. Dept. of Consevation Track Construction and Maintenance Guidelines: 13.4, 13.7 | Local Materail is any of the following: - Firm clay/silt soils - Sands/gravels - Boulder clay - Weathered rock If not, import. | Photos, Delivery Docket | Prior to the commencement of Works | Visual | C | SP/QE

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key) | Signature
4.1 | Site Clearance | The material obtained from site celarance must be dumped at an approved location outside the Site. Specs 1100: 5.1 | Location approved by the Engineer | Dumping Docket | After site clearance | Document Check | C | QE/SP/CR
4.2 | Trees Removal | No tree shall be cut down until the Engineer has given written authorisation for such work to commence. Specs 1100: 6.2 | Engineer Approval | Engineer Writen Authorisation | Before remove any tree | Client Consultation | H | CR
4.3 | Removal of Topsoil | Topsoil shall be stockpiled in areas approved by the Engineer for this purpose. stockpiling operations must ensure the maximum utilisation of each area. Specs 1110: 9.4, TNZ F/1 Clause 4 | Engineer Approval | Engineer Writen Authorisation | Before Topsoil Removal | Client Consultation | C | CR
4.4 | Hazardous Waste and Contaminated soils | Contaminated soils (Type H materials) encountered shall be treated and/or disposed off site in accordance with statutory requirements. Specs 1110: 9.3 | Dumping site approval for contamiantion type | Dumping Docket | If constaminated soils are found | Document Check | C | QE/SP/CR
4.5 | Checking Levels and Alignment | The Contractor shall inspect all set out prior to construction to confirm that the 2D linework has been interpreted appropriately to achieve the line and level of the finished works. Specs 1000: 3.2.4 | Levels and allignment Set Out matches marks shown on the Drawings, Design, 2D data and linework provided or agreed with the Engineer | Compliance surveys or spot checks | During and at the end of the Excavation | Visual, Instrumental | C | SP/QE/SV
4.6 | Cut and Fill Foot path Construction | Cut and fill construction involves cutting into the uphill sideslope and placing fill on the downhill slope. Depending of the sideslope. Dept. of Consevation Track Construction and Maintenance Guidelines: 13.1, 13.2 | Sideslope > 25° (50%), Cut Construction. Sideslope Between 6° - 25° (10% - 47%), Only Cut Construction. | Compliance surveys or spot checks | Before Excavation | Visual, Instrumental | C | SP/QE/SV
4.7 | Footpath Fill Compaction | Compaction may be checked when undertaking fill formation work. All fill material needs to be compacted in layers no greater than 250 mm (prior to compaction). Dept. of Consevation Track Construction and Maintenance Guidelines: 13.2, 13.5 | The Dynamic Cone Penetrometre can be used to indicate the compaction of soil and/or fill materials. If a large number of blows is needed to cause the cone to penetrate a short distance the soil/material is well compacted | Dynamic Cone Penetrometre Checksheet | After compaction of fill layer | Visual, Instrumental | C | SP/QE

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key) | Signature
5.1 | As-built Drawings | Two hard copies and one electronic copy of As-built drawings shall be prepared in draft and final versions following Schedule 1D in NZS4404:2010. Specs 1000: 3.9.2 | Engineer Approval | QA records | At completion | - | H | QE/CR
5.2 | Surplus Materials and Refuse Disposal | All surplus, redundant and faulty materials must be removed from the Site and dispose of them in a safe and legal manner. Any demolition material or rubbish coming from the execution of the project must be removed as well. Specs 1000: 3.13.2 | - | - | At completion | Visual | C | QE/SP/CR
5.3 | Cleaning | Completed items of construction about to be placed in service or occupied for their intended use must be properly and thoroughly cleaned of all foreign matter and other debris. Specs 1000: 3.13.3 | - | - | At completion | Visual | C | QE/SP/CR
SECTION 6 – COMMENTS
|  |  | Customer Release Granted: | ☐ Yes | ☐ No | Date:
Certificate Number: