## ITP-037
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # FHC-ITP-37
[11 empty] | Revision : 01 | Date : 09/08/2023
Client: |  |  |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Tarneit Bus Interchange |  | Inground Hearing Loops (AFILs) |  | Name: Martin Syawish |  | Name: Patrick Fagan |  |  | Name: Damon Bromwich
Job No: |  | 7428000 |  | Specifications: Australian Standards, NIST-013, IEC, IFC DRAWINGS
|  |  |  | Structure / Component: Hearing Loops |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Tarneit Train Station |  | Date : 09/08/2023 |  | Date : 09/08/2023 |  |  | Date : 09/08/2023
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Setting Out |  | Prior to start | Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections | Drawings | Visual Inspection | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.2 | Position of AFILs |  | Prior to application | AFILs shall be installed in coundit underneath concrete & above any reinforcing. The hearing loops shall be installed within a 25 or 32mm conduit with dimensions 4m x 8m to suit drawing setout. | NIST-013 6.1.3.1.3.2 | Visual inspection | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.3 | Materials |  | Prior to commencement | Hearing loop cable shall be 1C 6mm2 cable & feeder cable star quad 4C 4/6mm2 (twisted pair speaker cable). Hearing loop cable shall be placed in conduit underneath footpath concrete. | Drawings | Visual inspection | This ITP signed off | IP | Fulton Hogan Engineer / Subcontractor | N/A
2.4 | Jointing |  | Prior to commissioning | Hearing loop 1C 6mm2 cable shall be jointed to 4C feeder cable injunction box located in detector loop pit adjacent to each hearing loop. | Drawings | Visual inspection | This ITP signed off | IP | Fulton Hogan Engineer / Subcontractor | N/A
2.5 | OCS Room Connection |  | Prior to commissioning for feeder cables | The 4C feeder cable shall be connected to amplifiers in station OCS room ready for commissioning. | Drawings | Visual inspection | This ITP signed off | HP* | Fulton Hogan Engineer / Subcontractor | N/A
2.6 | Signage |  | Each hearing loop | Public Address loop signage shall be installed in compliance with the drawings. | Drawings, AS1428.1, NIST-013 6.1.3.1.5.1 | Visual inspection | This ITP signed off | IP | Fulton Hogan Engineer / Subcontractor | N/A
3 | Completion
3.1 | Commissioning |  | Each hearing loop | Each hearing loop shall be commissioined by an experienced sound technician / professional in accorance with relevant Australian Standards and IEC standards. | AS1428, AS60118.4, IEC 60118.4 NIST-013 6.1.3.1.3 | Verify | Commissioning Checklist & Commissioning Certification | TP | Fulton Hogan Engineer / Subcontractor | N/A
3.2 | As-Built |  | Post Completion | Red-line markup cable route and installation to suit actual conditions. | IFC Drawings Redline Markup | Document Review | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FHDB |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.