## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Uppper floor slab |  |  |  |  | Yes | Uppper floor slab | 031cc020-ec2a-4d9e-85a3-8219960365bd
checkpoint-status |  |  | checkpoint | Has area been handed over by W & H
checkpoint-status |  |  | checkpoint | Confirm hieghts
checkpoint-status |  |  | checkpoint | Boxing mark off grid
checkpoint-status |  |  | checkpoint | Shutter to hieght or over size
checkpoint-status |  |  | checkpoint | Has footing been cut back 500 mm from face of shutter line
checkpoint-status |  |  | checkpoint | Concrete hieght bead in place if required
checkpoint-status |  |  | checkpoint | Botls to bottom place every 600 mm
checkpoint-status |  |  | checkpoint | Braces in place - every 600
checkpoint-status |  |  | checkpoint | Strong back in place if required
checkpoint-status |  |  | checkpoint | Area stripped
checkpoint-status |  |  | checkpoint | Shower rabate in place
checkpoint-status |  |  | checkpoint | Bathroom rabate in place
checklist-flat |  |  | checklist | Precast Install |  |  |  |  | Yes | Precast Install | 27649068-6f99-49ae-9e4f-d16af55544b8
checkpoint-status |  |  | checkpoint | Has area been handed over by W & H
checkpoint-status |  |  | checkpoint | Confirm location
checkpoint-status |  |  | checkpoint | Grid marked / survey point given
checkpoint-status |  |  | checkpoint | Shims in place at base
checkpoint-status |  |  | checkpoint | Gap maintained between panels
checkpoint-status |  |  | checkpoint | Starters in place
checkpoint-status |  |  | checkpoint | Props installed as per plan
checklist-flat |  |  | checklist | Precast Install - Flat Slabs |  |  |  |  | Yes | Precast Install - Flat Slabs | 3d84679c-7858-4cd8-9c1c-0a4f8cf9857a
checkpoint-status |  |  | checkpoint | Has area been handed over by W & H
checkpoint-status |  |  | checkpoint | Confirm location
checkpoint-status |  |  | checkpoint | Grid marked / survey point given
checkpoint-status |  |  | checkpoint | Back propping in place and at height
checkpoint-status |  |  | checkpoint | Layout confirmed
checkpoint-status |  |  | checkpoint | Glav angle in place
checklist-flat |  |  | checklist | Boxing Pad |  |  |  |  | Yes | Boxing Pad | 53e5eec6-dff5-4dc9-9f9a-d63d0adb4cdc
checkpoint-status |  |  | checkpoint | Has area been handed over by W & H
checkpoint-status |  |  | checkpoint | Boxing mark off grid
checkpoint-status |  |  | checkpoint | Shutter to hieght or over size
checkpoint-status |  |  | checkpoint | Site concrete in place and 80 mm thick
checkpoint-status |  |  | checkpoint | Has footing been cut back 500 mm from face of shutter line
checkpoint-status |  |  | checkpoint | Concrete hieght bead in place
checkpoint-status |  |  | checkpoint | Botls to bottom place every 600 mm
checkpoint-status |  |  | checkpoint | Braces in place - every 600
checkpoint-status |  |  | checkpoint | Strong back in place if required
checkpoint-status |  |  | checkpoint | Area stripped
checklist-flat |  |  | checklist | Ground Floor Slab |  |  |  |  | Yes | Ground Floor Slab | 7d3ddbd2-a088-4403-826d-bcb685129ecc
checkpoint-status |  |  | checkpoint | Has area been handed over by W & H
checkpoint-status |  |  | checkpoint | Confirm heights
checkpoint-status |  |  | checkpoint | Boxing mark off grid
checkpoint-status |  |  | checkpoint | Shutter to height or over size
checkpoint-status |  |  | checkpoint | Rebate in place
checkpoint-status |  |  | checkpoint | Rebate type correct
checklist-flat |  |  | checklist | Boxing to footing |  |  |  |  | Yes | Boxing to footing | bf4c9c91-ddd2-4850-a150-d5d3b7f29597
checkpoint-status |  |  | checkpoint | Has area been handed over by W & H
checkpoint-status |  |  | checkpoint | Confirm cut ground hieghts
checkpoint-status |  |  | checkpoint | Boxing mark off grid
checkpoint-status |  |  | checkpoint | Shutter to hieght or over size
checkpoint-status |  |  | checkpoint | Site concrete in place and 80 mm thick
checkpoint-status |  |  | checkpoint | Has footing been cut back 500 mm from face of shutter line
checkpoint-status |  |  | checkpoint | Concrete hieght bead in place
checkpoint-status |  |  | checkpoint | Botls to bottom place every 600 mm
checkpoint-status |  |  | checkpoint | Braces in place - every 600
checkpoint-status |  |  | checkpoint | Strong back in place if required
checkpoint-status |  |  | checkpoint | Area stripped