## Basecourse Construction
|  |  |  | Inspection Test Plan |  |  | Approved / Signature
|  |  |  | Contract Name: | B1101A - Te Ngarue Bridge |  | Engineer | 2023-10-31 | Quality Manager | 2023-10-27
|  |  |  | Procedure: | Basecourse Construction
Inspection & Test Plan / Checklist
Lot No: B1101A - Te Ngarue Bridge |  |  |  | Corresponding Work Instruction: |  | https://trecnz.sharepoint.com/:f:/s/ZONEB-SH2SOUTHHAWKESBAY/Ev4wrE48H99GjthARCOzmRYBgYRCbqlHsP6YVUo2EPmPWg?e=7oCCTg |  | Compliance with Work Instructions and Specifications
Detailed Location: SH2 RS 626 RP 0.009
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Installation of Erosion and Sediment Controls | M | Monitor effectiveness of the ESCP Controls throughout the construction process |  | Visual Inspection |  |  | Site Engineer
2 | Sub Base Signed off | H | All previous Activities completed & signed off before Placing base course | Prior to commencement | Document Review | Previous ITP must be completed (and site must not be dormant for extended period) | Sub-base ITP | Site Engineer
3 | Survey Setout | H | Set out pegs installed every 20m if required | Prior to commencement | Survey |  | Survey receipt | WSP
4 | Material Compliance | M | All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number | During construction | Measurement and recording | Traceability of all materials delivered to site | Delivery Dockets, Aggregate Deliveries Register | Higgins
5 | Basecourse Construction | M | Basecourse Aggregate | 1 sample/10,000m3 or 1 per source stockpile. | PSD, Atterberg Limits, MDD, OMC and CBR | Results to comply with specification | Lab test result | Higgins
6 |  | H | Degree of Compaction | 1 per 1000m2 staggered | NDM Lab Testing | Avg. >= 98% MDD and Min. >= 95% MDD | Pavement Lab Testing Spreadsheet | Site Engineer
7 | Survey checks | W | Cross fall check Surface shape check | 1 per 20m staggered | Survey check & Measurement | The cross fall between 2 points more than 2m apart, transverse to the centreline, shall not depart from the design cross fall by more than 0.5% No point of the surface shall vary more than 10mm over a 3m long straight edge | Survey results | Higgins
8 | Surface finish visual inspection | H | Surface finish check | Prior to AC layer | Visual inspection by Design Engineer after site sweeping | The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping |  | Site Engineer | CPS
9 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | As-built Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date: