## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | TREC-ITP - B1101A - Te Ngarue Bridge - Asphalt - Surfacing (AC 14) | itp |  |  |  |  | TREC-ITP - B1101A - Te Ngarue Bridge - Asphalt - Surfacing (AC 14)
checkpoint | 1 - Installation of Erosion and Sediment Controls
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Monitor effectiveness of the ESCP Controls throughout the construction process
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Visual Inspection
checkpoint | 2 - Basecourse Signed off
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All previous Activities completed & signed off before Surfacing Asphalt laying commences
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Previous ITP must be completed
label | Records - Basecourse ITP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Set out pegs installed every 20m if required
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Determine paving run start/stop locations
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Mark out on site
label | Records - Subcontractor QA Records
checkpoint | 5 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Mix Design approved including peer review
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - Material is approved by a Notice to Supplier being issued
label | Records - Mix Design
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Asphalt Material Quality Testing
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - Fine and Coarse aggregate Weathering, Crushing, Sand Equivalent, Broken faces, PSD, PSV. Bitumen testing, Penetration @ 25 degrees Celsius, Dynamic Viscosity at 60 degrees Celsius
label | Records - Asphalt Plant Results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Asphalt Production Testing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Full volumetric and air voids test 1 test - 1 test per day, Binder content and grading 1 test per 100t.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing and measurements
label | Conformance Criteria - Binder content, PSD, Mix Volumetric, Mix performance related properties resilient Modulus and wheel tracking, mix production temperature and load out temperature
label | Records - Asphalt Plant Results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Tack Coat
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - A Spray sheet for every day
label | Frequency - Prior to placing Surfacing AC
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - Showing the required spray rate 0.2 L/m2 with a tolerance of +or- 0.1 L/m2
label | Records - Subcontractor QA Records
checkpoint | 9 - Construction of Surfacing Asphaltic Concrete
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Site team QA Checks
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Site Measurements
label | Conformance Criteria - Delivery temperature, mat thickness before compaction, mix temperature during compaction
label | Records - Subcontractor QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Surface finish visual inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Site walk over
label | Frequency - Post Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - No visible cracks, No obvious defect related to poorly constructed joins, No areas where water can pool; No part of all pavement surfaces deviate more than 5mm from a 2m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline.
label | Records - Subcontractor QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT