## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | TREC-ITP - B1101A - Te Ngarue Bridge - Basecourse Construction | itp |  |  |  |  | TREC-ITP - B1101A - Te Ngarue Bridge - Basecourse Construction
checkpoint | 1 - Installation of Erosion and Sediment Controls
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Monitor effectiveness of the ESCP Controls throughout the construction process
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
checkpoint | 2 - Sub Base Signed off
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All previous Activities completed & signed off before Placing base course
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Previous ITP must be completed (and site must not be dormant for extended period)
label | Records - Sub-base ITP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Set out pegs installed every 20m if required
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | Conformance Criteria - Traceability of all materials delivered to site
label | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint | 5 - Basecourse Construction
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Basecourse Aggregate
label | Frequency - 1 sample/10,000m3 or 1 per source stockpile.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - PSD, Atterberg Limits, MDD, OMC and CBR
label | Conformance Criteria - Results to comply with specification
label | Records - Lab test result
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Degree of Compaction
label | Frequency - 1 per 1000m2 staggered
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
label | Records - Pavement Lab Testing Spreadsheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Survey checks
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Cross fall check, Surface shape check
label | Frequency - 1 per 20m staggered
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey check & Measurement
label | Conformance Criteria - The cross fall between 2 points more than 2m apart, transverse to the centreline, shall not depart from the design cross fall by more than 0.5%
label | ○ No point of the surface shall vary more than 10mm over a 3m long straight edge
label | Records - Survey results
checkpoint | 8 - Surface finish visual inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Surface finish check
label | Frequency - Prior to AC layer
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by Design Engineer after site sweeping
label | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT