## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Embankment Construction | itp |  |  |  | Yes | ITP - Embankment Construction | 184bfb1c-ac47-49c2-9a9f-6f684d47e490
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | Source material properties
label | 3b6abf7b-e161-5a90-9475-94e7c04d34dc |  | note | INSPECTION BY: PM/PE/Engineer/Site Supervisor
label | 92004c5e-4d6b-5e45-b91d-59b31395012f |  | note | TASK TIMING OR TASK FREQUENCY: Frequency of lab testing as per Table 1.4.
label | 92f2190f-e2f5-5a74-b648-4e8a795e6e64 |  | note | ACCEPTANCE CRITERIA: Lab testing sent to Engineer for approval prior to placement of fill. Lab testing requirements as per Table 1.5 and Table 1.6, and KiwiRail standard C-ST-FO-4110.
checkpoint-status |  |  | checkpoint | Visual inspection of subgrade
label | fa63975f-5c7f-580d-9142-808705dd658d |  | note | INSPECTION BY: Engineer/PE/PM/Site Supervisor
label | cb6c241d-81b7-53b1-8ded-bd5c5e11d571 |  | note | TASK TIMING OR TASK FREQUENCY: 100% of subgrade
label | d695fe18-d8d2-51c7-b564-e26c2bc52510 |  | note | ACCEPTANCE CRITERIA: Subgrade free of debris, organics and unsuitables
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Proof roll
label | 17224428-bd92-59bc-bd88-5edc3b5d927f |  | note | INSPECTION BY: Engineer/PE/PM/Site Supervisor
label | fd3e1839-74a3-5a9b-97c4-bbd8fe694a3f |  | note | TASK TIMING OR TASK FREQUENCY: 100% of subgrade
label | adacd897-0a28-501e-b704-02f04f936245 |  | note | ACCEPTANCE CRITERIA: <5 mm deflection under a smooth drum roller
checkpoint-status |  |  | checkpoint | Subgrade density testing
label | b93c1772-5e8b-5c3a-b173-865a85eeba69 |  | note | INSPECTION BY: PM/PE/Engineer/Site Supervisor
label | 081aeb99-adbd-52d3-9bc6-4f2dfdad4940 |  | note | TASK TIMING OR TASK FREQUENCY: Scala testing every 10 m as per Section 1.5.6
label | 60863855-6a44-5e24-a532-1a744e24ca30 |  | note | ACCEPTANCE CRITERIA: Engineer must inspect and agree required formation treatment or undercutting. CBR requirements as per Section 1.5.6.
checkpoint-status |  |  | checkpoint | Compaction trials
label | 2c06312b-43f7-514e-be0d-a29450988a64 |  | note | INSPECTION BY: PM/PE/Engineer/Site Supervisor
label | 8de8739b-646b-54ff-ae44-4668875dcce0 |  | note | TASK TIMING OR TASK FREQUENCY: Each fill material type
label | d6b7c32f-cf75-5a06-a9c8-f2a984126184 |  | note | ACCEPTANCE CRITERIA: Compaction trial carried out to confirm compaction methodology and compaction standards can be met, refer Section 1.8.2.
checkpoint-status |  |  | checkpoint | Compaction testing
label | f206ba89-9874-56a9-99d1-5b2620258886 |  | note | INSPECTION BY: PM/PE/Engineer/Site Supervisor
label | 062d6797-948f-585f-9e02-fc8d7793457e |  | note | TASK TIMING OR TASK FREQUENCY: Frequency as per Table 1.4
label | 08da7f17-d772-5492-b300-071c8e3ef19e |  | note | ACCEPTANCE CRITERIA: Engineer notified and given the opportunity to inspect when fill testing occurs.Compaction requirements as per Table 1.3
checkpoint-status |  |  | checkpoint | Visual inspection of finished structural fill surface
label | 51d40283-f92d-58da-a910-d3133a25fa4a |  | note | INSPECTION BY: PM/PE/Engineer/Site Supervisor
label | 08b60e75-64b8-50a0-8961-71e7328e84c2 |  | note | TASK TIMING OR TASK FREQUENCY: 100% of structural fill surface
label | e5d8fc15-e8f1-557f-9421-071b92cb4962 |  | note | ACCEPTANCE CRITERIA: Engineer notified and must be inspected prior to next fill layer being placed. Well compacted surface and 3% fall to outside edge
checkpoint-status |  |  | checkpoint | Visual inspection of finished sub-ballast level
label | 2b45d25d-07b9-5734-b37e-8d6f891117f0 |  | note | INSPECTION BY: PM/PE/Engineer/Site Supervisor
label | dc7e5c71-83c3-5f3a-ad9c-200b390be8a9 |  | note | TASK TIMING OR TASK FREQUENCY: 100% of sub-ballast surface
label | 4d8c3003-0aac-5fa2-a8e5-e3a2a08f9a24 |  | note | ACCEPTANCE CRITERIA: Engineer notified and must be inspected prior to next fill layer being placed. Well compacted surface and 3% fall to outside edge
checkpoint-status |  |  | checkpoint | Level check
label | e502ccd1-0d39-50d9-9363-7afc01c1e620 |  | note | INSPECTION BY: PM/PE/Engineer/Site Supervisor
label | 5daa3e3d-bf86-5f8a-b934-593f18fdb148 |  | note | TASK TIMING OR TASK FREQUENCY: Finished section of structural fill or sub-ballast level
label | b0595363-1504-5b7c-bad6-a71c710f8367 |  | note | ACCEPTANCE CRITERIA: Engineer notified and given the opportunity to inspect when level checks on finished surface are being completed
checkpoint-group |  |  | section | Completion
checkpoint-status |  |  | checkpoint | Finished Coconut matt
label | 2d2cb540-19a2-5a5d-ac60-a5a2d47b9c3e |  | note | INSPECTION BY: PM/PE/Engineer/Site Supervisor
label | 1cf8b606-1bc8-5405-bde7-6a57880ea33a |  | note | TASK TIMING OR TASK FREQUENCY: 100% of batter faces
label | 4fd629fd-5a5e-54c7-a7de-f63b7fddd1ad |  | note | ACCEPTANCE CRITERIA: Engineer notified and should inspect completed matted/hydroseeded area
checkpoint-status |  |  | checkpoint | Visual inspection of geotextiles
label | 5ca16adf-af2d-5575-bfbf-cca02fb7edba |  | note | INSPECTION BY: PM/PE/Engineer/Site Supervisor
label | 32d0ad57-239f-5d53-90e6-22400fdbdd1f |  | note | TASK TIMING OR TASK FREQUENCY: Placement of all geotextile
label | 9f57af09-fef0-5027-a5f7-d67095e2eb0c |  | note | ACCEPTANCE CRITERIA: Engineer notified and given the opportunity to inspect
checkpoint-status |  |  | checkpoint | Visual inspection of geogrids
label | 680d4315-db29-5bac-b783-001ceaf6a53a |  | note | INSPECTION BY: PM/PE/Engineer/Site Supervisor
label | e8a5900b-cbf5-5a85-a7ba-99bd868bb522 |  | note | TASK TIMING OR TASK FREQUENCY: Placement of all geogrid
label | 49a76f15-9bbb-5207-9af8-abefad4bbd43 |  | note | ACCEPTANCE CRITERIA: Engineer notified and given the opportunity to inspect
checkpoint-status |  |  | checkpoint | Visual inspection of drainage trenches
label | 3e7b4567-620e-5add-be47-8d1d35cdcadc |  | note | INSPECTION BY: PM/PE/Engineer/Site Supervisor
label | c627af0e-7eeb-5c46-a439-5e44e64825e4 |  | note | TASK TIMING OR TASK FREQUENCY: All drainage trenches (subsoil drainage)
label | 40488d29-6bf3-503d-8bfc-836380c16e8b |  | note | ACCEPTANCE CRITERIA: Engineer notified and must inspect prior to backfilling of the drainage trench
checkpoint-status |  |  | checkpoint | Visual inspection of swale
label | b7f6d898-9261-58fe-8983-9a82690d855d |  | note | INSPECTION BY: PM/PE/ Engineer/ Site Supervisor
label | d4067117-e3e7-5e72-b447-660ddc7206b9 |  | note | TASK TIMING OR TASK FREQUENCY: Visual inspection of swale
label | f5a46f55-2b00-5255-aec1-88b6f9aba5ff |  | note | ACCEPTANCE CRITERIA: Engineer notified and must inspect finished surface
checkpoint-status |  |  | checkpoint | Visual inspection of duct installation
label | 69fbb45a-dde9-5ccc-8a0d-4e41d2737ab3 |  | note | INSPECTION BY: PM/PE/Engineer/Site Supervisor
label | ab05f1d9-bce8-5ff0-9ea7-83cb698af461 |  | note | TASK TIMING OR TASK FREQUENCY: Finished section of duct prior to backfilling
label | 75d613ee-29ff-557d-9264-0b8d3f54e501 |  | note | ACCEPTANCE CRITERIA: Engineer notified and given the opportunity to inspect.Duct laid according to the Specification and KiwiRail Standard S-ST-CW-2140
checkpoint-status |  |  | checkpoint | As-built Survey of Formation including top of rail
label | c43abb51-d78c-5d4e-9008-b7411f2f945f |  | note | INSPECTION BY: Surveyor
label | 43049c50-e8c7-57af-af5b-849b30ad6099 |  | note | TASK TIMING OR TASK FREQUENCY: Finished rail install
label | bcb3fc66-f224-5bf2-9c8e-e42f602ef81e |  | note | ACCEPTANCE CRITERIA: As-built drawings to be provided to the Engineer following completion of works. Tolerances as per the Specification. Where tolerances differ from the Specification they shall be agreed with the Engineer prior to completion of the works. Initial survey completed immediately following construction. A second as-built 4 weeks after rail is opened for settlement monitoring.
checkpoint-group |  |  | section | Tests for aggreagte quality
checkpoint-status |  |  | checkpoint | Density - General Fill (GAP 100 River Run)
label | 72c3c621-5917-54da-8f20-dba0b4e7f469 |  | note | TASK TIMING OR TASK FREQUENCY: Each 20 Linear meters for each lane
label | 459692b1-9c90-507c-852c-914770e83070 |  | note | ACCEPTANCE CRITERIA: Density >= 95% mean, Density >= 92% minimum
checkpoint-status |  |  | checkpoint | Density - Structural Fill (GAP 65)
label | 19f307be-6a0b-5104-8d81-f7604863b7f2 |  | note | TASK TIMING OR TASK FREQUENCY: Each 20 Linear meters for each lane
label | 53440aa0-84d6-5026-a37f-1cfaab502d62 |  | note | ACCEPTANCE CRITERIA: Density >= 98% mean, Density >= 95% minimum
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | ITP Sign Off for Construction
text | c4d66884-cad6-58e6-9ce7-d8b262196516 |  | textbox | Project Engineer:
text | 44d7b985-6182-54fa-ae7c-0e7052bb7087 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | All works completed, records attached and work conforming
text | c3f9cf03-358c-503e-8152-25240d2fe41f |  | textbox | Site Engineer:
text | e5bcdc5b-a626-5664-bbe7-433f058dbc45 |  | textbox | Date:
text | fd4739af-b04c-55c5-8fbe-7013d2e3c326 |  | textbox | Project Engineer:
text | 82f6c6df-5c33-53e9-9df9-f0720a4c0631 |  | textbox | Date:
text | 75d701f1-cbda-5f9f-83d7-38956a97f776 |  | textbox | Quality Manager:
text | de38c233-f345-5654-8e1e-c5bd0615068d |  | textbox | Date:
checklist-sectioned |  |  | checklist | Piling | itp |  |  |  | Yes | ITP - Piling | 3674277b-d0c1-47ff-83bb-c989ceb700f9
checkpoint-group |  |  | section | 1.0 - Preliminary Inspections and Tests
checkpoint-status |  |  | checkpoint | 1.1 - Design and Drawings are of 100% Detail Design Status
label | 4f662301-2bf5-53e7-af19-e43fdf431b53 |  | note | Responsibility: Spiral Drillers Engineer
label | 397c120d-e0cc-53aa-8ddd-3316504f6d91 |  | note | Spec Reference: N.A
label | a6039367-8ba7-5d76-b195-8513dc9c9637 |  | note | Conformance Criteria summary: Latest Issue Design Drawings issued via email
label | 3804b85e-a8bb-5cdd-b608-3cbe2b611a2a |  | note | Method: Document review/document control
label | af15c79d-a030-5304-8719-1113a6f3fa4f |  | note | Frequency: Prior to Start of work
label | 45e91f93-ac86-596b-887f-6877108fa3cc |  | note | Hold/Witness Requirements - C: HP
label | 877a97b1-ca8b-5db2-b2d9-379953684de1 |  | note | Hold/Witness Requirements - UCC: IP
label | 92bf1b67-0bae-5062-ab11-00e1a5164d9a |  | note | Records or Checklist Reference: SD Quality Control Checklist
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.1.1b - Submittal of construction methodology
label | 47ebbc22-3c28-5c4b-b112-f8b47b751c29 |  | note | Responsibility: Spiral Drillers
label | c92f7a39-320f-5c35-af6e-691fd7268592 |  | note | Spec Reference: Project Memo Section 2.1.iii
label | 125fdf30-1fca-57e7-a9d8-f0acc1abdd39 |  | note | Conformance Criteria summary: Include: Equipment, Pile construction methodology, delivery and storage of material, safe work area, pile concrete & sand placement.
label | 3ac847b3-d72b-5a2f-bb21-f2936a5eeeb6 |  | note | Method: Document review
label | cb3626c1-ed4a-535d-8227-f3b19b169d66 |  | note | Frequency: Prior to Start of work
label | 777dd99d-28ff-56a1-9f8f-73dd60fe38c7 |  | note | Hold/Witness Requirements - C: HP
label | 706f351d-7e3b-5d41-aa18-b07d5dba64d7 |  | note | Hold/Witness Requirements - UCC: HP
label | f3354a7f-b42b-596f-a831-6c903e506a44 |  | note | Hold/Witness Requirements - N P: HP
label | 32aabb95-0368-5edf-97c6-4e4deee3b8b1 |  | note | Records or Checklist Reference: Approved ITP
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 2.0 - Approved Materials
checkpoint-status |  |  | checkpoint | 2.1 - Reinforcing Cages
label | a00ab193-6e3d-5a46-a08d-099478994e61 |  | note | Responsibility: Spiral Drillers
label | 7028a785-db0d-5db9-a118-bf4da0a554a5 |  | note | Conformance Criteria summary: Mill Certifications
label | fe41fdaa-f6b2-5174-8b50-e3822fd439d7 |  | note | • Send notice in advance request for inspections
label | df7bc8cf-a915-5b6f-a105-4019172f4f4f |  | note | • 7.8.3 Micro-Alloying MA 300E or Grade 500E steel
label | 7702cab0-e4dd-5637-a150-c94778886fd2 |  | note | • Reinforcing as per approved detail sheets.
label | 6d1196f2-e810-5624-bb7c-c8687d4d64a7 |  | note | • Reinforcing to comply with AS/NZS 4671 & NZS3109. Any cutting, bending or welding of reinforcing on site to be approved in writing by the design engineer.
label | d53a23d9-7b6d-57e3-a2ef-92f93c55969d |  | note | Method: Detail Sheets approved by structural engineer prior to manufacture Mill certificates for reinforcing cages used. Engineer to inspect constructed cages.
label | abbc4946-c20d-5b8a-8ddf-135a00262cc2 |  | note | Frequency: Per pile type intended to be constructed, Prior to manufacture, Once arrived on site
label | 48829135-ee08-599d-a2cc-c9ad4c4eda08 |  | note | Hold/Witness Requirements - C: HP
label | 7d7e1409-02f2-59d1-89b3-e37d081eb9d2 |  | note | Hold/Witness Requirements - UCC: RR
label | a4f3baa9-d2dc-5c76-9086-d32411724d55 |  | note | Hold/Witness Requirements - N P: RR
label | d8886462-f34c-53d3-9b66-ff8c7f3cef21 |  | note | Records or Checklist Reference: Delivery Dockets SD, Pile cards, Reinforcing Mill cert testing
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.2 - Steel Pile Casing
label | 7ac15ef8-c655-583d-ac66-bbb0deb40756 |  | note | Responsibility: Spiral Drillers
label | 9a69d61c-7a53-5f1b-9c64-0099be7af14f |  | note | Spec Reference: SESOC Section 2.2.4
label | f43e7708-6395-51c1-a2a5-b723650df1e2 |  | note | Conformance Criteria summary: Sizing to be 762mm x 16mm WT
label | 1d00a7cb-57fa-53a2-9eb2-7159308febb4 |  | note | • Pile casing to comply with the requirements in the project drawings.
label | f1ae40c9-1eaf-5fa3-b551-1b0a405760d4 |  | note | • Deviation from straightness shall not be greater than 1/600 longitudinally.
label | 64559c4e-40ce-5361-b3bf-9a1ad6c7bc03 |  | note | Method: Steel casing mill certs, heat no. and material testing.
label | 22d7bdee-608f-58f2-b35b-729151166950 |  | note | Frequency: Tests/certs for steel casings rolled from different steel coils.
label | 1afd1971-49d1-5ca2-bda8-07d9e48697d8 |  | note | Hold/Witness Requirements - C: RR
label | 567c32b8-0bcd-5862-8e50-417c5bde5004 |  | note | Hold/Witness Requirements - UCC: RR
label | 1ffe121d-bd0e-53f2-9035-d09d05b73aa6 |  | note | Hold/Witness Requirements - N P: RR
label | 2f67c513-8adb-5603-982d-45ecb52e9333 |  | note | Records or Checklist Reference: Delivery Dockets, Heat Number and Mill certs.
checkpoint-status |  |  | checkpoint | 2.3 - Concrete mix design
label | 1e3b84ed-bb40-59b9-90d4-abeb98ee76f4 |  | note | Responsibility: Spiral Drillers
label | ffb4ba9d-c8f1-5be5-9be0-af6a4282179c |  | note | Conformance Criteria summary: Submit proposed concrete mix design in advance of concrete been placed on site
label | fd2c73f6-24e3-53ef-8460-2ee97546af96 |  | note | • Concrete batching plant will keep records to prove ongoing suitability of plant and mix design, production tests and delivery.
label | 75b41705-5176-58f8-b758-e62c6e004820 |  | note | • Concrete mix design to comply with NZS3104.
label | 0b07f4a9-c3d4-5c69-afcb-050e14b57d61 |  | note | • Maximum permittable aggregate size to be 19mm.
label | 995e868a-4a17-591a-b95a-a33b92e89bcc |  | note | • Mixing design intended strength to be XXMPa and meeting the requirements for exposure classification XX.
label | 1d7b5b64-677d-5b3d-a669-68f19c7d7c81 |  | note | Method: Concrete mix design, Submitted to the engineer prior to concrete being placed.
label | 2ab70fae-6480-53c5-8aa2-9b9f8eda1ae7 |  | note | Frequency: Prior to concrete being placed
label | ce5076a1-e5d7-5433-9d2f-e14b60dee93c |  | note | Hold/Witness Requirements - C: HP
label | f5ebb98b-82ca-55e6-b166-7261e16f97e2 |  | note | Hold/Witness Requirements - UCC: HP
label | 75e5754a-276e-5e3f-bbf2-878307ff0c12 |  | note | Hold/Witness Requirements - N P: RR
label | d838d5ab-5bce-5fbb-9e83-1f79a0cd34a3 |  | note | Records or Checklist Reference: Written confirmation for acceptance of mix deisng. SDC QA - Concrete pile schedule Certificates, testing records
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.4 - Welding on site
label | 7ca49e87-365c-52e9-be41-7a1ab729b2fc |  | note | Responsibility: Spiral Drillers
label | d77ba7cb-018f-528e-a027-b42c65b169e2 |  | note | Spec Reference: AS/NZS 1554.1. NZS 4781.
label | 2356daeb-1e06-5d0c-9c19-638fd7b1eb71 |  | note | Conformance Criteria summary: Welders WPS form in AS/NZS 1554.1 Individual welders qualified to the WPS, AS/NZS 2980 Welder Certificate
label | bf4f09c2-401c-5803-8fbe-49f32c816318 |  | note | Method: Welding WPS Certification of each welder
label | 95163c13-a8d0-5504-a45d-395a155e72d9 |  | note | Frequency: Prior to Start of work
label | bc35b560-1544-5b5a-b241-5f3d9f6ce2ac |  | note | Hold/Witness Requirements - C: HP
label | cecda120-da0f-508e-b8b9-56fa91a8b5ab |  | note | Hold/Witness Requirements - UCC: HP
label | 08ce0d25-0768-5ed1-b4ad-6d885055b8f7 |  | note | Hold/Witness Requirements - N P: RR
label | 8a62341d-8d7a-5555-816b-ccf951454382 |  | note | Records or Checklist Reference: Welding records and certificates, Current welding qualification
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.5 - Piling Hammer & Equipment
label | fabd0ab2-b857-5493-acd4-5b0fa38fcf92 |  | note | Responsibility: Spiral Drillers
label | d56567a9-f43a-5a4f-9e49-befd4cc9b517 |  | note | Conformance Criteria summary: Weigh bridge docket to verify the weight of the piling helmet.
label | e68d1c20-94b6-5d02-8b0a-331611f2c1d2 |  | note | • Driveability analysis to determine the drop height, Set and temporary compression requirements.
label | a5997e72-bbec-5bac-9ae4-4f3c61d97513 |  | note | Method: Weigh bridge dockets, Driveability analysis document
label | 31d7b85b-d97c-583c-94b4-ff37343116a5 |  | note | Frequency: Prior to start of work
label | e44007cf-ef57-5e18-9942-393a431b2bca |  | note | Hold/Witness Requirements - C: HP
label | 4db02471-3dc7-56a2-80d5-39420362492e |  | note | Hold/Witness Requirements - UCC: HP
label | 9042a952-99a9-52ce-99e2-cfca1f120773 |  | note | Hold/Witness Requirements - N P: RR
label | a923e29b-bb65-514d-b3c8-c3024e5951f6 |  | note | Records or Checklist Reference: Driveability analysis
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 3.0 - Setting Out
checkpoint-status |  |  | checkpoint | 3.1 - Set out and survey
label | b148d92d-94c1-5be5-a808-aa045e7e6dce |  | note | Responsibility: United Civil Construction
label | 6d2998ee-7666-595b-b736-931c032f35db |  | note | Spec Reference: Project drawings ASG Piling Specification Rev G – Section 1.13
label | 3f2c9082-826d-549c-a9cc-f0ce398b5863 |  | note | Conformance Criteria summary: UCC to set out pile centre lines on guide frames installed by SDC. Set out requirements will vary from location but will be required on multiple occasions.
label | fa2572d4-a220-5f6d-9f58-83020d6018b8 |  | note | • Setout gridlines to be within +- 3mm of design position.
label | 2915c9d1-4089-5472-980c-d4424ac0e6d4 |  | note | • UCC to provide several benchmark pegs along the alignment that are checked frequently to ensure accuracy.
label | a7cd926e-1949-5904-a9c8-0314854676f0 |  | note | • SDC will be responsible for offsets taken from the pile set out location.
label | 8906407f-5dee-5a23-b2a4-6e9060aa5932 |  | note | Method: Registered surveyor Inspection and Set out
label | d7ca525f-91df-525d-83dd-cb727d43d9e0 |  | note | Frequency: Each Pile position.
label | 89bf1551-4603-5efa-91ac-521ae1747ede |  | note | Hold/Witness Requirements - C: HP
label | 4b831a62-cdee-5e22-ba48-5f2f1206b027 |  | note | Hold/Witness Requirements - UCC: IP
label | d64adaaa-9acf-5289-8fb1-9599b1d15aff |  | note | Hold/Witness Requirements - N P: IP
label | 1ae54527-a846-5378-a5f2-9617f1432acd |  | note | Records or Checklist Reference: SD Quality Control Checklist, Set out report for tolerance, As-built Survey, Monitoring of benchmarks.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 4.0 - Construction stage
checkpoint-status |  |  | checkpoint | 4.1 - Reinforcing Cages
label | 2255e54a-27e1-5fa6-9d3c-7451335e2712 |  | note | Responsibility: Spiral Drillers
label | 61f1d706-f993-55ee-88cf-e5445a648371 |  | note | Spec Reference: SESOC Section 1.10
label | 6b280266-91a4-50ce-a3b9-463389260840 |  | note | Conformance Criteria summary: Stack reinforcing cages on suitable supports on firm ground, in a manner to eliminate excessive handling stresses or other damage.
label | c88356b6-4c10-5684-9ea7-90bb5e9f3105 |  | note | • Reject and replace reinforcing cages that are not as per the detail sheets.
label | a8230a4e-8ee0-56ce-9c5c-b2745b188403 |  | note | • Compile delivery dockets for reference to mill certs.
label | 7e471ea7-e1b9-5143-9743-ec4c90498d17 |  | note | Method: Each delivery
label | 3846f6b5-8768-57df-88c3-32f07f540951 |  | note | Frequency: Each delivery
label | 5e8de59e-b88f-54e7-94bc-664e14a59e09 |  | note | Hold/Witness Requirements - C: HP
label | 2ee91de9-0da7-5b5c-92ba-d63d90fb0148 |  | note | Hold/Witness Requirements - UCC: IP
label | b9086281-1009-5fb2-ad9a-01fe31393b7b |  | note | Hold/Witness Requirements - N P: IP
label | b474d2ab-40aa-512e-96d3-353c2f330d4b |  | note | Records or Checklist Reference: Structural engineer inspection of reinforcing cages, SD Pile QA sheet Delivery dockets.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.2 - Concrete Dockets
label | 0dceb5c8-3b27-5f80-98f2-1a2e2783f9c9 |  | note | Responsibility: Spiral Drillers
label | 96228dc3-36a1-5421-9209-2fdbc80f52ca |  | note | Spec Reference: Approved Mix design document.
label | 72481324-9412-521f-b4d9-259f460756da |  | note | Conformance Criteria summary: Mix design on delivery docket matches the approved mix design.
label | 3cfa1296-e46e-5848-85ce-79e8134918b5 |  | note | • On site material testing to confirm mix design characteristics are achieved.
label | ab200d96-2312-523c-8aa2-f2ff2121a0e2 |  | note | Method: Slump Tests & Concrete dockets.
label | b8744f40-3f51-543e-a0fe-b40c8d707795 |  | note | Frequency: Each Concrete truck.
label | 0ba5a5b1-1fa1-55e3-80c3-1cb1a5f296b3 |  | note | Hold/Witness Requirements - C: HP
label | 9f18358a-6b17-5d00-9689-d7cd34591bd2 |  | note | Hold/Witness Requirements - UCC: RR
label | fe2d7ee4-cc60-5886-ba6f-59ceed757092 |  | note | Hold/Witness Requirements - N P: RR
label | 0749cd5d-2baa-5be3-a1da-29f8afbfc59d |  | note | Records or Checklist Reference: SD Concrete pour QA Sheet, Concrete testing report.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.3 - Bottom Driving Plug Material
label | cb987d76-b3c9-5c7a-b21c-38aa52996d7e |  | note | Responsibility: Spiral Drillers
label | 28bfd9da-07dd-5e94-a20d-47dbf2441989 |  | note | Spec Reference: SESOC Section 4.12.1
label | 28433cfb-a49a-5984-8ca0-6a40c39ac71f |  | note | Conformance Criteria summary: Aggregate to conform to table 4.12-1 of SESOC Rev I (Sealing Chip).
label | 2cac48ce-e817-515b-bc20-ee7a87a3b962 |  | note | • Plug Length shall not be less than 1.5x casing diameter at commencement of piling and shall not exceed 4.0m unless approved by the Engineer.
label | 0742fd9b-fc08-5023-b85a-61245a2474e8 |  | note | Method: Material grading cert. Pile measurements.
label | 934ee0c1-8aed-5fa6-9dec-72fc73fbe0ae |  | note | Frequency: Daily
label | 64595fca-5bdf-5b99-92d2-53f141846702 |  | note | Hold/Witness Requirements - C: HP
label | bdb59763-1c6a-575c-bcbe-850084ab6028 |  | note | Hold/Witness Requirements - UCC: RR
label | ab7f0481-eb34-5c20-b430-e4d860cffa15 |  | note | Hold/Witness Requirements - N P: RR
label | e7046105-2a35-5896-bfed-3814ebbccaac |  | note | Records or Checklist Reference: SD Polymer Checklist.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.4 - Pile installation/founding level.
label | b924273e-720d-5873-ad92-a86f7276e345 |  | note | Responsibility: Spiral Drillers/UCC
label | 4b537fc2-6d40-5b8b-b50a-bf04940f5cad |  | note | Conformance Criteria summary: Tolerances:
label | 775b5686-5f02-5e04-9fd9-debd74844d80 |  | note | • The centre of the pile head at the design level of the head shall be within 75mm of its lateral position and 25mm of its vertical position.
label | e9a9b300-4ae0-54c8-ac2c-5eea48afb9b0 |  | note | • The pile shall be within 1:75 of its design. Do not force incorrectly placed piles into their correct position after they have been placed.
label | 992e8e62-92a5-56e5-b3fb-d9f9142e8d4c |  | note | • Pile as built survey to be completed by United Civil Construction
label | 9061f9c8-a944-517d-a9bf-dc773f6a2dfd |  | note | ○ Founding Capacity:
label | e4a0dedf-9c51-556d-bb5d-74fc255c1088 |  | note | • Pile locations to be driven to their required founding capacity verified using either Hiley or PDA.
label | ff4d65e0-b682-5a35-a53f-41230e67eebe |  | note | ○ Driving Records:
label | a3f9ebc8-cc6c-56e5-ab68-eadd8f9aef23 |  | note | • All Piles will have the drop height & no. of drops recorded at the following intervals.
label | d17cbd7c-7d33-5782-8543-14e9a4724943 |  | note | • 1.0m -> Up to 20m deep.
label | 4704b8ea-8a90-597d-bed5-13f2f74b7ba5 |  | note | • 0.5m -> To founding depth.
label | 8114485a-84a6-56f4-a6ee-9cc36613251a |  | note | • Set/temporary compression recorded over 10 No. consecutive blows using either a manual set card or a Pile Driving Monitor.
label | a3874afb-8741-52a4-9057-e3dac0b8b3bc |  | note | Method: Position of pile: 75mm horizontal, 25mm vertical and 1:75 of its design
label | 216e82df-fb76-5d3a-87ca-4c53182460bb |  | note | • Piles shall achieve a minimum founding resistance Outlined in IFC Drawings Cut off level to be +25, -25mm
label | 32630458-5c67-50a9-a0ac-07a64e9886df |  | note | Frequency: Each pile
label | c2ff9cc7-1f12-5f87-97b3-2b739d285d41 |  | note | Hold/Witness Requirements - C: HP
label | 355b1d3b-fad0-58fd-850a-b4df0229c9eb |  | note | Hold/Witness Requirements - UCC: HP
label | 0e958d2f-5978-59eb-8f45-17d8b8328868 |  | note | Hold/Witness Requirements - N P: RR
label | 24d8da38-d5c5-5e79-bf0e-6627f25eb2f0 |  | note | Records or Checklist Reference: SD Pile Card Geotechnical Engineer inspection record. PDA Record review
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.5 - Welding process
label | aedaeaab-eecb-5aae-809e-d8d3c3cadca7 |  | note | Responsibility: Spiral Drillers
label | 8dcf9520-0d1d-513b-9cd1-383a287199ed |  | note | Spec Reference: AS/NZS 1554.1 NZS 3404.1 and AS/NZS 5131. AS/NZS 1554.1, clause 1.8.2. SESOC Section 2.2.6
label | c9dcc801-f0cf-5cd3-ad21-57d6d735452e |  | note | Conformance Criteria summary: Welds to be carried out to the WPS form in AS/NZS 1554.1 Splicing will be a single bevel full strength butt weld, Flux-cored arc, self-shielded, welded one side with backing strip
label | de6a7027-07c1-5204-95fd-cb789a4e44f7 |  | note | • Weld testings: 10% Ultrasonic testing completed on Pile casing welds.
label | 46ba0cdf-fc73-56fb-a015-871cf09f4de3 |  | note | Method: Document review and on-site inspections (Radiograp hy or ultrasonic) Independent testing report.
label | c428ba6c-3155-5ab2-94d8-25c3d4f4ec07 |  | note | Frequency: Weld testings: 10% non destruction examination testing (UT testing)
label | 12225e99-ac7f-5a9a-8b29-3a26315c782e |  | note | Hold/Witness Requirements - C: HP
label | 7364da46-af5e-50b0-847a-b9b8f02fcadd |  | note | Hold/Witness Requirements - UCC: RR
label | 6c6e8b03-41f4-542a-97f8-c37afb4f9365 |  | note | Hold/Witness Requirements - N P: RR
label | d2db6637-5414-5934-8ed5-c070d651e6d1 |  | note | Records or Checklist Reference: Independent test report
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.6 - Concrete placing
label | 71454478-0c75-516d-8960-ee0510bbf902 |  | note | Responsibility: Spiral Drillers
label | adc5c3d7-5741-5459-bf72-379e71d50d86 |  | note | Conformance Criteria summary: Each pile is to be checked before each pour for any groundwater or contaminates in the pile
label | d200906b-4150-5026-9609-8a32d6351278 |  | note | • Daily concrete pour record to approved checklist
label | b1cd7148-b313-58d7-8e73-a713a128d247 |  | note | • Concrete docket to be submitted each pour
label | 94f795e1-294b-5aed-8bc2-4775b049c729 |  | note | ○ Testing
label | d1283523-474c-58c7-aab0-1003828d08e0 |  | note | • Carry out 7 and 28 days testing
label | 572782f3-dba3-56c0-bacc-28c4c33106b5 |  | note | • Standard cylinders for each 50m3. 1 at 7 days, 2 at 28 days.
label | 46b395ac-a84f-5a05-ae75-a4a4b2575708 |  | note | • 1 slump test per load
label | 247af547-9bac-54e8-9442-d86e3dbae469 |  | note | • Concrete to be poured in a manner that avoids hitting the reinforcing cage. Poured central down the pile hole. Concrete to be tested in an IANZ Accredited lab.
label | fb31b717-60d5-5023-a464-213d43049334 |  | note | • Depth to top of concrete, placement time and method to be recorded for each truck.
label | b6fdfb8f-5fb6-548f-953b-60e791b3369a |  | note | Method: Concrete dockets, Test results And Pile cards
label | 73dedb3d-0996-5dc9-a675-cec92ad6fa63 |  | note | Frequency: Every 50m3 or minimum of 1 per day, Each pile to be inspected before pouring concrete
label | 6cbd3ca9-2498-5685-86e4-f0c35347e0d0 |  | note | Hold/Witness Requirements - C: HP
label | 16546636-a276-5c0d-9456-0165ecc3b122 |  | note | Hold/Witness Requirements - UCC: IP/RR
label | a20c22f7-7357-5b0a-bc1c-cc24c2f9a8c6 |  | note | Hold/Witness Requirements - N P: IP/RR
label | 53892705-c672-51b6-ac26-623274f22095 |  | note | Records or Checklist Reference: Concrete dockets and laboratory test results, SD Concrete QA Card.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 5.0 - Completion
checkpoint-status |  |  | checkpoint | 5.1 - As- built pile survey
label | a7b62ec7-4a71-5270-9920-31b981dc2b61 |  | note | Responsibility: United Civil/Spiral Drillers
label | a473a2e5-2c28-57f5-a622-2bd445c2ce46 |  | note | Conformance Criteria summary: All piles installed are within the required tolerances as shown in the construction specification and drawings.
label | 87faa91e-13ea-5ae2-8d60-14575c4420b0 |  | note | • +-75mm horizontal tolerance
label | cc0c0744-71ee-574a-9056-3b1ace7ac583 |  | note | • +- 25mm vertical tolerance
label | 08fdb65c-6e97-5230-a73e-9545e1f966f4 |  | note | Method: As-built survey completed by a registered surveyor
label | 0dd4a06c-8bd1-5fb4-bd38-67a398144568 |  | note | Frequency: Upon completion of pile installation
label | d932c94e-b091-5411-aabe-0d6d46cdfa1e |  | note | Records or Checklist Reference: Complete As-built document referring position to design positions.
checkpoint-status |  |  | checkpoint | 5.2 - Warranty and code of compliance
label | e0d959be-1472-57df-8692-c71914ed6928 |  | note | Responsibility: Spiral Drillers
label | 662fe17d-5976-54ea-92d5-731475565095 |  | note | Conformance Criteria summary: Documented evidence Certificate, warranty or Producers statement
label | 4a861ba4-825b-5d3e-864a-fbc3db195e2f |  | note | • Warranty meets spec requirements
label | 0d17e894-ace3-5985-91ad-c44881c21d0b |  | note | • Commence warranty from date of practical completion
label | 246bf573-9d7c-513f-af96-0c8d09324fee |  | note | • Spiral Drillers will issue a Producer Statement for the entirety of their contracted works upon completion.
label | 69959893-2b52-57ad-a7ef-ee863a5f9812 |  | note | Method: Record review
label | 1711983a-9351-517f-a76f-60cf3620bd80 |  | note | Frequency: once
label | 4004d81f-4dee-53a7-ae62-26b3f5967633 |  | note | Hold/Witness Requirements - C: HP
label | 43e9132c-5763-5673-ad66-34124b909dcf |  | note | Hold/Witness Requirements - UCC: HP
label | 23734620-5f77-5a04-b1b5-bb07b36fbd0c |  | note | Hold/Witness Requirements - N P: RR/RR
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Sign Off
text | 45578b63-c366-53a5-b0d0-e9965662cccb |  | textbox | Comments:
text | f76d40d8-d5cd-5b2f-b464-9f9f33f444a7 |  | textbox | Work Completed:
label | 99f709c4-d1a6-571d-9343-d7fb39aa6c62 |  | note | The above items have been inspected and are in accordance with the drawings and specifications. All documentation as required by Specification is included in this Lot.
label | 3b3f4828-18cd-5459-8751-1f74cc907c75 |  | note | Contractor
text | 01eacb2c-1c05-5e0c-b491-9364fe47ea35 |  | textbox | Name:
text | 8bc3ec4f-8c75-5c70-bc96-5e1bbaeb93c1 |  | textbox | Position Title:
text | c201d284-13c1-5e11-b9aa-aad67fe596f0 |  | textbox | Company
text | 7811bf43-1657-5772-9472-4e3e69e60a07 |  | textbox | Date:
label | 39649baa-5572-5d5e-95df-d48222752acd |  | note | Ormat/Delegate
text | bd3cab03-d927-5f10-bb85-cadabb52a442 |  | textbox | Name:
text | f8f58f31-0271-5e6b-b6f1-415e1923624a |  | textbox | Position Title:
text | 26dad32a-ab3a-5b44-bcff-f14aff8ce6a3 |  | textbox | Company
text | 1f87914b-e3b1-5778-a4cc-61a6df4ad95a |  | textbox | Date:
checklist-sectioned |  |  | checklist | Structural Steel Fabrication | itp |  |  |  | Yes | ITP - Structural Steel Fabrication | 885a9a2e-ec68-41be-a6f8-d6b561e1faf8
checkpoint-group |  |  | section | 1.1 - Preliminaries: Method & Documentation
checkpoint-status |  |  | checkpoint | 1.1.1 - Shop Drawings
label | 23da6955-1c34-5aee-b947-eb085787ce5c |  | note | RI: PM
label | d726a2a3-29bd-5798-9241-02ae47d848e8 |  | note | Acceptance Criteria: Submit electronic copies of shop drawings, providing complete details of each assembley with respect to the steelwork fabrication, surface treatment and erection.
label | f0d8aae2-c129-52e2-ba4b-d7a0dc8c093a |  | note | Method: Review
label | 61632b84-7681-5793-9351-3cd50787f121 |  | note | Frequency: Per Assembly
label | 42e99062-6651-5cfa-8ca8-2d712631d217 |  | note | Verification Activity By - Eastbridge: H
label | 729f1181-2f2a-5726-9f77-950e5a39fd66 |  | note | Verification Activity By - Contractor: H
label | d669c64e-0509-5bde-b878-052440a6f02a |  | note | Verification Activity By - Client Rep: H
label | 6122c9c7-852e-5a74-ac84-6e2140bcbaaa |  | note | Verifying Record: Notice to Contractor: Permission to Fabricate
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.1.2 - Independent Welding Inspector
label | 25922363-ff6a-54d8-ba39-bc61d4f856a6 |  | note | RI: PM
label | 7a0009c0-3d11-5f7b-95a6-39001243c9af |  | note | Acceptance Criteria: Submit Third Party welding inspection entity, appropriately qualified in the welding inspection required by the Project.
label | 952d26f6-e9b0-5bf0-a3c9-6b72a0a67b19 |  | note | Method: Review
label | 197c32f9-76cf-5345-a1b3-68a374961814 |  | note | Frequency: Once
label | 4f7ab9b0-f143-5ba3-a98c-6ee70685453c |  | note | Verification Activity By - Eastbridge: H
label | 4394a692-4f30-5227-8bea-0f214afe550f |  | note | Verification Activity By - Contractor: H
label | 62a688c9-7412-5173-8f42-d4429b39d490 |  | note | Verification Activity By - Client Rep: H
label | 6141c7f6-5344-5549-9b7e-aa097a44e406 |  | note | Verifying Record: Approved Independent Welding Inspector
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 1.2 - Preliminaries: Material Compliance
checkpoint-status |  |  | checkpoint | 1.2.1 - Structural Steel Grades
label | e8cca43c-56be-51fb-97f7-766b32143ee4 |  | note | RI: PM
label | 98aa16dd-e6ca-5a00-83b9-6ee7c537fed0 |  | note | Acceptance Criteria: Project Specification
label | 1a8f6ba4-202b-5904-8eeb-ba0bf39fb1b9 |  | note | Applicable Standard and/or Technical Requirement: AS/NZS 3678, AS/NZS 3679.1
label | 2d7952aa-6e58-5b59-8b96-5547ace099df |  | note | Method: Review
label | ae2d4367-4d31-54e4-ba02-23708d7385f1 |  | note | Frequency: Per Material Order
label | 3a608b44-5580-5dcb-850b-66545710ca1a |  | note | Verification Activity By - Eastbridge: H
label | 772c74dc-674b-5d9e-ae55-89a9464378fc |  | note | Verification Activity By - Contractor: H
label | 77f5683a-f42c-531b-90ae-82c8d4786790 |  | note | Verification Activity By - Client Rep: R
label | d6d9720c-0483-5676-8989-f05fd67687d9 |  | note | Verifying Record: Shop Drawings & Mill Certificates
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.2.2 - Structural Bolts
label | 4bb85b5c-8803-5ca2-8f2e-e2fd7ecb26cd |  | note | RI: PM
label | aa6c6d71-9086-59e1-b83a-57901a1dfd76 |  | note | Acceptance Criteria: Bolts will be sourced in accordance with NZS 1252:2016, All bolts are to be high strength steel bolts of grade 8.8 or higher, uno.
label | 2a11b287-501d-54ed-bdd5-326fcfe1d9d1 |  | note | Applicable Standard and/or Technical Requirement: NZS 1252:1996
label | c1ad22f1-6978-5e48-9e79-e1e277873277 |  | note | Method: Review
label | 85609793-39ee-5b68-93f6-491c2a3c5eb0 |  | note | Frequency: Per Material Order
label | bb8e1a02-d13b-50c2-9028-e7ba33f2f162 |  | note | Verification Activity By - Eastbridge: H
label | 9c4527cc-021f-5ca0-9f31-6dd6e68c9cc5 |  | note | Verification Activity By - Contractor: H
label | b36f7394-0d8a-5833-9ee1-a6ae1ee4f60a |  | note | Verification Activity By - Client Rep: R
label | af578f70-73e9-538c-b38b-446c314f5c87 |  | note | Verifying Record: Material Conformance Certificates
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.2.3 - Shear Studs
label | 4c941806-e10e-5394-88bd-39115d0d1296 |  | note | RI: PM
label | c74e990f-1f77-56c1-9087-68b8f8a3902a |  | note | Acceptance Criteria: All shear studs be produced in accordance with AS/NZS 1554.2:2003, with the relevant mill certificates and testing records, including mill certificates to which they will be connected proving prequalification of welds.
label | 469a89cb-69c0-5a90-9230-614ff9f7c268 |  | note | Applicable Standard and/or Technical Requirement: AS/NZS 1554.2:2003
label | 65356408-ad39-5603-a70b-2efe04a65039 |  | note | Method: Review
label | 12c7c3f8-daa0-591b-ae48-47f951edd1e3 |  | note | Frequency: Per Material Order
checkpoint-status |  |  | checkpoint | 1.2.4 - Structural Steel Supply Traceability
label | 69404fa7-6d60-508a-b26a-77f39072b354 |  | note | RI: PM
label | 509acbab-320c-51b9-a96b-23d10e9bc00b |  | note | Acceptance Criteria: Refer Project Specification, All Plates are to be produced in accordance with NZS 5131 will mill certificates meeting the relevant grades given in 1.2.1.
label | a2490c79-8a7d-5f45-9e5d-3c4dc5a1e09c |  | note | Applicable Standard and/or Technical Requirement: AS/NZS 5131
label | ee923110-3f30-52fe-a31d-b02ee1904c1e |  | note | Method: Review
label | 2b141e50-7c04-5cdf-8000-8c4b3d385d74 |  | note | Frequency: Per Material Order
label | aaf7d6ad-0d61-58b1-adba-d7a0d5cd7e91 |  | note | Verification Activity By - Eastbridge: H
label | e50919d4-01ba-5f08-aea6-37088564b59d |  | note | Verification Activity By - Contractor: H
label | d4d9ba6e-b913-5370-aa40-ec0314174d38 |  | note | Verification Activity By - Client Rep: H
label | f7addc06-9765-5857-bba7-f83a50379e6b |  | note | Verifying Record: ACRS or JAS-ANZ Mill Certificatoin Certificates
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.2.5 - Verified Mill Certificates
label | 5c31c179-435e-50b7-a84d-f1ede07716e2 |  | note | RI: PM
label | e3a27715-6ebb-5064-8612-57ce1c96397b |  | note | Applicable Standard and/or Technical Requirement: Project Specification
label | 0cfeec63-3476-54cf-9da9-7eb7f8b2a296 |  | note | Method: Review
label | 0f8e973f-29a2-534f-a9d5-da4d9f70f9bb |  | note | Frequency: Per Mill Certificate
label | 50cae3b2-fd87-52c3-b80b-3c30e839f65a |  | note | Verification Activity By - Eastbridge: H
label | 4c3b116b-1914-5263-b4fe-a63a0fcbacc5 |  | note | Verification Activity By - Contractor: H
label | f50bb51a-2e94-52aa-be0a-976aa4038f73 |  | note | Verification Activity By - Client Rep: H
label | 4374c378-8d48-562c-956a-7f12468c0935 |  | note | Verifying Record: ILAC Endorsment
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.2.6 - Structural Steel & Bolt Third Party Testing
label | 50793ef1-5b57-5f90-a019-f2ee4e8815a5 |  | note | RI: PM
label | ac17849b-8d7f-513e-ae08-c229a804d75c |  | note | Acceptance Criteria: 3 No. samples from each batch of structural steel tested for mechanical and chemical properties at a certified IANZ lab in NZ, and the results submitted to the Engineer
label | b83c3267-f518-598a-a38b-16e18048254a |  | note | Applicable Standard and/or Technical Requirement: Project Specification
label | 26464650-df95-5380-8660-d4576d2d3b9a |  | note | Method: Material Test
label | 68d397a4-5dfb-5a74-b365-6f145a0a3d02 |  | note | Frequency: Per Batch
label | 39259653-5921-5eac-9b56-5bfca00cc5fc |  | note | Verification Activity By - Eastbridge: H
label | 47bc2bc5-9a6a-5c1c-8fd0-11d562038dca |  | note | Verification Activity By - Contractor: H
label | 5ab4f0c8-4506-5364-9249-815d215d9970 |  | note | Verification Activity By - Client Rep: H
label | 9e228696-feba-5e79-bb3d-acd145c141bd |  | note | Verifying Record: IANZ Laboratory Test Report
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 1.3 - Preliminaries: Welding Procedures & Certification
checkpoint-status |  |  | checkpoint | 1.3.1 - Welding Personnel Qualifications
label | e69111e6-635a-5957-8a14-b348a1fd432e |  | note | RI: PM
label | ffc10b24-f490-5538-be1f-752946d04140 |  | note | Acceptance Criteria: Review of proposed welders and their welding certificates and qualifications
label | 37a9a29c-dc65-5271-8b6f-48d8c61b2eb5 |  | note | Applicable Standard and/or Technical Requirement: AS/NZS ISO9606.1:2017
label | b96ed598-4a97-517d-8da1-064e95a4eba7 |  | note | Method: Review
label | 499e3d28-c86d-58b5-8448-4ee68a0a5d0d |  | note | Frequency: Per Welder
label | 6ff530d2-a7aa-53e4-ad8a-a6a45da6db3f |  | note | Verification Activity By - Eastbridge: H
label | e0bc2154-b4d9-5927-91d9-b2330460d1ac |  | note | Verification Activity By - Contractor: R
label | 8112ef60-ad96-509c-877d-7fc68305123e |  | note | Verification Activity By - Client Rep: R
label | 99e4ecda-1d31-5e26-9ee9-cfac33b0daf7 |  | note | Verifying Record: Personnel Welding Qualification Certificates
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3.2 - Welding Procedure Specification (WPS)
label | 333598d4-7cc2-5f72-b40c-7b0b62152505 |  | note | RI: PM
label | 39c0965a-3eb8-5955-b40b-c96f5bdefc1c |  | note | Acceptance Criteria: Pre-qualified to AS/NZS 1554.1:2014 as a minimum.
label | d5e96e50-e145-5b62-9217-a91c1a672cf5 |  | note | Applicable Standard and/or Technical Requirement: AS/NZS 1554.1:2014:2014
label | 3f364c43-0eca-5bc0-933c-b996d7c24ea7 |  | note | Method: PQR
label | bbaa7f2e-3804-5366-a2e3-68e33f2e8a7e |  | note | Frequency: Per WPS
label | f258f40c-5bb6-5563-b519-44bde24569ac |  | note | Verification Activity By - Eastbridge: H
label | 4c2d90a9-9636-59b5-8dcd-4e25436bc7cc |  | note | Verification Activity By - Contractor: R
label | dcf55747-fb8c-5c0c-9ee6-455984fcd1a1 |  | note | Verification Activity By - Client Rep: H
label | 9fc595b3-8f6f-5046-b35e-e611ea248625 |  | note | Verifying Record: Procedure Qualification Record
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3.3 - Independent Review of WPS
label | 3243bd63-1cde-5a63-89d0-ee631b0dad58 |  | note | RI: PM
label | fcea5200-5860-5d7d-9a55-1289b9e22db1 |  | note | Acceptance Criteria: Review by nominated IWI of WPS and PQR
label | a0b2d11f-368a-5068-8b24-24dc37341c97 |  | note | Method: Review
label | c37048e8-4b37-56fe-bedf-72043a6de9cf |  | note | Frequency: Per WPS
label | 7848f65c-91ae-55c6-9a46-ecbd992463e4 |  | note | Verification Activity By - Eastbridge: R
label | 1660b6f5-75bd-5a28-9363-2db17b6f95ff |  | note | Verification Activity By - Contractor: R
label | 50272acb-4d3d-56bb-8e02-17f8ba125cff |  | note | Verification Activity By - Client Rep: R
label | 4c136f82-3c4f-580a-80ea-605ba3ad7d34 |  | note | Verifying Record: Independent Review Record
checkpoint-group |  |  | section | 1.4 - Preliminaries: Corrosion Protection System
checkpoint-status |  |  | checkpoint | 1.4.1 - Coating Applicator
label | fb8bf104-442a-52d2-b95c-b80e183f6575 |  | note | RI: PM
label | 6d0055e9-ef7c-5854-83ae-5827557fd5fb |  | note | Acceptance Criteria: Contractors are required to be accredited under the Australian Paint Contractors Certification Program (PCCP)
label | 6ad19b98-384a-59d4-a1ab-dc76440bc109 |  | note | Method: Review
label | 70c7fc3d-3e5b-5654-a64f-043780f330af |  | note | Frequency: Once
label | 8bad903e-25bc-5712-b3f1-8d7a3037d3cb |  | note | Verification Activity By - Eastbridge: H
label | 6b0c3e75-8a41-5d01-b4ec-d04ee96c4b28 |  | note | Verification Activity By - Contractor: H
label | d72aba84-77d8-5334-a9f6-67d19f63d712 |  | note | Verification Activity By - Client Rep: H
label | 2cf4417b-0010-5beb-80f0-a57e9fc85f5c |  | note | Verifying Record: Coating Applicators Accreditation Certificate
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.4.2 - Coating Specifier
label | e25e6ce5-2481-5556-bf1b-ca2955a14927 |  | note | RI: PM
label | d9a63c98-cffb-5083-bdda-c7c9fa47d219 |  | note | Acceptance Criteria: Qualification to one of the following:
label | c184d919-a2db-5a6e-a885-6d5c375bfaf6 |  | note | • NACE Protective Coating Specialist
label | d08eb544-87ca-541f-9409-e96f178489de |  | note | • Australasian Corrosion Association
label | 2f3cf005-1028-5dc9-a267-202c497ba735 |  | note | • (ACA) Technician or Technologist with successful completion of the ACA's Coating Selection and Specification Course and/or certified to NAC Coating Inspection Program (CIP) Level 2
label | cbf929e1-fb7a-5db8-b48d-be95acd7eced |  | note | Method: Review
label | f0450c14-07ba-5658-940f-f4c26c80162d |  | note | Frequency: Once
label | 4548f45a-a1d9-5614-b878-45b759ca61d0 |  | note | Verification Activity By - Eastbridge: H
label | b62240cf-eebd-5221-8ee1-15b4fa8459a2 |  | note | Verification Activity By - Contractor: H
label | 43052af1-15b4-5521-b8c8-f4deb4dd0e60 |  | note | Verification Activity By - Client Rep: H
label | 3d57af6d-adf6-569e-8522-e66e517c3af5 |  | note | Verifying Record: Coating Specifier Qualification Certificate
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.4.3 - Coating Specification
label | 7536d9fe-286f-5518-a4dc-68f3283cd5ec |  | note | RI: PM
label | 4cb54e4f-bbb6-5341-82a3-3cdb60407b80 |  | note | Acceptance Criteria: Painting specification approved by an independent paint inspector. Note, only coatings approved by an independent body such as APAS, NEPCOAT or NORSOK shall be used.
label | 856a001f-2bf3-557c-90a1-610f97f72635 |  | note | Method: Review
label | 7e18ba50-26e5-52a0-bff4-a2963b918805 |  | note | Frequency: Once
label | cf6cb5b3-20a1-5a6e-82a9-7a37832c0721 |  | note | Verification Activity By - Eastbridge: H
label | 73ffa01c-b5a8-5eb2-b4b3-e58fe5c088df |  | note | Verification Activity By - Contractor: H
label | 93f3e672-3ee4-5d1c-ab99-fa56d9feddf2 |  | note | Verification Activity By - Client Rep: H
label | 2e9b8510-e565-529c-b2d8-794bc55898a6 |  | note | Verifying Record: Approved Paint Specification from Independent Paint
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 2 - Receiving & Storage of Parent Metals
checkpoint-status |  |  | checkpoint | 2.1 - Material Receiving into Store
label | e73cb112-1308-5086-b156-25e0b45aae3d |  | note | RI: PM
label | 154d870b-74ad-5651-bc4e-7f7cd2335c36 |  | note | Acceptance Criteria: All incoming mateials shall be inspected for conformance to the requirements of the Project and heat numbers checked against mill certificates
label | 060a7527-4fb8-54a0-b9e5-c1610c2a6b9b |  | note | Applicable Standard and/or Technical Requirement: PQP "Material Receiving" NZS3404.2:2009, 2.2.2
label | c74c00a7-0c59-5dc0-87bf-e7a13d9c67d0 |  | note | Method: Inspection
label | 10073b83-44c1-5495-a063-32671b59be97 |  | note | Frequency: Per Material Order
label | e5d89e59-fd67-5102-8a3b-bdbd2b74553f |  | note | Verification Activity By - Eastbridge: I
label | ffb3dd21-3a14-537e-82cc-ecc108d01bd3 |  | note | Verification Activity By - Contractor: R
label | 7b5d4a99-632a-5975-86ab-649bff4d75e6 |  | note | Verification Activity By - Client Rep: R
label | 8f4081f5-3499-5a74-b1c7-a671a6f7fb5b |  | note | Verifying Record: Material Receipt Certification
checkpoint-status |  |  | checkpoint | 2.2 - Storage
label | 9c4c0c2a-57ba-5c66-8917-2adad7eac260 |  | note | RI: PM
label | 701604e4-0e6b-56b3-badd-2a2161990621 |  | note | Acceptance Criteria: Materials shall be kept free from dirt, grease and other foreign matter and protected from corrosion as far as possible and shall be stored above ground on platforms, skids or other supports.
checkpoint-group |  |  | section | 3 - Fabrication: Cutting, Holing & Bending
checkpoint-status |  |  | checkpoint | 3.1 - Sharp Edges
label | 7be11615-a0e2-5a2b-a171-18f94564a339 |  | note | RI: FSUP
label | f2faed0c-f572-50ac-bdf9-902e77fe12d8 |  | note | Acceptance Criteria: Rounded to a 2 mm radius by grinding after fabrication to ensure that a protective coating of normal thickness will adhere to the edges
label | 4414af4a-1f32-55be-b4a5-bb5a071aabaf |  | note | Applicable Standard and/or Technical Requirement: AS/NZS 5131:2016 - Sect 6.5.4
label | 8df26cbb-7ee9-546a-ad47-48a137ec7f91 |  | note | Method: Inspection
label | 29451dbe-2873-59dd-80af-ce837906be2b |  | note | Frequency: Per Section
label | 37192385-eea3-5fec-aa6a-551ad4958fc1 |  | note | Verification Activity By - Eastbridge: I
label | d032fc21-ba01-559b-af5b-3251c88bf108 |  | note | Verification Activity By - Contractor: R
label | 12811455-fc85-54f1-abbc-25d6a5f49dfa |  | note | Verification Activity By - Client Rep: R
label | 37010ed0-b204-59d2-9def-ddbcd0142607 |  | note | Verifying Record: Eastrbidge Standard Fabrication Checksheet
checkpoint-status |  |  | checkpoint | 3.2 - As-Cut Surfaces
label | bcb3c376-981c-5640-b82c-47c4f42ee537 |  | note | RI: FSUP
label | 646c21ff-b2ba-553e-939e-9e291f2b8e6f |  | note | Acceptance Criteria: Australian Welding Research Association Class 2 surface
label | 0b111d28-9c4e-5062-b3f6-d42d11052a3c |  | note | Applicable Standard and/or Technical Requirement: AS/NZS 5131:2016 - Sect 6.5.2 Table 6.5
label | dc43c40c-f207-5c5f-81db-47b4eaadc9a5 |  | note | Method: Inspection
label | 99ef803d-2f60-5cd2-8481-a9ea9949bb17 |  | note | Frequency: Per Section
label | b5c5860f-3b71-5482-b1c9-4bfab8f9bfe0 |  | note | Verification Activity By - Eastbridge: I
label | a519f554-d987-566e-839b-4286d0ca45c8 |  | note | Verification Activity By - Contractor: R
label | 12678742-6631-5e2c-b863-09ab302180c2 |  | note | Verification Activity By - Client Rep: R
label | 11401c93-cb6d-52a0-9ada-4d9ff331b550 |  | note | Verifying Record: Eastrbidge Standard Fabrication Checksheet
checkpoint-status |  |  | checkpoint | 3.3 - Re-Entrant Corners
label | 7a0d2204-fa24-5166-8b0d-8f699114df75 |  | note | RI: FSUP
label | 86994424-6ab4-55fd-948f-4ac3246ead80 |  | note | Acceptance Criteria: Shaped notch free to a minimum radius of 10 mm unless specifically indicated otherwise by geometry detail or as indicated on the drawings
label | 9f8199fd-d017-571b-934d-ed33aed4ef99 |  | note | Applicable Standard and/or Technical Requirement: AS/NZS 5131:2016 - Sect 6.5.3
label | 106a27fb-dff9-57d1-9e85-39f4f813900f |  | note | Method: Inspection
label | e001b379-726a-5ce1-9fc5-f2a05b1c1e75 |  | note | Frequency: Per Section
label | e6fe0e98-b377-54aa-9ba7-b0d5e5e16946 |  | note | Verification Activity By - Eastbridge: I
label | 997a7224-dcbe-5503-baaf-4d7eb38ba11b |  | note | Verification Activity By - Contractor: R
label | 011af915-b567-5773-8a0d-119c776cf122 |  | note | Verification Activity By - Client Rep: R
label | 680567d9-9a81-51a1-94c8-1789274ff4d6 |  | note | Verifying Record: Eastrbidge Standard Fabrication Checksheet
checkpoint-status |  |  | checkpoint | 3.4 - Holing
label | 0443a865-1146-5b91-9f52-d7e13767d96b |  | note | RI: FSUP
label | 9ef0bc65-987b-5baa-bbdf-4edf29f6474f |  | note | Acceptance Criteria: Standard holes for bolts shall be D+2mm unless otherwise noted. Slotted holes shall be D=2mm wide and 2.5D long unless otherwise noted.
label | 3e0003b3-bded-5083-88c7-d8ee5c20ba71 |  | note | • Standard holes for pins shall be D+1mm unless otherwise noted.
label | e48b1043-b93e-5945-8a8f-d7c78e25c3a6 |  | note | • In the event of misalignment of bolt holes at any joint, reaming or drilling to more than 1.5mm larger than the bolt diameter will not be permitted unless specifically approved by the Engineer
label | 68c18467-e28e-5026-ab98-1d0e0d57bec1 |  | note | Applicable Standard and/or Technical Requirement: AS/NZS 5131:2016 - Sect 6.7
label | e4a8776f-46b4-52da-aa35-bed4f9ceca5d |  | note | Method: Inspection
label | 0459a467-e9b9-5a6c-be49-fd817a8b062f |  | note | Frequency: Per Section
label | 27f7e9a1-e660-5bcc-a7b4-8fdb17c6e398 |  | note | Verification Activity By - Eastbridge: I
label | e50e45c8-3476-5137-bda6-ca23315d54da |  | note | Verification Activity By - Contractor: R
label | 277e0eb9-05da-5dc5-ae73-57f074d2686d |  | note | Verification Activity By - Client Rep: R
label | 138e7b4b-f284-51b1-a8e7-9ea19346f754 |  | note | Verifying Record: Eastbridge Standard Fabrication Checksheet
checkpoint-status |  |  | checkpoint | 3.5 - Shaping
label | 01a767bd-638b-5d37-bfd8-883488af0c71 |  | note | RI: FSUP
label | cd7d0aad-f697-55c3-9f50-9a9be988bc12 |  | note | Applicable Standard and/or Technical Requirement: AS/NZS 5131:2016 - Sect 6.6
label | 233edf8a-1e4e-578f-9414-9b253b85a918 |  | note | Method: Inspection
label | 15329a40-eddf-5e4f-9612-618bb8f4f61b |  | note | Frequency: Per Section
label | 44f9302d-28ea-5a20-a043-b94f85febe19 |  | note | Verification Activity By - Eastbridge: I
label | 9efb4c61-8457-5d52-8c91-202c591a12f2 |  | note | Verification Activity By - Contractor: R
label | 2f7eddef-6627-582e-811a-306754ca4e15 |  | note | Verification Activity By - Client Rep: R
label | 3f4938f0-90d0-5bd3-8748-51ca9dcbb835 |  | note | Verifying Record: Eastbridge Standard Welding Checksheet
checkpoint-status |  |  | checkpoint | 3.6 - Markings & Identification
label | d20a3679-465a-5a20-b493-017c155dc165 |  | note | RI: FSUP
label | cd70b363-6d12-5269-b117-c06d268413e2 |  | note | Acceptance Criteria: Steelwork markings and indentification is correct as per shop drawings
label | 04ab933f-6a54-5fcb-bf17-a59ee83e80fc |  | note | Applicable Standard and/or Technical Requirement: NZS 3404.1
label | 5b17163f-6d22-5f05-a729-479c937b228d |  | note | Method: Inspection
label | d4df2436-1d58-5a19-b5a7-23e269e4637f |  | note | Frequency: Per Section
label | dc4a6f78-f21e-5f05-bdbd-6d9024efc00c |  | note | Verification Activity By - Eastbridge: I
label | 89d2fb0a-1f5e-55ee-bf2f-dbea475e159a |  | note | Verification Activity By - Contractor: R
label | 2a8f032d-71cd-5dc3-a308-4a2dc0e68cac |  | note | Verification Activity By - Client Rep: R
label | bd98ebba-3356-5bea-b966-eeca399d271f |  | note | Verifying Record: Eastbridge Standard Fabrication Checksheet
checkpoint-group |  |  | section | 4 - Welding
checkpoint-status |  |  | checkpoint | 4.1 - Check Welding Consumables
label | 0f6e2c2b-5505-5b82-90f6-d06d3c71eb8f |  | note | RI: EBWI
label | 38fd9254-f21c-5750-8038-e0e6b1e0de40 |  | note | Acceptance Criteria: Consumables to be stored in accordance with the manufacturers specification
label | 5d5d04c7-04ce-539d-9588-a2484fe79e2f |  | note | Applicable Standard and/or Technical Requirement: AS/NZS 1554.1:2014, AS/NZS 5131:2016 Sect 7.5.2
label | 05ff0fb5-b12c-567f-ad0c-e8812f50a81a |  | note | Method: Review
label | f0d730fa-99e8-58ac-b29f-28b8e0f3acd0 |  | note | Frequency: Once
label | cf368619-5f8c-5ab9-a09f-3beb33987b66 |  | note | Verification Activity By - Eastbridge: W
label | 64a17d11-a182-5a19-a800-bbeccd388d57 |  | note | Verification Activity By - Contractor: R
label | 8e81c286-54bd-5fa0-99af-3413f6cbcc01 |  | note | Verification Activity By - Client Rep: R
label | 65ab76d6-c6ce-5509-9d88-9e21dda29e51 |  | note | Verifying Record: Approved Weld Testing Regime
checkpoint-status |  |  | checkpoint | 4.2 - Welding Plan
label | a431e779-96e5-58b0-aa2a-7c4f81371cc9 |  | note | RI: EBWI
label | 00b2059f-7458-5d1c-91d3-bac9c81b1254 |  | note | Acceptance Criteria: Considerations for all welding to made in respect to Section 7.2.2 for all welding related matters
label | f9fc9ba2-70ef-5542-ad4a-71d8292e603a |  | note | Applicable Standard and/or Technical Requirement: AS/NZS 1554.1:2014, AS/NZS 5131:2016 Sect 7.2
label | b8543bd6-6ad3-54da-ba21-f58a226a3f5c |  | note | Method: Inspection
label | f4eb3942-304d-5671-9e45-0db73780dd9b |  | note | Frequency: Once
label | b985bb1f-1363-527a-b9de-a27b789ba1c0 |  | note | Verification Activity By - Eastbridge: R
label | 35e305d7-697d-52cc-b4e7-1ac783f1b13c |  | note | Verification Activity By - Contractor: R
label | c282786b-6fca-5c27-b08a-cca608df69b3 |  | note | Verification Activity By - Client Rep: R
label | f9e7c09e-bccd-59dd-aa0a-6d4eba0c286a |  | note | Verifying Record: Visual Scanning Weld Report
checkpoint-status |  |  | checkpoint | 4.3 - Allocate welders to specific welds
label | a2c0c25e-f4b5-5f72-9f19-39a19f4631d8 |  | note | RI: EBWI
label | d55ab9df-c840-5edb-a7e2-41f3320c5bfe |  | note | Acceptance Criteria: Welders to be qualified in accordance with AS/NZS ISO9606.1:2017
label | 03b727d6-e8aa-50f8-858e-9adc1a85783b |  | note | Applicable Standard and/or Technical Requirement: AS/NZS 1554.1:2014, AS/NZS ISO9606.1:2017
label | 4c54dfb9-eb6a-517c-bdba-daa326db5550 |  | note | Method: Inspection
label | 9f7cea27-1da4-531b-a272-fc6418bb4952 |  | note | Frequency: 100%
label | f745a15c-a5a7-5f84-8837-2cf4265778aa |  | note | Verification Activity By - Eastbridge: R
label | f1bdfdc5-45d4-5472-bc44-0f5d3fdcadac |  | note | Verification Activity By - Contractor: R
label | ec785092-3a99-52f5-90de-b5311a102583 |  | note | Verification Activity By - Client Rep: R
label | 2bbee17c-8fa1-5e85-a644-b8ef3149d697 |  | note | Verifying Record: Visual Examination Weld Report
checkpoint-status |  |  | checkpoint | 4.4 - Pre-weld inspections
label | 2531f4f0-8b2d-5d38-8c2e-f987560831bb |  | note | RI: IWCI
label | eba51164-730a-51a9-b63a-e2659a673be0 |  | note | Acceptance Criteria: Pre-weld inspections shall be made in accordance with Section 7.5.4
label | 6e929e56-e1f3-5022-b7e8-c0fa9149da48 |  | note | Applicable Standard and/or Technical Requirement: AS/NZS 1554.1:2014, AS/NZS 5131:2016 Sect. 7.5.4
label | f5e8651f-d919-5677-bf27-c4bf328637d6 |  | note | Method: Inspection
label | 470ca054-f8f6-550e-99e8-49c204549719 |  | note | Frequency: 100%
label | 311bf0cf-6dc1-5a02-93ce-19b7b7abed5c |  | note | Verification Activity By - Eastbridge: R
label | 15899f9c-0979-54f5-9be8-e8262c6e8023 |  | note | Verification Activity By - Contractor: R
label | 022b9ee0-7f98-52ae-aa03-6df223f09470 |  | note | Verification Activity By - Client Rep: R
label | 648cb7c1-63ca-5269-a0d2-c3f7e7b05e46 |  | note | Verifying Record: Non-Destructive Testing Weld Report
checkpoint-status |  |  | checkpoint | 4.5 - Welder traceability
label | a28104c3-e067-5a53-986d-6d2765509b0c |  | note | RI: IWCI
label | 36b5ee17-b433-5d63-bbc8-11eecc0e17c6 |  | note | Acceptance Criteria: Welders to be traceable in accordance with Table 7.4 - CC4
label | a94f1a58-7ee1-50fc-94d8-ad3b9b8fd537 |  | note | Applicable Standard and/or Technical Requirement: AS/NZS 1554.1:2014, AS/NZS5131:2016 Sect 7.4.3 Table 7.4
label | ced4b465-3fdf-52c2-9bb2-a97f55a56191 |  | note | Method: Review
label | a74b0b68-546e-5211-9cfc-4a4acfa4f216 |  | note | Frequency: 100%
label | 09cd1d70-b453-51a5-9aad-b5bebffb118e |  | note | Verification Activity By - Eastbridge: S
label | dc4ab373-fc27-5bde-a958-cf4bc3fc4988 |  | note | Verification Activity By - Contractor: R
label | 1146c82b-fe67-589c-9d25-0caccf53d716 |  | note | Verification Activity By - Client Rep: R
label | 710133ce-54a0-58eb-a17f-d08c2792ad57 |  | note | Verifying Record: Ultrasonic Weld Report
checkpoint-status |  |  | checkpoint | 4.6 - Stud Welding
label | b665e8a2-6d87-5dc1-b61a-9ee9b66a392c |  | note | RI: EBWI
label | 02e24edc-7f3a-53eb-906f-396410e1d0a5 |  | note | Acceptance Criteria: Welders to be selected in accordance with AS/NZS 1554.2:2003
label | 3ae8ff3c-e0e6-5957-87ce-cec24b6de615 |  | note | Applicable Standard and/or Technical Requirement: AS/NZS, AS/NZS 1554.2:2003 5131:2016 Sect. 5.6 & 7.5.11
label | 1a86237d-3ea0-5876-8e40-613d1cf8ea43 |  | note | Method: Review
label | 63b49b81-55c9-5fde-9277-8f742255a568 |  | note | Frequency: 100%
label | 92ecada7-d269-5d8d-946e-fdde9ca7d4b9 |  | note | Verification Activity By - Eastbridge: H
label | d607d203-aa0b-571d-a4aa-d5e3af51e7ee |  | note | Verification Activity By - Contractor: R
label | 1efbd8d5-2c07-5f7d-9047-68a1096c5264 |  | note | Verification Activity By - Client Rep: R
label | 93fab935-5243-5709-973d-66b1e6dc60fe |  | note | Verifying Record: Eastbridge Standard Welding Checksheet
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 5 - Welding Inspection & NDT
checkpoint-status |  |  | checkpoint | 5.1 - Weld Testing Regime
label | 6ce6d8be-4819-54f4-82cf-4bc4ad34bd57 |  | note | RI: PM
label | 0d13a1b9-a205-5abd-a20c-83122327e05e |  | note | Acceptance Criteria: Generally, spread across all weld types, all welders and multiple welds of the same type.
label | 3e24ad28-0878-552f-8021-9264b989a73d |  | note | Applicable Standard and/or Technical Requirement: AS/NZS 1554.1:2014
label | 165df49b-b056-5bdc-b582-194385b40cb9 |  | note | Method: Review
label | 6798b35c-a602-59c5-b070-8ae13640e35e |  | note | Frequency: Once
label | b8042eae-a27d-5d7a-b82e-9dd521a483bd |  | note | Verification Activity By - Eastbridge: H
label | 4c07c96f-c6ee-552c-b3e4-2a60530342d5 |  | note | Verification Activity By - Contractor: R
label | e1adc174-8786-5b78-a6b2-3b82c285cee6 |  | note | Verification Activity By - Client Rep: R
label | 78e9d23d-8815-57df-9433-8c4f57dca536 |  | note | Verifying Record: Approved Weld Testing Regime
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.2 - Weld Integrity: Visual Scanning
label | 6ab7aa6b-4b50-56a8-b15b-b3b3c150fabc |  | note | RI: EBWI
label | 09ee7229-4fa4-5f99-bb86-12419afbf64d |  | note | Acceptance Criteria: Weld location is as per shop drawing for each section
label | 8d6300a9-c384-5e12-93f2-65d73f611ec7 |  | note | Applicable Standard and/or Technical Requirement: AS/NZS 1554.1:2014
label | 3e6ee5c8-abc5-52e9-a6e0-a3aedc953da0 |  | note | Method: Inspection
label | 6b007aba-b3a1-5621-b2c9-64b1bc3439b1 |  | note | Frequency: 100%
label | 4e5c69fb-2c5f-5e58-9d8e-0b93f84dd646 |  | note | Verification Activity By - Eastbridge: H
label | 17032031-67f4-578b-8885-25096231dac5 |  | note | Verification Activity By - Contractor: R
label | 33055adf-21b3-5084-a94c-f871cea54ef8 |  | note | Verification Activity By - Client Rep: R
label | 68481828-84bc-5d2e-943e-20eb9e856895 |  | note | Verifying Record: Visual Scanning Weld Report
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.3 - Weld Integrity: Visual Examination
label | 18b46121-449a-5026-bb4f-21119964e713 |  | note | RI: EBWI
label | 9470f371-0561-5e5e-aff7-6dbcfb3ffd99 |  | note | Acceptance Criteria: Table 6.2.2: Permissible levels of imperfections in butt and fillet welds as determined by visual, magenetic particle and liquid penetrant examination of the weld zone
label | 734c3d2d-1fd6-5e20-817a-5b134badb7fd |  | note | Applicable Standard and/or Technical Requirement: AS/NZS 1554.1:2014
label | f0d5c52b-eff1-5c71-a0ae-c7b7ec96f701 |  | note | Method: Inspection
label | 8542c680-d6d4-5dd9-8c39-dbb4c4765222 |  | note | Frequency: 100%
label | f149b876-4479-5584-994e-1be1bca4556c |  | note | Verification Activity By - Eastbridge: H
label | bae40633-e168-57a7-a139-69ede5628df2 |  | note | Verification Activity By - Contractor: R
label | f5f0dc2f-838a-5be5-ab83-5cefd18cc7c4 |  | note | Verification Activity By - Client Rep: R
label | ade96f5c-886f-510f-9d90-19d7253aa690 |  | note | Verifying Record: Visual Examination Weld Report
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.4 - Weld Integrity: Magnetic Particle Inspection
label | 6482b94f-972a-5dd6-8202-393fd2824e25 |  | note | RI: IWCI
label | 4cb6bd04-4f47-5de8-b9da-39be4ae49300 |  | note | Acceptance Criteria: Structural fillet welds only
label | 41ba21cb-5f21-545b-ada1-6cbbb9e70922 |  | note | • Table 6.2.2: Permissible levels of imperfections in butt and fillet welds as determined by visual, magenetic particle and liquid penetrant examination of the weld zone
label | 8177e323-3957-5b8a-83fe-3d16eff9afc9 |  | note | Applicable Standard and/or Technical Requirement: AS/NZS 1554.1:2014
label | 469aa26f-d017-5ae2-9687-cd0bfb08ed9f |  | note | Method: MPI
label | 3edc5220-7444-5665-84dc-d7ff893dbb17 |  | note | Frequency: 25%
label | 48830358-72c6-5c7b-9f2f-ea1532ec92a5 |  | note | Verification Activity By - Eastbridge: H
label | bae659ff-82ad-5bb7-8659-8ac0f07ccb2b |  | note | Verification Activity By - Contractor: R
label | 94d5d8ce-4c00-5bda-bb5b-66412180717e |  | note | Verification Activity By - Client Rep: R
label | 1057f8f8-538b-5b43-9db9-5aff6653080a |  | note | Verifying Record: Non-Destructive Testing Weld Report
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.5 - Weld Integrity: Ultrasonic Testing
label | 27d4fbfb-facc-568c-b651-3def9830d7db |  | note | RI: IWCI
label | 90281217-12e3-5cb4-9420-257cb1b14cd2 |  | note | Acceptance Criteria: Structural butt welds only
label | 9cf72485-663d-5927-a09c-c739aab8ad90 |  | note | • Table 6.2.1: Permissible levels of imperfections as determined by radiograpic or ultrasonic examination for welds of category SP
label | 7efbe26e-93c1-5977-9497-f96a4582c9b2 |  | note | Applicable Standard and/or Technical Requirement: AS/NZS 1554.1:2014, AS 2207
label | 546f241d-cd2d-502f-81f0-cd85a42015ac |  | note | Method: UT
label | 0a270af2-2136-5eed-9186-4f4fafa40996 |  | note | Frequency: 25%
label | e7f7d190-d1fb-50eb-aaaf-6b00c23667c9 |  | note | Verification Activity By - Eastbridge: H
label | 164e49f5-c453-58f2-9a00-f24e1a586907 |  | note | Verification Activity By - Contractor: R
label | 29d894eb-494d-572b-a541-d106028a6e22 |  | note | Verification Activity By - Client Rep: R
label | af6d7415-3965-5557-a562-8949fdef7fb6 |  | note | Verifying Record: Ultrasonic Weld Report
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.6 - Stud Welds: Ring Testing
label | ccbce7cf-437d-5f88-bb74-0450d5567636 |  | note | RI: EBWI
label | 08755ed7-e7d5-5f95-932e-46581ad52570 |  | note | Acceptance Criteria: "Ring" sound of stud when tapped with a 3kg hammer in the direction of the beam.
label | b888d843-4b31-5258-afea-2fd8e53a6b9a |  | note | • If stud gives a "'dead' sound, the test is failed.
label | 7cc5d6f2-bf87-57fb-bfd1-884d29e27882 |  | note | Applicable Standard and/or Technical Requirement: AS/NZS 1554.2:2003
label | d3fcb001-c82c-5205-980f-62c4b6b67975 |  | note | Method: Ring Test
label | b1f1a494-caef-5ae6-a093-ba59f23267dc |  | note | Frequency: 100%
label | 6b3267e3-24e9-582d-b497-9172f70a6f2a |  | note | Verification Activity By - Eastbridge: H
label | f8a6e075-053e-5468-af74-20717f7a71fd |  | note | Verification Activity By - Contractor: R
label | 6893ecd5-a47e-5733-9c0d-b472b0934557 |  | note | Verification Activity By - Client Rep: R
label | 81d4fd14-e569-514e-ab68-c9175155285e |  | note | Verifying Record: Eastbridge Standard Welding Checksheet
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.7 - Stud Welds: Bend Testing
label | a9059750-a96b-53a8-8b7b-99039ed15cc2 |  | note | RI: EBWI
label | 33e5f4a6-a755-5260-84e7-544e0d57ac7a |  | note | Acceptance Criteria: No evidence of fracture under bending 15 degrees from original axis
label | 03f9764d-3446-52e3-a390-d20a25de3300 |  | note | • First and second for each production weld set-up followed by specified frequency
label | d3d0b646-330f-5ec7-94b0-be16ba25b8fe |  | note | Applicable Standard and/or Technical Requirement: AS/NZS 1554.2:2003
label | 6139ceb2-3f5f-5263-a922-6819d8a20e25 |  | note | Method: Bend Test
label | e8b19db2-dfca-5b30-bb66-abfb076212b6 |  | note | Frequency: 1 in 50
label | 2c675387-3906-58c3-8326-ad6b6ff6dcb6 |  | note | Verification Activity By - Eastbridge: H
label | bdb95933-cf0c-541c-8c3e-c6302039571d |  | note | Verification Activity By - Contractor: R
label | 265940cf-d2e2-5ad8-b892-aa87732c2efb |  | note | Verification Activity By - Client Rep: R
label | 13ef9119-bc38-5699-b555-8203320d0e67 |  | note | Verifying Record: Eastbridge Standard Welding Checksheet
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.8 - Fabricated Condition
label | 15ddd0f5-b27c-5c06-8b3a-2b913584d2a8 |  | note | RI: EBWI
label | 4449e153-da88-52b9-a6cf-fb6e84a98fc2 |  | note | Acceptance Criteria: Ensure slag, spatter, scale and flux has been removed and general appearance is acceptable
label | 99e21b5f-1b50-55ec-8056-2eed38f2d2ba |  | note | Applicable Standard and/or Technical Requirement: AS/NZS 1554.1:2014
label | a1627706-7f87-5b0a-b15c-3e32418d28f5 |  | note | Method: Inspection
label | 8a0e07ca-a5ad-59a9-b626-36be3bfd92ba |  | note | Frequency: Per Section
label | 7eecd31f-c31c-5b98-897c-b49ef2cf16fc |  | note | Verification Activity By - Eastbridge: I
label | cba4b526-795c-569c-907e-2f727fef1d90 |  | note | Verification Activity By - Contractor: R
label | 7b4f42c7-dfd1-5879-be17-9e1c7af093df |  | note | Verification Activity By - Client Rep: R
label | 2c2adc92-f6fa-5332-9b3f-2e7021e81955 |  | note | Verifying Record: Eastbridge Standard Fabrication Checksheet
checkpoint-group |  |  | section | 6 - Post Fabrication
checkpoint-status |  |  | checkpoint | 6.1 - Final Inspection
label | 9a033fe8-9d65-51a4-9329-abfbc6014bb3 |  | note | RI: PM
label | 20833c9b-8fc0-56b0-90cf-fa6297cb02ab |  | note | Acceptance Criteria: Ensure all inspections and tests are completed, all reports and documentation are available and all results comply with the requirements
label | ca20b0f0-00be-52bb-8412-b0790ad5a6ec |  | note | Applicable Standard and/or Technical Requirement: –
label | 397e42e0-0a61-5bb4-ac37-bb40983fd6de |  | note | Method: Review
label | a916975c-63c5-553d-a770-19ba2c9fff40 |  | note | Frequency: Per Dispatch
label | 3257d585-13cc-5730-946d-559bd457c3d7 |  | note | Verification Activity By - Eastbridge: H
label | 20c1265f-fad9-53b6-b279-5252a7cecb56 |  | note | Verification Activity By - Contractor: H
label | 9f7a280c-e329-5f4f-b8a6-246646ff77ec |  | note | Verification Activity By - Client Rep: H
label | 66843634-eb17-5ff4-8f5a-a2c65cffa654 |  | note | Verifying Record: Final Inspection Checksheet
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 6.2 - Dispatch
label | c6dc0831-4eea-533d-9c35-94db411dd43a |  | note | RI: PM
label | 193e02fa-b361-523b-b21e-88fe632b1a70 |  | note | Acceptance Criteria: Inspect delivery dockets and ensure that each item on packing list has been packed and in the correct quantity inclusive of weights
label | 666d46f9-b48e-57ce-af4b-9e1d7725ff34 |  | note | Applicable Standard and/or Technical Requirement: –
label | b9128002-69a6-5b33-8a2e-626bdbfba51e |  | note | Method: Review
label | f1eaf4e7-0384-515f-b285-226d8c0d4130 |  | note | Frequency: Per Dispatcj
label | deaf2588-8757-5331-b135-692ffc0d6565 |  | note | Verification Activity By - Eastbridge: H
label | eb5162cc-daa8-5ee0-a3eb-f6a245f26103 |  | note | Verification Activity By - Contractor: R
label | 37811740-40c2-5348-b527-2b9046fd9385 |  | note | Verification Activity By - Client Rep: R
label | fc2f33c9-4c3c-554d-bfb6-868d5d3b9c48 |  | note | Verifying Record: Dispatch Docket
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | ITP Sign Off for Construction
text | e27e7cae-4810-543b-bc2b-d16ca2195ce1 |  | textbox | Project Engineer:
text | f7615aa1-9d77-5048-a02c-1ace5bab43d3 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | All works completed, records attached and work conforming
text | 3b017e20-c39b-53a6-8623-bfcfb31a01fe |  | textbox | Site Engineer:
text | 85e8ff8d-1077-5f0c-8fc2-2a3988ac167d |  | textbox | Date:
text | 0efe9735-ef79-5061-9bf7-77885eb22415 |  | textbox | Project Engineer:
text | a4d06d4a-e5d0-5c6d-b961-f6de4774b785 |  | textbox | Date:
text | 3ca540b8-4555-56cf-83f4-eb2c380fa699 |  | textbox | Quality Manager:
text | 919a791f-a5b0-53b3-8e31-0b73da65bae5 |  | textbox | Date: