## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Timber Work | itp |  |  |  | Yes | ITP - Timber Work | 1d4f7de0-5db2-42cf-9b77-1347c2205dfc
checkpoint-group |  |  | section | Preliminary
checkpoint-status |  |  | checkpoint | Procurement
label | 045f6e78-5bed-5f94-8c62-f94e1f44f246 |  | note | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | 3977170c-1ed7-5b66-81e6-2ed14fdf939b |  | note | TEST REQUIRED - Dockets
label | 7cfc84b6-d9dd-5c88-90ca-672c3fca3243 |  | note | INSPECTION BY - UCCL
label | 11c8751f-346e-509d-b093-8a9b83d91527 |  | note | TASK TIMING OR TASK FREQUENCY - For any timber ordered for project
label | 23b113b3-0ef6-5927-855a-eb56c5ca510e |  | note | ACCEPTANCE CRITERIA - All timber to meet specified grade and Moisture content as specified in particular specification
label | cd675ea4-3504-50f8-9ddb-391cd32a0885 |  | note | UCCL - W
label | 57d02880-a3a6-59ef-9901-0e16f7d17b30 |  | note | WSP - W
checkpoint-status |  |  | checkpoint | Installation
label | 146a2f52-3932-5ede-a4c5-cafca68c7883 |  | note | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | e0b9aa0e-4071-524c-b0dd-bc57bcc6fcd7 |  | note | TEST REQUIRED - Visual Inspection/Photos
label | fe9e9ab3-3b7d-5442-8d09-ee1ff0aafbda |  | note | INSPECTION BY - Engineer
label | bcd82075-6c41-54fe-8d12-6d3f54488b0a |  | note | TASK TIMING OR TASK FREQUENCY - Random site visits
label | 61ce02b1-d677-53ac-b565-351f702c4d11 |  | note | ACCEPTANCE CRITERIA - All timber and Fastners installed as per IFC Drawing
label | b743f737-017f-565a-b451-34f294202959 |  | note | UCCL - W
label | 8619319a-2d0a-5bb0-8df4-28b32bf853db |  | note | WSP - W
checklist-sectioned |  |  | checklist | Piling | itp |  |  |  | Yes | ITP - Piling | 530c4f47-6d42-4d40-8cf5-d9b862a96c02
checkpoint-group |  |  | section | Preliminary
checkpoint-status |  |  | checkpoint | Shop Drawings
label | 27fd4e18-bf34-52ae-b21b-318f635ee9d6 |  | note | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | 5b987232-10cf-55d1-bd26-aa4d46c6d379 |  | note | TEST REQUIRED - Approved shop drawings prior to fabrication
label | 1b329a63-1f23-5e97-8508-598cceb1af05 |  | note | INSPECTION BY - Engineer
label | c5aa2d81-ba51-5b57-b279-ca0203309e84 |  | note | TASK TIMING OR TASK FREQUENCY - 5 Days before commencing fabrication
label | 7fe24ed6-33da-503c-aaf6-b3c624ab7b2b |  | note | ACCEPTANCE CRITERIA - Approved by Engineer
label | 9a81058b-32c1-5bd2-a466-052a5d8816b3 |  | note | UCCL - H
label | 30cfe072-e1b7-545a-abaf-0cafcd81e677 |  | note | WSP - H
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Concrete Mix Design Approved
label | 9ac87efe-f4ce-58fe-ae6d-5a6dcb48bb09 |  | note | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | b4f4a1c1-067f-57e0-9caf-0fc1f34aac8c |  | note | TEST REQUIRED - Approval from Engineer
label | 342cbd33-8697-5ed4-ac96-8dea970ef18b |  | note | INSPECTION BY - Engineer
label | 44c5959f-e135-522d-9e03-9f17a33a2852 |  | note | TASK TIMING OR TASK FREQUENCY - Per Mix Design
label | 1e2e61c7-843f-5407-8cc8-1aac639b3df4 |  | note | ACCEPTANCE CRITERIA - Approved by Engineer
label | 78199e73-292b-5a2a-9d53-5242af2dbd53 |  | note | UCCL - H
label | 774b45d2-1eed-5ca7-b0aa-6d98452079f1 |  | note | WSP - H
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Pre cast Piles
checkpoint-status |  |  | checkpoint | Pre Pour Inspection
label | fde25545-7718-53d8-918a-a31b64a585a3 |  | note | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | 620908ad-5754-5baa-9730-76cc6c640270 |  | note | TEST REQUIRED - Visual Inspection
label | 92ac2c57-7bfc-5c96-8a78-88466484433e |  | note | INSPECTION BY - Engineer
label | 9266700a-84c4-59b4-ba27-ebb1b6051cad |  | note | TASK TIMING OR TASK FREQUENCY - Pre pour inspection for each pile
label | da813a9a-6602-5628-a57c-04814bc047ce |  | note | ACCEPTANCE CRITERIA - Pre pour inspection checksheet
label | 44336646-544c-554e-b9cb-9c07b9a71897 |  | note | UCCL - H
label | 6b712b7d-a6bc-5786-a674-9cddca7e7036 |  | note | WSP - H
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Abutment A Piles
checkpoint-status |  |  | checkpoint | Pile setout
label | e9c57f91-d28e-5966-b427-9f95fd97462b |  | note | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | e9585041-e922-57b4-8d84-9b04782dc928 |  | note | TEST REQUIRED - Visual Inspection
label | d0119370-5a9a-5b2e-a3de-a36a4512105b |  | note | INSPECTION BY - Engineer
label | 6786ad16-dc1c-5956-900f-75228aff8081 |  | note | TASK TIMING OR TASK FREQUENCY - After setout of each pile
label | bb1cf645-bffb-56d5-9914-9b14c0e98202 |  | note | ACCEPTANCE CRITERIA - As per IFC Drawings. Top of Pile should be within tolerance iof 75mm Horizontally and 25mm Vertically. Maximum Daviation from vertical at any level shall not be more than 1:75
label | e14b9d0b-5ae4-56a9-9af3-0f38e48e02c4 |  | note | UCCL - H
label | 8a572494-742b-5fd0-b8c1-03a5affb2b9c |  | note | WSP - H
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Driving Of Piles
label | 0d0210ab-2536-52c0-a416-f0c99ca9dca3 |  | note | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | 9b284a62-ccbe-5ce0-9a30-e05bfb5c96e4 |  | note | TEST REQUIRED - Visual Inspection
label | 8d25ce56-a9cd-556f-b4fc-85b5f93a26e8 |  | note | INSPECTION BY - Engineer
label | c580e89b-b5c4-59d4-8d00-77de2f9bbe43 |  | note | TASK TIMING OR TASK FREQUENCY - For each Pile
label | 10649ca8-753d-59c2-a098-d9bf4c4b2188 |  | note | ACCEPTANCE CRITERIA - Pile shall be driven to an ultimate bearing capacity of 1000kN and a minimum embedment depth of 10.5m from top of abutment wall. Pile Installation Checksheet
label | d080a68f-4c61-55e3-86ee-7a78a5cbdd4d |  | note | UCCL - W
label | a11145a1-e5aa-5b70-aa18-f5b7b2a02341 |  | note | WSP - W
checkpoint-group |  |  | section | Abutment B Piles
checkpoint-status |  |  | checkpoint | Pile setout
label | 2311d41f-7070-5391-b978-8cf0ea144913 |  | note | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | 8be154df-caf3-5c8e-8851-80f957b5f0fd |  | note | TEST REQUIRED - Visual Inspection
label | cfea370a-18ad-5d35-b90d-fffb794fdf3a |  | note | INSPECTION BY - Engineer
label | 3ebd083d-ad30-5765-b0d4-eeb111942a53 |  | note | TASK TIMING OR TASK FREQUENCY - After setout of each pile
label | 382995c4-e998-590c-ab15-23126ad43f67 |  | note | ACCEPTANCE CRITERIA - As per IFC Drawings. Top of Pile should be within tolerance iof 75mm Horizontally and 25mm Vertically. Maximum Daviation from vertical at any level shall not be more than 1:75
label | bed70145-73b2-51b5-a48a-06b37592827a |  | note | UCCL - H
label | 597a8ba4-f3da-584a-a3e7-fb43bad1a955 |  | note | WSP - H
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Driving Of Piles
label | c6faac11-20e5-5651-be51-41cb5c2b91b4 |  | note | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | 9805ccd7-7072-5cf0-9571-991136f850e9 |  | note | TEST REQUIRED - Visual Inspection
label | d0fe6e43-6674-5dd6-b22f-cc1526eb566e |  | note | INSPECTION BY - Engineer
label | 21edb95d-e8f6-53e9-9b32-361369238408 |  | note | TASK TIMING OR TASK FREQUENCY - For each Pile
label | ad90d516-065a-58b9-a5f2-eaa5fdf29898 |  | note | ACCEPTANCE CRITERIA - Pile shall be driven to an ultimate bearing capacity of 1000kN and a minimum embedment depth of 10.5m from top of abutment wall. Pile Installation Checksheet
label | af1ab758-96bb-5149-a4f2-e658ef05d3d5 |  | note | UCCL - W
label | ebb81240-ee2c-5b50-9fce-de06e159f85a |  | note | WSP - W
checklist-sectioned |  |  | checklist | Concrete Inspection |  |  |  |  | Yes | Concrete Inspection | 7f152e51-4b61-4603-b420-2810bb791e33
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | Adequately braced and supported
checkpoint-status |  |  | checkpoint | Grout tight
checkpoint-status |  |  | checkpoint | Correct dimensions
checkpoint-status |  |  | checkpoint | Cleaned and oiled
checkpoint-status |  |  | checkpoint | Formed surfaces straight
checkpoint-status |  |  | checkpoint | Major penetrations located
checkpoint-status |  |  | checkpoint | Embedded items located
checkpoint-status |  |  | checkpoint | Correct for specified surface finish
checkpoint-status |  |  | checkpoint | Adequate seating Pre Cast units
checkpoint-status |  |  | checkpoint | Permit to Load Obtained
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | Reinforcement Content and size
checkpoint-status |  |  | checkpoint | Confirm correct grade markings
checkpoint-status |  |  | checkpoint | Placement, tolerance, clearance
checkpoint-status |  |  | checkpoint | Rigidity and cover
checkpoint-status |  |  | checkpoint | Clean steel
checkpoint-status |  |  | checkpoint | Lap location and lengths
checkpoint-status |  |  | checkpoint | Starters/dowels correctly located
checkpoint-group |  |  | section | Construction Joints
checkpoint-status |  |  | checkpoint | Location
checkpoint-status |  |  | checkpoint | Roughened
checkpoint-status |  |  | checkpoint | Clean
checkpoint-status |  |  | checkpoint | Water bar placed if specified
checkpoint-group |  |  | section | Post Pour
checkpoint-status |  |  | checkpoint | Correct mix ordered
checkpoint-status |  |  | checkpoint | Independent Survey – Check off critical survey points
checkpoint-status |  |  | checkpoint | Engineer’s Rep Notified
holdpoint |  |  | signoff | Pre-Pour Checked and Accepted
checkpoint-group |  |  | section | Wet Concrete Checks
checkpoint-status |  |  | checkpoint | Correct mix delivered
checkpoint-status |  |  | checkpoint | Slump/flow Target
checkpoint-status |  |  | checkpoint | Compliance Cylinders Taken
checkpoint-status |  |  | checkpoint | Site Cured Cylinders Taken
checkpoint-status |  |  | checkpoint | Concrete Vibrated
checkpoint-status |  |  | checkpoint | Mandrels drawn through all ducts to verify no leakage / disconnection
checkpoint-status |  |  | checkpoint | Finished Level: Finished to grout check / angle fillet worked to
checkpoint-status |  |  | checkpoint | Surface to required finish eg U2, U4
checkpoint-status |  |  | checkpoint | Retarder applied at end of the pour
checkpoint-status |  |  | checkpoint | Curing applied (specify type)
checkpoint-status |  |  | checkpoint | Concrete Supply Dockets collected
checkpoint-group |  |  | section | Post Concrete Inspection
checkpoint-status |  |  | checkpoint | Curing correctly carried out
checkpoint-status |  |  | checkpoint | Concrete Strength for Striking
checkpoint-status |  |  | checkpoint | Concrete Strength for backfilling
checkpoint-status |  |  | checkpoint | Preparation of Construction Joints Completed
checkpoint-status |  |  | checkpoint | Blow holes, tie bar holes filled
checkpoint-status |  |  | checkpoint | Inspection of surface/s & any authorised repairs have been completed
checkpoint-status |  |  | checkpoint | As-Built complete
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Pre-Pour Checked and Accepted
text | 48513fa4-beca-5b1a-93a6-f5d5b57046d7 |  | textbox | Contractor Name
text | f39933d9-8d12-5f14-bfbb-b589e08b7fe7 |  | textbox | Date
text | 9c7a0efd-ef54-5039-b577-68d8b70ae14b |  | textbox | Engineer Name
text | d0332bcb-dd67-5dbb-ba9e-c5bf48927d5e |  | textbox | Date
checklist-flat |  |  | checklist | Structural Steel Works |  |  |  |  | Yes | Structural Steel Works | 87ae7923-af38-48c6-96bb-de237ee693f9
checkpoint-status |  |  | checkpoint | Sub contractor's ITP
checklist-flat |  |  | checklist | Document: |  |  |  |  | Yes | Project Documentation | 949f82e2-8372-4e36-af0e-275f27b01b0c
checkpoint-no-status |  |  | checkpoint | Document Attached
checklist-sectioned |  |  | checklist | Abutment and Backwall | itp |  |  |  | Yes | ITP - Abutment and Backwall | a4e563a8-cf76-4995-a78e-437f85af550c
checkpoint-group |  |  | section | Preliminary
checkpoint-status |  |  | checkpoint | Concrete Mix Design Approved
label | 14d6aa92-1a88-54c0-a10d-d6eb98ea576f |  | note | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | c55515f4-33a2-5135-8113-7ef858569538 |  | note | TEST REQUIRED - Approval from Engineer
label | 9f538808-6682-5214-a2cc-b32e66abf5f6 |  | note | INSPECTION BY - Engineer
label | 5d5628e1-1d24-5134-8732-fcc7e8a4424b |  | note | TASK TIMING OR TASK FREQUENCY - Per Mix Design
label | 5e8888e5-9f0f-5654-8a95-b1219f0a6d42 |  | note | ACCEPTANCE CRITERIA - Approved by Engineer
label | 4bc19362-b806-5b22-b8b5-f71eb700e6b0 |  | note | UCCL - H
label | 4ae47f10-1ba5-5859-a14a-4bf7adab33f1 |  | note | WSP - H
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Abutment A Construction
checkpoint-status |  |  | checkpoint | Setout
label | a65854df-513e-52d4-8cec-add115f4150e |  | note | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | c272661b-9f22-5c88-a177-63459e151a61 |  | note | TEST REQUIRED - Visual Inspection
label | 93450af0-6fd0-52f1-8e11-d98f5d9f0cf0 |  | note | INSPECTION BY - Enginner
label | e1be8181-c6e8-51ff-8f25-1a7a68333190 |  | note | TASK TIMING OR TASK FREQUENCY - For set out of each Abutment
label | 4df9ac38-322b-516d-ab22-c3e11bb2a334 |  | note | ACCEPTANCE CRITERIA - As per IFC Drawings
label | b7be1c4a-7ced-53da-85f2-65239d87c640 |  | note | UCCL - W
label | ed91f2fa-be7f-56a7-867a-3fcbd68f1bb2 |  | note | WSP - H
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Pre Pour Inspection
label | f578fe2e-6c9d-5a30-91d2-b781cda5eb09 |  | note | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | e5c55f24-7ee6-5c6b-b703-283f1995a89f |  | note | TEST REQUIRED - Visual Inspection
label | 5ae2c214-8975-5c60-b831-6fec04682dbc |  | note | INSPECTION BY - Engineer
label | e1011cbf-f91e-566c-81a9-6cdf730cb9e6 |  | note | TASK TIMING OR TASK FREQUENCY - Pre pour inspection for Abutment
label | 0269f9db-0d10-55e3-9150-a7d396d78878 |  | note | ACCEPTANCE CRITERIA - Pre pour inspection checksheet
label | 01ab1961-67d6-54f9-87cb-90043ff0f811 |  | note | UCCL - H
label | 5622fa67-4593-5c60-95e0-91f7783488ae |  | note | WSP - H
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Abutment B Construction
checkpoint-status |  |  | checkpoint | Setout
label | 53838041-494e-53d1-808d-83226a0877b4 |  | note | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | 1ffb9f4a-2014-5a1c-8740-c947fa2e648b |  | note | TEST REQUIRED - Visual Inspection
label | 17398078-65d9-5cb5-9f0b-e1953da3cde4 |  | note | INSPECTION BY - Engineer
label | 668377de-13cf-5ae4-bb8c-b8d92ffd5e8b |  | note | TASK TIMING OR TASK FREQUENCY - For set out of each Abutment
label | 0fbfefbc-83b0-5ab9-90aa-41de24ffba0f |  | note | ACCEPTANCE CRITERIA - As per IFC Drawings
label | d5b486a6-0f1a-55b8-8cc0-f5d554a573c0 |  | note | UCCL - W
label | d3fe683e-b38e-53ed-9a0a-9cc3c082ace6 |  | note | WSP - H
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Pre Pour Inspection
label | adfbba8f-9a28-5bdb-9aaf-4ad8f083e911 |  | note | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | a1c112e7-76c6-5f27-afaf-4da40b2a94b1 |  | note | TEST REQUIRED - Visual Inspection
label | f0f777a7-fda2-534b-baaa-ec9a69ad7017 |  | note | INSPECTION BY - Engineer
label | de916968-1a63-5905-b0f2-4838b5088b6a |  | note | TASK TIMING OR TASK FREQUENCY - Pre pour inspection for Abutment
label | 4fecd3d3-a7a1-584f-b623-2940cf6dbbab |  | note | ACCEPTANCE CRITERIA - Pre pour inspection checksheet
label | edbc324c-ebe0-5026-9e91-67ed6f74168d |  | note | UCCL - H
label | af6a13c9-8212-5ff4-8daa-42d0639fc57c |  | note | WSP - H
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Abutment A Backwall Construction
checkpoint-status |  |  | checkpoint | Pre Pour Inspection
label | 29f9f0c1-42ea-51fb-8d2a-0b27800b0e57 |  | note | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | c49bc296-1256-5feb-94a7-f1a3ed43b323 |  | note | TEST REQUIRED - Visual Inspection
label | 143a7b8a-a64b-5f62-9bae-111d66ac966d |  | note | INSPECTION BY - Engineer
label | c86be9e5-dfa9-5ba1-93d0-57c631201da6 |  | note | TASK TIMING OR TASK FREQUENCY - Pre pour inspection for Abutment
label | 4a287f44-d851-5c54-be1c-f57412b60249 |  | note | ACCEPTANCE CRITERIA - Pre pour inspection checksheet
label | f54786b3-d997-5c2e-8cc0-6efd69d97dba |  | note | UCCL - H
label | 2f8514a5-4f40-54e4-ab6c-62ed53d47575 |  | note | WSP - H
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Abutment C Backwall Construction
checkpoint-status |  |  | checkpoint | Pre Pour Inspection
label | 3ed1791d-721f-558e-b450-38d08165f04c |  | note | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | 1a9d2aa7-60ca-51e4-b74c-5602a0dec020 |  | note | TEST REQUIRED - Visual Inspection
label | 02e12186-440a-5d02-8818-856fd1f8bba0 |  | note | INSPECTION BY - Engineer
label | 538000c3-9267-56ce-8696-f0cba7c36b3f |  | note | TASK TIMING OR TASK FREQUENCY - Pre pour inspection for Abutment backwall
label | c6c1fdbd-84c3-5059-a34e-9802d585d3c0 |  | note | ACCEPTANCE CRITERIA - Pre pour inspection checksheet
label | 17a0c8b5-9911-5db9-8daf-0d46a301595c |  | note | UCCL - H
label | eed11f64-8449-5b4d-845d-272bde13baed |  | note | WSP - H
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Construction of Mortar Bearing Pad
checkpoint-status |  |  | checkpoint | Pre Pour Inspection
label | a60f51b1-c494-54fb-9a88-a481fd32bd1d |  | note | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | f66f5b26-ec05-551d-84fb-7d0a8d1e746d |  | note | TEST REQUIRED - Visual Inspection
label | 7335d724-13d6-55a6-90d7-e41b849cc478 |  | note | INSPECTION BY - Engineer
label | d7c16a25-89af-5fce-810d-ead0eaac59eb |  | note | TASK TIMING OR TASK FREQUENCY - Pre pour inspection for Abutment
label | 16c7c292-5231-56dd-9191-5573c2646d9d |  | note | ACCEPTANCE CRITERIA - Pre pour inspection checksheet
label | 14e8f8ba-65c6-5673-9a91-40ce2c727d62 |  | note | UCCL - H
label | 9125bd1f-cebe-5d5f-8d21-6224b1505a87 |  | note | WSP - H
holdpoint |  |  | signoff | HOLD POINT
checklist-sectioned |  |  | checklist | Reinstate Approaches | itp |  |  |  | Yes | ITP - Reinstate Approaches | ac013813-a384-4c9f-bc53-65fb44744b3b
checkpoint-group |  |  | section | Preliminary
checkpoint-status |  |  | checkpoint | Backfill
label | fc6b2b71-c07d-519d-9480-dffddc7f8f68 |  | note | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | a4ca058c-dc61-5b11-bf46-420bc5048702 |  | note | TEST REQUIRED - Clegg Test
label | 137033f5-6051-5251-95bb-aa88404469af |  | note | INSPECTION BY - UCCL/Engineer
label | e4ec0ae3-22ef-545c-9eaf-c254db250251 |  | note | TASK TIMING OR TASK FREQUENCY - 5 Tests per approach per layer
label | bef40165-697c-5870-acb7-6369b3269df6 |  | note | ACCEPTANCE CRITERIA - Clegg Impact value of 40
label | ff9d7f22-c8c1-553d-9375-b9871290aae6 |  | note | UCCL - W
label | b6ebb3a1-651e-5460-b22c-72dda407cd61 |  | note | WSP - W