## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 77d6ea8a-7c68-4562-88ec-0056d611c1d8 |  | checklist | P |  |  |  |  | Yes | SYS - 1. Standard (old version) | 4bd2ac73-ce65-4dee-8751-7325c797c1e7
checkpoint-group | d84a9143-8c84-4cc2-b575-bd3288fd86a9 |  | section | Precast Element Details
checkpoint-status | 1932e93b-d3e9-402f-83d0-e322d0c77950 |  | checkpoint | Concrete Details Complete
text | cb71af8f-5c03-5976-9285-bcf09da65c1e |  | textbox | Concrete Volume
text | 64fa6122-b1b6-58c4-b601-0601918e839d |  | textbox | Concrete Strength
text | 89dd8c0a-f937-584a-942a-40d72eb87c4a |  | textbox | Enter Drawing Revision Number
text | 668630de-d845-5bf6-9383-4353f2e00931 |  | textbox | Cast Date
checkpoint-group | eec9927c-b1c5-4c74-ad8c-55127dd66414 |  | section | Reinforcing Yard Checks (Reo QA)
checkpoint-status | 21d3dbc3-941c-48c6-a5ee-c5b912086cbb |  | checkpoint | Operative on the reinforcing cutting line has uploaded clear photo of open stock bundle boar
checkpoint-status | bb308721-634f-4bbe-84b3-d179a4e31d53 |  | checkpoint | Cut and bent bars checked off against detail sheet
checkpoint-status | 61dd630f-70fb-4725-9653-100c8b5910fa |  | checkpoint | Perimeter bars and spacing marks confirmed
checkpoint-status | 6f468d98-e7a3-4541-956f-64ebaa447fb1 |  | checkpoint | Cast in Items checked and marked on cage (Dross Ducts, Inserts Weld Plates)
checkpoint-status | 5f0cdd3a-3cf3-4908-a9a4-9f9c9b156a08 |  | checkpoint | Overall cage dimensions in plan checked and there will be sufficient concrete cover to edges
checkpoint-status | 2f4fa979-ff3c-4149-a392-16a2624a489a |  | checkpoint | Overall cage thickness checked and there will be sufficient cover to MF and TF
checkpoint-status | e8337ee1-4b43-4477-897a-dbee87ff9293 |  | checkpoint | There is sufficient cover to rebates around openings or along edge forms
checkpoint-status | 60e24774-6ebd-4386-b1a7-eea778d30cad |  | checkpoint | Weld plates can be fitted to cage in correct locations?
checkpoint-status | b6cb4e1e-70c6-44ed-9da7-8c45faeb52bb |  | checkpoint | Reinforcing details checked/highlighted off against shop drawing (upload photo)
checkpoint-group | 1e24fb9c-0bdd-444d-a575-d59e48a8d185 |  | section | Formwork Set Up Checks (Tables QA)
checkpoint-status | d40db9c7-f72c-4b19-90ab-3ec27f928208 |  | checkpoint | Sides Straight & Magnets Fastened
checkpoint-status | 2b3fa28c-1d02-48bd-b200-601d54771389 |  | checkpoint | Mould Face Clean
checkpoint-status | e6e2a50f-eba6-40cb-9fce-8a4a426d4cf9 |  | checkpoint | Length/Width/Thickness/Cutouts
checkpoint-status | 13fc42e5-8241-4772-aec1-1a316f3a7e9c |  | checkpoint | Edge Details & Rebates
checkpoint-status | 27cc08be-13b6-47e1-ac43-9706d28bba35 |  | checkpoint | MF Weld plates in correct location and siliconed to table
checkpoint-group | 9a76a47f-01c0-4044-bc2e-e73b04b40309 |  | section | Prepour Checks (Tables QA)
checkpoint-status | 047df753-120f-4610-94b6-da1a778ffb3a |  | checkpoint | Main Reinforcing
checkpoint-status | 02e1bc10-24ee-4489-a785-f76908e00040 |  | checkpoint | Starters
checkpoint-status | cf30138b-9391-404e-9b21-a90eaaddc739 |  | checkpoint | Stirrups
checkpoint-status | 2c93000e-df16-4f5a-abd6-6dd011d50995 |  | checkpoint | Lifters
checkpoint-status | 8b61f742-fb4b-49f1-adb7-6a95ea675e1e |  | checkpoint | Mould Cleaned & Oiled
checkpoint-status | d055ca06-4e18-49ac-a1e8-81e7ac04fd05 |  | checkpoint | Tie wire Trimmed
checkpoint-status | e6f91a9a-a7f7-4310-8447-569cab61266c |  | checkpoint | General Photos Attached
checkpoint-status | 3405a17f-5544-4ff9-b719-a98f61a86cc4 |  | checkpoint | Concrete Docket Attached
checkpoint-status | 952645dd-8ca5-4f13-8211-12855b63e93e |  | checkpoint | Shop Drawing Checked Off (attach photo)
checkpoint-group | 6fb22540-791f-4672-893d-f31573baf76a |  | section | Post Pour (Table Supervisor)
checkpoint-status | 011988be-f85f-4982-ac4e-b38005829f51 |  | checkpoint | Confirm formwork has not shifted during placing of concrete
checkpoint-status | 76ff4f8e-3455-4f9a-b0ba-666b97833255 |  | checkpoint | Face lifters placed in correct location
checkpoint-status | ad8ff1a0-6dec-49f7-9e37-900190a90c67 |  | checkpoint | Roughening Lines Correct
checkpoint-group | 1f80346c-9123-45a3-8936-50ea508c88a6 |  | section | Demould Inspection (Yard QA)
checkpoint-status | d3e6b064-135b-4970-bc0f-2546302171e5 |  | checkpoint | Panel correctly labeled (check against shop drawing)
checkpoint-status | e6c5e5c5-6852-4003-9d16-39c4cb350dbe |  | checkpoint | Grout holes for Drossbach Ducts have been drilled (top and bottom)
checkpoint-status | 56b159f9-3248-40e1-93d6-65d10aef0265 |  | checkpoint | Bottom of Drossbach Duct is clear (any slurry/grout has been removed)
checkpoint-status | 3f743f29-ffa5-4c98-861f-2f4538934a04 |  | checkpoint | All lifters have been cleared/cleaned out (including top lifters for install)
checkpoint-status | 6e151f2c-1aea-4e9f-8a39-67f32a7a864b |  | checkpoint | All Inserts have been exposed and nail plates removed (caps that came with Ancon fixings should be put back on)
checkpoint-status | 2d6e8696-933b-4cc6-8c77-5022cd7b9a52 |  | checkpoint | Stitch joints have been jet washed
checkpoint-status | 93b9787d-01fd-4329-b273-ffa611d0b113 |  | checkpoint | MF roughening's jet washed
checkpoint-status | 914e3e46-ff77-4c1e-9cd6-68e95560cf07 |  | checkpoint | NF chamfers and square edges rounded with cup stone
checkpoint-status | 29141e77-230c-4730-9ee5-c7e1154f64c7 |  | checkpoint | Weld plates cleaned (NF weld plates to be cleaned with cup stone)
checkpoint-status | 7df3d99b-fd2f-4f5c-b342-49e0c0c77e9c |  | checkpoint | Grade 300 starters bent up for transport (only bend starter down if transport height is increased by bending up)
checkpoint-status | b9226aa3-a7b3-4984-a07e-0eccc606f8b7 |  | checkpoint | Grade 500 starters are straight
checkpoint-status | 5a662ac8-5324-46be-9f10-a95e8560313c |  | checkpoint | NF Quality acceptable (attach photo)
checkpoint-status | 62092cdc-b8a7-4c62-8b45-f6a626b21b4d |  | checkpoint | MF Quality acceptable (attach photo)
checkpoint-status | ce5dad22-2dfd-48f0-965a-ea2f8b68cfd1 |  | checkpoint | Structural repairs required (if yes photograph before)
checkpoint-status | d3e25f44-1624-4154-bf04-eba35b26b459 |  | checkpoint | Shop drawing checked off
checkpoint-group | 4617a534-6160-4bc3-a752-3471546931a2 |  | section | Overall Panel Quality (Yard QA)
checkpoint-status | 2f318a3d-ca93-4700-8e8d-01f94e206b03 |  | checkpoint | Overall Panel Quality Ratings Recorded Below
label | 7bc634cf-9e4e-570a-b6ed-58df08ff539f |  | note | The higher the number the better the quality
label | a57e9905-4280-55a0-ab19-c580d17e1080 |  | note | e.g. "1" is unacceptable
button | 6fb8cc9e-0e03-5c7f-85b7-7c810e1d1ed7 |  | button | Vibrating Quality | 5 , 4 , 3 , 2 , 1
button | 9b13678c-e71a-5f54-8e4b-d236ea8440a7 |  | button | Trowelling Quality | 5 , 4, 3 , 2, 1
button | db4530dc-497f-5c00-b6ad-b8a6ac80f619 |  | button | Silicone Quality | 5 , 4 , 3 , 2 , 1
button | 24801210-2974-52da-8987-3c7a9423da34 |  | button | Chamfer Quality | 5 , 4 , 3 , 2 , 1
button | 1ae93724-1cbc-59bf-8d7f-bfecbe19fdf2 |  | button | MF Quality | 5 , 4 , 3 , 2 , 1
checkpoint-group | d4ca5b98-3953-4889-80a6-ebd3fa525a3a |  | section | Loading Out (Yard QA)
checkpoint-status | 0bd8001d-5ed9-4869-ab96-060ed89d02c2 |  | checkpoint | Load Docket Given to Driver
checkpoint-status | e02acfd2-7889-4046-b780-ce16fe02e827 |  | checkpoint | Photo take of Panel on Truck
checkpoint-status | 4c41b5af-368a-4395-8e1b-949e64f5a502 |  | checkpoint | No remedial work required on site
checkpoint-group | d5983ea3-a2ee-4f20-bfab-4da717da2479 |  | section | Test Results, Certificates and Documentation (Reo & Yard QA)
checkpoint-status | 1e3071dd-4e8a-4340-b0a5-2bb273e9bf8c |  | checkpoint | Upload reinforcing detail sheets
checkpoint-status | d2c59a81-31c5-4cf1-ad9f-ffb5eae98a87 |  | checkpoint | Upload Photo of Reinforcing Stock Bundle Tags (Cast # Tracking)
checkpoint-status | 61db57d7-8ee6-41f7-b4b7-0b4ef3f0109a |  | checkpoint | Upload Concrete test results
checklist-sectioned | d881e732-20ed-407d-a3f6-d3da2bbd18bd |  | checklist | P |  |  |  |  | Yes | 3. LR WT2 Panel | 6ef56831-739b-49c7-8f3f-63c52dfce2c7
checkpoint-group | cf8c2e7f-3e1b-45be-b7f1-d3c7ae2b8fd8 |  | section | Precast Element Details
checkpoint-status | 9592644a-d4cd-4fce-af0e-8339d96d8673 |  | checkpoint | Concrete Details Complete
text | a6270242-0e36-5f74-82f5-7707f72d254c |  | textbox | Concrete Volume
text | ea47e1e4-bad1-5164-8122-9b775695d3b1 |  | textbox | Concrete Strength
text | 315bf288-bab0-5767-ae98-20595c230b37 |  | textbox | Enter Drawing Revision Number
text | 3858eea9-db3a-51f8-9e5e-0d2aee55c450 |  | textbox | Cast Date
checkpoint-group | ac72d3b9-e1df-456c-9bee-7596eaeabe7f |  | section | Reinforcing Yard Checks (Reo QA)
checkpoint-status | 94eb3b31-f325-4ead-827d-3ff7624ca2b5 |  | checkpoint | Operative on the reinforcing cutting line has uploaded clear photo of open stock bundle boar
checkpoint-status | 96007b94-531f-4dde-ba53-eff51ce14a20 |  | checkpoint | Cut and bent bars checked off against detail sheet
checkpoint-status | 5b61589a-eaa5-46b7-acec-3f3475bf251b |  | checkpoint | Perimeter bars and spacing marks confirmed
checkpoint-status | e0e1144e-cbce-4eba-bca3-db9377af301d |  | checkpoint | Cast in Items checked and marked on cage (Dross Ducts, Inserts Weld Plates)
checkpoint-status | 31af691c-cc0d-4472-970e-539d0e84cb5f |  | checkpoint | Overall cage dimensions in plan checked and there will be sufficient concrete cover to edges
checkpoint-status | 7317a4d2-6894-4905-b24c-4eda019451e7 |  | checkpoint | Overall cage thickness checked and there will be sufficient cover to MF and TF
checkpoint-status | 0cbbd829-fb1d-4f4e-91d6-4299c0d27450 |  | checkpoint | There is sufficient cover to rebates around openings or along edge forms
checkpoint-status | f0fc3aaa-a216-4f25-9009-85309df8e5ae |  | checkpoint | Weld plates can be fitted to cage in correct locations?
checkpoint-status | 93988056-bf35-4614-be0b-b10f0fd63b8d |  | checkpoint | Reinforcing details checked/highlighted off against shop drawing (upload photo)
checkpoint-group | d08689bc-970c-40c0-8ad9-538aa60041f1 |  | section | Formwork Set Up Checks (Tables QA)
checkpoint-status | b63450b8-24eb-43e2-bddd-1a09910447c6 |  | checkpoint | Sides Straight & Magnets Fastened
checkpoint-status | 3909e82b-38a9-4279-b241-2a95247a9129 |  | checkpoint | Mould Face Clean
checkpoint-status | 62b988b5-e479-4ce0-b4e8-4a8c7b84b88f |  | checkpoint | Length/Width/Thickness/Cutouts
checkpoint-status | 9eaea055-fda9-4777-87ac-122aa672e8c8 |  | checkpoint | Edge Details & Rebates
checkpoint-status | 7e88cc58-7be9-4065-8e1f-dfe94b9f25a5 |  | checkpoint | MF Weld plates in correct location and siliconed to table
checkpoint-group | 9b8f89d7-37af-45a9-af0a-1015e9f2c569 |  | section | Prepour Checks (Tables QA)
checkpoint-status | 73ebe86a-76ba-48bf-a582-2a0e9fdebf43 |  | checkpoint | Main Reinforcing
checkpoint-status | a40e3b03-3628-4357-9d6c-7ff384c29dc9 |  | checkpoint | Starters
checkpoint-status | 44e95c23-7151-4365-9131-4f3b0eefaeae |  | checkpoint | Stirrups
checkpoint-status | 445a6ef2-a539-4883-8cfc-81c800eb408c |  | checkpoint | Lifters
checkpoint-status | 416f1de5-1a5f-495b-8b84-98452bd72475 |  | checkpoint | Mould Cleaned & Oiled
checkpoint-status | d7cdc491-cb4e-463e-96bd-afe2d7cb80aa |  | checkpoint | Tie wire Trimmed
checkpoint-status | bbc14dd3-63db-4e8e-aa6d-e2c6f1f2127c |  | checkpoint | General Photos Attached
checkpoint-status | 8edcb013-847a-4e88-9fd3-88d9d774a2fc |  | checkpoint | Concrete Docket Attached
checkpoint-status | 24f06ea6-77ca-4689-bcaa-ca3a8e6aa31e |  | checkpoint | Shop Drawing Checked Off (attach photo)
checkpoint-group | bd8fe375-6f59-4f18-b7fb-3da9820f1dbe |  | section | Post Pour (Table Supervisor)
checkpoint-status | 9eaa97a1-a322-4fd7-a8ed-512789148791 |  | checkpoint | Confirm formwork has not shifted during placing of concrete
checkpoint-status | 6bb4d374-beb6-45ec-9b8b-bf7eda5108f8 |  | checkpoint | Face lifters placed in correct location
checkpoint-status | 62add4ca-1985-4514-ac8a-ba0a8cba4ae2 |  | checkpoint | Roughening Lines Correct
checkpoint-group | ae4df28f-068c-4993-afe1-f229505359ec |  | section | Demould Inspection (Yard QA)
checkpoint-status | 38acf5fd-2df2-4e26-836f-c7ea9869098f |  | checkpoint | Panel correctly labeled (check against shop drawing)
checkpoint-status | 4a48638f-8fb8-4438-b63a-49f25875e92d |  | checkpoint | Grout holes for Drossbach Ducts have been drilled (top and bottom)
checkpoint-status | d6683f54-9240-4c40-86bf-860cf36243ae |  | checkpoint | Bottom of Drossbach Duct is clear (any slurry/grout has been removed)
checkpoint-status | bc406297-016d-41b0-beda-fa1a790dcc9a |  | checkpoint | All lifters have been cleared/cleaned out (including top lifters for install)
checkpoint-status | 7aa4f782-12ba-4c88-96fb-04e123fbfe87 |  | checkpoint | All Inserts have been exposed and nail plates removed (caps that came with Ancon fixings should be put back on)
checkpoint-status | 32b9ddc6-71ba-4b75-8fd3-30a59fc448a0 |  | checkpoint | Stitch joints have been jet washed
checkpoint-status | dc8be59e-74eb-4fe4-b82f-5d1c59302d29 |  | checkpoint | MF roughening's jet washed
checkpoint-status | 731c5759-0192-47ef-bef7-714bd823490c |  | checkpoint | NF chamfers and square edges rounded with cup stone
checkpoint-status | 86f01b83-67af-4a1e-a3c5-4c312ad99b44 |  | checkpoint | Weld plates cleaned (NF weld plates to be cleaned with cup stone)
checkpoint-status | 12d628ab-404e-409b-9783-934338799507 |  | checkpoint | Grade 300 starters bent up for transport (only bend starter down if transport height is increased by bending up)
checkpoint-status | 4a9b90db-7c5d-43ae-8e19-12d5b3450683 |  | checkpoint | Grade 500 starters are straight
checkpoint-status | 32ef0eb1-337a-4019-9d40-c626691ce651 |  | checkpoint | NF Quality acceptable (attach photo)
checkpoint-status | abd0352d-1e45-4363-a5cc-a92a92dc8fcc |  | checkpoint | MF Quality acceptable (attach photo)
checkpoint-status | fe90b792-b281-4c03-b1e3-d2113489e6f3 |  | checkpoint | Structural repairs required (if yes photograph before)
checkpoint-status | 0bc42cc2-5c1b-4283-9964-4c91d6aa6d01 |  | checkpoint | Shop drawing checked off
checkpoint-group | 86cd8257-2944-4b47-bc2b-5f676c378595 |  | section | Panel Painting Checks (Yard Supervisor)
checkpoint-status | 260cdf24-7155-4ad8-a119-5ca752029134 |  | checkpoint | Panel MF Sprayed with Tiltwash and rinsed off with waterblaster (2 passes)
checkpoint-status | b73bb394-aaf8-4bbc-8f19-f19f744c1b1e |  | checkpoint | Window opening inspected and concrete finish acceptable
checkpoint-status | 8e52ed16-d546-4986-bae2-a3722bff863a |  | checkpoint | Large Pinholes or honey combing repaired with Sikadur UA (if required)
checkpoint-status | fccb0e71-0d5c-4a5d-b85e-9396377b5a5b |  | checkpoint | Panel allowed to cure for 48hours before applying primer
checkpoint-status | 1c181833-8db7-47de-9eed-87686e3986fe |  | checkpoint | Single coat of Dulux AcraTex Green Render Sealer applied (upload photo)
checkpoint-status | 22792c07-ec4e-45c5-9faa-b31c02b8c405 |  | checkpoint | Allow sealer coat to dry for 4 hours before applying topcoat
checkpoint-status | d4514e78-7269-4f86-bab4-b6bf688e176f |  | checkpoint | 2 coats of Dulux AcraTex AcraShield Advance Matt topcoat (upload photo)
checkpoint-status | b7d0fd6c-1233-409c-9013-bc63c3bcb667 |  | checkpoint | Masking tape in window opening removed and edges of panel clear of any overspray
holdpoint | 2521f779-6e72-460e-b8f4-5245fb8e1d91 | Multiple signoffs are not allowed | signoff | Window installer accepted quality of concrete opening
holdpoint | ae9d7d33-608e-4660-8892-a7e075e611f0 | Multiple signoffs are not allowed | signoff | Window installer confirmed they have completed their works and panel can delivered to site
checkpoint-group | 2395dd8a-8b33-49be-888f-90dc6d27a392 |  | section | Overall Panel Quality (Yard QA)
checkpoint-status | 596325ac-8e81-45bb-943c-cb82b0d7439d |  | checkpoint | Overall Panel Quality Ratings Recorded Below
label | 91b1eae9-4bbb-54a5-8b10-5f7873bc15c8 |  | note | The higher the number the better the quality
label | 490e3fa5-b38d-5dff-9c2d-4ec83a5c48b0 |  | note | e.g. "1" is unacceptable
button | ac01aa2e-1574-522f-a934-68383b35a5ee |  | button | Vibrating Quality | 5 , 4 , 3 , 2 , 1
button | f9e16d64-0107-517a-a054-77303b304989 |  | button | Trowelling Quality | 5 , 4 , 3 , 2 , 1
button | 5b9dbdf8-a597-5e5e-9252-8be6eb145061 |  | button | Silicone Quality | 5 , 4 , 3 , 2 , 1
button | 3e366dbb-4903-5ff4-9406-bec9c86cad3b |  | button | Chamfer Quality | 5 , 4 , 3 , 2 , 1
button | 977cfdcf-4fc2-54a5-b8a1-bab0e42d3166 |  | button | MF Quality | 5 , 4 , 3 , 2 , 1
checkpoint-group | 5b411030-f149-4bea-bcb6-c8147d62ce4f |  | section | Loading Out (Yard QA)
checkpoint-status | 077bea11-ea66-4504-90a0-a71515131736 |  | checkpoint | Load Docket Given to Driver
checkpoint-status | 1b3abd7c-ab85-422e-8e9e-63ecfe0d98f8 |  | checkpoint | Photo take of Panel on Truck
checkpoint-status | 604706b1-0dc7-49d1-b358-446c58e2a60d |  | checkpoint | No remedial work required on site
checkpoint-group | b183c741-1d4d-46ec-80f8-6a4d8fb4cfca |  | section | Test Results, Certificates and Documentation (Reo & Yard QA)
checkpoint-status | af2aa73a-7f8b-4a47-a262-07438cff3482 |  | checkpoint | Upload reinforcing detail sheets
checkpoint-status | 51e0d1c8-cfc4-4abc-98af-90522dda9a2f |  | checkpoint | Upload Photo of Reinforcing Stock Bundle Tags (Cast # Tracking)
checkpoint-status | 6c941966-b8bb-4fbc-9e9f-f8b990f867af |  | checkpoint | Upload Concrete test results
checklist-flat | 3a2edcf7-94ef-451e-b661-8c2c021a9af7 |  | checklist | Remedial - |  |  |  |  | Yes | Add Defect/Remedial | a28654fb-28bf-4f39-bc8d-85fca885653a
checkpoint-status | e970f2e8-38be-47ea-88e8-55a317040604 |  | checkpoint | Defect Details Inputted
select | 02fb74a6-9297-5b69-8d8f-5d0c48b9c66b |  | dropdown | What is the Defect | Chip in panel, Crack in the panel, Level of finish inadequate, Incorrect Location of Cast in Items, Missing Cast In Items, Other Remedial - Specify below
text | 5643327d-d65b-5388-9530-86f7463e6f6b |  | textbox | Other Defect (specify here if applicable)
text | 0a0c215a-1923-5c54-9bd7-a2a864f6723e |  | textbox | Defect Location on Panel (Attach Photo)
text | 7152a2c6-2eb2-5247-8f3c-096388865e18 |  | textbox | Remedial Work Required
checkpoint-status | 502296f5-6918-4b50-a34e-45b8d43935b1 |  | checkpoint | Panel Location Inputted
text | 96be865a-2544-5cb4-9d0c-5574d44c5bb8 |  | textbox | Panel Location
checkpoint-status | 98dc4c4e-edbc-4b97-8033-8b15d5166725 |  | checkpoint | NCR Raised if Required
checkpoint-status | 883a5a98-2c88-4d02-aa0d-e0db0e558895 |  | checkpoint | Remedial completed - (Attach Photo)
checklist-sectioned | b724e883-46ad-4066-bbd6-7b76ba27a411 |  | checklist | P |  |  |  |  | Yes | 4. LR WT3 Panel | c2071aab-da87-42a4-90d5-d238a564bc58
checkpoint-group | d50a8d64-f42a-4db5-b00b-3607d2c2c06e |  | section | Precast Element Details
checkpoint-status | 65b85a6f-9b67-48b7-bc9c-07b4c68cb279 |  | checkpoint | Concrete Details Complete
text | f93de833-ccdc-5608-8629-2316fa7f600c |  | textbox | Concrete Volume
text | 56b56db4-c506-5a41-af40-aff036996a3d |  | textbox | Concrete Strength
text | 71a28364-61e6-5596-9258-cc7c6a059f71 |  | textbox | Enter Drawing Revision Number
text | ca0a00f4-d2b5-5553-934b-5fb566b8821c |  | textbox | Cast Date
checkpoint-group | 2eea5c2b-988c-49fd-a1a1-2184f840f926 |  | section | Reinforcing Yard Checks (Reo QA)
checkpoint-status | 6aa62017-177a-49a9-b602-aac63163d958 |  | checkpoint | Operative on the reinforcing cutting line has uploaded clear photo of open stock bundle boar
checkpoint-status | dab16392-35b2-4430-93c8-84582d427495 |  | checkpoint | Cut and bent bars checked off against detail sheet
checkpoint-status | c87d5623-07e1-4a3a-8bff-1eb8f612c1f6 |  | checkpoint | Perimeter bars and spacing marks confirmed
checkpoint-status | f36abc39-4276-4da4-8ff9-78f0b57af286 |  | checkpoint | Cast in Items checked and marked on cage (Dross Ducts, Inserts Weld Plates)
checkpoint-status | 80fdf14f-f673-4f13-88e9-4631667290b3 |  | checkpoint | Overall cage dimensions in plan checked and there will be sufficient concrete cover to edges
checkpoint-status | 21dbfe01-bcdb-47ed-9e1e-ce41e2379986 |  | checkpoint | Overall cage thickness checked and there will be sufficient cover to MF and TF
checkpoint-status | 365be858-5d9b-4821-8ab1-b7839e899350 |  | checkpoint | There is sufficient cover to rebates around openings or along edge forms
checkpoint-status | ca22ec0c-f64b-4f89-a8be-605c24dba9f1 |  | checkpoint | Weld plates can be fitted to cage in correct locations?
checkpoint-status | 475dd75f-d023-44cd-a731-b873184a7b90 |  | checkpoint | Reinforcing details checked/highlighted off against shop drawing (upload photo)
checkpoint-group | 3d2304b6-a071-4e25-8d11-6b04a7db2bc3 |  | section | Formwork Set Up Checks (Tables QA)
checkpoint-status | 7d1d72d5-d3b9-4b10-bb5e-703a48945d74 |  | checkpoint | Sides Straight & Magnets Fastened
checkpoint-status | 65c3dee1-1c73-44d1-adb4-b71fd464eff3 |  | checkpoint | Mould Face Clean
checkpoint-status | 15976424-d03d-42b9-895a-b892e17e10e4 |  | checkpoint | Length/Width/Thickness/Cutouts
checkpoint-status | 750bbf26-1471-4adc-9d70-6eddaf1b923b |  | checkpoint | Edge Details & Rebates
checkpoint-status | d65eb75e-b297-48c5-8e07-66fd74f4e4c2 |  | checkpoint | MF Weld plates in correct location and siliconed to table
checkpoint-group | 938ba8e7-c008-4d6b-83e7-dcd1572232c0 |  | section | Prepour Checks (Tables QA)
checkpoint-status | 037c7b98-6806-4e63-b41d-08746a24ae4a |  | checkpoint | Main Reinforcing
checkpoint-status | fb844be8-a2ff-4b95-afe5-e3114de6f815 |  | checkpoint | Starters
checkpoint-status | 9c25e551-9e13-47ae-a999-f0aeabab3a0f |  | checkpoint | Stirrups
checkpoint-status | 79701048-ec04-45ef-b37e-57f82e191a7b |  | checkpoint | Lifters
checkpoint-status | 73384c8d-8264-49c4-8554-c6cc8ca43f48 |  | checkpoint | Mould Cleaned & Oiled
checkpoint-status | 867a7f81-b555-4d55-914a-acd3754bb9a7 |  | checkpoint | Tie wire Trimmed
checkpoint-status | 07849838-9a99-4424-9340-00e8c72e10b6 |  | checkpoint | General Photos Attached
checkpoint-status | bc42d565-97da-49ad-998a-4ab978ee2f41 |  | checkpoint | Concrete Docket Attached
checkpoint-status | b8aff650-fc59-4d7a-9e70-b5dc861c4c62 |  | checkpoint | Shop Drawing Checked Off (attach photo)
checkpoint-group | 4e6ccdfc-8afd-4618-96b8-9db0e9d8df2c |  | section | Post Pour (Table Supervisor)
checkpoint-status | 7515470f-9e12-4d1b-82f3-9cd28d6214f2 |  | checkpoint | Confirm formwork has not shifted during placing of concrete
checkpoint-status | 9d6cef15-b237-44c9-919c-27805c00bb23 |  | checkpoint | Face lifters placed in correct location
checkpoint-status | 24d944aa-177c-40ad-b4ff-dca6ba2e150c |  | checkpoint | Roughening Lines Correct
checkpoint-group | 8325d04d-03ec-43ba-85b5-17649266397d |  | section | Demould Inspection (Yard QA)
checkpoint-status | 15f0fed1-36ea-494a-a1ec-460dd0c1a81b |  | checkpoint | Panel correctly labeled (check against shop drawing)
checkpoint-status | 4eec067d-b46a-43e3-983d-6ac1c56943ef |  | checkpoint | Grout holes for Drossbach Ducts have been drilled (top and bottom)
checkpoint-status | a2b7bc2e-8679-475c-ad65-7c991bac6342 |  | checkpoint | Bottom of Drossbach Duct is clear (any slurry/grout has been removed)
checkpoint-status | 49ac45ca-9b4b-44ad-afaa-b8805c878eee |  | checkpoint | All lifters have been cleared/cleaned out (including top lifters for install)
checkpoint-status | b5875386-cb18-4732-815a-db0774dcf43f |  | checkpoint | All Inserts have been exposed and nail plates removed (caps that came with Ancon fixings should be put back on)
checkpoint-status | a9143544-3c2b-426b-8cbc-a55cea1060dc |  | checkpoint | Stitch joints have been jet washed
checkpoint-status | 8c25d55b-a3ea-43b4-a172-3cc622d1aa0c |  | checkpoint | MF roughening's jet washed
checkpoint-status | 3b4dc1f8-770b-4842-bf37-a2f5554725b0 |  | checkpoint | NF chamfers and square edges rounded with cup stone
checkpoint-status | 79e62c39-cec1-450d-872b-4142c70b3455 |  | checkpoint | Weld plates cleaned (NF weld plates to be cleaned with cup stone)
checkpoint-status | 76bd40bd-4dbc-4f68-a4a8-6e3bdc63fa65 |  | checkpoint | Grade 300 starters bent up for transport (only bend starter down if transport height is increased by bending up)
checkpoint-status | 8877fc6f-598a-428b-a26f-722f98707bd1 |  | checkpoint | Grade 500 starters are straight
checkpoint-status | 1f308c9f-0fea-4327-8361-6f146fe133a8 |  | checkpoint | NF Quality acceptable (attach photo)
checkpoint-status | 0e72cda3-ffe7-4754-85e0-d85e1a5eb587 |  | checkpoint | MF Quality acceptable (attach photo)
checkpoint-status | e79d0926-519e-4ec9-b9be-3e89379a972f |  | checkpoint | Structural repairs required (if yes photograph before)
checkpoint-status | 00481297-cd25-4982-a44c-cae53b69ec57 |  | checkpoint | Shop drawing checked off
checkpoint-group | fb2ab45e-4f82-4ca9-a9f3-25d04fcb8fa5 |  | section | Panel Painting Checks (Yard Supervisor)
checkpoint-status | 70446044-3882-4bc3-a235-9676ee9f289b |  | checkpoint | Panel MF Sprayed with Tiltwash and rinsed off with waterblaster (2 passes)
checkpoint-status | 2a6cc8d9-0387-4612-816b-d2ed247becae |  | checkpoint | Window opening inspected and concrete finish acceptable
checkpoint-status | 05bfac8b-4c1d-47b6-ae64-a820991b3088 |  | checkpoint | Large Pinholes or honey combing repaired with Sikadur UA (if required)
checkpoint-status | 90148788-b82a-4ac0-b921-33c804eae774 |  | checkpoint | Ecotone colouring system applied as per quality plan
checkpoint-status | b45bf808-b4c0-4230-bbae-94607fb1ceb2 |  | checkpoint | Masking tape in window opening removed and edges of panel clear of any overspray
holdpoint | 619ab959-3519-4208-9f6b-ab145baa2a3c | Multiple signoffs are not allowed | signoff | Window installer accepted quality of concrete opening
holdpoint | 0f434652-fe71-4eb1-bb55-31bfb52b4599 | Multiple signoffs are not allowed | signoff | Window installer confirmed they have completed their works and panel can delivered to site
checkpoint-group | 0873e2ba-5b39-4b39-a886-d668e9fdc45d |  | section | Overall Panel Quality (Yard QA)
checkpoint-status | 35b5ff2e-40e9-48a1-b583-c19cca553477 |  | checkpoint | Overall Panel Quality Ratings Recorded Below
label | 89229089-abe6-556d-bcb8-02df20595fc2 |  | note | The higher the number the better the quality
label | 3bacc4db-f3cf-5268-874b-d204448de3fc |  | note | e.g. "1" is unacceptable
button | 5b5001e1-c681-5a8b-9851-93809a8aff02 |  | button | Vibrating Quality | 5 , 4 , 3 , 2 , 1
button | 9cff5aa3-a33b-530a-88d9-2392fdcc67f9 |  | button | Trowelling Quality | 5 , 4 , 3 , 2 , 1
button | 7eb9c059-7eb9-57df-89f8-d576c10a15f2 |  | button | Silicone Quality | 5 , 4 , 3 , 2 , 1
button | f8d5cc93-b813-562b-9bbd-cfcb3ba1f551 |  | button | Chamfer Quality | 5 , 4 , 3 , 2 , 1
button | 2c2070d3-5446-51e8-8925-3b63dbebaac6 |  | button | MF Quality | 5 , 4 , 3 , 2 , 1
checkpoint-group | 8a0f5bcc-51f0-4431-9dbe-3b751f280f81 |  | section | Loading Out (Yard QA)
checkpoint-status | c7d434d8-2d96-4f8e-a016-62692ed9c804 |  | checkpoint | Load Docket Given to Driver
checkpoint-status | cdf7416b-3af7-4f4a-a649-27c4a72cff91 |  | checkpoint | Photo take of Panel on Truck
checkpoint-status | ac290861-b72d-4d6b-910f-4909161ca741 |  | checkpoint | No remedial work required on site
checkpoint-group | 07950d92-7d8b-4c72-8cb3-000353575e40 |  | section | Test Results, Certificates and Documentation (Reo & Yard QA)
checkpoint-status | 18c48cbd-61d7-49e9-a5c8-223bb3b5baf7 |  | checkpoint | Upload reinforcing detail sheets
checkpoint-status | 649b75c9-8a0c-423e-af85-5e49c1cc2813 |  | checkpoint | Upload Photo of Reinforcing Stock Bundle Tags (Cast # Tracking)
checkpoint-status | 7eb796b1-08ee-4d6e-b922-1b858a23d03d |  | checkpoint | Upload Concrete test results
checklist-sectioned | aa214230-9f31-4510-a4ad-3544a02afc05 |  | checklist | 1. Standard |  |  |  |  | Yes | 1. Standard | d2ab9a44-af67-4768-a67e-db6250651eb7
checkpoint-group | a0875ebd-ace3-482a-b36c-e3be6c86ecce |  | section | Precast Element Details
checkpoint-status | 6f461307-e0db-44f8-a20d-2b83e56e824d |  | checkpoint | Concrete Details Complete
text | 44b5c25a-012a-5512-ab13-c1e0260a205a |  | textbox | Concrete Volume
text | a2ab059f-2f9e-5797-a960-d283dbcc76b2 |  | textbox | Concrete Strength
text | 563c4c7c-2047-5e7c-9691-16546b268742 |  | textbox | Enter Drawing Revision Number
text | 7e1474cd-82d3-576c-b18f-51fc5758f153 |  | textbox | Cast Date
checkpoint-group | 953885dc-8d42-4754-b3fc-d1f406e0cdda |  | section | Reinforcing Yard Checks (Reo QA)
checkpoint-status | 59c631a9-8202-4c26-984d-149eb3a2fb4a |  | checkpoint | Operative on the reinforcing cutting line has uploaded clear photo of open stock bundle boar
checkpoint-status | fb155a60-abf1-4109-9a24-cfc95136ca05 |  | checkpoint | Cut and bent bars checked off against detail sheet
checkpoint-status | 4a748cf5-3d6e-4aa1-8b49-2a29047f0088 |  | checkpoint | Perimeter bars and spacing marks confirmed
checkpoint-status | 1f04111f-6dde-4fdb-8903-29a804f31542 |  | checkpoint | Cast in Items checked and marked on cage (Dross Ducts, Inserts Weld Plates)
checkpoint-status | 940db8d2-8e86-4483-8f3e-1f3230ac0599 |  | checkpoint | Overall cage dimensions in plan checked and there will be sufficient concrete cover to edges
checkpoint-status | af2badef-7d49-4032-9f1e-a2b93500b4fc |  | checkpoint | Overall cage thickness checked and there will be sufficient cover to MF and TF
checkpoint-status | 20b37b68-1099-4ba7-881a-adce0b92a5d5 |  | checkpoint | There is sufficient cover to rebates around openings or along edge forms
checkpoint-status | 2faa7289-3c94-463e-9439-eda2b9ac8e66 |  | checkpoint | Weld plates can be fitted to cage in correct locations?
checkpoint-status | 4ec47f1d-c242-40e6-b94f-72d1d3f23175 |  | checkpoint | Reinforcing details checked/highlighted off against shop drawing (upload photo)
checkpoint-group | 0105d36f-c75f-47f5-8137-a74692231c91 |  | section | Formwork Set Up Checks (Tables QA)
checkpoint-status | 8001b298-7fa9-4773-82ea-bce576cab8b9 |  | checkpoint | Sides Straight & Magnets Fastened
checkpoint-status | 2fb358b0-fd4e-4ee1-be13-f7d5281f56d0 |  | checkpoint | Mould Face Clean
checkpoint-status | dfea60b9-3d90-4044-8e58-d61cfdc8e2c9 |  | checkpoint | Length/Width/Thickness/Cutouts
checkpoint-status | 200c5ac7-9029-48e6-b11e-9bcad160f777 |  | checkpoint | Edge Details & Rebates
checkpoint-status | 792db42d-d6df-4526-9a1e-dc909a9574e4 |  | checkpoint | MF Weld plates in correct location and siliconed to table
checkpoint-group | 29544971-656c-4a28-80fc-4c7c2a665279 |  | section | Prepour Checks (Tables QA)
checkpoint-status | 1bf06b35-b316-4dbd-8db6-6513d7301788 |  | checkpoint | Main Reinforcing
checkpoint-status | 9b961234-ac60-41d1-a9e7-7c44b259750e |  | checkpoint | Starters
checkpoint-status | df6a157c-8237-4b02-8c68-80004ad8e71d |  | checkpoint | Stirrups
checkpoint-status | 68ef58b5-8486-4d67-bdf0-d31b87a3d19a |  | checkpoint | Lifters
checkpoint-status | 978cb05a-26b3-43ec-95fa-4db090963549 |  | checkpoint | Mould Cleaned & Oiled
checkpoint-status | 8839aec2-80c0-46e3-a37d-de4e23f3356f |  | checkpoint | Tie wire Trimmed
checkpoint-status | 701421cb-6c18-4d10-8545-975d3c6df0c3 |  | checkpoint | General Photos Attached
checkpoint-status | cb1fbdd3-0bcb-497f-be3c-fd702454719c |  | checkpoint | Concrete Docket Attached
checkpoint-status | 2ee3d7e2-60e8-416c-8bd9-c7f85ef0e8ae |  | checkpoint | Shop Drawing Checked Off (attach photo)
checkpoint-group | 813bbee7-4c50-4d13-a062-7e7223c1d69a |  | section | Demould Inspection (Yard QA)
checkpoint-status | 06143c04-452b-4a47-af58-86c8928928f7 |  | checkpoint | Panel correctly labeled (check against shop drawing)
checkpoint-status | f7416b8b-e413-4e19-a779-7d3daf109ef6 |  | checkpoint | Grout holes for Drossbach Ducts have been drilled (top and bottom)
checkpoint-status | 3e33238a-456d-432f-ae96-837bbb33c95b |  | checkpoint | Bottom of Drossbach Duct is clear (any slurry/grout has been removed)
checkpoint-status | 578b6490-67dd-49a9-8a28-0ff4fca58061 |  | checkpoint | All lifters have been cleared/cleaned out (including top lifters for install)
checkpoint-status | ac4ecbfb-98ab-42cd-b72b-ce7d6a95ac22 |  | checkpoint | All Inserts have been exposed and nail plates removed (caps that came with Ancon fixings should be put back on)
checkpoint-status | 1d424a14-cd83-4d52-a625-42020c202a93 |  | checkpoint | Stitch joints have been jet washed
checkpoint-status | 18fbcf1e-cf02-4ad4-9397-10cc5f282475 |  | checkpoint | MF roughening's jet washed
checkpoint-status | eade8689-885e-4ec9-b1c9-e4ad4cd85186 |  | checkpoint | NF chamfers and square edges rounded with cup stone
checkpoint-status | 7409ff51-e74e-4aea-9cc3-a3e44222473e |  | checkpoint | Weld plates cleaned (NF weld plates to be cleaned with cup stone)
checkpoint-status | 3e669d81-ddad-4f42-be05-7d184193ef5c |  | checkpoint | Grade 300 starters bent up for transport (only bend starter down if transport height is increased by bending up)
checkpoint-status | b9330b51-6d18-44d7-a116-423cfcab3a73 |  | checkpoint | Grade 500 starters are straight
checkpoint-status | f0a7f561-8cd4-4468-bacc-3b26b349b0d5 |  | checkpoint | NF Quality acceptable (attach photo)
checkpoint-status | 88edd113-c242-4b0f-9819-2b4ba1525251 |  | checkpoint | MF Quality acceptable (attach photo)
checkpoint-status | 446ab5fb-762d-4b3a-82d9-82becff72313 |  | checkpoint | Structural repairs required (if yes photograph before)
checkpoint-status | 744740fa-c035-4d41-9aef-f3f9a91ac4ab |  | checkpoint | Shop drawing checked off
checkpoint-group | c4d5a81c-7138-473b-b080-62f74dd1d3a5 |  | section | Loading Out (Yard QA)
checkpoint-status | 24bd7baa-cde2-4617-834c-a611dd0c0c18 |  | checkpoint | Load Docket Given to Driver
checkpoint-status | 2cb801cc-bc7c-4bdd-803a-dba91e9b28e0 |  | checkpoint | Photo take of Panel on Truck
checkpoint-status | 6d48d17e-9441-4c6d-a00f-20bc4bc5f035 |  | checkpoint | No remedial work required on site
checkpoint-group | 66dbcd2c-be76-4155-b33f-6a471f2f56e7 |  | section | Test Results, Certificates and Documentation (Reo & Yard QA)
checkpoint-status | 7f27b738-b444-4e11-8ae0-3bf9710d32be |  | checkpoint | Upload reinforcing detail sheets
checkpoint-status | 6fffd8d3-f14e-4284-9dc1-20d04101819d |  | checkpoint | Upload Photo of Reinforcing Stock Bundle Tags (Cast # Tracking)
checkpoint-status | 54cbe185-7cd9-4a8f-ba40-ecb1e8d0cd0d |  | checkpoint | Upload Concrete test results
checklist-sectioned | c9532baa-2661-46a0-81b6-9e05e793d95f |  | checklist | P |  |  |  |  | Yes | 2. Standard with Aquron2000 | ecaaba9e-5cb5-4411-b42f-c60215ea4b68
checkpoint-group | 3af0ed91-1a12-48d6-a8f8-8c0d94327c3d |  | section | Precast Element Details
checkpoint-status | 0d5daa81-d94e-4616-84ce-6d819a3e0693 |  | checkpoint | Concrete Details Complete
text | 3a85f9d4-703c-55f7-9b57-850154b27ffe |  | textbox | Concrete Volume
text | c8382481-315a-5d69-b033-00bfe99a280b |  | textbox | Concrete Strength
text | 44df4941-b51a-5c4f-b1da-1c81d7e8811f |  | textbox | Enter Drawing Revision Number
text | cbbe92d7-0e2f-55f3-bc1b-4274259dd7b5 |  | textbox | Cast Date
checkpoint-group | 82807428-795d-4908-b30e-16add4baed73 |  | section | Reinforcing Yard Checks (Reo QA)
checkpoint-status | 15df543a-6261-42b2-808e-30624be1003c |  | checkpoint | Operative on the reinforcing cutting line has uploaded clear photo of open stock bundle boar
checkpoint-status | 6a432f5b-40b0-4358-96fc-bfe523f2e3ef |  | checkpoint | Cut and bent bars checked off against detail sheet
checkpoint-status | 6c88ff88-bd04-4fbc-af87-8ced9cad3f5b |  | checkpoint | Perimeter bars and spacing marks confirmed
checkpoint-status | e9e7a835-8e09-48cc-9bf6-f4af47e011fd |  | checkpoint | Cast in Items checked and marked on cage (Dross Ducts, Inserts Weld Plates)
checkpoint-status | 82a7a611-592d-4544-8794-6da04b7e5ddd |  | checkpoint | Overall cage dimensions in plan checked and there will be sufficient concrete cover to edges
checkpoint-status | d10b12dd-5a81-4dc6-8156-e909d18a7194 |  | checkpoint | Overall cage thickness checked and there will be sufficient cover to MF and TF
checkpoint-status | 54c5301b-9ed2-47ec-8dfb-a6e809ad1ba3 |  | checkpoint | There is sufficient cover to rebates around openings or along edge forms
checkpoint-status | 2002d92f-add1-4de1-916b-87c8c3a0eca7 |  | checkpoint | Weld plates can be fitted to cage in correct locations?
checkpoint-status | 1ae09b2c-6b32-4da5-977f-db85e7f89f1b |  | checkpoint | Reinforcing details checked/highlighted off against shop drawing (upload photo)
checkpoint-group | f60fafe9-b006-4b9a-96a0-df64a825b0f6 |  | section | Formwork Set Up Checks (Tables QA)
checkpoint-status | 443a97be-3cbf-4341-873a-47e672c264c7 |  | checkpoint | Sides Straight & Magnets Fastened
checkpoint-status | 568de151-9781-4959-afd6-41b5903bfce6 |  | checkpoint | Mould Face Clean
checkpoint-status | 7d64f16f-4416-4c90-92d2-780e61232f90 |  | checkpoint | Length/Width/Thickness/Cutouts
checkpoint-status | 2aebe6a9-c12e-449d-b9c0-1668625fef22 |  | checkpoint | Edge Details & Rebates
checkpoint-status | 25d63464-79b5-4b8b-8e9c-a06025518391 |  | checkpoint | MF Weld plates in correct location and siliconed to table
checkpoint-group | 04d564f0-6e3c-4f47-b513-898742360659 |  | section | Prepour Checks (Tables QA)
checkpoint-status | 7d35586f-8a4b-4fcb-8875-30beb46d51d2 |  | checkpoint | Main Reinforcing
checkpoint-status | 4e481b78-33cc-4123-b6f3-6312ead1bea6 |  | checkpoint | Starters
checkpoint-status | b8559d72-a035-43c7-9567-5303c25a2e83 |  | checkpoint | Stirrups
checkpoint-status | 7014fec5-99a0-49ba-b8fb-357d386aa585 |  | checkpoint | Lifters
checkpoint-status | 260f757f-12db-463a-b474-896499452a70 |  | checkpoint | Mould Cleaned & Oiled
checkpoint-status | 4b890473-b1a7-4c3b-80dc-6087a3a05646 |  | checkpoint | Tie wire Trimmed
checkpoint-status | 2abea4b5-6d6e-4759-b9bf-8c8283b6cb81 |  | checkpoint | General Photos Attached
checkpoint-status | 02a6f973-348c-487e-9599-f04a177b5d83 |  | checkpoint | Concrete Docket Attached
checkpoint-status | 5f938220-45ed-4398-bc03-244528d68d6d |  | checkpoint | Shop Drawing Checked Off (attach photo)
checkpoint-group | a057cf1e-23da-4f2f-9114-b73cec5e5ff2 |  | section | Post Pour (Table Supervisor)
checkpoint-status | ca997259-066e-4475-bbd7-1dde1eef7efd |  | checkpoint | Confirm formwork has not shifted during placing of concrete
checkpoint-status | 5a2b9d3f-41cf-42ef-9030-77d64866c9c6 |  | checkpoint | Face lifters placed in correct location
checkpoint-status | 488d0deb-c0fc-491e-b88b-de7a137ce37c |  | checkpoint | Roughening Lines Correct
checkpoint-group | c92f3d80-ce2f-4db7-8884-7faf173e1b0a |  | section | Demould Inspection (Yard QA)
checkpoint-status | bac95f8e-cf57-43dc-adde-518a6f248c56 |  | checkpoint | Panel correctly labeled (check against shop drawing)
checkpoint-status | a3eba977-f22d-4e9c-b47d-0c8691f8b8ea |  | checkpoint | Grout holes for Drossbach Ducts have been drilled (top and bottom)
checkpoint-status | 277f257e-e4d4-4336-953f-96bf6a060971 |  | checkpoint | Bottom of Drossbach Duct is clear (any slurry/grout has been removed)
checkpoint-status | 0bfdfc50-4e9b-4bc6-8cc0-5f6a5be8f406 |  | checkpoint | All lifters have been cleared/cleaned out (including top lifters for install)
checkpoint-status | dbe2576f-fca6-4798-a37e-b7ea152107f6 |  | checkpoint | All Inserts have been exposed and nail plates removed (caps that came with Ancon fixings should be put back on)
checkpoint-status | 1461a022-4a3c-499e-8ffa-f6873665fb42 |  | checkpoint | Stitch joints have been jet washed
checkpoint-status | 17d0b46a-c24a-440e-838f-e230a569205c |  | checkpoint | MF roughening's jet washed
checkpoint-status | 864d8a8a-0a4a-42f0-b853-cd00a783cb7d |  | checkpoint | NF chamfers and square edges rounded with cup stone
checkpoint-status | 2bb34f40-b43f-432d-b6d3-bb78fcd74a81 |  | checkpoint | Weld plates cleaned (NF weld plates to be cleaned with cup stone)
checkpoint-status | e46bddd3-c149-4771-8e2c-49ef868740da |  | checkpoint | Grade 300 starters bent up for transport (only bend starter down if transport height is increased by bending up)
checkpoint-status | 5f6d402e-29ff-4e83-8243-47d545b6e27b |  | checkpoint | Grade 500 starters are straight
checkpoint-status | e43d11ce-0752-4e30-9276-05601eef0884 |  | checkpoint | NF Quality acceptable (attach photo)
checkpoint-status | 48ae86a5-fb44-4184-a054-f368f2531cc6 |  | checkpoint | MF Quality acceptable (attach photo)
checkpoint-status | e45cc533-1903-4bd8-91db-611bdc3eade4 |  | checkpoint | Structural repairs required (if yes photograph before)
checkpoint-status | c7596507-8e7f-4877-b407-d81759f11abd |  | checkpoint | Shop drawing checked off
checkpoint-status | c19c76fe-0b9e-4233-8f1f-141d20da1e93 |  | checkpoint | Aquron2000 applied to Mould Face of Panel
checkpoint-status | d6a6b1a2-61f5-499c-a32a-ef6557767030 |  | checkpoint | Upload photo of Batch no. for Aquron2000 applied to this panel
checkpoint-group | 9f009d2e-39d5-4ef1-8039-f98384cc9e93 |  | section | Overall Panel Quality (Yard QA)
checkpoint-status | 4986d13e-6244-4871-8b84-bf20b9c71151 |  | checkpoint | Overall Panel Quality Ratings Recorded Below
label | 2ff8b1cb-7ac1-53df-af46-78eb6d1693e9 |  | note | The higher the number the better the quality
label | 2c634f88-35d0-50a6-944e-55beebe44330 |  | note | e.g. "1" is unacceptable
button | f555994b-e225-5071-87e6-61d4a819a6e5 |  | button | Vibrating Quality | 5 , 4 , 3 , 2 , 1
button | 869a6493-be6c-565b-b276-f7c6dfec15cc |  | button | Trowelling Quality | 5 , 4 , 3 , 2 , 1
button | 8a798ac1-df4f-54dc-8a03-dee910cd0530 |  | button | Silicone Quality | 5 , 4 , 3 , 2 , 1
button | 30c0d8c2-31b5-5af4-9239-19f5b3ad476f |  | button | Chamfer Quality | 5 , 4 , 3 , 2 , 1
button | 05f8b9dd-c82b-5037-b1a8-d55a9c3592fb |  | button | MF Quality | 5 , 4 , 3 , 2 , 1
checkpoint-group | 5ed06998-d37e-4ae4-9da9-20c7c201c1db |  | section | Loading Out (Yard QA)
checkpoint-status | 410ca20a-5c94-4256-9575-dd334e21776b |  | checkpoint | Load Docket Given to Driver
checkpoint-status | b46c5ecb-24dc-4e79-a878-d3f206d09000 |  | checkpoint | Photo take of Panel on Truck
checkpoint-status | e43f0833-e66e-4a54-9d52-95f5ef05c416 |  | checkpoint | No remedial work required on site
checkpoint-group | e889270a-5643-4398-a04e-1e3cd1a34b63 |  | section | Test Results, Certificates and Documentation (Reo & Yard QA)
checkpoint-status | ad32e840-80a9-4714-8d4a-82539d67487e |  | checkpoint | Upload reinforcing detail sheets
checkpoint-status | 19a2f2db-d835-40e2-97a6-67c0eb10cf82 |  | checkpoint | Upload Photo of Reinforcing Stock Bundle Tags (Cast # Tracking)
checkpoint-status | b21cbe19-abb3-4760-a152-648e03328ad8 |  | checkpoint | Upload Concrete test results
checklist-flat | cb39f9e7-7e8f-4740-8ac4-ef68fc245ea4 |  | checklist | Job Details |  |  |  |  | Yes | Job Details Checklist | ed41acee-d06d-4515-84d2-177bddfc14a8
checkpoint-status | 3d098030-e418-4675-b5b1-7520caf5ee77 |  | checkpoint | Project details entered below
text | 8724734a-b967-59e4-b175-c5c6f1db0e60 |  | textbox | Job File Number
text | 45b6015f-22e3-5b0c-8117-3a27221048ee |  | textbox | Project Name
text | ef1b5d06-622a-5aca-84c2-8a00931e8d8a |  | textbox | Site Address
text | 31c83e66-7544-5cd3-a918-a8f6baca03e9 |  | textbox | Main Contractor (e.g. Teak)
text | b1590901-5990-5ddc-9dee-19725346ccbb |  | textbox | Main Contractor POC
text | 04d29bad-dab1-5357-9860-e83c0c02444f |  | textbox | Structural Engineer
text | 78611fa4-7a52-594c-8bc7-427229a97b3c |  | textbox | Architect
checklist-flat | 496ad6f2-797a-4b17-a0c0-69cd3b3dcd4a |  | checklist | Compliance Documentation |  |  |  |  | Yes | Compliance Documentation Checklist | f3e79d28-e6a7-4307-a43d-740ee207ed7e
checkpoint-status | f58889c0-5e6b-482f-bec0-0ae5a115ed21 |  | checkpoint | Concrete Test Results
label | 066d13f7-4c78-53cf-ae07-c6288d05b188 |  | note | Pass once all test results for this project are attached
text | 4fe06e26-34cc-58f5-876f-027f90ea4833 |  | textbox | Concrete test requirements for this project
checkpoint-status | a40742db-3201-4a72-ac32-2faed3ed3e97 |  | checkpoint | Mill Certification
label | 95c90d50-faae-57db-8f9a-9e8b3b1bada8 |  | note | Pass once all mill certs for this project are attached
checkpoint-status | 75aa4f73-99ce-4d2a-a05b-d954d6eb38ed |  | checkpoint | PS1 Attached (if applicable)
checkpoint-status | 49b1e850-1ca9-4741-8c28-ee80ef9b1a01 |  | checkpoint | PS3 Attached (if applicable)
checkpoint-status | 2e7a2ce4-b667-435d-b89d-f639ced12998 |  | checkpoint | PS4 Attached (if applicable)