## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | PRE - R - Fire Penetration |  |  |  |  | Yes | PRE - R - Fire Penetration | 041d7346-5c13-4170-93cb-7cddf695c934
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Edge Beams Installation completed and acceptable
checklist-flat |  |  | checklist | CST - R - Piling Consent |  |  |  |  | Yes | CST - R - Piling Consent | 05c47a66-8fa8-419d-a0e5-96c80bd2d2f1
checkpoint-status |  |  | checkpoint | Record of Title
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Construction Review
boolean | a7913e4f-e0f2-5925-87a8-22cd31b2f9da |  | tickbox | Producer Statement Review(PS4): Geotechnical
boolean | 8032b105-553c-5fe9-8de1-20f2cbc2f61e |  | tickbox | Producer Statement Review(PS4): Compaction of hardfill
boolean | d1399aaa-d6ed-5e44-aea6-4828f9209a08 |  | tickbox | Producer Statement Review(PS4): Drain Bridging
boolean | a9d1bf52-c84e-522f-b515-c58e35635060 |  | tickbox | Producer Statement Review(PS4): Engineer's observation
checkpoint-status |  |  | checkpoint | Producer Statement Construction(PS3): Piling
checkpoint-status |  |  | checkpoint | Pile records and cards
checkpoint-status |  |  | checkpoint | Surveyor certificate for siting
checkpoint-status |  |  | checkpoint | Mill certificates
checkpoint-status |  |  | checkpoint | Concrete dockets
checklist-flat |  |  | checklist | FC - R - STO Poly Plaster |  |  |  |  | Yes | FC - R - STO Poly Plaster | 0c06f0dd-3e25-42a8-a57c-f8c937e994b6
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | STO Poly Plaster works completed and acceptable
checklist-flat |  |  | checklist | FC - R - Symonite Alucobond Cladding System |  |  |  |  | Yes | FC - R - Symonite Alucobond Cladding System | 0db93469-109a-4ee4-9ece-7b47df9bf0c8
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Exterior Tiling works completed and acceptable
checklist-flat |  |  | checklist | Compliance documents |  |  |  |  | Yes | Compliance documents | 0e72861c-fc9e-402c-af7a-1f7e7e4db74d
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
checkpoint-status |  |  | checkpoint | Mill certs attached
button | 7dd9cf42-3199-56c3-aa77-ccb7dd0079a3 |  | button | LBP Memorandum/ Record of works filled out, signed and attached | Yes, No, N/A
button | aef92fbb-f97f-5b3d-96f3-1bfd8d9b0bc7 |  | button | Any Additional Compliance Documentation - Completed and Attached | Yes, No, N/A
label | 1917920a-50f0-5cfe-8b8b-7d624fbf5783 |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | CST - R - Site Inspection Details |  |  |  |  | Yes | CST - R - Site Inspection Details | 114e3511-7213-4de1-97e1-9139f1eafc4c
checkpoint-status |  |  | checkpoint | Specific site works location
checkpoint-status |  |  | checkpoint | Contractor QA reviewed and approved
checkpoint-status |  |  | checkpoint | Have the consented drawings been followed?
checkpoint-status |  |  | checkpoint | General comments, photos, and observations during inspection
checkpoint-status |  |  | checkpoint | Works completed to required specifications - Engineer signoff
checklist-flat |  |  | checklist | FC - R - Anchor Points - Anchor Point Installation |  |  |  |  | Yes | FC - R - Anchor Points - Anchor Point Installation | 12720ec8-80ca-42d7-84f8-8f96769e095f
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Anchor point installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - Passive fire |  |  |  |  | Yes | FC - R - Passive fire | 13b587de-9818-40eb-b5c6-15b343aaa7e0
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Passive Fire works completed and acceptable
checklist-flat |  |  | checklist | Code of Compliance (CCC) - |  |  |  |  | Yes | Add Council CCC Upload Checklist | 14e2fceb-d309-42eb-9faf-64733275556a
checkpoint-status |  |  | checkpoint | Final CCC (approved & attached)
checklist-flat |  |  | checklist | C - R - Asbestos Removal |  |  |  |  | Yes | C - R - Asbestos Removal | 1538d9fb-762c-4f1c-871f-aa1095565211
checkpoint-status |  |  | checkpoint | Demolition Survey reviewed and attached
checkpoint-status |  |  | checkpoint | Asbestos Removal Control Plan (ARCP) reviewed and attached
checkpoint-status |  |  | checkpoint | Background Air Monitoring Results (BGAM) reviewed and attached
checkpoint-status |  |  | checkpoint | Clearance Certificates reviewed and attached
checkpoint-status |  |  | checkpoint | All asbestos removed and approval given to progress with work
checklist-flat |  |  | checklist | CST - R - Foundation Consent |  |  |  |  | Yes | CST - R - Foundation Consent | 16306baa-6b02-4e55-a75a-a8248ce46e30
checkpoint-status |  |  | checkpoint | Record of title
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Pre-cast concrete
boolean | 38e2b72a-03c0-5a9b-8e7d-05eb785333ad |  | tickbox | Producer Statement Design(PS1): Prestressed concrete beams and floor units
boolean | 14b911aa-0791-5728-8e1c-5a4f6dfb33c2 |  | tickbox | Producer Statement Construction(PS3): Prestressed concrete beams and floor units
boolean | a243c39e-d43e-5da5-8d70-85a501defe46 |  | tickbox | Producer Statement Review(PS4): Prestressed concrete beams and floor units
boolean | 0e10e623-16ce-56f4-adb9-d021bcbd190b |  | tickbox | Shop drawings for concrete beams and floor units
checkpoint-status |  |  | checkpoint | Producer Statement Construction(PS3): sub-soil drainage
checkpoint-status |  |  | checkpoint | Waterproofing
boolean | e37ca62b-6a53-50e1-94de-55089945c262 |  | tickbox | Producer Statement Construction(PS3): Waterproofing Membrane
boolean | 7f436b03-414a-561d-995d-57317e991e2d |  | tickbox | Manufacturer's warranty for waterproofing membrane
checkpoint-status |  |  | checkpoint | Mill certificates
checkpoint-status |  |  | checkpoint | Concrete dockets
checkpoint-status |  |  | checkpoint | Producer Statement Review(PS4): Engineer's observation
checkpoint-status |  |  | checkpoint | Surveyor certificate for siting
checklist-flat |  |  | checklist | C - R - Bulk Excavation |  |  |  |  | Yes | C - R - Bulk Excavation | 16731c5a-7562-449f-8fc5-3f1bc304914c
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Excavation completed - Correct locations and RL's achieved
checklist-flat |  |  | checklist | On Grade Slab Pre-Pour |  |  |  |  | Yes | ITP - R - On Grade Slab Pre-Pour (per townhouse block) | 179872bf-0b7f-4586-bc53-e38b785a76f4
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Survey set out (height, location, setout) - confirmation attached.
checkpoint-status |  |  | checkpoint | Underground services installation completed
checkpoint-status |  |  | checkpoint | Backfilling completed
checkpoint-status |  |  | checkpoint | Waterproofing completed
checkpoint-status |  |  | checkpoint | DPM overlapping/taping with no tears or perforations. Council requirement
checkpoint-status |  |  | checkpoint | Reinforcing completed
checkpoint-status |  |  | checkpoint | Engineer sign off completed and approved for pour
button | d11c2df0-110a-51c6-9b0f-b634e15089b1 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Council inspection completed and approved for pour
button | 645bd602-5ff8-51ec-9e9b-aa38dabcef89 |  | button | Note remedial work needed | None, Minor, Major
text | 7737aebb-2621-5d54-bd98-66bb517a8180 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checklist-flat |  |  | checklist | CST - R - Structural Consent |  |  |  |  | Yes | CST - R - Structural Consent | 1c6975c9-e9e7-4302-8d5c-38ba4bccea5d
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Pre-cast concrete
boolean | 8665a751-ff54-5ff2-81ce-5340de842c31 |  | tickbox | Producer Statement Design(PS1): Prestressed beams, walls, stairs, columns and floor units
boolean | 72c4e1e6-bf50-57c2-966d-15f0980fe940 |  | tickbox | Producer Statement Construction(PS3): Prestressed beams, walls, stairs, columns and floor units
boolean | 0d1e7f5c-e1ad-5f9c-9e45-e682d50c89de |  | tickbox | Producer Statement Review(PS4): Prestressed beams, walls, stairs, columns and floor units
checkpoint-status |  |  | checkpoint | Structural Steel
boolean | 71bda686-abff-5d7c-b478-41b4ba840513 |  | tickbox | Producer Statement Construction(PS3): Corrosion Protection
boolean | 0b5c5ee0-ec6c-53b2-bc20-d21de9ddc6f7 |  | tickbox | ITPs approved by structural engineer
boolean | 75404302-72e9-5723-b20a-849c9ef320b7 |  | tickbox | weld inspection and test records
checkpoint-status |  |  | checkpoint | Fire rated (Intumescent) Coatings to Structural Steel
boolean | 4c1c653c-b336-5873-80ec-1be684d488dc |  | tickbox | Producer Statement Construction(PS3 - AC2334): Intumescent coatings to structural steel from approved applicator
boolean | 6d0305c1-86ad-579c-acab-7910a955c795 |  | tickbox | Suppliers material schedule - products used and thicknesses applied
boolean | c1481efb-6e62-5795-b1a7-a7f21aea3b82 |  | tickbox | Floor plan of intumescent coating locations
checkpoint-status |  |  | checkpoint | Trusses
boolean | 84657b65-96b6-5c19-9ce2-934b85a79d3a |  | tickbox | Producer Statement Design(PS1): Layout Plan for timber roof trusses
boolean | 3b92158c-0ff2-5de5-aaec-8d5aa2ab1f34 |  | tickbox | Producer Statement Construction(PS3): for timber roof trusses
checkpoint-status |  |  | checkpoint | Construction Review (Structural)
boolean | d9ecbd77-9dc2-5eac-a3d9-344e332780ea |  | tickbox | Producer Statement Construction Review(PS4): Certification of work in accordance with design, drawings, specifications and material codes
boolean | 5ea4297f-9486-5e44-9567-5f42621293e8 |  | tickbox | Producer Statement Construction Review(PS4): excavation near boundary and site observation notes
boolean | 8132b0a1-7ada-5bf8-8253-110af599b73e |  | tickbox | Producer Statement Construction Review(PS4): Raft slab and site observation notes
boolean | a2922f0d-002e-59ba-bfd3-3cdae8b02b1f |  | tickbox | Producer Statement Construction Review(PS4): Swimming pool and site observation notes
boolean | 19d384f6-91e0-506e-b377-dc7a095a1c91 |  | tickbox | Producer Statement Construction Review(PS4): Type A or B masonry and site observation notes
boolean | 81392b06-7f2c-5add-801f-b761b807e81f |  | tickbox | Producer Statement Construction Review(PS4): Underpinning and site observation notes
boolean | 8b000d73-a439-5dc5-b617-ecdc064bfd25 |  | tickbox | Producer Statement Construction Review(PS4): Structural steel including connections and site observation notes
boolean | 843b5d9d-3105-53ff-ad39-36e19050d02a |  | tickbox | Producer Statement Construction Review(PS4): Timber pole retaining wall and site observation notes
boolean | 6da9c6c2-557a-5001-8348-454bf36cec93 |  | tickbox | Producer Statement Construction Review(PS4): reinforced concrete foundations and site observation notes
boolean | 1e06dab5-7506-59c0-abbb-948ddd5300cf |  | tickbox | Producer Statement Construction Review(PS4): Suspended concrete slab and site observation notes
boolean | d4105d05-6b44-5b16-be56-98be8d0d0e12 |  | tickbox | Producer Statement Construction Review(PS4): Precast elements and site observation notes
boolean | 2619500c-534a-529e-a1f9-b4bdff654f8a |  | tickbox | Structural engineer's variations and contractor advice notes
checkpoint-status |  |  | checkpoint | Surveyor certificate for finished floor levels
checklist-flat |  |  | checklist | FC - R - Balconies |  |  |  |  | Yes | FC - R - Balconies | 1c72da76-2d2c-49f8-8271-ba09bfb24d1c
checkpoint-status |  |  | checkpoint | Waterproofing and flashing checked and acceptable
checkpoint-status |  |  | checkpoint | All screed to nib and deck falls checked and accurate
checkpoint-status |  |  | checkpoint | Soffit Checked and accurate
checkpoint-status |  |  | checkpoint | Flood test completed and acceptable
checkpoint-status |  |  | checkpoint | Installation of deck tiles completed and acceptable
checkpoint-status |  |  | checkpoint | All works on balcony are completed to required specification.
checklist-flat |  |  | checklist | CST - R - Civil Consent |  |  |  |  | Yes | CST - R - Civil Consent | 20a2bea3-7e99-4fa1-9da2-270e9ba922f2
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Drainage
boolean | 19768e1a-3604-509f-aff8-3d933dd107c3 |  | tickbox | Producer Statement Construction(PS3): sub-soil drains
boolean | 943f3155-0a4f-564b-a3a2-8183f521271d |  | tickbox | Producer Statement Construction(PS3): drainage
boolean | 8b51a533-6062-5722-8359-44a511b9579a |  | tickbox | Drainage as built plan
boolean | 4bf986dd-c0fe-57f5-87b0-f2a83949e915 |  | tickbox | Producer Statement Construction(PS3): Stormwater Management
boolean | 1fde7b8e-33ce-5bcb-a189-bb3342d9f39b |  | tickbox | Producer Statement Review(PS4): Stormwater management approved by council Engineer
boolean | 5edca8df-5cdf-52aa-a925-68960031ffa9 |  | tickbox | Operations and Maintenance manual for stormwater management systems
boolean | 1b6a3deb-a158-5b90-8b4e-a603f08f7c32 |  | tickbox | Backflow test Certificate | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Drainage Pump Systems
boolean | 88f84ee1-5722-50e5-9132-536711a17dcd |  | tickbox | Producer Statement Construction(PS3): installation of drainage pump system
boolean | 503c3ecf-5681-5421-9666-d84ba65f3930 |  | tickbox | Manufacturer's warranty for pump system
boolean | 13ae6b65-7d0b-582e-bd9b-bdea96e6f4db |  | tickbox | Maintenance agreement for pump system
checkpoint-status |  |  | checkpoint | On-Site wastewater Systems
boolean | cbd40c78-1a0e-50ca-8a90-fd2b801f5328 |  | tickbox | Producer Statement Construction(PS3): wastewater treatment and disposal system
boolean | 27c01d62-b37a-53d7-8453-23777425e134 |  | tickbox | Plan showing location of treatment and disposal of systems
boolean | b55087aa-74be-57cb-9e2d-89b555b7dcce |  | tickbox | Producer Statement Review(PS4): System of onsite treatment and disposal of wastewater
boolean | 6721d75a-2d0d-54c5-b345-6a0eb759ce3f |  | tickbox | Maintenance agreement for on-site wastewater treatment and disposal system
checkpoint-status |  |  | checkpoint | Development Engineering
boolean | 965baa6d-8dd2-514b-b17b-2a7e293dcf04 |  | tickbox | Written approval of works completed within 2m of public waste water drainage
boolean | 71c2fc76-cf16-5796-b986-86aeb2896335 |  | tickbox | Engineering Approval Completion Certificate for ENG
checkpoint-status |  |  | checkpoint | Watercare Services/Viola Approval
boolean | 45fd707f-6946-5d96-83e6-e8af7cf2dc1e |  | tickbox | Certificate of connection for both incoming and outgoing water to the public system
boolean | 7fd0800a-7f9d-5643-99bf-5992672dd68e |  | tickbox | Written approval of completed works
checklist-sectioned |  |  | checklist | Townhouse Block Build |  |  |  |  | Yes | ITP - R - Townhouse Block Build (per townhouse block) | 223d22c6-dbd0-4af6-be1e-ec4224c35d5f
checkpoint-group |  |  | section | Structure/Framing
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Timber Framing installed
checkpoint-status |  |  | checkpoint | Council pre-clad inspection completed and approved. Note date of inspection in comments
button | ae2440be-cda6-500b-8dd9-77d576e808a4 |  | button | Note remedial work needed | None, Minor, Major
text | de8cffb9-cd3e-53a6-b77d-784d42602592 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Roofing
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Verify materials supplied to site (material and fixings) are as specified or approved samples
checkpoint-status |  |  | checkpoint | Construction complies with specifications
checkpoint-status |  |  | checkpoint | Obtain and upload all performance and authority certificates as required by specification or statutory regulations.
checkpoint-status |  |  | checkpoint | Council Pre-Roof Inspection completed and passed
button | 2f280b5b-4dbf-505d-8c42-66ecd7c04b44 |  | button | Note remedial work needed | None, Minor, Major
text | f9414f19-9304-5e82-9d9e-e015da648e2a |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Façade
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Envelope/Watertightness Completed (requirements below)
button | 5ed943b8-cab2-56a4-940e-21a527ad172e |  | button | Ecoply Board installed | Yes, Reworked, N/A
button | ce9e96df-47c8-5e91-82f9-e96340278a6f |  | button | Lintels installed | Yes, Reworked, N/A
button | 54546223-a34b-5cc8-877e-892837ff97f7 |  | button | Tapes and VaproShield installed. | Yes, Reworked, N/A
button | c258087c-cc2c-5239-9ac9-f7d1d6631f3e |  | button | Windows and Sliders installed | Yes, Reworked, N/A
button | d1f5b10d-13fa-57cc-8c6f-0b68a5a26518 |  | button | Flashing installed | Yes, Reworked, N/A
button | 0467241e-d5c1-5d74-9fb3-439c3fe86b6b |  | button | Envelope Penetrations completed | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Council pre-wrap inspection completed and passed
button | 0ef82f6d-0d00-53f6-92ac-d1e31d7172c9 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Council brickwork 'half-high' inspection completed and acceptable
button | 187f3e0d-a4b3-5ec1-885d-8141659a2d20 |  | button | Note remedial work needed | None, Minor, Major
text | 76f712e6-48f4-5de5-a7db-550f7d16ff79 |  | textbox | Describe cladding type:
button | 33f1e5f7-f93e-5164-814f-f9cdbcd00ccd |  | button | Brick Works completed | Yes, Reworked, N/A
button | dee409d5-f152-5fc2-9d14-2bdb47ef6b50 |  | button | STO Poly Plaster completed | Yes, Reworked, N/A
text | eccfb8a9-4cab-5a98-8e5d-e4ff40c86e5f |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Pre-Line
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Pre-line completed
button | 88af1826-fe7c-5557-8994-9a6798baa652 |  | button | Timber frame installation completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Nogs Installed as below and comply
button | 18804492-42e4-5f48-b81e-9fae9e7277b4 |  | button | Steel Stud frame installation completed and acceptable | Yes, Reworked, N/A
button | 434bb102-384c-50b4-ae32-ef07e56a6694 |  | button | Electrical First Fix completed and acceptable | Yes, Reworked, N/A
button | c85ed566-e12f-58ee-a15c-beff2abff785 |  | button | Plumbing First Fix completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Insulation installation completed and acceptable
checkpoint-status |  |  | checkpoint | Security, Comms and Data First Fix completed and acceptable
button | 8b6e41ea-22be-5582-9268-2a44095c14d5 |  | button | HVAC First Fix completed and acceptable | Yes, Reworked, N/A
button | 8aeb823a-ecb8-59fb-9658-0328870d2258 |  | button | Fire Security First Fix completed and acceptable | Yes, Reworked, N/A
button | 022c7931-6be6-55bb-bec4-12cb4a08d181 |  | button | Underfloor heating First Fix (including screeding and soundproofing of the bathrooms/ wc) completed and acceptable | Yes, Reworked, N/A
button | 78901aba-88c3-5251-b2dd-7fa462f155c2 |  | button | Kitchen extract First Fix completed and acceptable | Yes, Reworked, N/A
button | e4a4f3ee-6741-57d4-8037-908c51c987fe |  | button | Passive fire installation completed and acceptable | Yes, Reworked, N/A
button | 1cba4380-6ab8-5d27-8158-52d45c5668f5 |  | button | Suspended ceiling grids installation completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Pre-line plumbing external inspections completed and uploaded. Any remedial work signed off.
button | fad15f96-52cf-5c96-8fcd-3c4a290b880e |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Pre-line building external inspections completed and uploaded. Any remedial work signed off.
button | 8bc0dd7a-b54f-519e-a907-b56577a6cd50 |  | button | Note remedial work needed | None, Minor, Major
text | d62c1240-bc4e-5002-b8b8-aeded3b6e334 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Post-Line GIB
checkpoint-status |  |  | checkpoint | GIB installation correct, screw types, pattern, etc..
checkpoint-status |  |  | checkpoint | Fire rated GIB installed to adjoining unit walls & garage, correct thickness.
checkpoint-status |  |  | checkpoint | Post Line Council Inspection completed and acceptable. GIB stopping to proceed
button | 8e15d56c-2104-533b-8c3b-1b14c1ec6ba6 |  | button | Note remedial work needed | None, Minor, Major
checklist-flat |  |  | checklist | FC - R - Air conditioning |  |  |  |  | Yes | FC - R - Air conditioning | 24c65776-f856-407c-a650-3574efad25a9
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Exterior Tiling works completed and acceptable
checklist-flat |  |  | checklist | CST - R - Hydraulic Consent |  |  |  |  | Yes | CST - R - Hydraulic Consent | 25771e01-dd07-4873-a844-431e45f630c4
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Plumbing
boolean | ece9321c-c8ea-5f4f-80a1-6d18090a7998 |  | tickbox | Producer Statement Construction (PS3): Plumbing
boolean | d7b80f01-26e1-5d0e-86e5-7bdc6159e3b8 |  | tickbox | Confirmation of water saving devices
boolean | 13b43adb-4ef7-5e92-a674-0cf96985f24f |  | tickbox | Plumbing under slab as built plan
boolean | c7cc96b6-f4fe-5e4e-bbae-42caf9867673 |  | tickbox | Producer Statement Review(PS4): hydraulic systems of the building from a council approved engineer
checkpoint-status |  |  | checkpoint | Gas-fitting Work Certificate
checkpoint-status |  |  | checkpoint | Automatic Backflow Preventers Connected to Potable Water supply
boolean | 8545d4b9-c664-52cd-834a-f799724e54de |  | tickbox | Backflow prevention - PS3 and test certificates showing location and type of devices
checkpoint-status |  |  | checkpoint | Application for compliance schedule (AC2102)
checkpoint-status |  |  | checkpoint | Confirmation of performance standards for specified systems (AC2150)
checklist-flat |  |  | checklist | CST - R - Restricted Building Works Consent |  |  |  |  | Yes | CST - R - Restricted Building Works Consent | 2d9dfba0-6ccd-4525-a636-4f67de345829
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Record of works
boolean | febebef9-b405-5882-b33e-69f478e94237 |  | tickbox | Foundations
boolean | fd93a3e2-17c5-5ecc-8097-b40cf11f32d0 |  | tickbox | Slab or subfloor framing
boolean | fdeb1c0f-9262-5f25-80ab-d5fadae41d81 |  | tickbox | Blockwork
boolean | 672eb158-2d56-5815-a50c-4cdbc809435a |  | tickbox | Walls
boolean | 3f693d5d-42a7-579d-a5c6-2afd58f70290 |  | tickbox | Roof
boolean | c23ef4b6-dc32-55e6-b649-7c7a8fc7fd74 |  | tickbox | Columns and Beams
boolean | ccb41977-cbe5-5441-a99c-ef7b69263a4f |  | tickbox | Bracing
boolean | 370dfac4-b4a5-5ac2-90e0-bab9ba10f2ec |  | tickbox | Damp proofing
boolean | ec6cf2a7-62ce-5edc-a6dd-c22608f0d23f |  | tickbox | Roof cladding or roof cladding system
boolean | 79b2388d-bf1b-51f1-b30f-b6128ca0568c |  | tickbox | Ventilation system
boolean | 2960e384-07ce-5d10-9e3a-d862415b9018 |  | tickbox | Wall cladding or wall cladding system
boolean | d896e4c6-9ebc-5431-9b65-f8b52a04ba00 |  | tickbox | Waterproofing
checkpoint-status |  |  | checkpoint | Record of warranties
checklist-flat |  |  | checklist | CST - R - Demolition Consent |  |  |  |  | Yes | CST - R - Demolition Consent | 2fd4deb6-3903-4142-93ae-af32dec12868
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection passed
checkpoint-status |  |  | checkpoint | Summary Sheet - Site inspection records
checkpoint-status |  |  | checkpoint | Summary Sheet - LBP Records
checkpoint-status |  |  | checkpoint | Asbestos - Asbestos Clearance Certificates & PS3
checkpoint-status |  |  | checkpoint | Demolition - PS3
checklist-flat |  |  | checklist | FC - R - Roofing |  |  |  |  | Yes | FC - R - Roofing | 31be49c5-5b79-4537-831d-576138bab285
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Roofing installation completed and acceptable
checklist-flat |  |  | checklist | Fitout |  |  |  |  | Yes | ITP - R - Fitout (per townhouse unit) | 32bad470-b2fc-43b8-adeb-a3d853c836df
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Finishing completed, meets benchmark standard. Refer separate checklist. Full response to the items below needed.
button | 44b8c990-b3fa-55f2-b4b6-74fe68fec498 |  | button | Hardware/Fittings | Yes, Reworked, N/A
button | cc2bd0b0-9ebe-59f8-a221-f166e5c543ca |  | button | Plumbing completed and acceptable | Yes, Reworked, N/A
button | b0edb564-09d4-5843-8087-450d24e2e1d2 |  | button | Electrical completed and acceptable | Yes, Reworked, N/A
button | 85e5398b-6a3e-5092-9ad9-338132df2da2 |  | button | Joinery/Doors completed and acceptable | Yes, Reworked, N/A
button | 0034d2f5-72f1-54d2-ace9-5e7f1b30c2ce |  | button | Decorating completed and acceptable | Yes, Reworked, N/A
button | f6f125e9-a837-5ef6-8d4e-d611c5642982 |  | button | Flooring completed and acceptable | Yes, Reworked, N/A
button | 66fa23e3-c0e0-50f1-9bc1-f5cfc916d171 |  | button | Other works completed (inc. client extras) and acceptable, state below. | Yes, Reworked, N/A
text | 323621c3-bc29-583f-a712-ccecce7e59f1 |  | textbox | Details:
checkpoint-status |  |  | checkpoint | Upload Related Ryman Fitout quality inspection record (QT-012)
holdpoint |  |  | signoff | Raise remedial as required.
checklist-flat |  |  | checklist | F - R - Piling |  |  |  |  | Yes | F - R - Piling | 32c2141d-4f49-476c-bd71-bbe0340ba9cb
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Piling completed as per the specifications
checklist-flat |  |  | checklist | ST - R - Intumescent Painting |  |  |  |  | Yes | ST - R - Intumescent Painting | 3437b8b7-71a0-404c-84f8-49b012f87641
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Intumescent Painting completed and acceptable
checklist-flat |  |  | checklist | Handover |  |  |  |  | Yes | H - R - Handover | 35dc7263-f571-4c03-b9d1-09cbbd3f5428
checkpoint-status |  |  | checkpoint | Hardware/Fittings
checkpoint-status |  |  | checkpoint | Plumbing
checkpoint-status |  |  | checkpoint | Electrical
checkpoint-status |  |  | checkpoint | Joinery/Doors
checkpoint-status |  |  | checkpoint | Decorating
checkpoint-status |  |  | checkpoint | Flooring
checkpoint-status |  |  | checkpoint | Other
checkpoint-status |  |  | checkpoint | Upload Related Ryman Fitout quality inspection record (QT-012)
checklist-flat |  |  | checklist | ST - R - Monier Tiled Roof Installation |  |  |  |  | Yes | ST - R - Monier Tiled Roof Installation | 3c1f7273-95f7-46ee-86cf-15c77321636f
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Monier Installation Guide Confirmed with Contractor
checkpoint-status |  |  | checkpoint | Subcontractor QA completed and passed
checkpoint-status |  |  | checkpoint | Fall Arrest Anchor Point Fixings in place
checkpoint-status |  |  | checkpoint | Producer Statement Construction (PS3) received and attached for installation of roof abseil and/or fall arrest system
checkpoint-status |  |  | checkpoint | Battens - jointing and fixing.
checkpoint-status |  |  | checkpoint | Sarking/Underlay
checkpoint-status |  |  | checkpoint | Tiles Laid and Secured
checkpoint-status |  |  | checkpoint | Hip and Ridge Tile Bedding and Pointing
checkpoint-status |  |  | checkpoint | Gable ends / Barge Boards - Finish
checkpoint-status |  |  | checkpoint | Fire Wall/Internal Separating Walls
checkpoint-status |  |  | checkpoint | Fire Consultant inspection completed and approved
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
text | a1d09d09-5c54-5ed4-89b7-ebd02029b01b |  | textbox | Note remedial work needed
holdpoint |  |  | signoff | Raise remedial as required.
checklist-flat |  |  | checklist | ST - R - Structural Steel Installation |  |  |  |  | Yes | ST - R - Structural Steel Installation | 3d1db999-097d-439d-bcf8-3fd32cb111d9
checkpoint-status |  |  | checkpoint | Chemical anchor proof tests conducted on the sample selected by the MV Engineer
boolean | 6e606869-0238-5116-8648-a89e1ce00c09 |  | tickbox | Chemical anchors are tested to 0.7xdesign load
boolean | 4d7b5aa5-6458-5f41-b5be-760b37e070ff |  | tickbox | The test load of the bar is provided by the MV Engineer
boolean | 34dbcbaf-fdcf-5197-80a0-cb5afa0c064d |  | tickbox | Proof load tests maintained for a minimum of 30 seconds
boolean | 74e9db9a-11d3-5ad9-8d47-d81df7217f8e |  | tickbox | The load did not drop more than 10% during the testing
checkpoint-status |  |  | checkpoint | If the proof of tests show failure of the anchors, installation of anchors should stop, cause of failure investigated and installation methodology should be reviewed. If failure is recorded, the minimum test sample shall be increased to 6 specimens or 5% of the total relevant anchor population, whichever is greater.
checkpoint-status |  |  | checkpoint | Mechanical anchor testing conducted on the sample selected by the MV Engineer and witnessed by the MV Engineer
boolean | bc45a741-a53d-5653-9f29-22a520d237f3 |  | tickbox | For trubolt or similar anchors the maximum tightening torque is reviewed
checkpoint-status |  |  | checkpoint | If the proof of tests show failure of the anchors, installation of anchors should stop, cause of failure investigated and installation methodology should be reviewed. If failure is recorded, the minimum test sample shall be increased to 6 specimens or 5% of the total relevant anchor population, whichever is greater.
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All structural steel correctly installed in respective area and acceptable
checklist-flat |  |  | checklist | Minor Variation - |  |  |  |  | Yes | Add Council Minor Variation Checklist | 3e8638bb-be1a-429d-8501-13080b2ec339
checkpoint-status |  |  | checkpoint | Minor variation status (Pass once approved & all information is attached including observations, correspondence & close out evidence)
label | d83c76ad-c2c4-422a-b3d0-5e46ac4be24f |  | note | PASS above checkpoint when variation is approved
label | ab21c4bc-c773-43ee-88d7-f338c674ee92 |  | note | If minor variation is a FAIL - document why below and follow appropriate corrective actions
text | e716f58a-4420-4e11-91ae-f4fef0f7ba87 |  | textbox | Date of application
text | 6931f74e-964b-42b5-905c-440c2ce0001a |  | textbox | Reason for application
text | 4ce69a81-cba4-4eac-b963-ff28392bbaf5 |  | textbox | Date of approval / acceptance
text | 78d9159e-0896-4188-a542-fa6b1bf43aaa |  | textbox | Inspection Type Code (If applicable e.g. Site meeting IME)
boolean | d24858c1-85f5-44b8-99c0-818a707a7f19 |  | tickbox | Council approval of minor variation attached
checklist-sectioned |  |  | checklist | FC - R - Scaffold Drop Checklist |  |  |  |  | Yes | FC - R - Scaffold Drop Checklist | 3ec2610c-48bd-42d8-bf81-a28feb8630f6
checkpoint-group |  |  | section | Brickwork
checkpoint-status |  |  | checkpoint | Weep holes installed.
checkpoint-status |  |  | checkpoint | Weep holes clean of mortar.
checkpoint-status |  |  | checkpoint | Vent holes installed.
checkpoint-status |  |  | checkpoint | Vent holes clear of mortar.
checkpoint-status |  |  | checkpoint | Mortar finish acceptable – no holes.
checkpoint-status |  |  | checkpoint | Mortar acceptable around vents.
checkpoint-status |  |  | checkpoint | Clean Lintel Cavity.
checkpoint-status |  |  | checkpoint | Vent holes full brick.
checkpoint-status |  |  | checkpoint | No damage to bricks.
checkpoint-status |  |  | checkpoint | Seals completed Nib / Brick. Soffit / Brick.
checkpoint-group |  |  | section | Sto
checkpoint-status |  |  | checkpoint | Seals completed Nib / Brick.
checkpoint-status |  |  | checkpoint | Sto finish good ( not damaged.)
checkpoint-status |  |  | checkpoint | Paint standard acceptable
checkpoint-status |  |  | checkpoint | Soffits complete
checkpoint-group |  |  | section | Windows
checkpoint-status |  |  | checkpoint | Windows are clean
checkpoint-status |  |  | checkpoint | Railside's sealed (good seal)
checkpoint-status |  |  | checkpoint | Transom rubber caps installed (not loose)
checkpoint-group |  |  | section | Misc
checkpoint-status |  |  | checkpoint | Downpipes installed
checkpoint-status |  |  | checkpoint | Roof capped & fascia installed
holdpoint |  |  | signoff | Raise remedial / Request Sign Off
checklist-flat |  |  | checklist | F - R - Waterproofing |  |  |  |  | Yes | F - R - Waterproofing | 40351550-8383-4266-9550-6ba1f89a5a82
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All waterproofing works completed as per the specifications
checklist-flat |  |  | checklist | FC - R - RAB Board |  |  |  |  | Yes | FC - R - RAB Board | 41770ce7-a063-4a7a-88e5-8f420f79cb70
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | RAB Board works completed and acceptable
checklist-flat |  |  | checklist | C - R - Detailed Excavation |  |  |  |  | Yes | C - R - Detailed Excavation | 46075eae-7496-46af-9c1b-4a5d8349bfae
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Excavation completed - Correct locations and RL's achieved
checklist-sectioned |  |  | checklist | ST - R - Concrete Pour Inspection |  |  |  |  | Yes | ST - R - Concrete Pour Inspection | 464d65bf-ae9e-4acf-900d-f2d14b0dbb8d
checkpoint-group |  |  | section | IMMEDIATELY PRIOR TO POUR
checkpoint-no-status |  |  | checkpoint | IMMEDIATELY PRIOR TO POUR
text | b6e51901-1c7b-5c9f-a0ea-5f9f9c43c97d |  | textbox | Confirm temperature on site is within allowable range to pour (Deg C)
boolean | d03a3535-b355-5051-8c22-cdb12195dd72 |  | tickbox | If air temp > 32°C then confirm aliphatic alcohol to be applied.
boolean | 721ddfb0-f8be-5317-9c01-331fa717dff4 |  | tickbox | Rain forecast?
checkpoint-status |  |  | checkpoint | Confirm concrete tester is onsite to take samples (slump & cylinder) as per approved testing rate
checkpoint-status |  |  | checkpoint | Confirm agreed concrete truck turn around times and supply rate with supplier
checkpoint-status |  |  | checkpoint | Confirm maximum waiting time with concrete supplier
checkpoint-status |  |  | checkpoint | Confirm positioning of pump is adequate to place concrete in a safe and timely manner
checkpoint-status |  |  | checkpoint | Confirm all required access permits, traffic control and the like are in place for movements of concrete trucks and pumps
checkpoint-status |  |  | checkpoint | Reinforcement installed as per structural design
checkpoint-group |  |  | section | DURING CONCRETE POUR
checkpoint-status |  |  | checkpoint | Concrete dockets - attach photo of each docket to this item
checkpoint-status |  |  | checkpoint | Confirm delivery docket complies with mix design prior to dispatching concrete, check for MPA, slump tolerance, max. time from plant to discharge.
checkpoint-status |  |  | checkpoint | Location of each batch of concrete marked up on pour plan
checkpoint-status |  |  | checkpoint | Ensure no water is added to the concrete mix (whether pump or truck).
checkpoint-status |  |  | checkpoint | Confirm vibrator use, rubber tipped vibrator used at regular intervals and penetrate vertically approx. 50mm into previous layer.
checkpoint-status |  |  | checkpoint | Confirm levels, as per drawings, confirm correct cover, falls and flatness tolerances achieved.
checkpoint-status |  |  | checkpoint | Confirm jointing as per drawings, do not relocate, eliminate or make other construction joints.
checkpoint-status |  |  | checkpoint | Confirm Finishing - As per drawings, confirm finish requirements achieved (sufficient to receive nominated floor coverings) - Steel trowel finish to carpet & vinyl areas, wood
checkpoint-group |  |  | section | IMMEDIATELY AFTER POUR
checkpoint-no-status |  |  | checkpoint | IMMEDIATELY AFTER POUR
text | 91259faf-f53d-5c10-a93e-ffcd317bcaab |  | textbox | Approved Curing Method (nominate)
checkpoint-status |  |  | checkpoint | Check cured when bleed water stops and able to access slab without marking and also amount used complies
checkpoint-status |  |  | checkpoint | Curing commenced and will continue from completion of finish - Fully enclosed internal surfaces/Early age concrete: 3 days - Other concrete surfaces: 7 days. Prevent rapid drying out at the end of the curing period.
checkpoint-status |  |  | checkpoint | Foreman Sign off to receive inspection results - concrete pour inspections completed by subcontractor. Pass this checkpoint once signed.
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO PROJECT MANAGER TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | ST - R - Blockwork |  |  |  |  | Yes | ST - R - Blockwork | 469ec822-8bea-4ebe-9e2b-430a5e30a57d
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Blockwork walls completed and acceptable
checklist-flat |  |  | checklist | ST - R - Precast Wall Bracket Installation |  |  |  |  | Yes | ST - R - Precast Wall Bracket Installation | 46de831e-1271-41b6-8a28-e460eba33b24
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Wall Bracket Installation completed and acceptable
checklist-flat |  |  | checklist | C - R - Service Trenches - Common Service Trenches |  |  |  |  | Yes | C - R - Service Trenches - Common Service Trenches | 49703f4e-51ad-4b7d-9e07-1fd104d875db
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Common service trench works completed as per the specifications
checklist-flat |  |  | checklist | FC - R - Windows and Sliders |  |  |  |  | Yes | FC - R - Windows and Sliders | 4bc91ade-1aee-4e29-8f59-dcef6fe5b2b2
checkpoint-status |  |  | checkpoint | Check clearance around opening min 6mm/ max 18mm
checkpoint-status |  |  | checkpoint | Packers to be correctly used and set back to allow continuous air seal
checkpoint-status |  |  | checkpoint | Check air seal is provided at the rear of the window reveal
holdpoint |  |  | signoff | Raise remedial/ request signoff
checkpoint-status |  |  | checkpoint | Window and slider installation completed and acceptable
checklist-flat |  |  | checklist | Inspection - |  |  |  |  | Yes | Add Consultant Inspection Checklist | 4c9637d8-57e8-467d-ab6e-0223daa73c62
checkpoint-status |  |  | checkpoint | Inspection completed, attached and any relevant observations closed out
text | e716f58a-4420-4e11-91ae-f4fef0f7ba87 |  | textbox | Date of Inspection:
text | 78d9159e-0896-4188-a542-fa6b1bf43aaa |  | textbox | Type of Inspection:
text | 534f8c4f-3a28-4d0b-8e31-2e870fe2cb87 |  | textbox | Area inspection relates to
boolean | d24858c1-85f5-44b8-99c0-818a707a7f19 |  | tickbox | Inspection attached
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All Relevant Observation Closeout evidence attached here if applicable (Pass once completed)
text | b4ff21c8-e458-474a-a19a-1cbce0361c6d |  | textbox | Corrective Actions Required
checklist-flat |  |  | checklist | CST - R - Façade Consent |  |  |  |  | Yes | CST - R - Façade Consent | 4cc9293f-b032-427e-bf12-4f7d14f27229
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Exterior
boolean | f968388a-cfce-55cd-9a4e-12eb4748d683 |  | tickbox | Producer Statement Construction(PS3): Plaster system and manufacturer's product warranty
boolean | e4a85445-0b8f-56f2-b1ce-d4aa94359c9f |  | tickbox | Producer Statement Construction(PS3): Brick work and manufacturer's product warranty
checkpoint-status |  |  | checkpoint | Glazing and external joinery
boolean | 5d0e3abf-dce0-5290-a234-30ba23f3281a |  | tickbox | Producer statement for aluminium joinery complying with NZS4211:2008
boolean | ef25734f-ae53-557f-b0ec-f3e5d454b54a |  | tickbox | Producer Statement Construction(PS3): safety glazing in compliance with NZS4211:2008
boolean | c26cab3e-3089-5564-bdef-146c3bd32e67 |  | tickbox | Producer Statement Design(PS1) from joinery manufacturer
boolean | d5bed982-61ff-5517-a534-49621a67287b |  | tickbox | Producer statement for fire rated windows confirming compliance with NZS4232
checkpoint-status |  |  | checkpoint | Waterproofing
boolean | ed611f4f-70bc-5f52-92c5-29cc2174f877 |  | tickbox | Producer Statement Construction(PS3): Roof membrane and Manufacturer's product warranty
boolean | d9199281-9fe8-5c55-8a57-d19b7aaeff44 |  | tickbox | Producer Statement Construction(PS3): Deck Membrane and manufacturer's product warranty
boolean | 39b2de31-1000-5db1-bf0f-d8b66728cc6d |  | tickbox | Producer Statement Construction(PS3): Tanking membrane and manufacturer's product warranty
checkpoint-status |  |  | checkpoint | Roof abseil and fall arrest system
boolean | a0f3495d-1f96-568c-b00b-484230376ba8 |  | tickbox | Producer Statement Design(PS1): installation of roof abseil and/or fall arrest system
boolean | 107fed0d-c26e-5fc7-af04-da7e2e8062c3 |  | tickbox | Producer Statement Construction(PS3): installation of roof abseil and/or fall arrest system
boolean | ad1a0c90-82bf-51b3-838e-829dbbf69c85 |  | tickbox | Producer Statement Review(PS4): installation of roof abseil and/or fall arrest system
checkpoint-status |  |  | checkpoint | Balustrades
boolean | 20dcd26e-9791-5dbf-a8e0-4dc0498021c8 |  | tickbox | Producer Statement Construction (PS3) for the balustrade installation
checkpoint-status |  |  | checkpoint | Façade systems
boolean | 8103f79a-5a74-590f-b0d3-be4a8f94c6aa |  | tickbox | Producer Statement Review(PS4): from council approved façade engineer for façade system
boolean | ad362eb1-eb79-51d8-9751-9c0ce13eb97d |  | tickbox | Written report from council approved façade engineer for façade system (supporting the PS4)
boolean | 22c03eed-ecaa-5b31-bb61-8b589fc905c4 |  | tickbox | Producer Statement Construction(PS3): installation of the façade system
boolean | 6f1f3a13-f415-5303-93d6-7e6e41f112fc |  | tickbox | Façade System Maintenance Manual
boolean | 2ccb4e50-0eb8-533c-9803-98ee15f4f9f8 |  | tickbox | Warranties/Guarantees from main and sub-contractors
checklist-flat |  |  | checklist | FC - R - Water Test |  |  |  |  | Yes | FC - R - Water Test | 501cb642-699b-4277-900a-7a3316f8dc9b
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Water Test completed and acceptable
checklist-flat |  |  | checklist | F - R - Crane Piling |  |  |  |  | Yes | F - R - Crane Piling | 53209094-0830-489b-be9a-0578ac463ccf
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Crane Piling completed and acceptable
checklist-flat |  |  | checklist | Balustrades Installation |  |  |  |  | Yes | FC - R - Balustrades | 53514832-6d72-4681-a3e0-a9015e187340
checkpoint-status |  |  | checkpoint | Chemset bolt pull testings completed and passed. Test results received and confirmed.
label | aca8cf72-9e54-5ba8-a628-5ac6b1872f88 |  | note | Record sample size (%)
checkpoint-status |  |  | checkpoint | Lateral load pull testings completed and passed. Test results received and confirmed.
label | f79a184e-361a-532f-8ea5-7ff6d5da43d6 |  | note | Record sample size (%)
text | 349fa016-ff3e-5329-a4f1-7e78ce0d7dee |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checklist-flat |  |  | checklist | CST - R - Fitout Consent |  |  |  |  | Yes | CST - R - Fitout Consent | 55dbb888-18fb-4151-88b9-42188357783e
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP records
checkpoint-status |  |  | checkpoint | Waterproofing
boolean | 0f539ab2-4cee-56de-a423-d3c9bf3bc927 |  | tickbox | Producer Statement Construction(PS3): Waterproofing Membrane
boolean | 5c7b388f-7349-53dd-a585-83cd264fce8b |  | tickbox | Manufacturer's warranty for waterproofing membrane
checkpoint-status |  |  | checkpoint | Surface Coatings
boolean | 5802bcf6-462e-56f6-8fa3-b552909014d2 |  | tickbox | Producer Statement Construction(PS3): surface finishes complying with (material categories 1-3 – NZBC clause C3.4(a)
boolean | b79aa63f-c23f-5b01-9177-acc0b41d54ab |  | tickbox | Producer Statement Construction(PS3): floor surface materials complying with (NZBC clause C3.4(b))
checkpoint-status |  |  | checkpoint | Acoustic testing
boolean | 8ec899b3-a437-54a8-b6a0-b4d6291929e0 |  | tickbox | Report/Test certificates from council approved acoustic engineer confirming compliance with NZBC G6
checkpoint-status |  |  | checkpoint | Balustrades
boolean | 46def76e-0af2-52db-abee-40912ca04739 |  | tickbox | Producer Statement Construction(PS3) for balustrade installation
checkpoint-status |  |  | checkpoint | Producer Statement Construction(PS3) for proprietary products
checklist-flat |  |  | checklist | FC - R - Exterior Timber Framing |  |  |  |  | Yes | FC - R - Exterior Timber Framing | 580de66b-aaf6-4a40-bbaf-4b6f193d0dd5
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Exterior Timber Framing works completed and acceptable
checklist-sectioned |  |  | checklist | Contractor Allocation |  |  |  |  | Yes | ITP - R - Contractor Allocation (Use at stage level for each subcontractor on the stage) | 5893e8e4-b813-4b78-973a-7a400387d9b3
checkpoint-group |  |  | section | Contractor Allocation
checkpoint-no-status |  |  | checkpoint | Contractor Allocation
text | 335a9046-1d97-503f-b8a0-edffa4e773c4 |  | textbox | Record Subcontractor Company Name
text | a823d756-e6f0-5497-93f3-aac8d2ee431e |  | textbox | Record scope of works
checkpoint-status |  |  | checkpoint | Specifications confirmed with subcontractor management
checkpoint-status |  |  | checkpoint | Programme milestones confirmed with subcontractor management
checkpoint-status |  |  | checkpoint | All subcontractor ITPs (inspection test plans) attached and agreed.
checkpoint-status |  |  | checkpoint | Quality expectations and requirements discussed and confirmed as understood.
text | 85e9bea5-f967-5512-822d-475a8c542388 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
holdpoint |  |  | signoff | Escalate concerns to QA Advisor
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Post-Line GIB
checkpoint-status |  |  | checkpoint | GIB installation correct, screw types, pattern, etc..
checkpoint-status |  |  | checkpoint | Fire rated GIB installed to adjoining unit walls & garage, correct thickness.
checkpoint-status |  |  | checkpoint | Post Line Council Inspection completed and acceptable. GIB stopping to proceed
button | 69830650-1928-55da-ba5d-8d57a88009d5 |  | button | Note remedial work needed | None, Minor, Major
checklist-flat |  |  | checklist | F - R - Underslab plumbing |  |  |  |  | Yes | F - R - Underslab plumbing | 5e359809-3957-4b02-90ec-3094bf0ffcb2
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All underslab plumbing installation completed as per the specifications
checklist-flat |  |  | checklist | FC - R - Louvres Installation |  |  |  |  | Yes | FC - R - Louvres Installation | 608a300d-9ee9-4e2d-8435-12932e623431
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Louvres installation completed and acceptable
checklist-sectioned |  |  | checklist | Rib & Infill Installation |  |  |  |  | Yes | ST - R - Rib & Infill Installation | 6cf9573d-2b25-4e59-bcb4-6735da65ac06
checkpoint-group |  |  | section | Pre-commencement
checkpoint-status |  |  | checkpoint | Rib lifting plan confirmed, correct chains and hooks verified.
checkpoint-status |  |  | checkpoint | Propping layout confirmed as "issued for construction" with contractor and attached.
checkpoint-status |  |  | checkpoint | Floor area cleared for propping to be erected.
checkpoint-status |  |  | checkpoint | Rib grid layout confirmed with contractor and drawing attached.
checkpoint-group |  |  | section | Rib Installation
checkpoint-status |  |  | checkpoint | Rib inspection results received from the contractor
checkpoint-status |  |  | checkpoint | Ribs placed as per layout.
checkpoint-status |  |  | checkpoint | All ribs visually supported as per plan, no visual damage. Ready for infill panels.
checkpoint-group |  |  | section | Infill Panel Installation
checkpoint-status |  |  | checkpoint | Infill panel inspection results received from the contractor
checkpoint-status |  |  | checkpoint | Infill boards constructed as panels, including 'backbone', 6 to 10 boards in length and fitted tightly between the ribs
checkpoint-status |  |  | checkpoint | Infill panel adjacent ends are joined, locked with timber blocks to prevent lateral movement, and secured to wall supports
checkpoint-status |  |  | checkpoint | No obvious visual defects on infill boards, no knots, no cracks or other weakness across 25% of the width.
checkpoint-group |  |  | section | Completion
checkpoint-status |  |  | checkpoint | All propping below timber infill complete
checkpoint-status |  |  | checkpoint | Handrails installed on all edges (top of slab)
checkpoint-status |  |  | checkpoint | All penetrations closed or exclusions in place
checkpoint-status |  |  | checkpoint | Pass to indicate agreement to proceed to lay reinforcing.
holdpoint |  |  | signoff | Raise Remedial if failed
checklist-flat |  |  | checklist | FC - R - Brick Works |  |  |  |  | Yes | FC - R - Brick Works | 6dcd59b9-cab9-4f93-bbc9-1240207bb57f
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Brick works completed and acceptable
checklist-flat |  |  | checklist | ST - R - Precast Balcony Installation |  |  |  |  | Yes | ST - R - Precast Balcony Installation | 6f55241d-b185-42a1-8194-677c2760c1b6
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Joints grouted with Sika 212 and PEF rod.
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Balcony Installation completed and acceptable
checklist-flat |  |  | checklist | Council Structural Audit Checklist |  |  |  |  | Yes | Add Council Structural Audit Checklist | 75746dc5-233c-40da-a81c-e4a4998ceb3f
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Concrete pour completed and acceptable
checklist-flat |  |  | checklist | PRE - R - PRE-line |  |  |  |  | Yes | PRE - R - PRE-line | 8306af56-bfbe-487a-aa9b-fcb427e78d99
checkpoint-status |  |  | checkpoint | PRE-line works completed and acceptable. Trades QA received, reviewed, attached and approved for all pre-line trades. Approved to line the area.
button | fb321579-505f-5a64-ad17-d66237cdabe3 |  | button | Timber frame installation completed and acceptable | Yes, N/A
button | c31ed93d-d647-529d-a077-e5d8cf12748f |  | button | Steel Stud frame installation completed and acceptable | Yes, N/A
button | a65e0718-d3b1-55bd-a38f-f4c7b7ad4f01 |  | button | Electrical First Fix completed and acceptable | Yes, N/A
button | 13ac3df8-2122-5903-ac89-ce3449ca34c1 |  | button | Plumbing First Fix completed and acceptable | Yes, N/A
button | e07660a9-2bbe-59d0-b6fe-396d7416981f |  | button | Security, Comms and Data First Fix completed and acceptable | Yes, N/A
button | 875215f0-c879-5ebe-8954-282e8b36a75f |  | button | HVAC First Fix completed and acceptable | Yes, N/A
button | dbcba945-c56a-5ce2-8e9e-c5210927502e |  | button | Fire Security First Fix completed and acceptable | Yes, N/A
button | 733aad78-5bb6-5eb5-b178-f9fe7f599a24 |  | button | Under floor heating First Fix (including screeding and soundproofing of the bathrooms/ wc) completed and acceptable | Yes, N/A
button | 4ea83982-639c-5c57-90f9-1dba3fbf1241 |  | button | Kitchen extract First Fix completed and acceptable | Yes, N/A
button | 4a782faa-323f-528f-9d1a-b0b5ea2187fa |  | button | Insulation installation completed and acceptable | Yes, N/A
button | 28d75e86-8e14-50cd-af43-bfe08e6a5777 |  | button | Passive fire installation completed and acceptable | Yes, N/A
button | 64cfe183-7974-55e4-a85b-3aebfa17895e |  | button | Suspended ceiling grids installation completed and acceptable | Yes, N/A
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checklist-flat |  |  | checklist | ST - R - Stair Installation |  |  |  |  | Yes | ST - R - Stair Installation | 8562c745-e3fb-4641-ba04-2264d2d02995
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Stair Installation completed and acceptable
checklist-flat |  |  | checklist | ST - R - Roof structure - Steel |  |  |  |  | Yes | ST - R - Roof structure - Steel | 882d96a2-e0f3-45dd-9f7e-818d26c36a4b
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All structural steel correctly installed in respective area and acceptable
checklist-flat |  |  | checklist | FC - R - Envelope Penetrations |  |  |  |  | Yes | FC - R - Envelope Penetrations | 8aaec5c8-eacc-44c4-8b01-6718b65a33e1
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Envelope Penetrations completed and acceptable
checklist-sectioned |  |  | checklist | Site Visit Report: |  |  |  |  | Yes | I - C - Site Visit Report | 8eaf2e31-8ad8-4c06-bac4-7a458addbd17
checkpoint-group |  |  | section | Site Visit Details
checkpoint-no-status |  |  | checkpoint | Site Details
text | d7f88bb0-1257-5b01-b710-8dc10929bd3a |  | textbox | Area of site visited:
text | 6eca56ec-beee-5709-875f-99a2a5dc3051 |  | textbox | Work element monitored / purpose of visit:
text | e92ec27a-699c-50fe-8399-0fcc3ca31084 |  | textbox | Date of site visit:
text | 69c291c3-d6cc-595a-9a47-81c400341f21 |  | textbox | Time on site (include start and end times):
text | a1f986e7-594a-572e-ac62-eac6dfcf1af7 |  | textbox | Weather conditions:
text | e04bb04f-6685-5b63-9d86-19914395c0a6 |  | textbox | Report prepared by:
text | a805cd18-358a-581b-9c26-a98273436126 |  | textbox | Additional personnel accompanying:
checkpoint-status |  |  | checkpoint | Consented drawings have been followed
text | 53b5b825-83de-5710-ae02-cbc8e7ad8278 |  | textbox | Building Consent Number:
text | 472a538a-d9a0-5e68-8f9d-5232a5e1e196 |  | textbox | Drawing & Revision Number(s):
checkpoint-status |  |  | checkpoint | Health and Safety acceptable
checkpoint-group |  |  | section | Site Report Summary/Closeout
checkpoint-status |  |  | checkpoint | Works accepted and may proceed
label | a0b035ec-559e-5013-807b-6b88caa0f0ef |  | note | Select Pass if works accepted or Fail if reinspection required to defective elements
boolean | d0d0e6c5-59da-51fa-addf-37874cdc0238 |  | tickbox | Report attached or remedials summarised below
text | 31aa8ccc-4d3e-54c8-bb47-f3c91864856b |  | textbox | Remedial(s)
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | F - R - Shell Beam Installation |  |  |  |  | Yes | F - R - Shell Beam Installation | 8f747ff4-6be6-4c87-b7ba-0773d212f619
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Shell Beam installation completed as per the specifications
checklist-flat |  |  | checklist | Fascia/Gutter |  |  |  |  | Yes | FC - R - Fascia/Gutter | 918b744a-0809-4852-84ea-12709d46cf76
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Fascia/Gutter installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - Anchor Points - Intermediate, Corner and End Plate Installation |  |  |  |  | Yes | FC - R - Anchor Points - Intermediate, Corner and End Plate Installation | 953e12ef-c38f-41b7-a376-80e4b32fec21
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Intermediate, Corner and End Plate installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - Lintels |  |  |  |  | Yes | FC - R - Lintels | 9ea4edc8-55b9-436f-8b10-79d1329ef612
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Lintels completed and acceptable
checklist-flat |  |  | checklist | FC - R - Anchor Points - Static line installation |  |  |  |  | Yes | FC - R - Anchor Points - Static line installation | a0a769da-9cc7-4285-b0a3-f11115fcfebf
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Static line installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - Cladding Sealant |  |  |  |  | Yes | FC - R - Cladding Sealant | a0ef6a25-5d5d-4d7f-9408-826a6276e998
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Cladding sealant completed and acceptable
checklist-flat |  |  | checklist | F - R - Sheet Piling |  |  |  |  | Yes | F - R - Sheet Piling | a2032a70-3344-4ac3-81a2-9daea9ce39a1
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Sheet pile installation completed and acceptable
checklist-flat |  |  | checklist | C - R - Pipe Laying - Stormwater |  |  |  |  | Yes | C - R - Pipe Laying | a3c75e34-8334-4124-9b7c-f38840b990c5
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Wastewater pipe laying completed as per the specifications
checklist-flat |  |  | checklist | C - R - Manhole Installation |  |  |  |  | Yes | C - R - Manhole Installation | a488d32f-5407-4e5e-bd41-4f78cabbe47f
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Manhole Installation completed as per the specifications
checklist-flat |  |  | checklist | F - R - Survey Certificates |  |  |  |  | Yes | F - R - Survey Certificates | a581bfba-5091-4841-89e0-66c5db45cc7d
checkpoint-status |  |  | checkpoint | survey certificates for correct building height/location/setout attached
checklist-flat |  |  | checklist | ST - R - Timber Framing |  |  |  |  | Yes | ST - R - Timber Framing | a83fe237-decf-47ea-b827-b14a9399b296
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Timber frame installation completed and acceptable
checklist-flat |  |  | checklist | ST - R - Precast Edge Beams Installation |  |  |  |  | Yes | ST - R - Precast Edge Beams Installation | ab1da910-3a68-4695-8998-00fdc6add997
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Edge Beams Installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - Tapes and VaproShield |  |  |  |  | Yes | FC - R - Tapes and VaproShield | adda6184-0257-44dc-8e0a-75015989454c
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Tapes/VaproShield works completed and acceptable
checklist-flat |  |  | checklist | Project Manager Handover to Operations |  |  |  |  | Yes | ITP - R - Project Manager Handover to Operations (per townhouse unit) | b10c5521-855b-4aab-ba5d-ccb87d46d579
checkpoint-status |  |  | checkpoint | No outstanding defects/snag list items
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Chattels confirmed as operational
checkpoint-status |  |  | checkpoint | Chattel manuals provided.
checkpoint-status |  |  | checkpoint | Unit meets benchmark standards and expectations
checkpoint-status |  |  | checkpoint | Resident "Welcome Letter" completed by PM and left in property.
checkpoint-status |  |  | checkpoint | Formal handover to Sales/Operations conducted by PM.
checklist-flat |  |  | checklist | FC - R - Flashing installation |  |  |  |  | Yes | FC - R - Flashing installation | b1a73795-274e-4889-9c18-0718f67b079b
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Flashing installation completed and acceptable
checklist-sectioned |  |  | checklist | Constructor Audit - Structural Foundations - |  |  |  |  | Yes | Add Constructor Audit (Auckland Council Assessment) - Structural Foundations Checklist | b44db7ed-446b-4784-b748-e438d9d47815
checkpoint-group |  |  | section | Foundations Assessment - Details / Drawings / Documentation
checkpoint-status |  |  | checkpoint | Clearly identify area/element covered in this assessment (Pass once detailed below)
text | 16bc1ae2-6d21-44be-9ceb-88b5cdc52f81 |  | textbox | Date of assessment (format - dd/mm/yyyy)
text | 43ce7fb3-5029-4481-9d01-a0e1394d79ac |  | textbox | Detailed breakdown of element(s) including location and grid references relating to this audit
label | 688abc83-17e1-4ac3-b6ee-aa6fd7c4b947 |  | note | Add description for what work was carried out on the element. Inspector cannot tell if the beam was erected, coated, welded etc
boolean | 47ce8365-010c-40ad-a621-de65eaf47501 |  | tickbox | Attach marked up plan detailing element(s), location and grid references relating to this assessment
checkpoint-status |  |  | checkpoint | Description of work being undertaken (PASS once all below details are entered)
button | 59717df6-8d3c-4ed3-b547-afffcc04c741 |  | button | Does the work being undertaken comply with the issued building consent or approved minor variations or amendments | Yes, No
text | 2bd35dcd-01ac-4e1c-b9b3-d5a87dddd93b |  | textbox | If "NO" what are the discrepancies? clearly detail here
text | a2fbfe4b-28e9-48c5-bf83-939ffe92cebb |  | textbox | Latest building consent number, stage and amendments (if applicable)
text | 9070dfd6-aa49-42bd-996b-7095a977dc93 |  | textbox | Relevant drawings & revision numbers
boolean | c7f88aa1-b67d-436e-8cda-843af4072fb1 |  | tickbox | Attach all relevant drawings with revision numbers clearly detailed
button | a4e8524a-cc22-4656-8235-2fa928236141 |  | button | Construction drawing revisions match consented drawing revisions | Yes, No
text | a42c5d21-373b-4fdc-b766-db4b919c051a |  | textbox | If "NO" what are the discrepancies? (comment here and attach evidence of discrepancies)
button | f1e863b7-ae74-4df8-9492-9175eb0d5e99 |  | button | Does the installation of this building element compromise any previously assessed/inspected building elements? | Yes, No
label | 5b5b7ce9-036b-4a16-bbf3-40969961fa19 |  | note | Select "NO" if this has been considered & does not compromise any previously assessed/inspected building elements (attach any relevant supporting evidence below)
text | dd7f94fb-492c-4360-8e79-3fb79e93205c |  | textbox | If "YES" explain here (what is compromised, how it it is compromised & how this will be mitigated/managed)
checkpoint-status |  |  | checkpoint | Select "PASS" and progress if all above items have been considered and sufficient supporting documentation attached
checkpoint-group |  |  | section | Structural Foundations Assessment - Council / Consultant Summary
checkpoint-status |  |  | checkpoint | Structural foundations assessment details (Pass once inputted below)
text | 8d5f5e25-fd9b-4efd-90c7-7b8c97e4ce4f |  | textbox | Describe progress of construction since last audit
button | 05616b1e-837e-404f-810d-9f277450dbac |  | button | NEW BC AMENDMENTS - has there been any requirement for a new amendment since the last council audit/inspection | Yes, No
text | e5ccfac7-e9f6-4f36-a0ce-394076867275 |  | textbox | If yes - detail amendment here including status
button | 947db561-2dca-4eb6-949b-d07448e6b5fd |  | button | APPROVED BC AMENDMENTS - have any previously open AMENDMENTS been responded to by Auckland Council since the last audit/inspection | Yes, No, N/A
text | 51eec31d-b808-45ba-9748-defa6ed9d82a |  | textbox | If yes - detail here and ensure latest Building Consent (including amendment) is uploaded into Conqa
button | a4fdaa28-e534-4f77-9318-3003a9066782 |  | button | WIP AMENDMENTS - are there any AMENDMENTS which will maintain a "Work in Progress" status for this audit | Yes, No, N/A
text | e0aad338-b290-4688-9d8e-e034cab77295 |  | textbox | If yes - detail amendment here and provide an update on the status
button | 6d6d4d71-2ec8-4025-9287-b5c82babd0db |  | button | NEW MINOR VARIATIONS - has there been any requirement for a new minor variation since the last council audit/inspection | Yes, No
text | 1ae3d881-14cb-4929-b47f-cb07a23b89a9 |  | textbox | If yes - detail here including status
button | a966e8df-3096-4b45-a85e-7b69f5c61298 |  | button | APPROVED MINOR VARIATIONS - have any previously open minor variations been responded to by Auckland Council since the last audit/inspection | Yes, No, N/A
text | 16b57858-8e01-4645-8941-5fcf3f70fe7c |  | textbox | If yes - detail here and ensure latest status (including approval) is uploaded into Conqa
button | 3943822b-aa3a-4b98-9dfa-41f32a431e08 |  | button | WIP MINOR VARIATIONS - are there any minor variations which will maintain a "Work in Progress" status for this audit | Yes, No, N/A
text | 7608b8e7-8a3e-4e38-9f23-3e50f84da682 |  | textbox | If yes - detail variation here and provide an update on the status
checkpoint-status |  |  | checkpoint | PREVIOUS COUNCIL AUDITS/ INSPECTIONS - Any previous council audit / inspection issues (fails / anomalies) relating to this BC have been addressed & closed out
label | 0dc4de0f-153f-4322-b106-b379f6071242 |  | note | "Pass" if there are no outstanding issues (fails / anomalies) from previous council audits/inspections relating to this Building Consent
label | 00d18b98-50d8-4147-882f-a5a106fea336 |  | note | "Fail" if outstanding issues (fails / anomalies) remain un actioned/closed from previous inspections / audits and provide context
label | 4811cf76-59a5-41f2-af52-6f843b1082f2 |  | note | Prior to selecting "Pass" and confirming there are no outstanding fails / anomalies, ensure these have been appropriately closed out and the appropriate evidence attached HERE & in the appropriate audit/inspection
checkpoint-status |  |  | checkpoint | Engineer / Consultant Inspection Summary & Observation Closeout
button | d8a1fe6b-31e8-4cdf-bd7d-697dd648ca23 |  | button | Are the relevant engineers / consultants attending site & achieving the correct level of monitoring | Yes, No, N/A
text | 3f0089c3-3659-40c1-b903-d378ae54562d |  | textbox | List all engineers / consultants who have been to site since the last Council audit/inspection & describe all elements/work checked by the engineer
button | 0882353a-49a1-4f47-b603-41ecc54e8ec9 |  | button | Viewed all engineers reports since last audit undertaken & have identified what elements and areas have been checked by the engineer | Yes, No
label | 04909e22-12ac-4d91-b515-2ecf1b85b887 |  | note | "Pass" ABOVE checkpoint if there are no outstanding engineers remedials/observations
label | 081e3c92-6a31-40fe-b2d0-6460e656d3d2 |  | note | "Fail" ABOVE checkpoint if outstanding engineers remedials/observations remain unresolved and provide context
button | 0b9c188e-9144-4b41-8ed2-d233d77a271d |  | button | NEW OBSERVATIONS/REMEDIALS - has there been any new engineer / consultant remedials/observations since the last council audit/inspection | Yes, No
text | 794610ae-9b6e-48d8-b4dd-6630cf2aa04d |  | textbox | If yes - detail here including status
button | 2a886bd5-6ead-4eba-b0fa-d0c9c59990b7 |  | button | APPROVED OBSERVATIONS/REMEDIALS - have any previously open remedial/observations been approved by the appropriate engineer / consultant since the last audit/inspection | Yes, No, N/A
text | fd2ad9b9-4e66-4f55-aa18-b59dc9d8c8eb |  | textbox | If yes - detail here and ensure latest status (including approval) is uploaded into Conqa
button | bf5c2c48-5b8c-424a-925e-0ac0a132b2bc |  | button | WIP OBSERVATIONS/REMEDIALS - are there any remedials/observations which will maintain a "Work in Progress" status for this audit | Yes, No, N/A
text | cf2004b1-3705-4e76-ab6b-c9bef0283569 |  | textbox | If yes - detail here and provide an update on the status
boolean | b756337d-37eb-4ddd-9e1f-7d623729c682 |  | tickbox | All relevant consultant inspections completed since the last Auckland Council audit/inspection attached HERE including any corrective action undertaken with sufficient evidence of close out.
checkpoint-status |  |  | checkpoint | ANY OTHER THIRD PARTY CONSULTANTS - Described work / elements checked by others (third party)
text | dad29600-6840-4c76-8aa7-ef7bc79a536d |  | textbox | If applicable, describe any action/remedial items still to be signed off by others
boolean | 5a837a8f-d1f8-4381-802c-27874659e44b |  | tickbox | Any relevant third party consultant inspections completed since the last Auckland Council audit/inspection attached HERE including any corrective action undertaken with sufficient evidence of close out.
label | 3268cafd-9722-46a1-9109-0396b962f0f8 |  | note | If required use this checkpoint to detail and other action/remedial items have been signed off or select "N/A" if there has been no requirement for a third party
checkpoint-group |  |  | section | Main Contractors & Trades QC/QA and supporting documentation
checkpoint-status |  |  | checkpoint | General Site Photos / As Builts
label | 58808f5d-3896-4f11-8534-cb4756660a66 |  | note | Attach a minimum of 10 site photos giving an overview of the on site progress relating to this Building Consent since the last audit / inspection
label | ec2941ff-3506-4c89-bc80-89e6a1fe1b5c |  | note | Attach any relevant progressive as builts / mark ups
checkpoint-status |  |  | checkpoint | PILING - trade / element applicable to this audit
label | 3632ee01-1688-49b8-9f4b-709cbf6ee106 |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | c144eca8-76cb-442e-9b95-70649250cd41 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | f5870b1c-56b1-442a-90ad-a34aba029e74 |  | textbox | Overview of progress relating to this trade/element (Piling) since last audit
label | 582bdaf3-0f1d-49b1-a95d-91b8ba38fd3d |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, Pile/post type recorded, Piles/post footing sizes and general layout, concrete batch certs confirming mPa and any additives, reinforcing detail sheets
label | be3a2090-19a1-4a12-b979-abdca2f52d7d |  | note | COMPLIANCE CONSIDERATIONS - PS3, PS4, all reinforcing steel bars/ mesh mill certs or steel grade confirmation from supplier, all reinforcing steel fabricator detail sheets for cages/ bent rebar- must verify rebar sourced from approved supplier, concrete cylinder tests for previous month deliveries
boolean | 21ed294e-0766-4eeb-974b-87074383f43d |  | tickbox | Piling - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status |  |  | checkpoint | EXCAVATION (Bulk/Detailed) - trade / element applicable to this audit
label | ff18f01b-e87a-4e3b-b4e2-722ceacf9d10 |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | cee67b87-92e4-4fa6-a130-9b164b3f1593 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | 4faebaeb-6b9c-4878-a114-7d273891c376 |  | textbox | Overview of progress relating to this trade/element (Excavation) since last audit
label | f06cf420-8cd8-404f-80c7-2cecc2a557bc |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, resource consent considerations, environmental considerations, footing size, batters, soft spots, compaction methodology, heights
label | 4f8967c5-5243-4dfb-bd58-1eb13eef8054 |  | note | COMPLIANCE CONSIDERATIONS - Compaction methodology & results, geotechnical overview, PS4
boolean | 1058a14c-7643-4fbe-9d24-e4b56c731e87 |  | tickbox | Excavation - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status |  |  | checkpoint | PLUMBING/DRAINAGE - trade / element applicable to this audit
label | 065b879a-e1a0-4022-a523-682ca030c047 |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 75dbfbc3-f535-4f9f-a125-44cbd738206e |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | b0a34c59-bbd1-49a2-9f18-0f925bec6cb9 |  | textbox | Overview of progress relating to this trade/element (Plumbing/Drainage) since last audit
label | 62a6eded-51e5-42f2-8c69-813ea58bd474 |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, Trade details & license, materials, heights / gradients, protection for services (bedding, sleeves, other), tests (water, air or other), consideration for specifics (floor waste gully, HWC overflow etc), backfill methodology
label | a7183597-9690-4fe2-b869-f920f552d7a6 |  | note | COMPLIANCE CONSIDERATIONS - As builts, product conformity, test reports, CCTV, PS3, PS4
boolean | 80a89d5e-58d1-43e1-a8ed-e1cc54b3ce30 |  | tickbox | Plumbing/Drainage - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status |  |  | checkpoint | UNDERSLAB SERVICES - trade / element applicable to this audit
label | 748fe0d3-632c-429d-bb17-ad5748f5badd |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 52ad57b6-db07-488b-810d-619359a10da9 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | e6b68ac0-4a5e-4741-9f38-ee9c0fe474d5 |  | textbox | Overview of progress relating to this trade/element (Underslab Services) since last audit
label | dac9a1bd-be94-4384-b875-3bd28166c789 |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, Trade details & license, materials, heights / gradients, protection for services (bedding, sleeves, other), tests (water, air or other), consideration for specifics, backfill methodology
label | 4d52b766-d446-4c39-ac46-a53e303f8471 |  | note | COMPLIANCE CONSIDERATIONS - As builts, product conformity, test reports, CCTV, PS3, PS4
boolean | f5cfc77c-ce1b-49f4-b570-e644912baa9a |  | tickbox | Underslab Services - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status |  |  | checkpoint | TANKING/WATERPROOFING - trade / element applicable to this audit
label | 51c1ef90-34ef-4912-9b0f-6d53c9d4c8bd |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | e408a7de-070f-4bc7-9cab-58245b747162 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | 157b6e30-8e89-48aa-801f-d3e6f56927a4 |  | textbox | Overview of progress relating to this trade/element (Tanking/waterproofing) since last audit
label | fea58956-c42c-455e-884f-69da0043e271 |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, Trade details & license, materials/system, manufacturer's specifications, substrate, drainage, installation, joints / controll joints, terminations, protection, backfill methodology
label | 55ee828a-d779-4669-a3b3-5c33820fe71b |  | note | COMPLIANCE CONSIDERATIONS - manufacturer's warranty, workmanship warranty, PS3, PS4
boolean | a1192a27-0378-4fff-8261-7242c92c906c |  | tickbox | Tanking/waterproofing - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status |  |  | checkpoint | FORMWORK - trade / element applicable to this audit
label | 5139fa67-1b55-46f6-93c7-658f3b6c432b |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 44cc05f8-0044-4409-b7e2-c4d5160a9f84 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | 52f9a79d-c1a9-43b8-b6c4-e3ac58486094 |  | textbox | Overview of progress relating to this trade/element (Formwork) since last audit
label | b5eedf6c-42e2-48dd-8e21-0fa2f2083fb0 |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, setout, heights, stability/bracing, DPM / terminations
boolean | 6231a682-7779-4a55-956e-748f9e79bdda |  | tickbox | Formwork - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status |  |  | checkpoint | REINFORCING - trade / element applicable to this audit
label | b0f99f5a-65ae-4ea8-8672-ad5f219bf5ff |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 0cb69b85-a785-4954-a575-7096ab34ae55 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | e3979441-64b1-4df4-9821-24adc90a470a |  | textbox | Overview of progress relating to this trade/element (Reinforcing) since last audit
label | e36913e5-6787-425f-b2c4-7f2ecee2164f |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, detail sheets, reo mill certs, size, grade, laps, bends, cover, starters (size & location), cast in items
label | e0be6c8c-d28d-4a98-85d6-95df14929328 |  | note | COMPLIANCE CONSIDERATIONS - PS3, PS4, all reinforcing steel bars/ mesh mill certs or steel grade confirmation from supplier, all reinforcing steel fabricator detail sheets for cages/ bent rebar- must verify rebar sourced from accredited supplier
boolean | 58dc22df-0ca1-4df9-9ad0-a627dd9409f7 |  | tickbox | Reinforcing - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status |  |  | checkpoint | CONCRETE PLACEMENT - trade / element applicable to this audit
label | 1c0a11ea-7eef-4190-9585-c6e123ccf93f |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 67de6868-5a9e-4c4b-a345-81c493fe318a |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | 0f533a9f-1c39-4139-afb8-242474b4b763 |  | textbox | Overview of progress relating to this trade/element (Concrete Placement) since last audit
label | 9c058e1f-e58d-44c8-b206-5a90dad9b642 |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, approval, mPa, slump tests, vibration, finish, curing, concrete batch certs confirming mPa and any additive
label | aa098653-bd18-4f5f-a722-befba1852cbc |  | note | COMPLIANCE CONSIDERATIONS - PS3, PS4, concrete cylinder tests for previous month deliveries (7, 14 and/or 28 days as required)
boolean | 11082fd9-9038-4cff-b3c0-dedce5c79164 |  | tickbox | Concrete Placement - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status |  |  | checkpoint | BLOCKWORK INC REINFORCING - trade / element applicable to this audit
label | bea44542-5e95-4b71-b2b3-9830cec3435a |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 7a20cba0-22c2-4c82-afd5-0427421c4c2f |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | d6fd772d-7668-4bb1-a41f-d7c6c5800973 |  | textbox | Overview of progress relating to this trade/element (Blockwork Inc Reinforcing) since last audit
label | 37d01b08-1758-4c36-ab0a-b503636608c0 |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, compliance method, masonry grade, size, setout, level and plumb, heights, wash outs, stretcher or stack bond, Mortar joint sizes (7-13mm), tooled to match proposed finish, bond beams, control joints, Approval, mPa, slump tests, vibration, finish, sealer, concrete batch certs confirming mPa and any additive
label | 96ed8f23-e064-42db-8954-42fc5d1fdae6 |  | note | COMPLIANCE CONSIDERATIONS - PS3, PS4, all reinforcing steel bars/ mesh mill certs or steel grade confirmation from supplier, all reinforcing steel fabricator detail sheets for cages/ bent rebar- must verify rebar sourced from approved supplier, concrete cylinder tests for previous month deliveries (7, 14 and/or 28 days as required)
boolean | 1ae7de1b-00e9-477d-87f1-d49d4f1b6327 |  | tickbox | Blockwork Inc Reinforcing - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status |  |  | checkpoint | PRECAST MANUFACTURE - trade / element applicable to this audit
label | 8586011d-cb9e-4b6c-b2d0-0fb3e04a6a0d |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 64deb068-a483-46bc-a67c-535a40c3d73a |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | 08fa7b67-37c8-49c3-951b-f1e30068bfa5 |  | textbox | Overview of progress relating to this trade/element (Precast Manufacture) since last audit
label | b91f7865-68c7-49ca-acf6-89d34fc6c59d |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, mPa, slump tests, vibration, finish, curing, concrete batch certs confirming mPa and any additive, detail sheets, reo mill certs, size, grade, laps, bends, cover, inserts / cast in items, starters (size & location)
label | eea7e0c0-26db-4867-b73b-d5db56dc5895 |  | note | COMPLIANCE CONSIDERATIONS - PS1, concrete test results (7, 14 and/or 28 days as required), mill certs & steel grade confirmation from accredited supplier, PS3, PS4
boolean | e0f5ce13-c7a0-47fa-b821-7d83e734ebb4 |  | tickbox | Precast Manufacture - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status |  |  | checkpoint | PRECAST INSTALLATION - trade / element applicable to this audit
label | 39a26094-3ea9-40a5-b5ed-13f5d5dc522a |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 9d4a1461-10a5-4390-be21-9f5e3e9869cc |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | e2e2a16e-2627-47a1-92f2-43ffffd34a13 |  | textbox | Overview of progress relating to this trade/element (Precast Installation) since last audit
label | cbbfde7f-9738-4bc1-a0f6-6658ac67e6fc |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, setout, precast starters (size & length), seating, bracing/propping, alignment/plumb/level, joints/connections
boolean | de6fae1d-de48-4945-9656-4f502bf8c717 |  | tickbox | Precast Installation - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status |  |  | checkpoint | Any other trade / element - trade / element applicable to this audit
label | 0ffa3d08-7ec3-497d-a4d0-52adc829463c |  | note | "PASS" and detail below if any other trade/element is applicable to this audit. Complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 16bffadb-8e27-4cfa-85e2-a90b51b52a41 |  | note | "N/A" if no other trade/element is applicable to this audit, comment below if required
text | 82d6aa26-2790-46e7-a81e-bdd8aab10e8d |  | textbox | Overview of progress relating to this trade/element since last audit
boolean | fe057607-efce-467c-a00d-7f1c1ed6a166 |  | tickbox | Any other trade / element - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status |  |  | checkpoint | Select "PASS" and notify Auckland Council if all above items have been considered and sufficient supporting documentation attached
text | d56edffd-799a-470c-bd63-1684cfbc1c05 |  | textbox | Date this Audit report was sent to Auckland Council
text | d0feac1e-23b9-4d05-be41-03999f2a5053 |  | textbox | Inspector(s) from Auckland Council who this was sent to (including email address)
checkpoint-group |  |  | section | Close out of Audit
checkpoint-status |  |  | checkpoint | Close out of Audit - Pass once Council Audit is completed and attached with any corrective actions detailed and closed out below
text | 3fe460f9-75bb-43e7-803b-4b62448a5ca6 |  | textbox | Date Auckland Council Inspector sent receipt / audit response
boolean | f3681205-aec3-40fe-bf12-4ebabee3d18e |  | tickbox | Council Audit completed and attached
text | d568c5a7-2746-45b1-a80b-a44eb5e0f04f |  | textbox | As detailed in this Council Audit or discussed - next Audit will occur on
checkpoint-status |  |  | checkpoint | Any Relevant Observation Closeout evidence attached here if applicable (Pass once completed)
text | 39255968-2939-4146-9a76-423e07e03822 |  | textbox | Corrective actions required before next audit
label | 7599ddd3-e408-4a53-8f93-fafa888e15a4 |  | note | These should include a summary list of close outs still to be addressed from any of the above line items and comments made in the council audit or any outstanding from previous audits/inspections relating to this building consent
checklist-flat |  |  | checklist | C - R - Demolition |  |  |  |  | Yes | C - R - Demolition | b5f3d038-9ccc-4f74-8fb8-42de7337231d
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Demolition completed and acceptable
checklist-flat |  |  | checklist | [5 empty] | Yes | Facade - Concrete Block/Concrete Panels | bab9f811-d5c7-4957-b1c3-609cc760df5e
checkpoint-status |  |  | checkpoint | All gaps sealed with non shrink grout
checkpoint-status |  |  | checkpoint | Sealer applied to window openings
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checklist-flat |  |  | checklist | ST - R - Roof structure - Timber Trusses |  |  |  |  | Yes | ST - R - Roof structure - Timber Trusses | bb18f098-6b24-414c-acd9-0cbdf63737cc
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All timber trusses correctly installed in respective area and acceptable
checklist-sectioned |  |  | checklist | Concrete Planning and Pour |  |  |  |  | Yes | ITP - R - Concrete - Planning and Pour (per townhouse block) | bc48c75f-1cf8-4904-8f20-3517f9ae3170
checkpoint-group |  |  | section | Pre Pour Planning
checkpoint-status |  |  | checkpoint | Concrete pour planning completed with subcontractor
text | b1fcf03d-4b3b-5fae-85b0-7123729b8bd8 |  | textbox | Date of pour
text | 8d3b6fb5-3cd5-5868-826e-281a272542c2 |  | textbox | Specified concrete strength:
text | 298a238e-28d4-5ef8-974a-0be64f8878cc |  | textbox | Concrete strength ordered:
text | fb122155-5358-5a5d-aff8-86ed026ce12e |  | textbox | Concrete quantity ordered:
text | 7f07c3c5-910d-5de3-b7af-170d998dd372 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | Request to pour received and approved
button | b88c4f9f-ce60-5cc5-bd02-6f5d26ed02e1 |  | button | Reinforcing meets specification | Yes, Reworked, N/A
button | 2a052e03-1e03-5494-8b39-95546c44ce10 |  | button | Service penetrations present and correct | Yes, Reworked, N/A
button | ad2fab36-1ca8-5ee2-8d54-2c66d14c570a |  | button | Waterproofing elements present and correct | Yes, Reworked, N/A
button | 1e56f7e3-f747-55d7-b149-0d995865d9d5 |  | button | Couples present and correct | Yes, Reworked, N/A
button | 33b821f2-076a-50d1-8bd6-dcb7762f27a1 |  | button | Control joints/ stop ends installed accurately and correctly braced | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Engineer Inspection conducted and passed
button | 1cda705e-567d-5866-b8cf-d85eec3260de |  | button | Note remedial work needed | None, Minor, Major
text | f0dbcc9b-aab2-5836-8001-0281c0819168 |  | textbox | Inspected by and date:
checklist-flat |  |  | checklist | Punch Windows Frames (unglazed) |  |  |  |  | Yes | FC - R - Punch Windows Frames (unglazed) | c0f44980-bbce-4d61-bfa4-0e153e02f50a
checkpoint-no-status |  |  | checkpoint | Window # / Elevation / Level
text | 62f652fa-b557-59b1-b262-a0e04e353f68 |  | textbox | Window # / Elevation / Level
checkpoint-status |  |  | checkpoint | Installation (By others) completed as per detail Y/N
checkpoint-status |  |  | checkpoint | Check the joinery is free from damage
checkpoint-status |  |  | checkpoint | All glazing beads attached to Frame PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Check Frame number PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Inspection of Backing rubber - no damage and continuous around perimeter
checkpoint-status |  |  | checkpoint | Glazing Blocks inserted correctly PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Correct Glass units installed (Glass sticker) PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Glazing Beads fitted correctly PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Correct Wedge Rubber installed and rubbered off as per WGANZ guidelines
checkpoint-status |  |  | checkpoint | Glass Stickers removed
checkpoint-status |  |  | checkpoint | Trade Clean
checkpoint-status |  |  | checkpoint | Final Inspection PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Glazing complete for handover to Ryman Healthcare
holdpoint |  |  | signoff | Raise Remedial
checklist-flat |  |  | checklist | ST - R - Precast Spandrel Panel Installation |  |  |  |  | Yes | ST - R - Precast Spandrel Panel Installation | c1b35de5-a348-4630-8886-ed65cc15c68f
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Spandrel Panel Installation completed and acceptable
checklist-flat |  |  | checklist | ST - R - Precast Flat Slab Installation |  |  |  |  | Yes | ST - R - Precast Flat Slab Installation | c5f33fec-0499-4847-9c3e-1766c55ea219
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Flat Slab Installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - External Plaster - Nibs & Beams |  |  |  |  | Yes | FC - R - External Plaster - Nibs & Beams | ce178cc1-7438-4b6a-a3fb-070a26d006a1
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | External Plaster works for Nibs & Beams completed and acceptable
checklist-flat |  |  | checklist | CST - R - Fire Consent |  |  |  |  | Yes | CST - R - Fire Consent | cf5fae34-cd5d-446b-b6cd-5777d217555d
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Electrical
boolean | e8f88e76-9e0f-5b52-a8c5-acc604a1e034 |  | tickbox | Electrical compliance and safety certificate
boolean | 46352c42-5d17-567f-b895-958d1c0473a4 |  | tickbox | record of inspections for high risk works
checkpoint-status |  |  | checkpoint | Fire rated (Intumescent) Coatings to Structural Steel
boolean | 26461592-3393-5a6b-90ed-a05efb1ad76d |  | tickbox | Producer Statement Construction(PS3 - AC2334): Intumescent coatings to structural steel from approved applicator
boolean | 6bd1d668-a112-54d9-b6c1-10d4062a4986 |  | tickbox | Suppliers material schedule - products used and thicknesses applied
boolean | 46d75a84-bc64-5074-98ed-53c3c032919c |  | tickbox | Floor plan of intumescent coating locations
checkpoint-status |  |  | checkpoint | Fire Rated and Stopping Systems
boolean | 9685acd2-f5a9-593f-bd65-626aa6f05420 |  | tickbox | Producer Statement Construction(PS3): Fire stopping of penetrations(collars, wraps, sealants) for Plumbing, Mechanical, Ventilation and Communication services
boolean | 4a416b89-cb98-560c-9469-bb15b1d77234 |  | tickbox | Fire rated penetration Schedule: Plumbing, Mechanical, Ventilation and Communication Services
boolean | f90a25e9-6781-50e3-b301-b37a6a60f129 |  | tickbox | As built plans: penetrations
boolean | af739581-5675-5162-88b1-147ed4fc9d97 |  | tickbox | Producer Statement Construction(PS3): Installed fire rated constructions; fire rated walls, partitions, floors and ceilings to show fire rating
boolean | 661a6c93-6453-5ea9-8ff1-1882960c4e2a |  | tickbox | Fire door declaration documentation and register of door sets by the manufacturer (refer NZS4520: 2010 clause 6.4.3
checkpoint-status |  |  | checkpoint | Sprinkler systems
boolean | c796bced-d7d7-580d-9858-9953195371ef |  | tickbox | Producer Statement Construction(PS3): Automatic sprinkler system (in compliance with NZS4514:2013)
boolean | 3969487d-f0e6-5341-8e7d-5bf4ee2250a1 |  | tickbox | Accredited inspection company's automatic sprinkler system certification confirming compliance with NZS4514:2013
boolean | b6c75799-66ad-509c-9429-8262716ade39 |  | tickbox | As built documentation; sprinkler block plan, equipment manufacture register
checkpoint-status |  |  | checkpoint | Manual and Automatic fire alarms
boolean | 8f466daf-2b6b-5d9d-b507-9bebe0750653 |  | tickbox | Producer Statement construction(PS3): Manual/automatic fire alarm in compliance with NZS4512:2010
boolean | 3dce436c-7832-5700-a3dd-fa3e8d6f0c90 |  | tickbox | Accredited inspection company's fire alarm certification confirming compliance with NZS4512:2010 (new system)
boolean | 7d3793a3-42ac-5ed2-a2a6-b405e8e27f11 |  | tickbox | As built documentation; zone index plan, operation manual and maintenance manual
checkpoint-status |  |  | checkpoint | Riser Mains for use by fire services
boolean | f7d0f9f6-805c-524b-b0c8-cf691c62e471 |  | tickbox | Producer Statement Construction(PS3): fire hydrant riser confirming compliance with NZS4510:2008
boolean | 5c9d1df4-074b-5f97-b6d7-afa692c13d42 |  | tickbox | Certificate of Compliance or Verification Report for fire hydrant riser confirming compliance with NZS4510:2008
boolean | bad372b8-9c90-5874-ba7f-065a2e62555a |  | tickbox | As built documentation; fire hydrant schematic as built
checkpoint-status |  |  | checkpoint | Emergency Lighting systems
boolean | b28d21a4-4c98-52bd-a1f5-08dc790f03d1 |  | tickbox | Producer Statement Construction(PS3): Emergency lighting from electrical contractor confirming compliance with NZBC F6
boolean | eb545322-385c-53dc-a81b-5c5c362a8548 |  | tickbox | Producer Statement Review(PS4): Emergency Lighting from council approved electrical engineer confirming compliance with NZBC F6
boolean | da7e1879-d342-565e-8fbf-e97c2f4b5c33 |  | tickbox | Duration test results for emergency light fitting from electrical contractor or IQP
boolean | 48f8fb30-c2a3-5e97-aaf6-edd9ea7ba506 |  | tickbox | Lux test results for the emergency lighting system
boolean | 86eb340f-4c3b-5b31-9791-45dd8d25c376 |  | tickbox | As built plan with model of systems installed
boolean | d664d608-b7c8-517c-8e45-2ce0540e1909 |  | tickbox | Electrical work certificate
checkpoint-status |  |  | checkpoint | Fire separation that forms part of the means of escape from fire
boolean | ef230326-ac24-54d3-b486-2d8903f24c0b |  | tickbox | As built plans confirming final location of Fire separation that forms part of the means of escape from fire
checkpoint-status |  |  | checkpoint | Smoke separation that forms part of the means of escape from fire
boolean | 9ce799ce-8fab-5988-b63d-741a59ed3ff4 |  | tickbox | As built plans confirming final location of walls forming a protected path in a building, smoke resistant lift lobby, smoke stop door, smoke cell
checkpoint-status |  |  | checkpoint | interfaced fire or smoke doors on windows
boolean | d35b5a7c-14b0-5241-bdda-5c3448aa3436 |  | tickbox | Producer Statement Construction(PS3): installation of magnetic door holders
boolean | 8cb82cea-abd9-5498-a188-9a1e8381a4e7 |  | tickbox | As built documentation; location of systems, the make of the systems, operation manuals and maintenance manuals
checkpoint-status |  |  | checkpoint | final exits
boolean | ffd82570-c503-5741-891a-830fbe50f85b |  | tickbox | as built plans confirming location of final exit (include info on if any doors are automatic or access controlled)
checkpoint-status |  |  | checkpoint | Signs for all systems
boolean | b70c6fd6-b128-5591-aa20-28a30c40e64e |  | tickbox | SS 1/1: Sign showing maximum storage heights
boolean | d7f73606-2701-5968-a4f3-869fecfcbe4d |  | tickbox | SS 2/1: Sign showing how to operate a fire alarm call point
boolean | 12841188-323c-547e-81c6-52a6119bb5e8 |  | tickbox | SS 3/1: Sign showing location of accessible automatic
boolean | a1b50147-4184-568e-a537-84d308e06fa8 |  | tickbox | SS 3/2: Sign showing and automatic closing fire or smoke door
boolean | 48b254d0-2b1a-5da7-b058-99ebdfc7ea7e |  | tickbox | SS 3/2: Sign showing location of an emergency door release on access control doors
boolean | 1c4f25ad-7ad4-556f-8c61-ab4e983b54ec |  | tickbox | SS 8/1: Sign showing location of accessible lift
boolean | c1c298f3-6395-52c5-b9de-fee7c2f154ba |  | tickbox | Sign showing not to use the lift in event of fire
boolean | df7618e9-8cbd-5442-aff3-8649d00a6f0e |  | tickbox | Sign showing lift load ratings
boolean | 38f39874-e6de-590f-833d-f0afed1ca958 |  | tickbox | SS 8/3: Sign showing hazards to escalators and moving walks
checkpoint-status |  |  | checkpoint | Fire safety construction review
boolean | 56378233-6df0-57cb-83fc-9a3ddf37c4f0 |  | tickbox | Producer Statement Review(PS4): council approved fire engineer to confirm systems conform with the relevant NZBC clauses and fire reports
checkpoint-status |  |  | checkpoint | Application for compliance schedule (AC2102)
checkpoint-status |  |  | checkpoint | Confirmation of performance standards for specified systems (AC2150)
checklist-sectioned |  |  | checklist | Constructor Audit - Structural Superstructure - |  |  |  |  | Yes | Add Constructor Audit (Auckland Council Assessment) - Structural Superstructure Checklist | cf783645-5843-40b1-aa57-1326e0f8da1c
checkpoint-group |  |  | section | Superstructure Assessment - Details / Drawings / Documentation
checkpoint-status |  |  | checkpoint | Clearly identify area/element covered in this assessment (Pass once detailed below)
text | 1d15eb54-cc31-49de-a834-a0b34903f909 |  | textbox | Date of assessment (format - dd/mm/yyyy)
text | 0d5f9bcd-d449-42c6-ba7d-36d5f20f95e2 |  | textbox | Detailed breakdown of element(s) including location and grid references relating to this audit
label | a7d0f8c8-e001-4a53-8ee4-35b11f3b30e2 |  | note | Add descripton for what work was carried out on the element. Inspector cannot tell if the beam was erected, coated, welded etc
boolean | e5bd75b6-ba61-40b2-bd85-82573c3b9fc3 |  | tickbox | Attach marked up plan detailing element(s), location and grid references relating to this assessment
checkpoint-status |  |  | checkpoint | Description of work being undertaken (PASS once all detailed below are entered)
button | 32765559-2b61-4a4b-acda-383f53aa3c46 |  | button | Does the work being undertaken comply with the issued building consent or approved minor variations or amendments | Yes, No
label | 8e0f195b-ffaf-41e3-9acc-e54bc51fa52b |  | note | If "NO" what are the discrepancies? clearly detail below
text | 11212934-4b67-4568-9579-07ff1fc7ed53 |  | textbox | Latest building consent number, stage and amendments (if applicable)
text | 0c164971-c09c-414d-81ac-436935bac688 |  | textbox | Relevant drawings & revision numbers
boolean | 15b993e5-3efe-4063-95f2-83879222b882 |  | tickbox | Attach all relevant drawings with revision numbers clearly detailed
button | 122a30e0-0bbe-472b-86ba-375abade838f |  | button | Construction drawing revisions match consented drawing revisions | Yes, No
label | 049711f2-62d2-4d7a-8601-41b554ebe185 |  | note | If "NO" what are the discrepancies? (comment below and attach evidence of discrepancies)
button | 8234ff17-121d-4007-a8e9-3aba8f9f3fcb |  | button | Does the installation of this building element compromise any previously assessed/inspected building elements? | Yes, No
label | a4141cf2-6795-450c-8ecd-7b702abd0400 |  | note | Select "NO" if this has been considered & does not compromise any previously assessed/inspected building elements (attach any relevant supporting evidence below)
label | 770d7156-8af4-4dcd-9ebd-df41853f0f53 |  | note | If "YES" explain below (what is compromised, how it it is compromised & how this will be mitigated/managed)
checkpoint-status |  |  | checkpoint | Select "PASS" and progress if all above items have been considered and sufficient supporting documentation attached
checkpoint-group |  |  | section | Structural Superstructure Assessment - Council / Consultant Summary
checkpoint-status |  |  | checkpoint | Structural superstructure assessment details (Pass once inputted below)
text | 51feebe6-1f3a-4efd-995a-06895dec848c |  | textbox | Describe progress of construction since last audit
button | f5d9061a-a15b-41cf-929a-b69b62eb7251 |  | button | NEW BC AMENDMENTS - has there been any requirement for a new amendment since the last council audit/inspection | Yes, No
text | b5cd2cbe-2306-468a-a3cf-83372f34261d |  | textbox | If yes - detail amendment here including status
button | 533ec2fa-de3d-471c-aa48-817ce88c7b4c |  | button | APPROVED BC AMENDMENTS - have any previously open AMENDMENTS been responded to by Auckland Council since the last audit/inspection | Yes, No, N/A
text | 47c8c76d-42b0-41e5-af3c-f8f18ebd579f |  | textbox | If yes - detail here and ensure latest Building Consent (including amendment) is uploaded into Conqa
button | a37babf9-02e1-4f48-8483-6faeb152ccab |  | button | WIP AMENDMENTS - are there any AMENDMENTS which will maintain a "Work in Progress" status for this audit | Yes, No, N/A
text | 6e7ebbd5-b696-43b0-b228-92a265563165 |  | textbox | If yes - detail amendment here and provide an update on the status
button | d9a509fb-0333-4176-bdb5-939b2603993d |  | button | NEW MINOR VARIATIONS - has there been any requirement for a new minor variation since the last council audit/inspection | Yes, No
text | 11147a05-6b45-4196-87bd-2e3220a127b2 |  | textbox | If yes - detail here including status
button | 63dcbb3f-1b77-429b-b608-d4f7ccd5e33d |  | button | APPROVED MINOR VARIATIONS - have any previously open minor variations been responded to by Auckland Council since the last audit/inspection | Yes, No, N/A
text | 3efd929d-6e4e-461d-8548-e4251b57be80 |  | textbox | If yes - detail here and ensure latest status (including approval) is uploaded into Conqa
button | 3848ecf4-cede-44a7-93a5-39ecf184cd26 |  | button | WIP MINOR VARIATIONS - are there any minor variations which will maintain a "Work in Progress" status for this audit | Yes, No, N/A
text | 60143860-e136-4d57-b86e-c20849af86e8 |  | textbox | If yes - detail variation here and provide an update on the status
checkpoint-status |  |  | checkpoint | PREVIOUS COUNCIL AUDITS/ INSPECTIONS - Any previous council audit / inspection issues (fails / anomalies) relating to this BC have been addressed & closed out
label | 3f7bc8bd-ce72-403e-b5cb-ae5dcbaa929c |  | note | "Pass" if there are no outstanding issues (fails / anomalies) from previous council audits/inspections relating to this Building Consent
label | 77cf85bd-93e8-4b48-b7f9-e96d8060979e |  | note | "Fail" if outstanding issues (fails / anomalies) remain un actioned/closed from previous inspections / audits and provide context
label | d8ac2897-19ea-47a2-b62f-90092fcbd92e |  | note | Prior to selecting "Pass" and confirming there are no outstanding fails / anomalies, ensure these have been appropriately closed out and the appropriate evidence attached HERE & in the appropriate audit/inspection
checkpoint-status |  |  | checkpoint | Engineer / Consultant Inspection Summary & Observation Closeout
button | c87f05cf-3e31-472c-a6a6-563a666da957 |  | button | Are the relevant engineers / consultants attending site & achieving the correct level of monitoring | Yes, No, N/A
text | affd552f-48aa-4108-9279-aab40a566cbb |  | textbox | List all engineers / consultants who have been to site since the last Council audit/inspection & describe all elements/work checked by the engineer
button | c6c52ae7-e9d6-41ad-b145-5e09568d767f |  | button | Viewed all engineers reports since last audit undertaken & have identified what elements and areas have been checked by the engineer | Yes, No
label | b9cc8a08-c313-4a29-a1ca-1efd15f3be02 |  | note | "Pass" ABOVE checkpoint if there are no outstanding engineers remedials/observations
label | 65ad8797-b5b3-40e5-9c66-4e640af08e49 |  | note | "Fail" ABOVE checkpoint if outstanding engineers remedials/observations remain unresolved and provide context
button | d8aac606-7c67-41dd-8728-44476dd15263 |  | button | NEW OBSERVATIONS/REMEDIALS - has there been any new engineer / consultant remedials/observations since the last council audit/inspection | Yes, No
text | cf264bae-a822-4862-b8d6-668fbeac3ddf |  | textbox | If yes - detail here including status
button | 3110f445-ee17-4a18-bc6a-ab408156c4de |  | button | APPROVED OBSERVATIONS/REMEDIALS - have any previously open remedial/observations been approved by the appropriate engineer / consultant since the last audit/inspection | Yes, No, N/A
text | d74bfb06-5e48-45e2-ab9b-23246d5c2c0c |  | textbox | If yes - detail here and ensure latest status (including approval) is uploaded into Conqa
button | 27077dff-248a-4f07-8e04-c5edf69771e8 |  | button | WIP OBSERVATIONS/REMEDIALS - are there any remedials/observations which will maintain a "Work in Progress" status for this audit | Yes, No, N/A
text | d7a2273f-2208-440e-86b4-3497786e0aeb |  | textbox | If yes - detail here and provide an update on the status
boolean | 8097a03b-bf6f-48df-8fe2-58f91d1b3ad8 |  | tickbox | All relevant consultant inspections completed since the last Auckland Council audit/inspection attached HERE including any corrective action undertaken with sufficient evidence of close out.
checkpoint-status |  |  | checkpoint | ANY OTHER THIRD PARTY CONSULTANTS - Described work / elements checked by others (third party)
text | 08f62631-5e6e-4f8b-ab29-eaea77f846a7 |  | textbox | If applicable, describe any action/remedial items still to be signed off by others
boolean | 84e9e7d9-895c-4135-b6f6-140fc0809752 |  | tickbox | Any relevant third party consultant inspections completed since the last Auckland Council audit/inspection attached HERE including any corrective action undertaken with sufficient evidence of close out.
label | 18d7de02-d06b-4d6a-93e4-d1ac04ce7ce1 |  | note | If required use this checkpoint to detail and other action/remedial items have been signed off or select "N/A" if there has been no requirement for a third party
checkpoint-group |  |  | section | Main Contractors & Trades QC/QA and supporting documentation
checkpoint-status |  |  | checkpoint | General Site Photos / As Builts
label | 011276ed-142c-40c3-9ab6-f4b69149e010 |  | note | Attach a minimum of 10 site photos giving an overview of the on site progress relating to this Building Consent since the last audit / inspection
label | 0fca93a7-f81f-4153-9558-c7e73247adee |  | note | Attach any relevant progressive as builts / mark ups
checkpoint-status |  |  | checkpoint | FORMWORK - trade / element applicable to this audit
label | 6ba1abeb-aaa8-4a7f-8878-cccd762d8a6d |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 73f7bec3-e074-46e7-804f-589d8ab4bf6f |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | 286afa27-7567-4444-b85d-f56f8d4e6100 |  | textbox | Overview of progress relating to this trade/element (Formwork) since last audit
label | ee3fab46-f5aa-4cbb-8896-d564e7907433 |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, setout, heights, stability/bracing, DPM / terminations
boolean | 0fac06a4-ab41-4fcc-83f9-d6ece508b300 |  | tickbox | Formwork - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status |  |  | checkpoint | REINFORCING - trade / element applicable to this audit
label | 0c9cd040-ab41-4c37-823a-a535757aaf7a |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | b5b7e31b-4c47-490e-a080-432026d76a07 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | adb621c5-3e7f-4038-8cad-d8361197882b |  | textbox | Overview of progress relating to this trade/element (Reinforcing) since last audit
label | fdba52a0-2d12-4f26-abee-9474ef44f5f9 |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, detail sheets, reo mill certs, size, grade, laps, bends, cover, starters (size & location), cast in items
label | 50d133a3-d7f2-4dcc-b729-54f0bca64ded |  | note | COMPLIANCE CONSIDERATIONS - PS3, PS4, all reinforcing steel bars/ mesh mill certs or steel grade confirmation from supplier, all reinforcing steel fabricator detail sheets for cages/ bent rebar- must verify rebar sourced from accredited supplier
boolean | b6226eed-9cfd-4d5a-b0ba-72f5018efcde |  | tickbox | Reinforcing - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status |  |  | checkpoint | CONCRETE PLACEMENT - trade / element applicable to this audit
label | 9f79b09b-a14e-41a7-a42c-0d5feaebd90e |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | a1081352-a8b7-4979-9838-a5cafc8fc20a |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | da53f8a9-f77f-4e4f-bef9-f3a33dcce56c |  | textbox | Overview of progress relating to this trade/element (Concrete Placement) since last audit
label | 7b1885c1-bd00-40e6-a06e-40de4d927be4 |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, approval, mPa, slump tests, vibration, finish, curing, concrete batch certs confirming mPa and any additive
label | 2bd2de13-1c29-464e-be00-923a5c0cecbb |  | note | COMPLIANCE CONSIDERATIONS - PS3, PS4, concrete cylinder tests for previous month deliveries (7, 14 and/or 28 days as required)
boolean | eeeccbdb-b8a0-4993-a086-8811013cccfe |  | tickbox | Concrete Placement - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status |  |  | checkpoint | BLOCKWORK INC REINFORCING - trade / element applicable to this audit
label | c653f758-0976-4c53-a293-df19c92bb71a |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 0e2c435a-6511-4d93-a3c1-a574eecab36b |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | 0bd03265-041b-406b-ad48-ab99bf28c7d5 |  | textbox | Overview of progress relating to this trade/element (Blockwork Inc Reinforcing) since last audit
label | b91c8982-812c-4488-838e-e0d624c0b2e8 |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, compliance method, masonry grade, size, setout, level and plumb, heights, wash outs, stretcher or stack bond, Mortar joint sizes (7-13mm), tooled to match proposed finish, bond beams, control joints, Approval, mPa, slump tests, vibration, finish, sealer, concrete batch certs confirming mPa and any additive
label | fc35e658-5f7d-446b-89f3-7390b6376135 |  | note | COMPLIANCE CONSIDERATIONS - PS3, PS4, all reinforcing steel bars/ mesh mill certs or steel grade confirmation from supplier, all reinforcing steel fabricator detail sheets for cages/ bent rebar- must verify rebar sourced from approved supplier, concrete cylinder tests for previous month deliveries (7, 14 and/or 28 days as required)
boolean | 9b60ce17-9c14-4731-85be-6f0b86c1203a |  | tickbox | Blockwork Inc Reinforcing - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status |  |  | checkpoint | PRECAST MANUFACTURE - trade / element applicable to this audit
label | 9d73edab-8294-4300-a2f5-959ebd33768f |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | fccf2bf3-5854-40cc-bfeb-6a7d87cf9aa2 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | 09338bb9-ee99-498f-a2ac-902f4ec791d4 |  | textbox | Overview of progress relating to this trade/element (Precast Manufacture) since last audit
label | 3144008e-bd59-4d78-b7b9-b0a8d85dc044 |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, mPa, slump tests, vibration, finish, curing, concrete batch certs confirming mPa and any additive, detail sheets, reo mill certs, size, grade, laps, bends, cover, inserts / cast in items, starters (size & location)
label | 68d77fdc-168e-4822-a089-c50366dfb918 |  | note | COMPLIANCE CONSIDERATIONS - PS1, concrete test results (7, 14 and/or 28 days as required), mill certs & steel grade confirmation from accredited supplier, PS3, PS4
boolean | 377368e0-be2a-40a7-89bd-e2d810557ccc |  | tickbox | Precast Manufacture - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status |  |  | checkpoint | PRECAST INSTALLATION - trade / element applicable to this audit
label | 8255afb7-4bee-4cb8-8d44-d7268d838b0f |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 64f131bf-1908-4586-94ba-8f54d0eb1417 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | 411a845a-58d5-4603-8ef1-9f421314ccd8 |  | textbox | Overview of progress relating to this trade/element (Precast Installation) since last audit
label | 621fa5e4-4300-4f38-b7be-344839460a41 |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, setout, precast starters (size & length), seating, bracing/propping, alignment/plumb/level, joints/connections
boolean | 671c7d21-6e80-4aa0-8e29-6d286a810edd |  | tickbox | Precast Installation - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status |  |  | checkpoint | Structural Grouting - trade / element applicable to this audit
label | 750c1595-7e32-4d35-8935-cfe92982a7a8 |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 0a0259d6-09f4-4668-b4ea-02ad7dea8967 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | ada2c96e-6a79-4f4a-b61a-c73ececf5a89 |  | textbox | Overview of progress relating to this trade/element (Structural Grouting) since last audit
label | 0218b7dc-213e-492c-a4e2-2c956188945b |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, approval, product alignment with specification, mPa, slump tests, installation
label | 2f3663e0-3251-43a9-997e-c836fc0b3f07 |  | note | COMPLIANCE CONSIDERATIONS - manufacturer's warranty, workmanship warranty, PS3
boolean | 0787cec4-df93-4012-8f81-2442ffd1188d |  | tickbox | Structural Grouting - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status |  |  | checkpoint | Structural Steel - trade / element applicable to this audit
label | f996f7c6-3726-40a9-8573-330419263dce |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 1d90ffde-f4e9-4b4b-a42c-6e7e895d5d10 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | 8c3039b2-0b70-41f8-9aa7-7d7f7115e21f |  | textbox | Overview of progress relating to this trade/element (Structural Steel) since last audit
label | 675700a4-16a4-421b-afc9-d9f8059352ac |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, mill certs, fabrication and welding(NDT report, Coatings report) / ONSITE- Delivery dockets, Hold down/Structural connections (setout, size & type), Erection - Location & orientation - Level & Plumb, propped/braced, all connections adequate and to spec & onsite welds, bolt tightening logs
label | 4529c9fa-a966-45fb-b26b-40e3d3dd31a0 |  | note | COMPLIANCE CONSIDERATIONS - PS3, PS4, all steel has mill certs or steel grade confirmation from supplier, all reinforcing steel fabricator detail sheets for cages/ bent rebar- must verify rebar sourced from accredited supplier
boolean | 55155dba-2fa8-4ee5-8bc1-41b71986c9a0 |  | tickbox | Structural Steel - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status |  |  | checkpoint | Intumescent Painting - trade / element applicable to this audit
label | fb1ddf2e-5218-4ce3-80a6-b88ed697eba6 |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | dd4f1044-bd79-4f32-8cfd-a4cd03a29808 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | fd50fdd4-a808-492b-8830-1fb823269448 |  | textbox | Overview of progress relating to this trade/element (Intumescent Painting) since last audit
label | a5a215db-4271-42d7-876b-ac8da4531feb |  | note | ON SITE KEY CONSIDERATIONS -Design & Specifications, product alignment with specification (incl any testing/certification(s)), substrate & surface conditions, Ambient conditions (atmospheric), Micrometer readings - Coatings report
label | 064b8cb8-28e3-4307-8072-08fc4968249f |  | note | COMPLIANCE CONSIDERATIONS - manufacturer's warranty, workmanship warranty, PS3
boolean | 9bdd6be3-2ed2-4fe5-896e-53e72bd7bbe6 |  | tickbox | Intumescent Painting - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status |  |  | checkpoint | Tanking/waterproofing - trade / element applicable to this audit
label | b49af962-d2e3-4600-a25a-962ea02f1110 |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | bde40489-a086-46da-848c-c7dc57e106d6 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | 8c90f1bf-92d1-4695-a7c7-edaa0a47e10c |  | textbox | Overview of progress relating to this trade/element (Tanking/waterproofing) since last audit
label | 4cddea81-fc57-493a-b765-ecedbcfb3893 |  | note | ON SITE KEY CONSIDERATIONS -Design & specifications, Trade details & license, materials/system, manufacturer's specifications, substrate, drainage, installation, joints / control joints, terminations, protection, backfill methodology
label | 50cf5927-5a1c-4682-842d-2c602e13e5d1 |  | note | COMPLIANCE CONSIDERATIONS - manufacturer's warranty, workmanship warranty, PS3, PS4
boolean | d9a423f7-1eb8-4c13-987c-646a12e0c1a7 |  | tickbox | Tanking/waterproofing - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status |  |  | checkpoint | Any other trade / element - trade / element applicable to this audit
label | ea0dde6c-2174-42e8-b6f0-7890653f0262 |  | note | "PASS" and detail below if any other trade/element is applicable to this audit. Complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | f64aebe5-2893-47b8-b46e-3fc487f3d0d3 |  | note | "N/A" if no other trade/element is applicable to this audit, comment below if required
text | b32f2383-4e79-40d5-a699-c6ba2ada655d |  | textbox | Overview of progress relating to this trade/element since last audit
boolean | 1b2dd3cb-777f-4aa4-8946-1ed3f2973ce9 |  | tickbox | Any other trade / element - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status |  |  | checkpoint | Select "PASS" and notify Auckland Council if all above items have been considered and sufficient supporting documentation attached
text | 629f2f58-86ab-4498-bbc7-56e108331ebf |  | textbox | Date this Audit report was sent to Auckland Council
text | 9172d540-f32a-44fd-b49c-742e353c48ab |  | textbox | Inspector(s) from Auckland Council who this was sent to (including email address)
checkpoint-group |  |  | section | Close out of Audit
checkpoint-status |  |  | checkpoint | Close out of Audit - Pass once Council Audit is completed and attached with any corrective actions detailed and closed out below
text | 7c585405-8a98-446e-a423-de54a23e31b7 |  | textbox | Date Auckland Council Inspector sent receipt / audit response
boolean | 1cfd6ab8-3dd8-4308-add5-579a0bbb8f68 |  | tickbox | Council Audit completed and attached
text | fc37fdd9-f69d-4dd5-ba10-c145fa83f652 |  | textbox | As detailed in this Council Audit or discussed - next Audit will occur on
checkpoint-status |  |  | checkpoint | Any Relevant Observation Closeout evidence attached here if applicable (Pass once completed)
text | e08cfeb3-25ac-4378-be22-2c5a63b7ea14 |  | textbox | Corrective actions required before next audit
label | 4f8d1615-2a78-4c28-aad8-0b2a575ae382 |  | note | These should include a summary list of close outs still to be addressed from any of the above line items and comments made in the council audit or any outstanding from previous audits/inspections relating to this building consent
checklist-sectioned |  |  | checklist | Pour: |  |  |  |  | Yes | ST - R - Concrete Pour - Ryman Owned | d0e84f11-1e05-4249-b913-01494e123207
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour details entered
text | 5e9c93c8-423d-5c8f-80d9-3f0693e043f1 |  | textbox | Area to be poured:
text | ce7abc03-900a-597d-8eb3-d4f9fd0a8afc |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork and Embedded Items
checkpoint-status |  |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
checkpoint-status |  |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
boolean | f6d3000b-e4b8-5286-9d24-cd6dee310f84 |  | tickbox | Appointment with the engineers confirmed (Enter date & time of the appointment)
boolean | 87f060df-6876-57ef-aabc-a688d5ce3b58 |  | tickbox | Reidbar – coupler and flange nut installations are inspected by the MV Engineer
checkpoint-status |  |  | checkpoint | IMBMS couplers testing carried out for Village Podiums in the form of tensile testing in accordance with NZS3101.1.2006 and results acceptable
checkpoint-status |  |  | checkpoint | All starter bars are installed correctly (location, size and spacing )
checkpoint-status |  |  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Welding certificates sited and attached
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Relevant service requirements completed (locations checked and accurate)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint-status |  |  | checkpoint | Ryman inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-status |  |  | checkpoint | Concrete Supplier details entered
text | 2e01f497-a2e2-5531-b67e-38d038efcdb6 |  | textbox | Supplier Name:
text | c515c82c-6020-5ad3-af11-554cf25bd46f |  | textbox | Specified concrete strength: |  |  | mPA
text | d75e88a0-e5b4-50e9-b4a5-6b426131dd84 |  | textbox | Concrete strength ordered: |  |  | mPA
text | 7ee21b00-f44f-5337-bae5-0c46aae9f692 |  | textbox | Concrete quantity ordered: |  |  | m3
button | 1e8f80e4-3a6a-54f8-81c8-963a484655b1 |  | button | Test blocks booked | Yes, No, N/A
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-group |  |  | section | Placement Method
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint-status |  |  | checkpoint | Heights and falls checked/confirmed before placement
button | 148adc55-bcbc-57fa-8b45-c70a378b51ca |  | button | Is the cover correct to specification | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
holdpoint |  |  | signoff | Raise remedial/ Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist-flat |  |  | checklist | C - R - Service Trenches - Pulling Pits |  |  |  |  | Yes | C - R - Service Trenches - Pulling Pits | d103f2c0-c7fa-4960-ad02-6c3701c094b5
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Pulling Pits trench works completed as per the specifications
checklist-flat |  |  | checklist | C - R - Lift Pit Installation |  |  |  |  | Yes | C - R - Lift Pit Installation | d1d4ea42-3ce7-4749-a1b4-14bae2ebc944
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Lift Pit installation completed and acceptable
checklist-flat |  |  | checklist | ST - R - Precast beam installation |  |  |  |  | Yes | ST - R - Precast beam installation | d4326d02-1e5b-4e66-8899-71b5d76f73e8
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Anchor point installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - Exterior Tiling |  |  |  |  | Yes | FC - R - Exterior Tiling | d82dfa54-a093-42e6-8ca0-90d8f08d7a70
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Exterior Tiling works completed and acceptable
checklist-flat |  |  | checklist | FC - R - Eyebrow - Canopy |  |  |  |  | Yes | FC - R - Eyebrow - Canopy | da8c1191-7463-4e34-831e-7c8f4234426d
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Exterior Tiling works completed and acceptable
checklist-flat |  |  | checklist | Council Inspection - |  |  |  |  | Yes | Add Council Inspection Checklist | db76e9c0-a749-4451-9f5f-85a1e12dd91f
checkpoint-status |  |  | checkpoint | Inspection completed, attached and any relevant observations closed out (Pass once all information is attached including observations with evidence of closeout)
text | e716f58a-4420-4e11-91ae-f4fef0f7ba87 |  | textbox | Date of inspection:
text | 78d9159e-0896-4188-a542-fa6b1bf43aaa |  | textbox | Inspection Type Code:
text | 6931f74e-964b-42b5-905c-440c2ce0001a |  | textbox | Area inspection relates to
select | ca58c4ad-f5b3-41c0-ae49-ce6c1c3289f9 |  | dropdown | Inspection Outcome | Pass,Fail,Partial Pass,N/A
boolean | d24858c1-85f5-44b8-99c0-818a707a7f19 |  | tickbox | Council inspection attached
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All Relevant Observation Closeout evidence attached here if applicable (Pass once completed)
text | 659f0de8-c7a9-45fe-9851-606ecd798dd2 |  | textbox | Outstanding Information Required
checklist-flat |  |  | checklist | Building Consent - |  |  |  |  | Yes | Add Council BC Upload Checklist | dda159c9-884e-4333-9914-be48f7ae2d5c
checkpoint-status |  |  | checkpoint | Latest building consent attached (superseded and attached as required)
checklist-flat |  |  | checklist | ST - R - Precast Wall Panel Installation |  |  |  |  | Yes | ST - R - Precast Wall Panel Installation | ddd9ef0b-0fe8-47b7-a420-559b4d83de62
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Wall Panel Installation completed and acceptable
checklist-flat |  |  | checklist | F - R - Backfilling |  |  |  |  | Yes | F - R - Backfilling | e04e535f-db00-4284-8213-34ab447f121f
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Backfilling completed as per the specifications
checklist-flat |  |  | checklist | ST - R - Concrete Pour |  |  |  |  | Yes | ST - R - Concrete Pour | e0a18857-45f2-4e89-a4c3-4a06847cddaa
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Correct size and grade of the propping timbers
checkpoint-status |  |  | checkpoint | Correct size and grade of the props
checkpoint-status |  |  | checkpoint | Props placed in the correct location as indicated on the propping plan
checkpoint-status |  |  | checkpoint | Temporary anchors and fixings installed
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Concrete pour completed and acceptable
checklist-flat |  |  | checklist | C - R - Connection to public systems |  |  |  |  | Yes | C - R - Connection to public systems | e0adc9af-8819-4c5a-aed8-4200eca18834
checkpoint-status |  |  | checkpoint | Approval to connect given by relevant Authority (AC, Watercare, Vector, etc)
checkpoint-status |  |  | checkpoint | Area signed off by engineer
checkpoint-status |  |  | checkpoint | Pipe line connected in accordance with requirements, checked and accurate
checklist-flat |  |  | checklist | CST - R - Mechanical Constant |  |  |  |  | Yes | CST - R - Mechanical Constant | e0bba570-6473-4fd6-8f83-334a0754e597
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Electrical
boolean | 9542d075-e028-5882-aac0-cce9b08f948b |  | tickbox | Electrical compliance and safety certificate
boolean | c139e1cd-6126-5ba8-b278-27aa58598452 |  | tickbox | record of inspections for high risk works
checkpoint-status |  |  | checkpoint | Automatic doors
boolean | 351d3c3f-c4e2-59de-90fa-f7a501d74c23 |  | tickbox | Producer Statement Construction(PS3): automatic door installation and failsafe override
boolean | 21f43799-2589-5abf-b3c9-0fa33e033b8c |  | tickbox | As built documentation; plans, operation and maintenance manual
checkpoint-status |  |  | checkpoint | Access controlled doors
boolean | bd2ef425-12fd-5324-a5e0-59cfb943dc4a |  | tickbox | Producer Statement Construction(PS3): installation of access control to doors and failsafe override
boolean | b4e684a6-3ef5-5dad-8c08-c7ad1cd4dcb0 |  | tickbox | As built documentation; location of systems, the make of the systems and operation manuals
checkpoint-status |  |  | checkpoint | Escape route pressurization systems
boolean | 7be47b26-e295-59aa-853f-187726f08825 |  | tickbox | Producer Statement Construction(PS3): Installation of escape route pressurization systems from approved mechanical contractor
boolean | caad5aa7-6e0d-5395-9838-85c80cd45d1d |  | tickbox | Producer Statement Review(PS4): Installation of escape route pressurization systems from approved mechanical contractor
boolean | 3f1fed4f-8981-5cb3-b20b-b6b21fee6c13 |  | tickbox | test/commissioning results verifying measured airflow rates meet design and interface with alarm system
boolean | d2d1442a-b50b-5a78-92c9-d376f07c72ec |  | tickbox | As built documentation; equipment schedules and make of systems, operation and maintenance manuals
boolean | c6d92d1c-22da-564f-a0cc-0e13b400879a |  | tickbox | Electrical work certificate
checkpoint-status |  |  | checkpoint | Passenger Carrying Lifts
boolean | 69ddf56c-7e8d-59ec-ab52-537c0bc6acb8 |  | tickbox | Codemark construction certification and inspection/maintenance sheets
checkpoint-status |  |  | checkpoint | Mechanical ventilation or air conditioning system
boolean | a833269c-8c5d-5091-9ea6-516749bd2727 |  | tickbox | Producer Statement Construction(PS3): Kitchen extract system (compliance with NZBC G4)
boolean | 77daac09-c96a-540c-9cc9-6621bdee60d2 |  | tickbox | Producer Statement Construction(PS3): Confirmation from mechanical contractor the systems comply with NZBC G4
boolean | 0fd6bc5f-e208-5090-aa45-b27e1329bb7c |  | tickbox | Producer Statement Review(PS4): Confirmation from council approved mechanical engineer that the systems comply with NZBC G4
boolean | fdbcc4da-c84b-59a4-8e83-98b9a031d20e |  | tickbox | Producer Statement Review(PS4): Installation of seismic restraints in accordance with NZS 4219:2009:"Seismic Performance of Engineering Systems in Buildings"
boolean | 4d08359f-2760-59b6-be82-06f8833e0710 |  | tickbox | test/commissioning results verifying measured airflow rates meet design and interface with alarm system
boolean | 41ca4e85-8cb4-55b4-bc08-79e86b21413d |  | tickbox | As built documentation; equipment schedules and make of systems, operation and maintenance manuals
checkpoint-status |  |  | checkpoint | Application for compliance schedule (AC2102)
checkpoint-status |  |  | checkpoint | Confirmation of performance standards for specified systems (AC2150)
checklist-flat |  |  | checklist | CST - R - Council Inspection |  |  |  |  | Yes | CST - R - Council Inspection | e46bc85a-cf06-45da-8c75-8b729e610e80
checkpoint-no-status |  |  | checkpoint | Inspection Details:
text | 8d57dd33-b531-58ed-b698-5a7df22bb057 |  | textbox | Date of Inspection
text | 6dffb1c5-a532-55cb-8485-097b88575f95 |  | textbox | Type of Inspection
text | 5f52e5cf-402f-5e2d-a2be-db0bfabab468 |  | textbox | Area Inspection relates to
select | 9de274d0-4f8b-592d-b463-a5fd234b344a |  | dropdown | Inspection outcome | Pass, Partial Pass, Fail
boolean | c9031085-1b00-583c-84a4-4ed0f7af415c |  | tickbox | Council inspection attached
checkpoint-status |  |  | checkpoint | Relevant Observation Closeout evidence attached below if applicable (pass once completed)
text | 271dfed7-026a-5a17-b5ba-cda062acc4a3 |  | textbox | Failed comments and Required Action
checklist-flat |  |  | checklist | F - R - Underground services |  |  |  |  | Yes | F - R - Underground services | e862efb7-b1e5-4953-8f67-38eed995f5a0
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All underground services installation completed as per the specifications
checklist-flat |  |  | checklist | FC - R - Soffits |  |  |  |  | Yes | FC - R - Soffits | ecab2c0b-e8cd-40ad-9771-9592d839498c
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Soffit works completed and acceptable
checklist-flat |  |  | checklist | Observation: |  |  |  |  | Yes | Add Observation/Remedial Item | eee90b69-b494-4d37-9a9a-0fda90201f56
checkpoint-status |  |  | checkpoint | Observation/Remedial Status
text | ae7fc046-dca9-4fab-98f8-374caeb04456 |  | textbox | Location
text | 28d26279-c304-4689-8317-1deb797dc8fe |  | textbox | Observation Description
text | e0506f57-5442-4fec-b602-ea7a300f1166 |  | textbox | Action Required
holdpoint |  |  | signoff | Request Signoff on Remedial
checklist-flat |  |  | checklist | Concrete Reinforcing |  |  |  |  | Yes | Concrete Reinforcing | ef0a6e25-334e-4da3-b814-fa3ca46800ca
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
boolean | aa89e74f-28bc-583d-9703-48bea01fcf8e |  | tickbox | Appointment with the engineers confirmed (Enter date & time of the appointment)
boolean | 03446e6d-a87b-5627-92d3-5803eec34b1f |  | tickbox | Reidbar – coupler and flange nut installations are inspected by the MV Engineer
checkpoint-status |  |  | checkpoint | IMBMS couplers testing carried out for Village Podiums in the form of tensile testing in accordance with NZS3101.1.2006 and results acceptable
checkpoint-status |  |  | checkpoint | All starter bars are installed correctly (location, size and spacing )
checkpoint-status |  |  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Welding certificates sited and attached
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checklist-flat |  |  | checklist | Timber Framing - |  |  |  |  | Yes | Add Trade's QA Attached Checklist | f1c84aab-420e-43c2-9c1f-1e9ea4242a51
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
holdpoint |  |  | signoff | Raise Remedial/Trade Contractor QA and Sign off
checklist-flat |  |  | checklist | ST - R - Precast Shell Beam Lintel Installation |  |  |  |  | Yes | ST - R - Precast Shell Beam Lintel Installation | f3383b7d-3529-473d-aff7-597c2658d518
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Shell Beam Lintel Installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - Ecoply Board |  |  |  |  | Yes | FC - R - Ecoply Board | f388b9dd-b6c9-48b3-840d-cfbfaadeb0a1
checkpoint-status |  |  | checkpoint | Fixing and spacings checked in accordance with manufacturers specs.
checkpoint-status |  |  | checkpoint | Bracing checked and accurate
checkpoint-status |  |  | checkpoint | Penetrations and punctures sealed with flashing tape
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Ecoply board installation completed and acceptable
checklist-flat |  |  | checklist | Unit Benchmarking |  |  |  |  | Yes | ITP - R - Unit Benchmarking (Use at stage level) | f87fbea5-2287-4bf8-9e5c-f61d1bb821be
checkpoint-status |  |  | checkpoint | Benchmark standard agreed as per Quality Management Plan
button | 40ac3beb-b417-5f61-a696-6825f676fda7 |  | button | Project Manager or delegate present | Yes, No, N/A
button | 5fde1c18-b10f-543b-82d2-6b3fd8ae3d03 |  | button | Sales representative or delegate present | Yes, No, N/A
button | 1ee8be12-0642-5661-910a-7e3b9681b695 |  | button | QA Advisor or delegate present | Yes, No, N/A
button | 11b56cf3-8d8d-5c15-80dc-b1fa3686d345 |  | button | Design representative or delegate present | Yes, No, N/A
text | 9f4ed0b1-387f-5fce-a10e-6d54fb2caddd |  | textbox | Benchmark details (e.g. apartment number or explanation)
text | b63c21b3-de68-5849-b34a-d8a219cc3801 |  | textbox | Record benchmark date