## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Sarking |  |  |  |  | Yes | Sarking | 1d70e1f9-253b-48c4-a87f-05ddfc021b97
checkpoint-status |  |  | checkpoint | Sarking used is as per approved and specified material
checkpoint-status |  |  | checkpoint | NEX-WMK-AR-SP-AR1000 AR-1060 (Interior Finishes Schedule)
checkpoint-status |  |  | checkpoint | Sarking fixed on stud framing
checkpoint-status |  |  | checkpoint | As Per Manufacturer Specifications And Standards, TBA Firefly Sarking Installation Manual
checkpoint-status |  |  | checkpoint | All opening cut out with sarking cut and folded into reveals and sealed with foil tapes,
checkpoint-status |  |  | checkpoint | All joint and fixing point taped
checkpoint-status |  |  | checkpoint | Supervisor inspection
checklist-flat |  |  | checklist | Rigid insulation |  |  |  |  | Yes | Rigid insulation | 354f30dd-72d2-4f71-b9de-c86213697239
checkpoint-status |  |  | checkpoint | Installer confirmation slab condition is acceptable including any set downs are correct.
label | f13d61ee-868c-5d36-b4d7-75c7da5142be |  | note | NEX-WMK-AR-SP-AR1000 Section 0531 Suspended Ceilings -Combined (Clause 3.2)
checkpoint-status |  |  | checkpoint | Rigid insulation sued is as per approved and specified material
label | 91b07f70-35b2-5c27-a88b-c5e1c7451d35 |  | note | NEX-WMK-AR-SP-AR1000 AR-1060 (Interior Finishes Schedule)
checkpoint-status |  |  | checkpoint | Insulation panel are level, clean and free from contaminants.
label | 4c99586c-120f-50bc-a3c6-03b2d38aa6cb |  | note | As Per Manufacturer Specifications And Standards;https://primepanel.com.au/wp-content/uploads/2019/12/PrimePanel-Insulation-Soffit-Installation-Guide.pdf
checkpoint-status |  |  | checkpoint | Level off high point for concrete soffit
checkpoint-status |  |  | checkpoint | Installation of pins as per manufacturer installation guide
checklist-flat |  |  | checklist | Ceiling Framing |  |  |  |  | Yes | Ceiling Framing | 3b41429f-fb52-42da-ab3d-f00270a2d13b
checkpoint-status |  |  | checkpoint | Ceiling Frame set out complete
label | 64246aaa-7281-5f63-91bf-b29988508ac3 |  | note | NEX-WMK-AR-SP-AR1000 Section 0531 Suspended Ceilings -Combined (Clause 3.2)
checkpoint-status |  |  | checkpoint | Ceiling Framing complete as per Reflected Ceiling Plans and Project Details
label | fe8c726e-f219-53cd-8196-2930e9774bf1 |  | note | NEX-WMK-AR-SP-AR1000 Section 0531 Suspended Ceilings -Combined (Section 3.0)
checkpoint-status |  |  | checkpoint | Ceiling Noggins and all other concealed elements installed as per RCP’s
checkpoint-status |  |  | checkpoint | All frames plumb and square
label | a91c05b4-f7df-5f38-8456-83c4a1a986b8 |  | note | As Per Studco Inspection Report
checklist-flat |  |  | checklist | Plasterboard for Ceiling |  |  |  |  | Yes | Plasterboard for Ceiling | 94a152c7-e83a-4a65-8318-a045948d30b4
checkpoint-status |  |  | checkpoint | Confirm Ceiling height
label | fde26178-45d9-5fe4-b89a-cde43055bf90 |  | note | NEX-WMK-AR-SP-AR1000 Section 0531 Suspended Ceilings -Combined (Clause 3.2)
checkpoint-status |  |  | checkpoint | Access panels have been installed as per RCP and match the ceiling area in appearance and performance
label | 38c4fbf5-4be5-546d-a872-97da3139ed27 |  | note | NEX-WMK-AR-SP-AR1000 Section
checkpoint-status |  |  | checkpoint | Ceiling framework install as per project documentation and requirements.
label | 599a170c-a3b7-5b1f-a65b-b9dd2d8cd2de |  | note | NEX-WMK-AR-SP-AR1000 Section 0531 Suspended Ceilings -Combined (Section 3.0)
checkpoint-status |  |  | checkpoint | Ceiling bulkheads where required
label | 0456e262-e83a-5b67-b7db-f08cddef880f |  | note | NEX-WMK-AR-SP-AR1000 Section 0531 Suspended Ceilings -Combined (Clause 3.6)
checkpoint-status |  |  | checkpoint | Pelmets install as per project documentation and requirements.
checkpoint-status |  |  | checkpoint | Ceiling Insulation complete as per project documentation and requirements
label | 2785b23e-83a6-5372-b02c-6cd82a363ad9 |  | note | NEX-WMK-AR-SP-AR1000 Section 0471 Thermal Insulation and Pliable membranes (Clause 3,4 & 3.5), Section 0472 Acoustic Insulation (Clause 3.4)
checkpoint-status |  |  | checkpoint | Correct type of plasterboards and thickness installed as per wall details, project drawings and BCA requirements
label | e7e5f961-2e45-59c8-b256-d84bca96c998 |  | note | NEX-WMK-AR-SP-AR1000 AR-1060 (Interior Finishes Schedule)
checkpoint-status |  |  | checkpoint | Ceiling plasterboard Lining installed as per manufacturer specifications and standards
label | 3a86de22-4198-5286-b5fd-f8e922715004 |  | note | NEX-WMK-AR-SP-AR1000 Section 0531 Suspended Ceilings -Combined (Section 3.0)
checkpoint-status |  |  | checkpoint | All acoustic seals are installed as per drawings &All fire rated seals are installed as per drawings
label | c5b2c305-aac7-546f-a1d8-a051df11d329 |  | note | NEX-WMK-AR-SP-AR1000 Section 0531 Suspended Ceilings -Combined (Clause 3.0)
checkpoint-status |  |  | checkpoint | Seismic requirements have been considered
checkpoint-status |  |  | checkpoint | Any ceiling trims are completed and installed to form neat junctions between linings, finishes and other adjacent surfaces
label | 95c6ef02-701a-5749-9521-b61c29888482 |  | note | NEX-WMK-AR-SP-AR1000 Section 0531 Suspended Ceilings -Combined (Clause 3.7)
checkpoint-status |  |  | checkpoint | All joints are complete to specified level of finish
label | d762ad35-211d-5053-9489-09e2b4bc7461 |  | note | NEX-WMK-AR-SP-AR1000 Section 0531 Suspended Ceilings -Combined (Clause 3.0)
checklist-flat |  |  | checklist | Wall Framing |  |  |  |  | Yes | Wall Framing | 9901c074-c393-4857-a20f-e265d8848e0b
checkpoint-status |  |  | checkpoint | Installer confirmation slab condition is acceptable including any set downs are correct
label | f2ce4d34-24ec-5fa3-9655-397dbe5d37f2 |  | note | NEX-WMK-AR-SP-AR1000 Section 0520 Partitions – Combined (Clause 3.1)
checkpoint-status |  |  | checkpoint | All frames/studs set out correctly
checkpoint-status |  |  | checkpoint | All frames plumb and square
checkpoint-status |  |  | checkpoint | Fix to structural members
checkpoint-status |  |  | checkpoint | All window and sliding door openings are as per plan and line up with above elements.
checkpoint-status |  |  | checkpoint | Nogging all installed correctly
checkpoint-status |  |  | checkpoint | Plywood installed to all wet areas to adaptable units
checkpoint-status |  |  | checkpoint | Door Frames Installed as per project documentation
checkpoint-status |  |  | checkpoint | Fire rated door frames installed as per project documentation
checkpoint-status |  |  | checkpoint | Studco/Rondo Supplier inspection (Provide report to builder)
label | 7f6a361e-293b-5e24-a1ce-14c09986927e |  | note | Studco Design - NextSense Macquarie University - Internal Wall - 9816-0-A
checkpoint-status |  |  | checkpoint | Wall Frame installation is complete. All frame types are installed as per wall type plans.
checklist-flat |  |  | checklist | Vitradual Aluminium cladding |  |  |  |  | Yes | Vitradual Aluminium cladding | a90a5922-57df-4d9a-b8e1-af5b54cf14fb
checkpoint-status |  |  | checkpoint | Check external wall frames alignment
label | be2ca037-647f-53fc-b411-88ee3b368400 |  | note | NEX-WMK-AR-SP-AR1000 Section 0520 Partitions – Combined (Clause 3.1)
checkpoint-status |  |  | checkpoint | Check panel fabrication as per shop drawing
label | f1789ec0-c067-5c50-a323-4f331a2bc15a |  | note | As Per Shop Drawing
checkpoint-status |  |  | checkpoint | Install all flashing as per wall detail and project drawings
checkpoint-status |  |  | checkpoint | Install sarking and tophats
label | cdc46b88-e004-5bf6-ab69-21d34e4531de |  | note | As Per Manufacturer Specifications And Standards. https://media.architectureau.com/media/files/Vitradual%20Installation%20Manual_Cassette%20Fix.pdf
checkpoint-status |  |  | checkpoint | Horizontal & Vertical Alignment
checkpoint-status |  |  | checkpoint | Install Vitradual Aluminium panels as per shop drawing
checkpoint-status |  |  | checkpoint | Joints caulking & Sealing
checkpoint-status |  |  | checkpoint | Defects rectified as per instruction by ADCO and inspection by supervisor
checkpoint-status |  |  | checkpoint | Final Inspection (water test by builder)
checklist-flat |  |  | checklist | Setting & Sanding |  |  |  |  | Yes | Setting & Sanding | c6998b0c-0563-4093-98cf-9aca41749769
checkpoint-status |  |  | checkpoint | Angle /LB/P50 installed as per project documentation and requirements
checkpoint-status |  |  | checkpoint | NEX-WMK-AR-SP-AR1000 Section 0520 Partitions Combined (Clause 3.0) NEX-WMK-AR-SP-AR1000 Section 0511 Lining (Clause 3.0), Section 0520 (Clause 3.0)
checkpoint-status |  |  | checkpoint | First coat setting applied as per manufacturer specifications and standards
checkpoint-status |  |  | checkpoint | Second coat setting applied as per manufacturer specifications and standards
checkpoint-status |  |  | checkpoint | Final coat setting applied as per manufacturer specifications and standards
checkpoint-status |  |  | checkpoint | Sanding applied as per manufacturer specifications and standards
checkpoint-status |  |  | checkpoint | patching applied as per manufacturer specifications and standards
checkpoint-status |  |  | checkpoint | Defects rectified as per instruction by ADCO and inspection by supervisor
checkpoint-status |  |  | checkpoint | Final Inspection
checklist-flat |  |  | checklist | Plasterboard & Insulation for Walls |  |  |  |  | Yes | Plasterboard & Insulation for Walls | d0e56e9c-0f2f-4c7b-8612-2685d8a5ee1b
checkpoint-status |  |  | checkpoint | Installer confirmation All studwork and blocking complete as required
label | 925ae348-0a7c-5ade-ab18-635b661c48ed |  | note | NEX-WMK-AR-SP-AR1000 Section 0520 Partitions – Combined (Clause 3.3)
checkpoint-status |  |  | checkpoint | All materials have been procured as per project reports, architectural documentation and specification
checkpoint-status |  |  | checkpoint | Wall insulation installation complete. All insulation is installed as per wall types plan.
label | c1e07cfd-19bf-58a2-9ed9-f081bb24e663 |  | note | NEX-WMK-AR-SP-AR1000 Section 0471 Thermal Insulation and Pliable membranes (Clause 3,3), Section 0472 Acoustic Insulation (Clause 3.3)
checkpoint-status |  |  | checkpoint | Wall noggins and all other concealed elements are installed as per wall outlines and elevation drawings
checkpoint-status |  |  | checkpoint | Rough-in sign off
checkpoint-status |  |  | checkpoint | All acoustic seals are installed as per drawings &All fire rated seals are installed as per drawings
label | dd886b01-22bc-5b44-b7ac-871a5f17f3a0 |  | note | NEX-WMK-AR-SP-AR1000 Section 0520 Partitions Combined (Clause 3.0)
checkpoint-status |  |  | checkpoint | Correct type of plasterboards and thickness installed as per wall details, project drawings and BCA requirements
label | 72e249da-9662-581a-ba8c-1bd5e72b2133 |  | note | NEX-WMK-AR-SP-AR1000 AR-1060 (Interior Finishes Schedule)
checkpoint-status |  |  | checkpoint | Penetrations are correct sizes – dependent on system of drywall dampers
checkpoint-status |  |  | checkpoint | Any wall trims are completed and installed to form neat junctions between linings, finishes and other adjacent surfaces
label | fca7d196-a694-5637-8b5c-f175038233f2 |  | note | NEX-WMK-AR-SP-AR1000 Section 0511 Lining (Clause 3.7)
checkpoint-status |  |  | checkpoint | Villaboard to wet areas ONLY
label | 6dd758d8-07cb-5782-a3e6-1d5a87fb4815 |  | note | NEX-WMK-AR-SP-AR1000 Section 0520 Partitions – Combined (Clause 3.3)
checkpoint-status |  |  | checkpoint | Plasterboard Lining to be installed as wall set out plan
label | 86dbe855-8304-5beb-89cc-2ac89d1b262c |  | note | NEX-WMK-AR-SP-AR1000 Section 0520 Partitions – Combined (Clause 3.3
checkpoint-status |  |  | checkpoint | All joints are complete to specified level of finish
label | ef11b170-2212-5c23-9cd6-242cc345fbc4 |  | note | NEX-WMK-AR-SP-AR1000 Section 0520 Partitions Combined (Clause 3.0)