## General
Modify template as required prior to use, e.g. to accommodate project or customer specific requirements, then delete this instructional text when complete.
SECTION 1 – GENERAL DETAILS
Project Name: | SH58-M2TG | [5 empty] | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | DS2681 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Waka Kotahi NZ Transport Agency | [5 empty] | B | Report by Breach | PM | Project Manager | Gordon Lemon | GL
Contract Number: | 106877 | [5 empty] | C | Check | CM | Construction Manager | Jamie Nisbet | JN
Area/ Sub-System: | CIVILS |  |  | Lot ID Number: | 19 |  | D | Dimension Inspection | ER | Stantec Representative | Sam Parkinson | SP
[7 empty] | E | Examine | QE | Quality Engineer | Lyssa Gatehouse | LG
ITP Number: | DS2681-SH58-ITP-C-034 |  |  | Version: | Rev1 |  | H | Hold Point | QM | QA Manager | Diliban Sengottian | DS
ITP Description: | Subsoil Drain Installation | [5 empty] | I | Inspection | SV | Surveyor | Jim Robbins | JR
Discipline: | Pavements | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | John Masters | JM
Specification: | Project Specifiation, NZTA F/2:2013, NZTA F/6:2003, NZTA F/7 | [5 empty] | O | Operation | ST | Superintendent | Craig Maloney | CM
[7 empty] | R | Review | PE | Project Engineer
Drawings: | C600-80510096-02B-100-C601, C600-80510096-02B-100-C602, C600-80510096-02B-100-C603, C600-80510096-02B-100-C606 | [5 empty] | S | Subcontractor | SE | Site Engineer
[7 empty] | V | Visual Verification | EM | Environmental Manager | Ross Glubb | RG
Prepared By: (Name) | Tyler Collinson |  |  | Date: | 30/092025 |  | W | Witness Point
Quality Specified:
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: | Jamie Nisbet |  |  | Signature: |  | #VALUE! |  |  | Date: | 2025-09-30
Downer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:

## Material
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Inspection Point/ Signature & Date
[7 empty] | Key | By (Role Key) | Downer Signature | Date | Customer Requirements Verification Record / Location
3.1 | Material Acceptance - 110mm Subsoil with sock | Approval of subsoil drainpipe and filter sock | Subsoils to be 110mm OD twin wall perforated HDPE subsoil pipe (smooth inner wall and corrugated outer wall) that complies with the requirements of Clause 3.1.8 NZTA F/2:2013 | Confirmation from Stantec representative | Prior to works | Holdpoint | H | ER
3.2 | Material Acceptance - Geotextile Cloth | Approval of geotextile cloth | Geotextile complying with the requirements of NZTA F/7, Strength Class B, Filtration Class 1 | Confirmation from Stantec representative | Prior to works | Holdpoint | H | ER

## Construction
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
4.1 | Trench Excavation | Subsoil drain trench dimensions are to be checked against specifications | Trench has been excavated to the following dimensions: - Trench depth to ensure 600mm minimum below subgrade level, or 1200mm below finished level whichever is greater - Trench width to be 400mm. | Visual inspection, site photos | Continuous | Witness point | W | SE
4.2 | Subsoil Drain Installation - bedding and geotextile material | Inspection of bedding drainage chip and geotextile placement | Placement of bedding layer, and geotextile cloth must meet specifications outlined in Clause 16.3.27 of the Project Specification and be cosistent with the methodology statement. Minimum 75mm drainage chip bedding. Geotextile to be wrapped around 40/20 drainage chip. | Visual inspection, site photos | Continuous | Witness point | W | SE
4.3 | Subsoil Drain Installation - drainpipe | Inspection of installed subsoil drain pipe | Pipe is to be free of punctures and dents. Subsoil drain to have a minimum grade of 0.5%. | Visual inspection, site photos, as-built records | Continuous | Witness point | W | SE
4.4 | Subsoil Drain Installation - 40/20 chip backfill | Check backfill of drainage chip and wrap of geotextile | Minimum 300mm drainage chip above subsoild drain, thin layer of drainage chip used to hold the geotextile in place. | Visual inspection, site photos | Continuous | Witness point | W | SE
4.6 | Backfill | Inspect thickness of lifts and compaction is sufficient | Backfill with material as specified by the engineer. Backfill in 200-250mm lifts and compact. | Visual inspection, site photos | Continuous | Witness point | W | SE
4.7 | Flushing point installation | Inspection of flushing point | Flushing points shall be provided on subsoil drains and shall generally be at 50m centres and every high point. Flushing points include PVC-U pipes and fittings, which shall comply with TNZ specifications outlined in Clause 16.1.1 Project Specification. Access to flushing points shall be via a cast iron valve box with a cover marked “RE” (rodding eye). The valve box and cover shall comply with PCC specifications and be placed behind the protection of the guardrail and out of the traffic live lane. | Visual inspection, site photos, as-built records | Continuous | Witness point | W | SE

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
5.1 | Survey As-built | Surveyor supply as-built of completed section once backfilling has been completed | As-built survey of subsoil line and associated flushing points | Site photos, survey as-builts | Per site | Witness Point | W | SV
SECTION 6 – COMMENTS
|  |  | Customer Release Granted: | ☐ Yes | ☐ No | Date:
Certificate Number: