## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DS2681-SH58-ITP-C-034 Subsoil Drain Installation | itp |  |  |  |  | DS2681-SH58-ITP-C-034 Subsoil Drain Installation
section | SECTION 4 – IN-PROCESS INSPECTIONS
checkpoint | 3.1 - Material Acceptance - 110mm Subsoil with sock
label | Inspection Point: Quality Control Activity - Approval of subsoil drainpipe and filter sock
label | Acceptance Criteria - Subsoils to be 110mm OD twin wall perforated HDPE subsoil pipe (smooth inner wall and corrugated outer wall) that complies with the requirements of Clause 3.1.8 NZTA F/2:2013
label | Verifying Document - Confirmation from Stantec representative
label | Frequency - Prior to works
label | Inspection Type (Visual, other) - Holdpoint
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Material Acceptance - Geotextile Cloth
label | Inspection Point: Quality Control Activity - Approval of geotextile cloth
label | Acceptance Criteria - Geotextile complying with the requirements of NZTA F/7, Strength Class B, Filtration Class 1
label | Verifying Document - Confirmation from Stantec representative
label | Frequency - Prior to works
label | Inspection Type (Visual, other) - Holdpoint
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 – IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Trench Excavation
label | Inspection Point: Quality Control Activity - Subsoil drain trench dimensions are to be checked against specifications
label | Acceptance Criteria - Trench has been excavated to the following dimensions:
label | — Trench depth to ensure 600mm minimum below subgrade level, or 1200mm below finished level whichever is greater
label | — Trench width to be 400mm.
label | Verifying Document - Visual inspection, site photos
label | Frequency - Continuous
label | Inspection Type (Visual, other) - Witness point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.2 - Subsoil Drain Installation - bedding and geotextile material
label | Inspection Point: Quality Control Activity - Inspection of bedding drainage chip and geotextile placement
label | Acceptance Criteria - Placement of bedding layer, and geotextile cloth must meet specifications outlined in Clause 16.3.27 of the Project Specification and be cosistent with the methodology statement. Minimum 75mm drainage chip bedding. Geotextile to be wrapped around 40/20 drainage chip.
label | Verifying Document - Visual inspection, site photos
label | Frequency - Continuous
label | Inspection Type (Visual, other) - Witness point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.3 - Subsoil Drain Installation - drainpipe
label | Inspection Point: Quality Control Activity - Inspection of installed subsoil drain pipe
label | Acceptance Criteria - Pipe is to be free of punctures and dents. Subsoil drain to have a minimum grade of 0.5%.
label | Verifying Document - Visual inspection, site photos, as-built records
label | Frequency - Continuous
label | Inspection Type (Visual, other) - Witness point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.4 - Subsoil Drain Installation - 40/20 chip backfill
label | Inspection Point: Quality Control Activity - Check backfill of drainage chip and wrap of geotextile
label | Acceptance Criteria - Minimum 300mm drainage chip above subsoild drain, thin layer of drainage chip used to hold the geotextile in place.
label | Verifying Document - Visual inspection, site photos
label | Frequency - Continuous
label | Inspection Type (Visual, other) - Witness point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.6 - Backfill
label | Inspection Point: Quality Control Activity - Inspect thickness of lifts and compaction is sufficient
label | Acceptance Criteria - Backfill with material as specified by the engineer. Backfill in 200-250mm lifts and compact.
label | Verifying Document - Visual inspection, site photos
label | Frequency - Continuous
label | Inspection Type (Visual, other) - Witness point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.7 - Flushing point installation
label | Inspection Point: Quality Control Activity - Inspection of flushing point
label | Acceptance Criteria - Flushing points shall be provided on subsoil drains and shall generally be at 50m centres and every high point. Flushing points include PVC-U pipes and fittings, which shall comply with TNZ specifications outlined in Clause 16.1.1 Project Specification. Access to flushing points shall be via a cast iron valve box with a cover marked “RE” (rodding eye). The valve box and cover shall comply with PCC specifications and be placed behind the protection of the guardrail and out of the traffic live lane.
label | Verifying Document - Visual inspection, site photos, as-built records
label | Frequency - Continuous
label | Inspection Type (Visual, other) - Witness point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
section | SECTION 5 – FINAL INSPECTION AND HANDOVER
checkpoint | 5.1 - Survey As-built
label | Inspection Point: Quality Control Activity - Surveyor supply as-built of completed section once backfilling has been completed
label | Acceptance Criteria - As-built survey of subsoil line and associated flushing points
label | Verifying Document - Site photos, survey as-builts
label | Frequency - Per site
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SV