## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 0690dccd-cae3-4fb6-925d-e7c836fc7818 |  | checklist | Watermain- Pipeline Installation Checklist |  |  |  |  | Yes | Watermain- Pipeline Installation Checklist | 042c18b7-9a3f-443a-a374-5b246e630118
checkpoint-group | 51c34c22-5be9-4eb5-8798-5156f4d932b5 |  | section | Pipe Laying
checkpoint-status | 7ce716bb-416a-4c28-ab38-4a957fa05a54 |  | checkpoint | Latest consented drawings
text | a1863d60-ec49-5365-a34d-774de7296327 |  | textbox | Drawing Ref No.
checkpoint-status | 9a1b2fce-4f06-41e0-b067-15fcdaedf7af |  | checkpoint | Setout completed checked and accurate
checkpoint-status | f1a11029-f115-4169-bb30-3ed3773a8426 |  | checkpoint | Excavation Accurate - Location & Depth
checkpoint-status | da4b8a36-1e96-4b93-8bb7-ddc2254ec439 |  | checkpoint | Ground Conditions Checked & Acceptable
checkpoint-status | 033813ff-6157-45f3-b38f-b9e3e9580086 |  | checkpoint | Bedding depth and material correct
checkpoint-status | 31a0d007-a4d1-4a2e-86bb-6b168540b14a |  | checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
text | 850285ef-338b-528c-bd56-a3b71ca36bb5 |  | textbox | Start Invert
text | e33c4b8a-dde8-5909-8435-ad9e6ebb9bed |  | textbox | Finish Invert
text | a6fef0b0-e3ee-5f72-a5ba-4e618d7e6c93 |  | textbox | Grade of Pre-Line %
text | f2e29fab-0140-5b12-949f-aae662451fe9 |  | textbox | Product Type
checkpoint-status | 4b29e5a2-296d-42ad-844b-d53275a00483 |  | checkpoint | Install Tests completed, reviewed & approved
text | 200161c6-c77e-51a6-8013-7e6d5028583b |  | textbox | Local Authority Inspection Passed
text | bacff545-7a4f-5666-89f2-ff2e6800303f |  | textbox | Name of inspector
text | 8c5f4fa3-4a74-59a4-9ae9-077298de4ea8 |  | textbox | Date
checkpoint-status | 7d6aae14-0d80-4edd-a75f-58e7ef0ce262 |  | checkpoint | Pipe Laying Completed
checkpoint-status | 97b3d8a8-6027-4ed7-874f-6bfd8b63ca49 |  | checkpoint | Laid by
boolean | 171f7a97-ffcc-5ab0-aab1-ba80ef54abb9 |  | tickbox | Bedding Sound
boolean | 2a079242-4186-5b2b-98b5-ef2cfe11edc9 |  | tickbox | Soil Removed
boolean | 57db6ac2-061a-582b-817b-9106e41ea8d8 |  | tickbox | Trench Compacted
boolean | 40142255-a857-58ac-94a7-544746dc6f84 |  | tickbox | Hard Filled
checkpoint-status | f12bb6d5-fddf-4c53-be98-508602dc38eb |  | checkpoint | Connections to manholes complete and approved
checkpoint-status | 9b64a1dc-eabb-4631-827f-f5629d710614 |  | checkpoint | Air Test Complete
checkpoint-status | 6afc2620-56e3-4c55-820b-8625f0fd8f78 |  | checkpoint | Area of Work Inspection Completed & Sign Off
text | 678e2daa-9837-559c-b170-9d3866c5c58c |  | textbox | Sign Off By
text | e3a82a27-a875-52e1-bc7d-cfabf67bf3ef |  | textbox | Acknowledgement of checklist by
text | bddea5f4-fa9b-5985-8228-87ae4b2732c8 |  | textbox | Foreman
checkpoint-group | e3aec73e-230d-4ff7-8e43-82f4db2cc02a |  | section | Backfill
checkpoint-status | 462744a7-e89a-4bc2-bf33-849a7cb09250 |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status | 1ff40407-c0da-44d0-8a66-4f3ac82e901e |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status | 6d24aaa2-87b0-4477-a9f5-ec097c0e7769 |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status | 54f3aa77-4a8d-4831-a27b-2ea95f4aeadb |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closed out
checkpoint-status | ba0652d9-56b1-4ff0-bb83-f1941becffd3 |  | checkpoint | General photos and observations during backfill
checkpoint-status | 8446756a-739f-4e59-903f-e0f6ec28f3aa |  | checkpoint | Backfill completed correctly and heights checked/ correct
checklist-sectioned | 6ecc2119-fc1a-4d30-8b1e-78ea69016604 |  | checklist | Drainage - Manhole Install Checklist |  |  |  |  | Yes | Drainage - Manhole Install Checklist | 044ab001-a416-4487-ba13-d31694301e30
checkpoint-group | abe53c1c-fc32-44bd-b930-a5a4d202ffd3 |  | section | Manhole Install
checkpoint-status | 1c483020-30a2-4674-b26e-b4897c8a776b |  | checkpoint | Latest consented drawings
text | 3beaced0-f87a-50cf-b211-c5c51974415b |  | textbox | Drawing Ref No.
checkpoint-status | 26a3ed75-e698-44f8-b025-0839bee9805d |  | checkpoint | Setout Completed checked and accurate
checkpoint-status | 8126d293-ac96-4bd9-b124-638acf7d12f7 |  | checkpoint | Excavation Accurate - Location & Depth
checkpoint-status | 5c808052-49de-4a4f-9fa1-bb7c89d65669 |  | checkpoint | Ground conditions checked & acceptable
checkpoint-status | 47935344-74d5-4ee6-8e57-5115b7f92fc8 |  | checkpoint | Bedding depth and material correct & compacted
checkpoint-status | 64b2900c-0e00-4350-96d5-2203faa7a2f9 |  | checkpoint | Correct manhole installed to specified height and sitting level
checkpoint-status | 4c72ee95-6532-434d-9fd2-e08b5a279cdc |  | checkpoint | Manhole Risers Installed (if applicable)
checkpoint-status | 0cabbc1d-96ef-40fd-9d8d-656ccf268895 |  | checkpoint | Joints & connections correctly sealed as specified
checkpoint-status | b49d095f-664f-47f2-8801-624a39a2840b |  | checkpoint | Manhole benching completed and acceptable
checkpoint-status | 4771c75b-ba4a-43e3-b9d5-c66e12d6e345 |  | checkpoint | Concrete Lid Installed and sitting appropriately
checkpoint-status | 0a2f86fc-31b0-4e07-8e6b-ba56e1c926b0 |  | checkpoint | Cast Iron Lid Installed and sitting flush
checkpoint-status | 1c6ec73e-e355-4097-86c8-14e775d42412 |  | checkpoint | Sign Off on Completed Work (Council etc)
checkpoint-group | 50fa77a7-04fd-4afa-ac01-0802ce310007 |  | section | Backfill
checkpoint-status | 8fce1c6b-884e-49ce-a1f3-ee9fed74e7e8 |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status | f2748008-167e-4608-8609-7b7dfe4859e7 |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status | 0501719d-a55a-4a51-b2d1-04500282feab |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status | 9ebf7c5c-a1f8-4a81-9e46-19f916e00195 |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closed out
checkpoint-status | 8fedf9af-adaf-4511-8930-30967ec54921 |  | checkpoint | General photos and observations during backfill
checkpoint-status | 3cced3e2-aee9-4b17-8844-a9dd429f3e14 |  | checkpoint | Backfill completed correctly and heights checked/ correct
checklist-flat | e4225935-74a9-4a1b-9a5b-1265c10cadc5 |  | checklist | As Built |  |  |  |  | Yes | As Built | 0989f63e-fb5e-4e29-a9ae-12f162f8ec27
checkpoint-status | 99e473a1-1d77-4efe-9f83-976594056f59 |  | checkpoint | As built Pipework complete and ready for sign off
checklist-flat | 27827a81-a48f-4485-8a79-9de121793a03 |  | checklist | Cesspit Installation |  |  |  |  | Yes | Cesspit Installation | 0b3089f2-15e3-4ad1-bbe8-3b6633b5f3f1
checkpoint-status | 69f471ca-c4d7-4665-9662-fa9cb59f7d2e |  | checkpoint | Setout & position checked and confirmed
checkpoint-status | afa3efd0-8541-4e45-ac83-e169085f9b68 |  | checkpoint | Cesspit installed as per standards
checkpoint-status | 7b13ac7d-3482-4f3e-bfdb-7bac59255f20 |  | checkpoint | Setout & position checked and confirmed
checkpoint-status | d87496b6-d2b3-4022-9f36-30ccbd4d07c2 |  | checkpoint | All cut pipes epoxied
checkpoint-status | d07c6c30-107a-43ee-adac-1dd94bc4dcc5 |  | checkpoint | Confirm Levels Correct
checkpoint-status | 75cb1f99-05ce-430a-9a65-7785994b0a46 |  | checkpoint | Cesspit cleaned of all Debris
checkpoint-status | ee917ee0-b603-47a4-81a0-88d3abf9d8b3 |  | checkpoint | Concrete Apron installed (if required)
checkpoint-status | 44daec64-a1c8-4c32-873b-bdc31949b149 |  | checkpoint | Frame & Grate alignment checked
checkpoint-status | d36638bd-4718-4e51-83d0-b29f2573affb |  | checkpoint | Minimum sump depth checked
checkpoint-status | 73543494-8fe3-4c09-8f10-1bedac639ff9 |  | checkpoint | Captive Grates installed (if required)
checkpoint-status | 2545730f-310a-4b61-9e3b-d6eae97c1214 |  | checkpoint | Cesspit complete & ready for sign off
checklist-flat | 1b2afe89-27e1-4d12-bca7-f65d5f89dc94 |  | checklist | Below Ground Services Checklist |  |  |  |  | Yes | Below Ground Services Checklist | 0e047bd1-13f9-4146-8cfe-a7f16eab701d
checkpoint-status | ba482a56-d212-4699-9e1a-4b0e5c351a20 |  | checkpoint | Pre-Installation
checkpoint-status | fcc8a262-2a73-4518-a7f6-5f1db1392104 |  | checkpoint | Pre-Installation checks complete
checkpoint-status | ed83189f-79a8-4f9f-84a5-bcdbf0bc81ea |  | checkpoint | Drawing Red No:
checkpoint-status | c9d84188-c21b-48f4-bd56-1a11499ad0e5 |  | checkpoint | Starting Point:
checkpoint-status | b581fbb2-28f8-4afa-a3ab-2c800ce28fc2 |  | checkpoint | Finishing Point Established
checkpoint-status | 47f23427-08bf-4611-9ac5-fcf385d47ea7 |  | checkpoint | Grade of Pre-Line%
checkpoint-status | 9b8a5236-4350-4056-add5-c32d5b324442 |  | checkpoint | Level Obtained
checkpoint-status | adcc9105-2cf3-4d75-ac02-22feb70ec338 |  | checkpoint | Installation
checkpoint-status | 239b79e9-930c-42b6-acb8-53235ff13715 |  | checkpoint | Pipe Work Tested
checkpoint-status | 27d0d1c1-eb9e-421e-9042-8dc22ffc7dd3 |  | checkpoint | Air
checkpoint-status | 7e8374a4-760a-4a4d-a6e7-4994b21ae10f |  | checkpoint | Water
checkpoint-status | ed5c2e7c-9c03-43fc-8021-3923d12ba12e |  | checkpoint | Visual
checkpoint-status | 85db7899-7710-498a-a9fa-6503942a076e |  | checkpoint | Backfill Material
checkpoint-status | a0efc86e-9b57-451d-8fcd-45643e9ee411 |  | checkpoint | Local Authority Inspection Passed
checkpoint-status | 6dbd56b6-955e-492f-8305-d546e88f8c6c |  | checkpoint | Name of Inspector:
checklist-sectioned | c090580a-4904-4cbe-8149-9c7476b0433d |  | checklist | Services Trench Checklist |  |  |  |  | Yes | Services Trench Checklist | 1b0d798d-0b0a-47ee-820a-c0fa71e25d9e
checkpoint-group | 1fda1255-c916-456c-96f9-2d8167dfa6e3 |  | section | Trench Excavation
checkpoint-status | 449084a5-0f2b-489c-9a16-797e54bdf98b |  | checkpoint | Latest consented drawings
text | 402e62da-ff9c-5f20-87e2-5ffecdaedc6a |  | textbox | Drawing Ref No.
text | 0669519d-38e1-5afb-aabb-5fc9bf3a289c |  | textbox | Trench type
checkpoint-status | 8ca33564-5418-4ae9-bbf3-738d624b28d4 |  | checkpoint | Setout completed checked and accurate
checkpoint-status | 31c9f39a-a33a-495e-a048-a65f0323aa37 |  | checkpoint | Excavation Accurate - Location & Depth
checkpoint-status | c415d2a1-f4ee-4277-af56-a8c5f72d08ef |  | checkpoint | Ground Conditions Checked & Acceptable
checkpoint-status | ae4e20f2-c24d-4f52-af83-3132a503e68a |  | checkpoint | Bedding depth and material correct
checkpoint-status | c0f7f464-8f15-4070-a80d-99a43dba083c |  | checkpoint | Services laid as per detail - attach relevant cross section
boolean | c1e4c960-3e31-54b8-aa27-c426a50b61e3 |  | tickbox | Bedding Sound
boolean | 609e88a3-aa43-5ef8-9866-02ddcb9b8a08 |  | tickbox | Soil Removed
boolean | 115e61f9-2021-533e-9184-3d703bb9d8e0 |  | tickbox | Trench Compacted
boolean | be587e9f-de7f-52b4-a84c-09ac7f0998fd |  | tickbox | Hard Filled
checkpoint-status | d1a7e657-dec6-426f-9b64-e204219fab4a |  | checkpoint | Area of Work Inspection Completed & Sign Off
text | 10562310-a2bc-55c8-ba91-31c38708e51e |  | textbox | Sign Off By
text | 7979ce5b-8c95-567b-a8d4-17947cc23453 |  | textbox | Acknowledgement of checklist by
text | 8ea17b4e-9faa-5b2b-8ef1-89796743d5f2 |  | textbox | Foreman
checkpoint-group | e8370e4a-64b8-4469-ab63-d9a81dbcff59 |  | section | Backfill
checkpoint-status | e0537b7a-2c73-4b5b-b17c-f15e735c7c7d |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status | d558d4e4-36bd-4565-ad68-b01000b30115 |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status | 03c55fae-be60-4d10-9286-190db944e0da |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status | eea995e7-8fef-4b18-bf03-9b3b933d46a6 |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closed out
checkpoint-status | d7bde71d-3961-4ce8-b07a-ae5d131118c7 |  | checkpoint | General photos and observations during backfill
checkpoint-status | 23919324-1fb3-4fc6-a604-022f421d782a |  | checkpoint | Backfill completed correctly and heights checked/ correct
checklist-flat | c13c9711-9589-470f-92e6-7ed30752c2a4 |  | checklist | Drainage As Built Details |  |  |  |  | Yes | Drainage As Built Details | 1f9b7d8f-2979-41a4-a167-cf32ede6eab1
checkpoint-status | 83b5f651-9f32-479f-a109-d729102e17eb |  | checkpoint | As built Pipework complete and ready for sign off
checkpoint-status | b6eb7558-bedf-41ff-a821-5658b8251919 |  | checkpoint | Pipe Diam (mm)
checkpoint-status | 2973b4e0-2e95-4a87-82de-51d206ba923c |  | checkpoint | Pipe Length from MH Centres(mm)
checkpoint-status | 752cb585-e7a5-4488-b3f7-40357ca83e2e |  | checkpoint | Pipe Type
checkpoint-status | 256ff914-42aa-44d6-8ee2-a73bd6d80a08 |  | checkpoint | Pipe Supplier
checklist-sectioned | 1096c840-db21-4f47-b65d-18705aa1c935 |  | checklist | Weekly Safety Inspection |  |  |  |  | Yes | Weekly Safety Inspection | 29c955a9-22b9-40bd-a794-918a12a01d63
checkpoint-group | a916d636-d326-4be7-9496-91ffbd803791 |  | section | Site Control
checkpoint-status | 8bc1c732-4065-4cdb-8b9d-66f083f38533 |  | checkpoint | Hazard board and signage up-to-date
checkpoint-status | 15ef482a-8c05-4088-84fb-35525bac82c6 |  | checkpoint | Environmental plan - issues
text | 1733e9e6-dd28-5336-977d-de35dfd3aabe |  | textbox | Toolbox meeting last date
checkpoint-status | bf4cc1b7-6048-4232-8e31-8c9f18ca781f |  | checkpoint | Safety inductions for all on site
checkpoint-status | 26877c05-42f8-465c-8cfe-a05874bc9589 |  | checkpoint | Safety notice board current
checkpoint-group | d8fc0a6f-ee60-4250-8f84-490e28bea3cd |  | section | Site Facilities
checkpoint-status | f029ab87-100b-47b5-97e2-f4f63ef854ea |  | checkpoint | Offices-Clean, adequate and good lighting
checkpoint-status | 040fa55c-6012-490a-a652-ecefbf543f59 |  | checkpoint | Smoko sheds-clean portable water
checkpoint-status | 587b9f26-2987-4c99-a580-3c58efb63fdf |  | checkpoint | Toilets-Clean, Washing water
checkpoint-status | 48392658-e1c7-408b-b275-7e7472ae7fd9 |  | checkpoint | Tool/equipment sheds adequate
checkpoint-group | 6731767e-31f6-40c5-8208-294d1f18c4e2 |  | section | General Site Tidiness and Access ways
checkpoint-status | ce56b2b8-09ba-4189-8aa5-880d63c0a4ce |  | checkpoint | Clear access to work areas
checkpoint-status | 7578bfc8-f229-48ab-9c8c-8ed5d02ef09e |  | checkpoint | Stairways and access ways clear
checkpoint-status | 3d654c9e-384f-49b1-86d9-b8d7c006cb24 |  | checkpoint | Hoardings/fence and gates secure
checkpoint-status | e1c5fd06-8c47-43c0-b43d-e427fe12a6af |  | checkpoint | Loose materials secure from wind
checkpoint-group | c4afd05a-fa31-497a-a702-9460986ff8bd |  | section | Personal Safety Equipment
checkpoint-status | e449f570-f3c5-40a3-925e-3fca93708298 |  | checkpoint | Signage displayed and legible
checkpoint-status | f8179061-1608-4606-bc92-1a4dbac141f8 |  | checkpoint | Hardhats being worn
checkpoint-status | bb1c8bda-183b-4cf0-8c8c-5db59574e75f |  | checkpoint | Correct footwear being worn
checkpoint-status | 697af41c-1440-4217-a7db-d586951aae2a |  | checkpoint | Glasses/ear muffs/vests/ masks used
checkpoint-group | cd23d45f-431d-4e84-ad60-fecfe557936d |  | section | First Aid/Fire Prevention
checkpoint-status | a4426837-4c28-4e0d-8c05-e428d8613444 |  | checkpoint | First Aid Box available and current
checkpoint-status | 0ed046ae-34bc-42bb-8b9c-884048fc140a |  | checkpoint | Accident Register
checkpoint-status | f42d5def-3f1d-4128-b0b6-49f56ecc24e4 |  | checkpoint | Fire Extinguishers
label | 5395b677-2b7b-5227-b0d7-d4a4369ff918 |  | note | Available
label | 1a5c598a-9782-5362-a530-e1422bda3126 |  | note | Current(12mth)
label | bbc21863-a22e-5101-8a45-3785d5f57dc4 |  | note | Sufficient
checkpoint-status | 5335fe31-691e-4535-bbab-f93518570f30 |  | checkpoint | Evacuation
label | 153212e4-4aae-5647-80bc-0c437e82bde1 |  | note | Procedure Current
label | 18098f41-830a-5708-a4d0-16f99faa3328 |  | note | All emergencies Incl.
checkpoint-group | 133b7656-da0f-45d6-9a8e-5c14b4e5b853 |  | section | Cranes/Hoist/Lifting equipment
checkpoint-status | a8a02b3d-0c7e-4beb-b6bc-74d0e5630a4e |  | checkpoint | Proper lift assessment plan done
checkpoint-status | feaa3f2b-0075-42f1-8e30-98a6126287a1 |  | checkpoint | Crane Certification current
checkpoint-status | a4d8d9b3-b5b9-4b76-aa41-0ca5100c6936 |  | checkpoint | Slings/Chains Certified
checkpoint-status | 56eafc9c-b2ee-486c-bc61-1d4095c80d8a |  | checkpoint | Operator procedures in place
checkpoint-status | f971483b-372b-4d7e-92b0-b0f869831570 |  | checkpoint | Inspections being done
checkpoint-status | b68a3e5f-5b12-4391-9244-53bddfcf53ce |  | checkpoint | Man cage available
checkpoint-status | e54fcfef-7657-4925-8f71-b4704e78936d |  | checkpoint | Emergency plan in place
checkpoint-group | c5026b2c-02ef-44ab-860f-e5a1189185f4 |  | section | Compressed Air Equipment
checkpoint-status | 8e0bf4ef-650b-4435-94d3-52e4b7e92384 |  | checkpoint | In good condition
checkpoint-status | 75b19406-92e5-443a-bcfe-14e5cadb6d5b |  | checkpoint | Appropriate guards fitted
checkpoint-status | 354e6cd2-604b-49e5-aed9-4f8f32f8eedc |  | checkpoint | Trained User
checkpoint-status | 9ed6b0de-4991-4bca-a572-a6a0268f73dd |  | checkpoint | Excavations Correctly shored
checkpoint-group | f6b608ee-c41d-41af-a30b-484ab360c6b8 |  | section | Welding/Gas Cutting
checkpoint-status | 075657e9-ad7f-4d2f-8f28-50f6798e27af |  | checkpoint | Hot works permits being issued
checkpoint-status | 3798e94d-053e-457a-b57a-2a1eba28bcbe |  | checkpoint | Fire extinguishers on hand
checkpoint-status | 1c032eed-cc1f-4a92-a894-f23b9fe304cc |  | checkpoint | Operators using PPE
checkpoint-group | 87d6dde7-2510-422e-8c8e-223369f91e63 |  | section | Electrical Equipment
checkpoint-status | 73c50e42-cc52-4d01-8f7f-75b740573884 |  | checkpoint | Main board lockable/weatherproof
checkpoint-status | 8ed9a143-0b3d-4148-baac-8043e269a292 |  | checkpoint | Current tagged and damage free leads
checkpoint-status | d65e4337-84c9-407e-ba10-52364a0c6418 |  | checkpoint | Current tagged plant
checkpoint-status | 5ec1f4d3-d8a8-4eb0-a5bc-220e29dd4389 |  | checkpoint | Current tagged Lifeguards
checkpoint-status | 776fdabf-67c6-4c87-b9a9-12ab9a967e96 |  | checkpoint | Leads safely placed
checkpoint-status | 8635a59c-e0a3-4424-ad01-3fdd7c36062f |  | checkpoint | Equipment in good condition
checkpoint-status | 030bfb60-534f-45e5-98bd-9635ccbdffb5 |  | checkpoint | Appropriate guards on equipment
checkpoint-status | 59749096-f8b0-4a9e-a709-5e076322f2d3 |  | checkpoint | Adequate temporary lighting
checkpoint-group | 57cdeb7c-41be-490b-bbe9-fbfffdf8ab98 |  | section | Chemicals
checkpoint-status | 6ba4194c-baab-4bcd-8848-affc22fd4fca |  | checkpoint | Correctly Stored
checkpoint-status | b7461d81-cc15-4483-86bf-1b822202d78b |  | checkpoint | MSDS available
checkpoint-status | 742ec8df-4f1f-4872-b442-b7145c988d81 |  | checkpoint | Operators using PPE
checkpoint-group | cb47cb73-fcb7-49ed-aadf-03fd1e8afc8b |  | section | Tools
checkpoint-status | a41577a1-3e3d-46f6-9008-80e5f1acc571 |  | checkpoint | PAT tool WOF current and secure
checkpoint-status | 549296d8-b3bd-4890-b9ba-0c0f6dda8246 |  | checkpoint | Staff trained in tool use (SWPS)
checkpoint-status | 89525ef0-80ae-40b8-b70e-63ca63c89e4a |  | checkpoint | PAT signage on site
checkpoint-group | 28800d07-9a88-4db5-8d44-19bb89ab017a |  | section | Scaffolding
checkpoint-status | 8e1a1cf1-7087-4c36-b8fe-b57352f0c906 |  | checkpoint | Notifiable weekly Scaftag/current
checkpoint-status | e69040e7-b0a8-4a64-bb7e-0fe751dab30f |  | checkpoint | Handrails/mid-rails
checkpoint-status | 6f90e98e-49a5-4170-b9ad-e98b40c57da7 |  | checkpoint | Toe boards
checkpoint-status | c6838f7a-afb1-40ce-a54a-465ab1b47e28 |  | checkpoint | Platforms
checkpoint-status | 47da0e26-6a6a-4ef6-b7df-55164dd61769 |  | checkpoint | Ladders/stairs
checkpoint-status | bd3fc63a-22ec-4b0c-a597-070806e87449 |  | checkpoint | Base sound
checkpoint-status | 1a865257-b384-412a-803a-087237268fed |  | checkpoint | Work platforms clear
checkpoint-status | cb0a034c-90b0-4ca6-9be8-ee5023a786e6 |  | checkpoint | Platforms trip free
checkpoint-status | c5bd9dff-42be-4d2a-979f-140161fc0c0c |  | checkpoint | Planks tied down
checkpoint-status | ec72a559-93ff-49db-839c-6d4d132d770b |  | checkpoint | Headroom clear
checkpoint-status | 3102f6d9-26f9-4610-8d73-396f909490e2 |  | checkpoint | Ties/bracing adequate
checkpoint-group | 3ed58799-e597-4436-8f24-cad0be286e6f |  | section | Ladders
checkpoint-status | afac2cfd-5a9b-4edc-bbc9-752ebb7288ef |  | checkpoint | Good Condition
checkpoint-status | cabdcd31-6667-4c25-a37a-eb019db397a1 |  | checkpoint | Secured top and bottom
checkpoint-status | d4f3a297-42a4-4c19-92f2-2f8d09a506e8 |  | checkpoint | Stays to step ladders
checkpoint-status | ee944e67-9063-4862-b64b-9c84c9b019bb |  | checkpoint | Working 2 Steps down
checkpoint-group | a0b451ef-314b-414b-9704-af3b00e3568c |  | section | Fall Hazards
checkpoint-status | a0d4864a-abfe-48ca-8f58-89e4fa6c022c |  | checkpoint | Floor edges
checkpoint-status | 868b2665-45ad-4f23-b106-b74ff5612c6e |  | checkpoint | Floor openings
checkpoint-status | 27e63365-e8e6-412f-b1f1-aece43170fc6 |  | checkpoint | Lift shafts
checkpoint-status | f0291368-50d4-4a9b-a61a-7d116c19f132 |  | checkpoint | Stairs
checklist-sectioned | edee38a6-f0fa-46b5-9340-b6bb2f2acb26 |  | checklist | Stormwater- Pipeline Installation Checklist |  |  |  |  | Yes | Stormwater- Pipeline Installation Checklist | 47dd7387-806c-429f-a515-ca3b2a971048
checkpoint-group | 76989a2e-2471-4f73-93a5-e44557d40827 |  | section | Pipe Laying
checkpoint-status | dfd429f7-3321-49f9-9a3b-122d959e6945 |  | checkpoint | Latest consented drawings
text | 625f9356-2eaa-5f58-ba90-27f8aca5e514 |  | textbox | Drawing Ref No.
checkpoint-status | 6a38643d-0cc3-49d6-a15d-8678817727dc |  | checkpoint | Setout completed checked and accurate
checkpoint-status | c2b38e59-2e86-482c-a3f3-e780705f8d64 |  | checkpoint | Excavation Accurate - Location & Depth
checkpoint-status | 533d5740-2982-4628-8c7b-7667e1b72bd7 |  | checkpoint | Ground Conditions Checked & Acceptable
checkpoint-status | 871e280a-f48b-428f-b7a1-f1471ece28f7 |  | checkpoint | Bedding depth and material correct
checkpoint-status | 4d4ac16b-4fd0-4698-b212-e00379e3f176 |  | checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
text | baeb7784-3aad-5b48-948d-12f9654de04a |  | textbox | Start Invert
text | cf01b221-033e-5c6c-9458-6794bf4be9ee |  | textbox | Finish Invert
text | 8587cb96-6a0f-5f35-977b-3c090046f4eb |  | textbox | Grade of Pre-Line %
text | c95f51a7-061d-5dd3-9691-b86bd3046e43 |  | textbox | Product Type
checkpoint-status | efbc03d2-7c0e-4c35-aa0d-87fda9b2eff9 |  | checkpoint | Connections to manholes complete and approved
checkpoint-status | 61092098-e008-43ef-ae30-bc80d32295b4 |  | checkpoint | All Downpipes have been checked, installed and approved
text | 028ce431-a3a6-53bc-b93a-a84fb8f466ba |  | textbox | How many installed?
boolean | ba22e421-3afc-5a73-b07b-4b7e282a5f7d |  | tickbox | Location confirmed
boolean | cfb16be6-40e8-5016-bfc8-56d1e65fd811 |  | tickbox | Heights are correct
boolean | a3fd7253-e9f9-5405-b888-2464fd82be12 |  | tickbox | Caps are secure
checkpoint-status | 43f16142-85c9-4399-bbd8-b43488fd01dc |  | checkpoint | All Cess Pits have been checked, installed and approved
text | 08989e43-56d4-52d2-badc-3f85902e1152 |  | textbox | How many installed?
boolean | 0b8a480a-282a-577a-af09-904ab6b87291 |  | tickbox | Location confirmed
boolean | 3162e2d1-9f06-5e01-82ae-e9e193317267 |  | tickbox | Heights are correct
boolean | 24263dc7-2c37-5e18-b308-faf6449ae62e |  | tickbox | Caps are secure
checkpoint-status | c6110cbf-e82a-4eda-b024-db5c25448cee |  | checkpoint | Pipe Laying Completed
checkpoint-status | c8c15fd6-2249-4d2e-85ef-3cfe9a73e31a |  | checkpoint | Laid by
boolean | a962cafe-302f-5cfa-9c0b-14928c6d6bd8 |  | tickbox | Bedding Sound
boolean | c779bfdc-7062-5dde-ad6d-18035517a395 |  | tickbox | Soil Removed
boolean | 55669472-d904-55ff-9fc8-a4d788a30fb1 |  | tickbox | Trench Compacted
boolean | 703f74dd-7145-514c-9f39-2163c325e9f5 |  | tickbox | Hard Filled
checkpoint-status | d26704c8-022f-43e9-bb1f-a95b11b386a5 |  | checkpoint | Install Tests completed, reviewed & approved
text | a745f9d6-2adc-57fa-a2f1-0e99ec8623a8 |  | textbox | Local Authority Inspection Passed
text | 138dcecd-b4cd-5778-aced-e05143a91455 |  | textbox | Name of inspector
text | a393cd3f-a5bd-5831-badc-1155c7763034 |  | textbox | Date
checkpoint-status | a59e55a3-1fbd-4335-8360-0f9e31173ca8 |  | checkpoint | Area of Work Inspection Completed & Sign Off
text | 638b8ad1-a2fb-5443-8e55-f65e01ba09db |  | textbox | Sign Off By
text | b23ecb2d-fe7c-5b3e-9531-607275417501 |  | textbox | Acknowledgement of checklist by
text | 0c90c74a-4164-5c48-b41b-03857cd80de1 |  | textbox | Foreman
checkpoint-group | d40855f7-cb36-49d0-a95a-ec8559acfc7e |  | section | Backfill
checkpoint-status | 1d57420f-f5c9-41d6-88e5-3294e8721f60 |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status | 04cddcec-c4a1-4736-9ca1-76d91a8a9757 |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status | 211df1c1-5033-4bb4-b7ac-8955a43f5b5f |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status | 3b18655c-31f3-4cc0-8840-f0f49e455003 |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closed out
checkpoint-status | 4272242a-0e89-415d-ad0c-c3dee50f377f |  | checkpoint | General photos and observations during backfill
checkpoint-status | 1298166f-fb83-467c-bae9-fdc5cf2fc195 |  | checkpoint | Backfill completed correctly and heights checked/ correct
checklist-flat | 34a8654c-1f52-458e-83cf-fce0515b1fbd |  | checklist | Drainage Installation |  |  |  |  | Yes | Drainage Installation | 5347122f-5db8-4e02-acce-862bf0f888d4
checkpoint-status | 5cc0981e-8fc7-4667-9b01-7833cc086c86 |  | checkpoint | Setout and position checked and confirmed
checkpoint-status | 21c56e71-c121-40fa-bf91-d0069f0fadf4 |  | checkpoint | Trench width and lid level (attach photos)
checkpoint-status | 4c6b5f1f-a673-4422-ba06-53be03721fb0 |  | checkpoint | Gap 10 & 65 measured and ordered
checkpoint-status | d7700422-a1dd-400f-a346-69a6b650a50d |  | checkpoint | Stockpiles & cart out confirmed
checkpoint-status | 95953fce-6037-4295-bc47-e076eebee08a |  | checkpoint | Pipework installed as per specification
checkpoint-status | 85447de1-ab76-4626-94a8-c1aa325012a2 |  | checkpoint | Pipe test booked and test ready
checkpoint-status | 4e654c8b-db5d-4b5b-b173-7dd89fae1f34 |  | checkpoint | CCTV complete
checkpoint-status | 0eda533d-685f-461c-bc8c-62f9af12c1b5 |  | checkpoint | As built plans complete
checkpoint-status | d7079536-e7ca-4ba0-ac06-435dd9ecf07e |  | checkpoint | Clegg test on hardfill (results recorded)
checkpoint-status | 2d249972-ff36-48ce-aad1-4a6f05db5d3b |  | checkpoint | RON & CAR signed off
checkpoint-status | 1c0c2634-0e4d-4e8e-9ca9-88fbd6693dd8 |  | checkpoint | Pipework complete & ready for sign off
checklist-flat | f660dd93-ad12-4087-9f32-29f658e58dae |  | checklist | Civil Checklist |  |  |  |  | Yes | Civil Checklist | 7e462027-8cf4-4aea-93d4-d86741620b87
checkpoint-status | 60eef94d-0fe2-463b-9067-bb15bea35a44 |  | checkpoint | Foundation Set Out (Comment, pass or not)
checkpoint-status | d98b50c5-b05f-40e4-be1c-d2c9a1c79d2c |  | checkpoint | Confirm Levels Correct (pass or not)
checkpoint-status | 60205788-e041-4f36-a2e1-96e9e795fc0d |  | checkpoint | Backfill
checkpoint-status | 38c469d1-ce33-4fdd-bdd7-94995d9b1177 |  | checkpoint | As Built
checklist-flat | f721bbd7-1c9d-42a8-a34a-dfcc63d9e743 |  | checklist | Connection Checklist |  |  |  |  | Yes | Connection Checklist | 82ad13f4-670c-4693-9edc-ef3c1e8011dd
checkpoint-status | 71e3461c-420f-4563-88eb-cf97ac5da5a6 |  | checkpoint | Approval given to connect
checkpoint-status | df81febb-8c2c-494c-acc6-d78fa97ecf19 |  | checkpoint | Heights confirmed - Invert level
checkpoint-status | f947b5fa-ab2a-4d90-996a-36ae02431ec7 |  | checkpoint | General comments & photos during installation
checkpoint-status | d28de23a-c4f1-4ca7-90a7-4b979fc381c1 |  | checkpoint | Connection completed
checklist-flat | 91047ece-70b6-4c4e-8eb1-026ccc03d18d |  | checklist | Civil Install Checklist |  |  |  |  | Yes | Civil Install Checklist | 841763f0-3185-424d-8b49-420fcd0e63f9
checkpoint-status | da5b83d6-a52b-4661-8d97-e7814956ba57 |  | checkpoint | Foundation Set out
checkpoint-status | 0dedcbde-3839-4edd-9a7a-a735f9fdfb49 |  | checkpoint | Confirm Levels Correct
checklist-sectioned | 1626da16-ebcf-491e-80dd-98054f51ab46 |  | checklist | Firemain- Pipeline Installation Checklist |  |  |  |  | Yes | Firemain- Pipeline Installation Checklist | 953f18e2-87ee-4bc3-827a-d59115a19e65
checkpoint-group | 8da15ad8-e6b1-4008-8d48-7e3b69fc2eaa |  | section | Pipe Laying
checkpoint-status | 56d0170e-66f5-4262-b5a7-06e1ed1830ca |  | checkpoint | Latest consented drawings
text | 9c8efb61-e000-5397-bfda-0d266adf84f3 |  | textbox | Drawing Ref No.
checkpoint-status | da86af9f-83e2-4f61-82df-ecc35033a77b |  | checkpoint | Setout completed checked and accurate
checkpoint-status | abfa5adc-e768-443f-ac4a-aeac2e519643 |  | checkpoint | Excavation Accurate - Location & Depth
checkpoint-status | 2b7c5b37-c18f-4339-acc9-ee1a3de9bbba |  | checkpoint | Ground Conditions Checked & Acceptable
checkpoint-status | b198804b-aaac-4798-b6bf-8816116b87a1 |  | checkpoint | Bedding depth and material correct
checkpoint-status | 81771d57-0a56-4348-8073-0f9b7d981c48 |  | checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
text | 2d5f18e8-273b-55f6-8a7b-9947358badc2 |  | textbox | Start Invert
text | 2510d478-3388-5ab1-8bfd-0b30a06aad6f |  | textbox | Finish Invert
text | 96e9488d-62fe-5615-835f-6f2a60d0e253 |  | textbox | Grade of Pre-Line %
text | 721a6453-d08a-534e-a64b-3673c10d7a97 |  | textbox | Product Type
checkpoint-status | f1cd6e9d-b3b8-4b49-81aa-799f88ccb138 |  | checkpoint | Install Tests completed, reviewed & approved
text | 746ebd9c-14f8-5b66-96be-a6cbd7afa754 |  | textbox | Local Authority Inspection Passed
text | 94f2e706-da73-5160-83f1-4b5d01804acd |  | textbox | Name of inspector
text | 061fdd32-a8ff-5ce2-ab94-fd1e216c3622 |  | textbox | Date
checkpoint-status | 0cdf874d-485c-47db-88b1-c040db69ec45 |  | checkpoint | Pipe Laying Completed
checkpoint-status | 4048d524-c447-48cb-8ec8-92b7b2bec6b2 |  | checkpoint | Laid by
boolean | 13e132fe-df39-52e7-8c58-d27f3b10c2f3 |  | tickbox | Bedding Sound
boolean | 82336003-3f43-573a-b9cc-0725d2a0a607 |  | tickbox | Soil Removed
boolean | 8a0cd60e-bb02-5865-bb67-7a8e36630712 |  | tickbox | Trench Compacted
boolean | 97661d30-7dab-595b-b0b0-3efd2e9546f2 |  | tickbox | Hard Filled
checkpoint-status | e190bc43-71a9-45b3-b365-d697d7c1f62c |  | checkpoint | Connections to manholes complete and approved
checkpoint-status | 49669ce7-f237-42ae-8147-c57114613344 |  | checkpoint | Air Test Complete
checkpoint-status | 984a2644-0877-40dd-b4bb-4f5bce092aad |  | checkpoint | Area of Work Inspection Completed & Sign Off
text | e07655b2-ed11-5c25-9d11-67222d224f2d |  | textbox | Sign Off By
text | a825784c-56e2-5bbb-a4a4-708b4067e6dd |  | textbox | Acknowledgement of checklist by
text | 3a7a247f-77f1-5123-b386-ce22f3ce0aac |  | textbox | Foreman
checkpoint-group | c4771a2a-24d2-41cc-9b1a-c994a80788ed |  | section | Backfill
checkpoint-status | f978415b-573e-4b99-bd7e-241790061d06 |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status | fca4442c-e5f8-4b46-b1d3-77e391c75798 |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status | 94390b9f-6383-4f5e-a7ba-1ab3d86e0be1 |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status | 640618e0-2b30-4a38-a3b4-f2c9f2f1efa2 |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closed out
checkpoint-status | a9de66e1-bbc9-40db-93ca-d02f5e4df168 |  | checkpoint | General photos and observations during backfill
checkpoint-status | a6325737-6dd3-4a4e-b16a-d4914f0d7553 |  | checkpoint | Backfill completed correctly and heights checked/ correct
checklist-sectioned | 09f82799-dffa-4488-812e-6c440ab73f4f |  | checklist | Gasmain- Pipeline Installation Checklist |  |  |  |  | Yes | Gasmain- Pipeline Installation Checklist | 95552ea4-e7c9-40ce-80e1-197b8e8e7d5f
checkpoint-group | 010ce64e-36b5-4c7c-9aeb-ca4132908612 |  | section | Pipe Laying
checkpoint-status | dc4ff350-667b-477d-87ad-62b2ea917403 |  | checkpoint | Latest consented drawings
text | dded2b8b-f645-504b-8f63-006b77f7437f |  | textbox | Drawing Ref No.
checkpoint-status | 42e65139-b6c3-45e1-ab01-a1027b32976c |  | checkpoint | Setout completed checked and accurate
checkpoint-status | be79dc8b-62ec-4223-b9c0-76925315506c |  | checkpoint | Excavation Accurate - Location & Depth
checkpoint-status | 8c96021b-b0c0-45cd-ab9e-4406f2e64b20 |  | checkpoint | Ground Conditions Checked & Acceptable
checkpoint-status | 02c57286-f756-497a-8d0d-7a3747d70bec |  | checkpoint | Bedding depth and material correct
checkpoint-status | 1e8b2451-3814-4664-a0e7-7e0e0570febd |  | checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
text | 31dac14c-9689-55fe-8da2-d3a54546af2e |  | textbox | Start Invert
text | 26df1375-fe24-5720-938c-cdd4122ad3bd |  | textbox | Finish Invert
text | 6702b1c8-84eb-59f1-9c18-c6385e48f29e |  | textbox | Grade of Pre-Line %
text | d2b8f1af-f1c1-5391-8518-681e0942004f |  | textbox | Product Type
checkpoint-status | 6196c7f4-450b-485a-b362-307a27bc94ef |  | checkpoint | Install Tests completed, reviewed & approved
text | 5f78cf2e-8309-5778-b370-fc73ea448038 |  | textbox | Local Authority Inspection Passed
text | c5b72ef8-1a46-5850-bb82-878ec9250f18 |  | textbox | Name of inspector
text | 8988cce2-10a7-5895-b483-46b3aedb6656 |  | textbox | Date
checkpoint-status | 855bc66e-77d6-454e-a4a1-6ad6f97bd22b |  | checkpoint | Pipe Laying Completed
checkpoint-status | 98a04fd2-d063-4409-8f76-b158b3a035d5 |  | checkpoint | Laid by
boolean | c0d73506-04e0-5776-babc-d992974428d7 |  | tickbox | Bedding Sound
boolean | 17fe9114-2b38-5cb1-b048-b3e70fbfb560 |  | tickbox | Soil Removed
boolean | 0e42ea43-1d7e-5ec9-8133-6fb4616ee285 |  | tickbox | Trench Compacted
boolean | de0d5cb9-f54e-5424-b911-59580ff9a7f8 |  | tickbox | Hard Filled
checkpoint-status | 9c7e227a-b75d-4fdb-ac56-a81f96be7220 |  | checkpoint | Connections to manholes complete and approved
checkpoint-status | 7b267c3f-107c-41e3-82ab-657342472ca2 |  | checkpoint | Air Test Complete
checkpoint-status | 1e5329ff-515c-462e-9a18-94a5dc6a34f9 |  | checkpoint | Area of Work Inspection Completed & Sign Off
text | 5b0e40aa-cea0-563d-8dba-d757117d5670 |  | textbox | Sign Off By
text | def6571c-e549-52af-b2de-e157c9438ca4 |  | textbox | Acknowledgement of checklist by
text | 9abd618b-fcbe-5b1c-ac04-5c480bf0f97f |  | textbox | Foreman
checkpoint-group | 12be50a8-2ad2-483e-afba-2d31539e15d0 |  | section | Backfill
checkpoint-status | af4a97ef-79ec-4dee-bcfd-6d4b7f41b8d2 |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status | 5b0d82b3-e0c3-4eb8-acfa-13fd8fd6b31b |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status | 567e986f-1fa5-412c-b01d-4aabc110b153 |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status | 60211322-0d32-4abe-afe5-e63527616b55 |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closed out
checkpoint-status | b33db521-3817-48a7-be9e-565b54c4646d |  | checkpoint | General photos and observations during backfill
checkpoint-status | 30c6f24f-0d32-4d3f-a50d-8583ac2c0b1d |  | checkpoint | Backfill completed correctly and heights checked/ correct
checklist-flat | a39d2919-df83-499d-aed3-abf8d66958da |  | checklist | Pressure Test |  |  |  |  | Yes | Pressure Test | 9a7aa57b-73fa-4b85-a968-f293b0f69325
checkpoint-status | 52e06336-08d6-4230-b182-d104045c0737 |  | checkpoint | Test Media(Water/Gas/Fire)
checkpoint-status | 264ea5b3-6bda-4313-b2e3-a19ede5970ea |  | checkpoint | Working Pressure
checkpoint-status | 648925b1-6977-4bbb-b02d-0ecc80a3a485 |  | checkpoint | Test Pressure(PSI/Kpa)
checkpoint-status | cf4b910f-28a3-45ef-a04b-84a49b24af31 |  | checkpoint | Duration of Test (mins)
checkpoint-status | 18089055-f878-48ac-9cd7-1497d3126322 |  | checkpoint | The above systems have been installed and pressure tested
checkpoint-status | 54367477-ab42-4320-a502-ce8dda4682eb |  | checkpoint | Witness Name & Company
checkpoint-status | 8723f6ce-f8b1-4c41-a974-32f6134bfbcb |  | checkpoint | Bassett Representative
checklist-flat | 6ab109eb-44e6-412c-bd46-958b7aaab3c1 |  | checklist | Backfill |  |  |  |  | Yes | Backfill | e3d3a2b2-c5ec-40db-ac74-e772ff2e365c
checkpoint-status | e630f327-16e7-46bb-8c97-31860061c496 |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status | aa7f0849-5605-4d78-aa4e-986cde4d6e68 |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status | ce7ebfca-dfd8-4a41-8905-46406ee7060d |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status | 56eb5cee-1b90-4a93-8ef5-cbf8e877d94a |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closedout
checkpoint-status | 8e222516-0bc4-4d8d-9d12-6d8c7f616b8e |  | checkpoint | General photos and observations during backfill
checkpoint-status | e5b5779b-87b9-4bc8-978d-5d0591400365 |  | checkpoint | Backfill completed correctly and heights checked/ correct
checklist-sectioned | 040dc8b0-7510-4d8c-882c-7ff4be8148be |  | checklist | Sewer- Pipeline Installation Checklist |  |  |  |  | Yes | Sewer- Pipeline Installation Checklist | fa0dc3d5-b84b-4341-aec6-502230ea5d44
checkpoint-group | f22500cc-69a2-4dff-8adb-cc2106ba065d |  | section | Pipe Laying
checkpoint-status | 4bbe689b-278f-47f4-8031-04344bcfa44a |  | checkpoint | Latest consented drawings
text | 26ebe837-c93b-5912-a19c-14b57a2135e6 |  | textbox | Drawing Ref No.
checkpoint-status | 2869715b-ea08-475f-933b-690831b1feb2 |  | checkpoint | Setout completed checked and accurate
checkpoint-status | 0ae9ee17-1a36-4469-b8fe-7e257dc243df |  | checkpoint | Excavation Accurate - Location & Depth
checkpoint-status | 598c502f-e70e-4297-b636-a3aaf1bfc0eb |  | checkpoint | Ground Conditions Checked & Acceptable
checkpoint-status | 79092128-4ea3-42a8-89cd-f7bff2d14a29 |  | checkpoint | Bedding depth and material correct
checkpoint-status | 734f22fc-4ccb-4432-b37b-44e9b9e41b9c |  | checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
text | a96a8fb8-04e8-5ebf-a1a1-dbd0288130dc |  | textbox | Start Invert
text | c6226861-3490-5890-8b5f-2cbd017dcd44 |  | textbox | Finish Invert
text | bf205089-4edf-558f-80b9-5ca04e41a6c3 |  | textbox | Grade of Pre-Line %
text | c8170698-c7d4-51ba-adca-1b44facc94da |  | textbox | Product Type
checkpoint-status | 108b2cff-25b7-4bc6-8a08-ad4801db0f62 |  | checkpoint | Install Tests completed, reviewed & approved
checkpoint-status | 33c12e4e-d261-4329-ae7f-563b4bef300c |  | checkpoint | Local Authority Inspection Passed
text | fccbcd9f-1346-5374-a98d-268c97318ca1 |  | textbox | Name of inspector
text | 9676ec37-5671-575b-9920-72f6a6b6d943 |  | textbox | Date
checkpoint-status | 4341ca05-8c33-4eda-b8d1-92f47b47d687 |  | checkpoint | Pipe Laying Completed
checkpoint-status | 12fc2ecb-59ea-4489-85ec-21abf4875a4e |  | checkpoint | Laid by
boolean | cc3e7138-99d1-5789-9532-48517da6bc8b |  | tickbox | Bedding Sound
boolean | 3aabd47f-eaf4-516a-a43c-c33512be6039 |  | tickbox | Soil Removed
boolean | 5b0cf822-04b6-5074-bc7a-3344444fed32 |  | tickbox | Trench Compacted
boolean | 162c643d-0b89-57e4-9093-f24796c00a71 |  | tickbox | Hard Filled
checkpoint-status | 9d874fd1-553a-4f4f-82eb-cd4ba66175b9 |  | checkpoint | Connections to manholes complete and approved
checkpoint-status | be755ee5-e7d9-4c72-9fbd-0efd196cc7c6 |  | checkpoint | Air Test Complete
checkpoint-status | 573b5498-cdd3-4dfd-a70b-b34d16213e80 |  | checkpoint | Area of Work Inspection Completed & Sign Off
text | 7658e46e-4e83-5eee-8a8f-0e388bc23def |  | textbox | Sign Off By
text | 0239205b-e258-59f0-80d5-81fc9be5e573 |  | textbox | Acknowledgement of checklist by
text | ced49762-502a-56ea-949e-f371b7c073b9 |  | textbox | Foreman
checkpoint-group | 143c3683-39cb-4b5b-9911-2d377d1708b1 |  | section | Backfill
checkpoint-status | 259b656f-f44a-44f7-952a-7f38e2936094 |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status | 67b6ba0b-8375-4e66-8909-09dbb573cda3 |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status | f3030d83-c439-4cf3-b825-cea8e14cea57 |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status | 02e26b91-395c-4728-9d21-097767c55934 |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closed out
checkpoint-status | 16ae05de-d46c-4bc5-935b-a8274a29d789 |  | checkpoint | General photos and observations during backfill
checkpoint-status | 85e38ee4-e019-42ab-8c4a-fc0b4c7b58d1 |  | checkpoint | Backfill completed correctly and heights checked/ correct