## Cover Page
Mechanical Completion - Civil Installation - OTG
Applicability: | C&P - bp pulse
Approver: | Alam Abboud
Approval Date: | 2025-01-28
Author: | Michael Skyrme
Checker: | John Wood
Checker Date: | 2025-01-28
Security Classification: | General
Document Number | EV001-QA-ITR-000-ANZ-0023
Revision Code: | B04
Next Review Date: | 2025-06-01

## Revision Info
Revision History
Rev | Reason for Issue/Revisions | Author | Checker | Checker Date | Approver | Approval Date
B01 | Approved for Use | Andrew Maddams | Gareth Jones | 2022-12-12 | Shane Wilson | 2022-12-12
B02 | Approved for Use [Additional checks added for Excavation. Removed monolithic and anchor bolt checks] | Gareth Jones | Andrew Maddams | 2023-08-31 | Shane Wilson | 2023-08-31
B03 | Approved for Use [Additional checks added for lighting column, bollards, fencing] | Gareth Jones | Andrew Maddams | 2024-06-05 | Shane Wilson | 2024-06-05
B04 | Inclusion of ANZ requirements | Michael Skyrme | John Wood | 2025-01-28 | Alam Abboud | 2025-01-28
Hold References
Hold Reference |  | Description / Reason for Hold |  | Relevant Section(s) of this Document
Operating Management System
OMS Sub-Element |  | OMS Sub-Element Title
4.1 |  | Practices and Procedures
Reviewers
Name |  | Role |  | Date Reviewed | Type of Review
Informative References/Related Documents
Document Number |  | Document Title
EV001-CG-PRO-000-0002 |  | Electric Vehicle Charging Execution Procedure - System handover and acceptance
Unless stated otherwise in the content of this document, reference to the documents above is for information. Specific sections of the referenced documents will be given in the content of this document if conformance is required.
Scope and Exclusions
This document does not include any new mandatory requirements. Any reference to a mandatory requirement in this document cites the source bp Requirement Document. Thus, you should exercise care when relying upon mandatory requirements cited in this document by confirming they have not been modified in a subsequent version of the cited bp Requirement Document.
Use and Interpretation of this document
This document is classified as General unless labelled otherwise. It contains bp proprietary information. bp’s Code of Conduct requires you to protect that information. Refer to the Protecting our Information Policy for more details.
Outside bp, you can only distribute and use this document in accordance with the terms of any agreement under which it was supplied or received. BP accepts no liability or responsibility for the use of this document outside bp, unless an agreement with bp says otherwise.
This document applies only if it is consistent with applicable legal and regulatory requirements. If you are within BP and you identify an apparent conflict with those requirements, you should consult bp Legal.
This document has been approved for BP’s purposes only and not to describe or establish an industry standard or practice. Any recommendations or guidance are to help users to consider and evaluate potential options. Another approach may be appropriate. The authoritative, English version of this document is held online at https://bp-eb.bentley.com/CIS/Framework/Default.aspx. It takes precedence over any prior version and any non-English version.
Copyright © 2022 bp International Ltd. All rights reserved. All rights reserved.

## Civil - OTG ANZ
Project Title:
Site ID, Name & Address:
Mechanical Completion - Civil Checklist
Item # | Information/ Action Needed | Description of Check | Complete (Y / N / N/A) | Verification Signature (Contractor) | Acceptance Criteria (I/T/W/H/R) I – Inspection; T – Test; W – Witness Inspection Point; H – Hold Point for Inspection; R – Document Review |  |  |  | Comments
[5 empty] | Contractor | Contractor Signature& Date | Client | Client Signature& Date
HV Transformer Substation
1 | External Checks (1) | Confirm equipment location matches detailed design |  |  | I |  | I |  | Accredited Service Provider (ASP3) or DNSP where applicable
1 | External Checks (2) | Confirm Transformer enclosure is free from damage |  |  | I |  | I
1 | External Checks (3) | Confirm Transformer enclosure is installed as per manufacturers instructions with the recommended sealant applied between base and foundation |  |  | I |  | I
1 | External Checks (4) | Confirm warning labels and contact numbers are present on the enclosure |  |  | I |  | I
1 | External Checks (5) | Verify foundation is level and installed as per manufacturers instructions |  |  | I |  | I
2 | Construction Checks (1) | Proof rolling and compaction inspections / reports |  |  | I |  | I
2 | Construction Checks (2) | Concrete pre-pour and steel reinforcing inspections / reports (including any earthing/bonding as required) |  |  | I |  | I
2 | Construction Checks | Verify that concrete compressive strength is as per design |  |  | I |  | I |  | Concrete dockets / test cylinders with results at 7, 14 and 28 days post pour
SMSB Foundation
3 | SMSB foundation (1) | Verify location/orientation matches approved design |  |  | W |  | I
3 | SMSB foundation (2) | Verify foundation is level and installed as per manufacturers instructions |  |  | I |  | I
4 | Fixing | Verify SMSB is appropriately fixed in place bolted down in the four fixing points and to required torque value as per manufucturer guidelines |  |  | I |  | I
5 | Construction Checks (1) | Proof rolling and compaction inspections / reports |  |  | I |  | I
5 | Construction Checks (2) | Concrete pre-pour and steel reinforcing inspections / reports |  |  | I |  | I
5 | Construction Checks (3) | Verify that concrete compressive strength is as per design |  |  | I |  | I
LV Pillar Foundation
6 | LV Pillar foundation (1) | Verify location/orientation matches approved design |  |  | W |  | I
6 | LV Pillar foundation (2) | Verify foundation is level and installed as per manufacturers instructions |  |  | I |  | I
7 | Fixing | Verify LV pillar is appropriately fixed in place bolted down in the four fixing points and to required torque value as per manufucturer guidelines |  |  | I |  | I
8 | Construction Checks (1) | Proof rolling and compaction inspections / reports |  |  | I |  | I
8 | Construction Checks (2) | Concrete pre-pour and steel reinforcing inspections / reports |  |  | I |  | I
8 | Construction Checks (3) | Verify that concrete compressive strength is as per design |  |  | I |  | I
Ducting/Conduits
9 | Ducts between power connection and LV Pillar | Size and quantity, Routed, and laid depth as per detail design |  |  | W |  | I |  | Photographs to be taken during construction (to show all stages) and shared. Conduit tracer tape installed in trench.
10 | Ducts between Pillar and EVSE | Size, Routed, and laid depth as per detail design |  |  | W |  | I |  | Photographs to be taken during construction (to show all stages) and shared. Conduit tracer tape installed in trench.
11 | Ducts between Pillar and Retail facility | Size, Routed, and laid depth as per detail design |  |  | W |  | I |  | Photographs to be taken during construction (to show all stages) and shared. Conduit tracer tape installed in trench.
EVSE Foundations
12 | EV Rectifier Foundation (1) | Verifiy the location matches the approved design |  |  | W |  | I
12 | EV Rectifier Foundation (2) | Verify EV Rectifier Unit foundation is installed as per the design drawings |  |  | W |  | I
13 | Construction Checks (1) | Proof rolling and compaction inspections / reports |  |  | I |  | I
13 | Construction Checks (2) | Concrete pre-pour and steel reinforcing inspections / reports |  |  | I |  | I
13 | Construction Checks (3) | Verify that concrete compressive strength is as per design |  |  | I |  | I
14 | EV Charger Foundation/s (1) | Verifiy quantity and location matches the approved design |  |  | W |  | I
14 | EV Charger Foundation/s (2) | Verify EV Charger foundation/s are installed as per the design drawings |  |  | W |  | I
15 | Construction Checks (1) | Proof rolling and compaction inspections / reports |  |  | I |  | I
15 | Construction Checks (2) | Concrete pre-pour and steel reinforcing inspections / reports |  |  | I |  | I
15 | Construction Checks (3) | Verify that concrete compressive strength is as per design |  |  | I |  | I
16 | Bollards are: (1) | Verify bollards are located per design drawing and counts verified (provide protection to EVC) |  |  | I |  | I
16 | Bollards are: (2) | Verify bollards are installed as per the design drawings |  |  | I |  | I
16 | Bollards are: (3) | Pass pull test / unable to be lifed out by hand |  |  | I |  | I
17 | Drawpits and Cable Chambers (1) | Located as per design |  |  | I |  | I
17 | Drawpits and Cable Chambers (2) | Installed as per design/manufactures installation instructions (Appropriate Duct glands are installed where required) |  |  | W |  | I
Miscellaneous Site Civil
18 | Excavations | Confirm excavations through surfaces have been satisfactorily reinstated as per AFC drawings |  |  | W |  | W
19 | Joint Sealing | All required edge sealing/over banding completed satisfactorily |  |  | W |  | I
20 | New kerb / gutter footpath per plans | Concrete is consistent and installed to match existing appearance and levels |  |  | I |  | I
21 | Existing kerb / gutter sidewalk undamaged | No damage to existing kerb/gutters |  |  | I |  | I
22 | Landscaping removed/damaged during construction | Replacement match what was damaged/removed |  |  | I |  | I |  | Note - removed grass shall be re-seeded
23 | Air & Water Station Relocation | Verify air & water station has been moved to agreed new location and is functioning after relocation |  |  | W |  | I
24 | Lighting Columns | Installed as per detail design and have been installed such that the access panel is facing away from oncoming traffic |  |  | W |  | I
25 | Wheel stops are installed per drawings | Dimensions, height and width are per drawings |  |  | I |  | I
26 | Parking signage complete per plans | Confirm the height of sign posts above grade is accurate and matches drawings |  |  | I |  | I
27 | Signage footings | Inspection of signage footings confirming conformance with certified design |  |  | W |  | I
28 | Signage complete | Vendor signage installation checklists completed by installation contractor |  |  | I |  | I
29 | Fencing | If fencing has been installed e.g. around the LVP, has been treated with fence paint |  |  | I |  | I
30 | Site clean-up | All debris removed. Housekeeping maintained to minimize disruption |  |  | I |  | I
EV Charging Bay Marking
31 | Verify dimensions match drawings | Depth, length and width are per drawings |  |  | I |  | I
32 | Painted stripes are clean and correct colour | No over spray. Colour is correct and lines are straight. Marking in accordance with approved detail design. |  |  | I |  | I
|  | Name |  |  | Signature |  |  |  | Date
CONTRACTOR
bp Pulse