## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Walkdown Punchlist | [5 empty] | EV Walkdown Punchlist PC Template
section | Details
checkpoint-no-status | Details
textbox | Site Name:
textbox | Date of Site Walk:
textbox | Members Onsite:
textbox | Company Name:
textbox | bp Representative:
label | This list is to be completed during the final site walk with the members mentioned above, the scope equipment document to be referenced during the site walk to ensure all delvierables are completed as per pre-construction site walk
label | Category:
label | Cat "A" - Denotes major items that shall be completed or corrected before equipment can be safely energised for commissioning and/or the site considered "mechanically completed".
label | Cat "B" - Denotes items that shall be completed or corrected before Site Handover and software commissioning of the equipment with the view to going "Live" on the map.
label | Cat "C" - Denotes minor items that can be repaired,completed or corrected on the day of commissioning such that full handover can take place.
section | Walkdown Punchlist
checkpoint | Item #1
textbox | Item Description
textbox | Actioned By
textbox | Category (A/B/C)
textbox | Responsibility to Close Out.
checkpoint | Item #2
textbox | Item Description
textbox | Actioned By
textbox | Category (A/B/C)
textbox | Responsibility to Close Out.
checkpoint | Item #3
textbox | Item Description
textbox | Actioned By
textbox | Category (A/B/C)
textbox | Responsibility to Close Out.
checkpoint | Item #4
textbox | Item Description
textbox | Actioned By
textbox | Category (A/B/C)
textbox | Responsibility to Close Out.
checkpoint | Item #5
textbox | Item Description
textbox | Actioned By
textbox | Category (A/B/C)
textbox | Responsibility to Close Out.
checkpoint | Item #6
textbox | Item Description
textbox | Actioned By
textbox | Category (A/B/C)
textbox | Responsibility to Close Out.
checkpoint | Item #7
textbox | Item Description
textbox | Actioned By
textbox | Category (A/B/C)
textbox | Responsibility to Close Out.
checkpoint | Item #8
textbox | Item Description
textbox | Actioned By
textbox | Category (A/B/C)
textbox | Responsibility to Close Out.
checkpoint | Item #9
textbox | Item Description
textbox | Actioned By
textbox | Category (A/B/C)
textbox | Responsibility to Close Out.
checkpoint | Item #10
textbox | Item Description
textbox | Actioned By
textbox | Category (A/B/C)
textbox | Responsibility to Close Out.
checkpoint | Item #11
textbox | Item Description
textbox | Actioned By
textbox | Category (A/B/C)
textbox | Responsibility to Close Out.
checkpoint | Item #12
textbox | Item Description
textbox | Actioned By
textbox | Category (A/B/C)
textbox | Responsibility to Close Out.
checkpoint | Item #13
textbox | Item Description
textbox | Actioned By
textbox | Category (A/B/C)
textbox | Responsibility to Close Out.
checkpoint | Item #14
textbox | Item Description
textbox | Actioned By
textbox | Category (A/B/C)
textbox | Responsibility to Close Out.
checkpoint | Item #15
textbox | Item Description
textbox | Actioned By
textbox | Category (A/B/C)
textbox | Responsibility to Close Out.
checkpoint | Item #16
textbox | Item Description
textbox | Actioned By
textbox | Category (A/B/C)
textbox | Responsibility to Close Out.
checkpoint | Item #17
textbox | Item Description
textbox | Actioned By
textbox | Category (A/B/C)
textbox | Responsibility to Close Out.
checkpoint | Item #18
textbox | Item Description
textbox | Actioned By
textbox | Category (A/B/C)
textbox | Responsibility to Close Out.
checkpoint | Item #19
textbox | Item Description
textbox | Actioned By
textbox | Category (A/B/C)
textbox | Responsibility to Close Out.
checkpoint | Item #20
textbox | Item Description
textbox | Actioned By
textbox | Category (A/B/C)
textbox | Responsibility to Close Out.
section | Signoff
checkpoint | Contractor confirms all RFIs related to the site commissioning and closeout have been reviewed and closed. bp Pulse confirm that all Defects and ITR Documentation have been completed for this Project.
date | Site has now reached Practical Completion on:
textbox | bp Representative: NAME
textbox | Contractor Representative: NAME
holdpoint | SIGNED
checklist | EV001-QA-ITR-000-ANZ-0023_B03_Mech Completion Civil Installation | [5 empty] | EV001-QA-ITR-000-ANZ-0023_B03_Mech Completion Civil Installation
section | HV Transformer Substation
checkpoint | 1 - External Checks (1)
label | Description of Check - Confirm equipment location matches detailed design
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
label | Comments - Accredited Service Provider (ASP3) or DNSP where applicable
checkpoint | 1 - External Checks (2)
label | Description of Check - Confirm Transformer enclosure is free from damage
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 1 - External Checks (3)
label | Description of Check - Confirm Transformer enclosure is installed as per manufacturers instructions with the recommended sealant applied between base and foundation
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 1 - External Checks (4)
label | Description of Check - Confirm warning labels and contact numbers are present on the enclosure
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 1 - External Checks (5)
label | Description of Check - Verify foundation is level and installed as per manufacturers instructions
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 2 - Construction Checks (1)
label | Description of Check - Proof rolling and compaction inspections / reports
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 2 - Construction Checks (2)
label | Description of Check - Concrete pre-pour and steel reinforcing inspections / reports (including any earthing/bonding as required)
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 2 - Construction Checks
label | Description of Check - Verify that concrete compressive strength is as per design
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
label | Comments - Concrete dockets / test cylinders with results at 7, 14 and 28 days post pour
section | SMSB Foundation
checkpoint | 3 - SMSB foundation (1)
label | Description of Check - Verify location/orientation matches approved design
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
checkpoint | 3 - SMSB foundation (2)
label | Description of Check - Verify foundation is level and installed as per manufacturers instructions
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 4 - Fixing
label | Description of Check - Verify SMSB is appropriately fixed in place bolted down in the four fixing points and to required torque value as per manufucturer guidelines
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 5 - Construction Checks (1)
label | Description of Check - Proof rolling and compaction inspections / reports
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 5 - Construction Checks (2)
label | Description of Check - Concrete pre-pour and steel reinforcing inspections / reports
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 5 - Construction Checks (3)
label | Description of Check - Verify that concrete compressive strength is as per design
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
section | LV Pillar Foundation
checkpoint | 6 - LV Pillar foundation (1)
label | Description of Check - Verify location/orientation matches approved design
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
checkpoint | 6 - LV Pillar foundation (2)
label | Description of Check - Verify foundation is level and installed as per manufacturers instructions
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 7 - Fixing
label | Description of Check - Verify LV pillar is appropriately fixed in place bolted down in the four fixing points and to required torque value as per manufucturer guidelines
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 8 - Construction Checks (1)
label | Description of Check - Proof rolling and compaction inspections / reports
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 8 - Construction Checks (2)
label | Description of Check - Concrete pre-pour and steel reinforcing inspections / reports
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 8 - Construction Checks (3)
label | Description of Check - Verify that concrete compressive strength is as per design
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
section | Ducting/Conduits
checkpoint | 9 - Ducts between power connection and LV Pillar
label | Description of Check - Size and quantity, Routed, and laid depth as per detail design
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
label | Comments - Photographs to be taken during construction (to show all stages) and shared. Conduit tracer tape installed in trench.
checkpoint | 10 - Ducts between Pillar and EVSE
label | Description of Check - Size, Routed, and laid depth as per detail design
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
label | Comments - Photographs to be taken during construction (to show all stages) and shared. Conduit tracer tape installed in trench.
checkpoint | 11 - Ducts between Pillar and Retail facility
label | Description of Check - Size, Routed, and laid depth as per detail design
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
label | Comments - Photographs to be taken during construction (to show all stages) and shared. Conduit tracer tape installed in trench.
section | EVSE Foundations
checkpoint | 12 - EV Rectifier Foundation (1)
label | Description of Check - Verifiy the location matches the approved design
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
checkpoint | 12 - EV Rectifier Foundation (2)
label | Description of Check - Verify EV Rectifier Unit foundation is installed as per the design drawings
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
checkpoint | 13 - Construction Checks (1)
label | Description of Check - Proof rolling and compaction inspections / reports
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 13 - Construction Checks (2)
label | Description of Check - Concrete pre-pour and steel reinforcing inspections / reports
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 13 - Construction Checks (3)
label | Description of Check - Verify that concrete compressive strength is as per design
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 14 - EV Charger Foundation/s (1)
label | Description of Check - Verifiy quantity and location matches the approved design
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
checkpoint | 14 - EV Charger Foundation/s (2)
label | Description of Check - Verify EV Charger foundation/s are installed as per the design drawings
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
checkpoint | 15 - Construction Checks (1)
label | Description of Check - Proof rolling and compaction inspections / reports
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 15 - Construction Checks (2)
label | Description of Check - Concrete pre-pour and steel reinforcing inspections / reports
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 15 - Construction Checks (3)
label | Description of Check - Verify that concrete compressive strength is as per design
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 16 - Bollards are: (1)
label | Description of Check - Verify bollards are located per design drawing and counts verified (provide protection to EVC)
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 16 - Bollards are: (2)
label | Description of Check - Verify bollards are installed as per the design drawings
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 16 - Bollards are: (3)
label | Description of Check - Pass pull test / unable to be lifed out by hand
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 17 - Drawpits and Cable Chambers (1)
label | Description of Check - Located as per design
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 17 - Drawpits and Cable Chambers (2)
label | Description of Check - Installed as per design/manufactures installation instructions (Appropriate Duct glands are installed where required)
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
section | Miscellaneous Site Civil
checkpoint | 18 - Excavations
label | Description of Check - Confirm excavations through surfaces have been satisfactorily reinstated as per AFC drawings
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - W
checkpoint | 19 - Joint Sealing
label | Description of Check - All required edge sealing/over banding completed satisfactorily
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
checkpoint | 20 - New kerb / gutter footpath per plans
label | Description of Check - Concrete is consistent and installed to match existing appearance and levels
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 21 - Existing kerb / gutter sidewalk undamaged
label | Description of Check - No damage to existing kerb/gutters
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 22 - Landscaping removed/damaged during construction
label | Description of Check - Replacement match what was damaged/removed
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
label | Comments - Note - removed grass shall be re-seeded
checkpoint | 23 - Air & Water Station Relocation
label | Description of Check - Verify air & water station has been moved to agreed new location and is functioning after relocation
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
checkpoint | 24 - Lighting Columns
label | Description of Check - Installed as per detail design and have been installed such that the access panel is facing away from oncoming traffic
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
checkpoint | 25 - Wheel stops are installed per drawings
label | Description of Check - Dimensions, height and width are per drawings
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 26 - Parking signage complete per plans
label | Description of Check - Confirm the height of sign posts above grade is accurate and matches drawings
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 27 - Signage footings
label | Description of Check - Inspection of signage footings confirming conformance with certified design
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
checkpoint | 28 - Signage complete
label | Description of Check - Vendor signage installation checklists completed by installation contractor
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 29 - Fencing
label | Description of Check - If fencing has been installed e.g. around the LVP, has been treated with fence paint
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 30 - Site clean-up
label | Description of Check - All debris removed. Housekeeping maintained to minimize disruption
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
section | EV Charging Bay Marking
checkpoint | 31 - Verify dimensions match drawings
label | Description of Check - Depth, length and width are per drawings
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 32 - Painted stripes are clean and correct colour
label | Description of Check - No over spray. Colour is correct and lines are straight. Marking in accordance with approved detail design.
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
section | Signoff
checkpoint | CONTRACTOR
holdpoint | Signature
checkpoint | bp Pulse
holdpoint | Signature
checklist | EV001-QA-ITR-000-ANZ-0024_B01 Mech Completion - Electrical Installation | [5 empty] | EV001-QA-ITR-000-ANZ-0024_B01 Mech Completion - Electrical Installation
section | SMSB
checkpoint | 1 - SMSB - Set-up & Installation (1)
label | Description of Check - Record Serial Number
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
textbox | Comments - Serial Number:
checkpoint | 1 - SMSB - Set-up & Installation (2)
label | Description of Check - Confirm SMSB has been installed as per manufactuers installation instructions (IOM)
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 1 - SMSB - Set-up & Installation (3)
label | Description of Check - Confirm SMSB is free from damage and paintwork is in good order with no scratches.
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
checkpoint | 1 - SMSB - Set-up & Installation (4)
label | Description of Check - Required padlocks fitted with correct code applied. If applicable, client keys handed to bp PM.
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 1 - SMSB - Set-up & Installation (5)
label | Description of Check - Confirm cubicle doors can be fully opened without obstruction and door hinges are installed correctly. Confirm door seals are free from damage.
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 1 - SMSB - Set-up & Installation (6)
label | Description of Check - Confirm internal equipment is clean and dry. Check that all preservation (i.e. silica gel) has been removed (require prior to energisation)
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 1 - SMSB - Set-up & Installation (7)
label | Description of Check - Confirm all equipment carries the correct label identification
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 1 - SMSB - Set-up & Installation (8)
label | Description of Check - Confirm LV cable terminations are completed correctly and are torqued as per IOM with torque markings present
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
checkpoint | 1 - SMSB - Set-up & Installation (9)
label | Description of Check - Confirm lifting lugs have been removed from SMSB and stowed inside panel
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 1 - SMSB - Set-up & Installation (10)
label | Description of Check - Confirm all warning labels and customer information labels are present on the SMSB.
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 1 - SMSB - Set-up & Installation (11)
label | Description of Check - Thermographic inspection of switchboards has been completed
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
label | Comments - Once PSSR Complete and LV Pillar under load
section | LV Pillar
checkpoint | 1 - LV Pillar - Set-up & Installation (1)
label | Description of Check - Record Serial Number
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
textbox | Comments - Serial Number:
checkpoint | 1 - LV Pillar - Set-up & Installation (2)
label | Description of Check - Confirm LVP has been installed as per manufactuers installation instructions (IOM)
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 1 - LV Pillar - Set-up & Installation (3)
label | Description of Check - Confirm LVP is free from damage and paintwork is in good order with no scratches.
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
checkpoint | 1 - LV Pillar - Set-up & Installation (4)
label | Description of Check - Required padlocks fitted with correct code applied?
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 1 - LV Pillar - Set-up & Installation (5)
label | Description of Check - Confirm cubicle doors can be fully opened without obstruction and door hinges are installed correctly. Confirm door seals are free from damage.
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 1 - LV Pillar - Set-up & Installation (6)
label | Description of Check - Confirm internal equipment is clean and dry. Check that all preservation (i.e. silica gel) has been removed (require prior to energisation)
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 1 - LV Pillar - Set-up & Installation (7)
label | Description of Check - Confirm all equipment carries the correct label identification
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 1 - LV Pillar - Set-up & Installation (8)
label | Description of Check - Confirm LV cable terminations are completed correctly and are torqued as per IOM with torque markings present
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
checkpoint | 1 - LV Pillar - Set-up & Installation (9)
label | Description of Check - Confirm lifting lugs have been removed from LV pillar and stowed inside panel
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 1 - LV Pillar - Set-up & Installation (10)
label | Description of Check - Confirm the 24VDC battery fuse is present and is in the stowed position (socket provided at the right hand end of the battery)
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 1 - LV Pillar - Set-up & Installation (11)
label | Description of Check - Confirm all warning labels and customer information labels are present on the LV pillar.
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 1 - LV Pillar - Set-up & Installation (12)
label | Description of Check - Thermographic inspection of switchboards/LV Pillar has been completed
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
label | Comments - Once PSSR Complete and LV Pillar under load
section | Cables/Cable Entry Points/Cable Containment
checkpoint | 2 - LV Pillar - Cable Entry Points/Cable Containment (1)
label | Description of Check - Cable entries and ducts are correct to design requirements and entries are correctly blanked off/sealed with Rayflates/Foam or other approved method
label | Acceptance Criteria: Contractor - H
label | Acceptance Criteria: Client - I
label | Comments - Cross check to Civils to ensure depths and clearances of conduits have been achieved.
checkpoint | 2 - LV Pillar - Cable Entry Points/Cable Containment (2)
label | Description of Check - Confirm all cable containment (Trays/Ladders) and cable cleats match the approved design, have no sharp edges and are installed to an acceptable standard with all metallic items earthed/bonded as required. Ensure bonds between tray joints are installed.
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
label | Comments - Cross check with Civils that the appropriate indicator tape has been installed as per standards.
checkpoint | 2 - LV Pillar - Cable Entry Points/Cable Containment (3)
label | Description of Check - Cable tray lids/covers are installed as per design
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
checkpoint | 3 - Cables (1)
label | Description of Check - All cables installed are the correct type/size, as per the approved design
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
checkpoint | 3 - Cables (2)
label | Description of Check - Confirm the cable identifiers match the approved cable schedule
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 3 - Cables (3)
label | Description of Check - Minimum bending radius of cables have not been compromised throughout their installation.
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
checkpoint | 3 - Cables (4)
label | Description of Check - Confirm cables are appropriately supported where required
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 3 - Cables (5)
label | Description of Check - Confirm cables have been appropriately dead tested after installation and prior to terminating to the LV pillar (continuity & insulation resistance test) and record values
label | Acceptance Criteria: Contractor - T
label | Acceptance Criteria: Client - R
checkpoint | 3 - Cables (6)
label | Description of Check - Cable ends have been wrapped or covered after installation in ducts, to avoid water ingress in the cable (unless terminated directly after installation and testing)
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
section | Network Earthing System
checkpoint | 4 - Network Earthing System
label | Description of Check - Check earthing system is installed as per the approved design, (including any footing earthing bonding) test and record earth loop impedence.
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
section | Metering
checkpoint | 5 - Metering (1)
label | Description of Check - Confirm metering cabinet is free from damage and locked with padlock
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 5 - Metering (2)
label | Description of Check - Confirm Meter is installed and operational
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
section | Lighting and Small Power
checkpoint | 6 - Lighting Columns (1)
label | Description of Check - Verify the number of lighting columns is as per the detailed design
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
checkpoint | 6 - Lighting Columns (2)
label | Description of Check - Confirm lighting heads are facing the correct way as per the Detailed design and into EV bays as required
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
checkpoint | 6 - Lighting Columns (3)
label | Description of Check - Confirm lighting is fully operational
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
section | Signoff
checkpoint | CONTRACTOR
holdpoint | Signature
checkpoint | bp Pulse
holdpoint | Signature
checklist | EV001-QA-ITR-000-ANZ-0025_B02_Mech Completion - Telecom Installation | [5 empty] | EV001-QA-ITR-000-ANZ-0025_B02_Mech Completion - Telecom Installation
section | Cables
checkpoint | 1 - Cables (1)
label | Description of Check - Confirm FO cables installed are the correct type (e.g. Multimode, OM2) as per the approved design.
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 1 - Cables (2)
label | Description of Check - Confirm unused FO cable cores have dust caps applied. All unused connectors shall have these left on.
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
label | Comments - If missing caps, the contractor shall source and install. This will be recorded as a punchlist item.
checkpoint | 1 - Cables (3)
label | Description of Check - Confirm Ethernet Cat6 cables have been run to correct location (at shop side and LVP side (and direct to EVSE if applicable))
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 1 - Cables (4)
label | Description of Check - Confirm suitable RJ45 connectors have been terminated to the end of all ethernet cables and the cables have been tested and passed
label | Acceptance Criteria: Contractor - T
label | Acceptance Criteria: Client - I
checkpoint | 2 - Cable Entry Points/Cable Containment (1)
label | Description of Check - Confirm cables are routed as per AFC Detail Design. Confirm duct ends (and any penetrations into buildings) are appropriately sealed.
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
checkpoint | 2 - Cable Entry Points/Cable Containment (2)
label | Description of Check - Confirm fibre optic cables are glanded correctly at each end or each run. If ethernet cable is run, and to be left coiled, is left coiled at correct location with sufficient spare length for potential future use.
label | Acceptance Criteria: Contractor - I
label | Acceptance Criteria: Client - I
section | CCTV
checkpoint | 3 - CCTV network
label | Description of Check - Confirm CCTV coverage of the EV Charger area and that chargers and vehicles are clearly visible
label | Acceptance Criteria: Contractor - W
label | Acceptance Criteria: Client - I
section | Signoff
checkpoint | CONTRACTOR
holdpoint | Signature
checkpoint | bp Pulse
holdpoint | Signature