## ITP-008
ConQA Team Notes:
Document Title: |  | ITP-269-CIV-CPD-Bio-Retention Basin Supply & Installation
ITP Description: |  | Bio-Retention Basin Supply & Installation
Discipline (e.g. CIV/STR/RAIL): |  | CIV
Revision Number: |  | 0
Revision Date: |  | 13/05/2025
ITP created by: |  | Nicholas Damcevski
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | This ITP is only to be used in Calder Park Drive Project
Inspection & Test Plan - Stormwater Drainage Suppy & Installation
[9 empty] | Revision: | 0
[9 empty] | Date: | 13/05/2025
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | IFC Drawings - Package 13 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | Melbourne Water 21.A.038 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | Melbourne Water MUSIC Guideline | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries-Materials
2.1 | HDPE Lining | IFC Drawing | HDPE Flexible Membrane - 1.5mm Thick Install according to Manufacturers Specifications Enter: Teambinder Material Approval number [free text box] | Document Review | Each lot | HP | Nominated Authority | Teambinder Material Approval
2.2 | Drainage Layer | IFC Drawing MW MUSIC GL MW 21.A.038 | Drainage Material supplied in accordance with IFC Drawing, MW 21.A.038 & MW MUSIC GL Enter: Teambinder Material Approval number [free text box] | Document Review | Each lot | HP | Nominated Authority | Teambinder Material Approval
2.3 | Transition Layer | IFC Drawing MW MUSIC GL MW 21.A.038 | Drainage Material supplied in accordance with IFC Drawing, MW 21.A.038 & MW MUSIC GL Enter: Teambinder Material Approval number [free text box] | Document Review | Each lot | HP | Nominated Authority | Teambinder Material Approval
2.4 | Filteration Media | IFC Drawing MW MUSIC GL MW 21.A.038 | Drainage Material supplied in accordance with IFC Drawing, MW 21.A.038 & MW MUSIC GL Enter: Teambinder Material Approval number [free text box] | Document Review | Each lot | HP | Nominated Authority | Teambinder Material Approval
3 | Preliminaries-Documents
3.1 | Check for correct documentation | IFC Drawing | Ensure that all employees and subcontractors are: – using the correct and complete set of drawings – all drawings are the latest revision | Visual Inspection | Prior to commencing any activity | HP* | PE | This ITP Sign-Off
4 | Pre-Construction Activities
4.1 | Survey Set Out - Bio-Retention Basin | IFC Drawings | Prior to commencement of excavation for the Bio-Retention Basin the Contractor shall confirm the position of the Bio-Retention Basin with the Superintendent. | Survey | Each Lot | HP* | PE | IFC drawings - package 13
5 | Construction / Installation Activities
5.1 | Excavation | IFC Drawings | Excavation shall be to the depth indicated on the IFC drawings. | Visual inspection Measure | Each Lot | IP | SE | IFC drawings - package 13
5.2 | Placement of HDPE Linear | IFC Drawings | Placed in accordance to Manufacturers Specifications | Visual inspection | Each Lot | IP | SE | IFC drawings - package 13
5.6 | Installation of Subsurface Drainage | IFC Drawings | uPVC Pipe shall be placed with 2m spacing between pipes. Pipes, geocompotises and geotextiles placed, joined and lapped in accordance with specified requirements. | Visual inspection | Each Lot | IP | SE | IFC drawings - package 13
5.3 | Placement of Drainage Layer | IFC Drawings | Placed in confirming to IFC Drawing shall be supplied and compacted to a Thickness: >=200mm | Visual inspection | Each Lot | IP | SE | IFC drawings - package 13
5.4 | Placement of Transition Layer | IFC Drawings | Placed in confirming to IFC Drawing shall be supplied and compacted to a Thickness: >=100mm | Visual inspection | Each Lot | IP | SE | IFC drawings - package 13
5.5 | Placement of Filteration Layer | IFC Drawings | Placed in confirming to IFC Drawing shall be supplied and compacted to a Thickness: >=300mm Filter Media to be installed in two parts. Each Layer of Filter Media to be lightly compacted with a single pass of vibrating plate | Visual inspection | Each Lot | IP | SE | IFC drawings - package 13
6 | Post-construction / Post-installation Activities
6.1 | As Built Survey | Design surface level as per IFC drawings | Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10 | Document Review | Each lot | IP | SE | This ITP As Built Survey Report
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: