## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-269-CIV-CPD-Bio-Retention Basin Supply & Installation | itp |  |  |  |  | ITP-269-CIV-CPD-Bio-Retention Basin Supply & Installation Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-269-CIV-CPD-Bio-Retention Basin Supply & Installation
label | ITP Description: Bio-Retention Basin Supply & Installation
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 13/05/2025
label | ITP created by: Nicholas Damcevski
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - IFC Drawings - Package 13
label | 1.2 - Non Dependent
label | Reference - Melbourne Water 21.A.038
label | 1.3 - Non Dependent
label | Reference - Melbourne Water MUSIC Guideline
section | 2. Preliminaries-Materials
checkpoint | 2.1 - HDPE Lining
label | Reference - IFC Drawing
label | Acceptance Criteria - HDPE Flexible Membrane - 1.5mm Thick
label | ○ Install according to Manufacturers Specifications
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Teambinder Material Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Drainage Layer
label | Reference - IFC Drawing MW MUSIC GL, MW 21.A.038
label | Acceptance Criteria - Drainage Material supplied in accordance with IFC Drawing, MW 21.A.038 & MW MUSIC GL
label | ○ Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Teambinder Material Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Transition Layer
label | Reference - IFC Drawing MW MUSIC GL, MW 21.A.038
label | Acceptance Criteria - Drainage Material supplied in accordance with IFC Drawing, MW 21.A.038 & MW MUSIC GL
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Teambinder Material Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Filteration Media
label | Reference - IFC Drawing MW MUSIC GL, MW 21.A.038
label | Acceptance Criteria - Drainage Material supplied in accordance with IFC Drawing, MW 21.A.038 & MW MUSIC GL
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Teambinder Material Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries-Documents
checkpoint | 3.1 - Check for correct documentation
label | Reference - IFC Drawing
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | Method - Visual Inspection
label | Frequency - Prior to commencing any activity
label | Category - HP*
label | Responsibility - PE
label | Verifying Documents - This ITP Sign-Off
date | Date Completed:
section | 4. Pre-Construction Activities
checkpoint | 4.1 - Survey Set Out - Bio-Retention Basin
label | Reference - IFC Drawings
label | Acceptance Criteria - Prior to commencement of excavation for the Bio-Retention Basin the Contractor shall confirm the position of the Bio-Retention Basin with the Superintendent.
label | Method - Survey
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - PE
label | Verifying Documents - IFC drawings - package 13
date | Date Completed:
section | 5. Construction / Installation Activities
checkpoint | 5.1 - Excavation
label | Reference - IFC Drawings
label | Acceptance Criteria - Excavation shall be to the depth indicated on the IFC drawings.
label | Method - Visual inspection, Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - IFC drawings - package 13
date | Date Completed:
checkpoint | 5.2 - Placement of HDPE Linear
label | Reference - IFC Drawings
label | Acceptance Criteria - Placed in accordance to Manufacturers Specifications
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - IFC drawings - package 13
date | Date Completed:
checkpoint | 5.3 - Installation of Subsurface Drainage
label | Reference - IFC Drawings
label | Acceptance Criteria - uPVC Pipe shall be placed with 2m spacing between pipes. Pipes, geocompotises and geotextiles placed, joined and lapped in accordance with specified requirements.
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - IFC drawings - package 13
date | Date Completed:
checkpoint | 5.4 - Placement of Drainage Layer
label | Reference - IFC Drawings
label | Acceptance Criteria - Placed in confirming to IFC Drawing shall be supplied and compacted to a Thickness: >=200mm
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - IFC drawings - package 13
date | Date Completed:
checkpoint | 5.5 - Placement of Transition Layer
label | Reference - IFC Drawings
label | Acceptance Criteria - Placed in confirming to IFC Drawing shall be supplied and compacted to a Thickness: >=100mm
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - IFC drawings - package 13
date | Date Completed:
checkpoint | 5.6 - Placement of Filteration Layer
label | Reference - IFC Drawings
label | Acceptance Criteria - Placed in confirming to IFC Drawing shall be supplied and compacted to a Thickness: >=300mm
label | ○ Filter Media to be installed in two parts.
label | ○ Each Layer of Filter Media to be lightly compacted with a single pass of vibrating plate
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - IFC drawings - package 13
date | Date Completed:
section | 6. Post-construction / Post-installation Activities
checkpoint | 6.1 - As Built Survey
label | Reference - Design surface level as per IFC drawings
label | Acceptance Criteria - Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10
label | Method - Document Review
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP, As Built Survey Report
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP