## Master List Templates
Warnings | Id | Type | Name | Values | Prompting Name
| 888ae02b-04ac-49ad-b409-58ed5312b28e | checklist | 1. Standard |  | 1. Standard
| 6c36f296-e45a-4cdb-bf92-c6afa94259e4 | section | Precast Element Details
| 210ea1e7-2b49-4212-a6e7-864f6c88147e | checkpoint | Concrete Details Complete
| e60845e7-311e-5010-bd8c-b77aba89e4b7 | textbox | Concrete Volume
| 5388bff2-c21f-5651-aa6f-a546844f144d | textbox | Concrete Strength
| 82ee082b-96a9-5528-8301-b5e600f5e207 | textbox | Enter Drawing Revision Number
| b348e89b-fb78-5dc3-802b-14c3a842e6bb | textbox | Cast Date
| 97eebc5b-4b98-5e29-8c8b-a749f13a1048 | textbox | Admixture Required
| 082377d9-99a4-407a-a5c6-4c7e1f509532 | section | Reinforcing Yard Checks
| 38a44764-8dcb-4bd3-b5de-b5ab46080097 | checkpoint | Reinforcing details checked/highlighted off against shop drawing (Bar sizes, grades and spacings)
| 2b9bd64e-c72f-44a0-adb8-d43c540e6985 | checkpoint | Cast in Items coordinated and marked on cage (Dross Ducts, Inserts Weld Plates)
| 5b215c52-1170-4ea1-afe7-2908f81175ac | checkpoint | Overall cage dimensions in plan checked and there will be sufficient concrete cover to edges
| 8cda3086-f80b-4e05-8d34-cbc6e9a633d7 | checkpoint | Overall cage thickness checked and there will be sufficient cover to MF and TF
| fe10f23f-5f3b-4129-b750-2e4a0f11a94b | checkpoint | There is sufficient cover to rebates around openings or weatherproofing details
| aa6bac79-5691-4039-9896-bdaf570cbf8d | section | Formwork Set Up Checks
| 2c992907-738d-412f-b627-13ec7f512ae4 | checkpoint | Length/Width/Thickness/Cutouts/Diagonals
| 3ca86a17-a308-44a1-9783-a5d535834366 | checkpoint | Edge Details & Rebates
| db3218ba-1b01-48f9-b96f-7ab433cc0cb8 | checkpoint | Inserts on MF (Weld plates, RB's, TIM's, Penetrations, DB Bottoms)
| e1a020e5-82ad-4b4d-8103-bb87db0b8575 | checkpoint | MF roughening's
| b54927e9-6be7-4f7c-9abe-ca283b61d67b | checkpoint | Sides Straight & Magnets Fastened
| 7a7c8090-a806-4d69-90bc-42d5777e3947 | checkpoint | Mould Face Clean
| da70a40f-183f-420a-b054-197c1b79ccc7 | section | Prepour Checks
| e11dd016-b6a9-4989-8b4c-dac91119298c | checkpoint | Mould Cleaned & Oiled
| 9f5e2fc5-e829-44e5-8cb7-afc1a4ef623e | checkpoint | Check covers on all sides, MF and TF, openings
| ce985fea-fe6a-40dc-b878-ad355b3d5492 | checkpoint | Starters (Size, Grade, Setout and Length)
| f686182e-b245-4d3e-9b8c-f40191713f89 | checkpoint | Inserts on TF (Weld plates, RB's, TIM's, Penetrations, DB's, Rebates)
| 7dcefd45-26ae-425e-9588-487412187fc2 | checkpoint | Lifters
| 40647ea8-cdbb-46b0-905c-9537c5823153 | checkpoint | Tie wire Trimmed
| 7677866e-857c-4458-b977-b9625bca5c79 | checkpoint | Panel fully clean
| 6a406d25-ac34-405a-ac7f-e50aff1e4231 | checkpoint | General Photos Attached
| 9183db28-ce82-4e15-aff5-01a04b4cf36c | checkpoint | Concrete Docket Attached
| f9bf9297-c41d-4ebb-91a1-a66fabe17e2a | checkpoint | Shop Drawing Checked Off (attach photo)
| 209edfa4-355f-46a7-8de9-5029a3445c6a | section | Post Pour
| 4baade08-c32b-46c6-b006-e177efdecdcd | checkpoint | Confirm formwork has not shifted during placing of concrete
| 20663429-0311-4634-ba9d-c7298f34dbf0 | checkpoint | Face lifters placed in correct location
| e1e6f4d2-9726-4543-96ee-3be2977115ed | checkpoint | Roughening Lines Correct
| 8a652e73-1ded-41d3-89b1-246a2f99e954 | section | Demould Inspection
| 8973bb61-aa31-4660-a8f7-672922c3c192 | checkpoint | Mould Face Acceptable?
| e1fd58c1-885e-460a-b0e0-db510088258f | checkpoint | Trowel Face acceptable?
| f2a55c62-aacb-4437-a826-4ba9d6828fa4 | checkpoint | Item Labelled?
| 8b4b1866-89b2-4122-8da5-f3248e227a95 | checkpoint | Drossbachs cleaned out and clear?
| fdf9e859-093a-4ee8-914d-808aa17549ec | checkpoint | Top lifters are cleared out and eyes are free of concrete?
| 6f654f0b-ce4c-4365-b91b-5006f8f954aa | checkpoint | Drossbachs drilled ?
| 2d382d5f-3885-44f3-bf02-edc942382aed | checkpoint | Nail plates removed?
| 8442a120-1e73-4889-8620-ea0af0a76181 | checkpoint | Jet washed?
| 60d79a94-5454-4d4f-87b7-d2f522b6560a | checkpoint | Weld plates are cleaned and free of concrete?
| 9eaaa2e7-4ec1-49f7-a82c-586756a1e698 | checkpoint | Starter bars bent for transportation?
| b1da6ad0-fc1d-45c4-87aa-fb26cd7284a3 | checkpoint | Structural repair required?
| 952d92f1-95d4-4840-80df-1e8aee5443aa | checkpoint | Chamfer Inspection
| 12d90b58-5b2c-45a7-af00-cab22e20cc65 | checkpoint | Silicone Inspection
| 9ee51ac8-48f0-4dff-863b-1eb98cdfcee5 | checkpoint | Honey combing from Vibrating
| 9960eae4-e7e0-47b8-9161-f2e76ed25f61 | checkpoint | Final check with drawing
| ffc9a475-8859-45f1-8ed4-beaec83ae7bf | section | Loading Out
| 4ca5fc7d-8cdb-40ee-b1d5-4073ff2fb67e | checkpoint | Photo taken of Panel on Truck
| ed28e9b2-f873-405a-a6db-8c111af8bcaf | checkpoint | No remedial work required on site
| 68b30628-65e2-4266-91e5-e1e7af196107 | section | Test Results, Certificates and Documentation
| 584f35b7-7ade-4890-a208-25255966c0b4 | checkpoint | Upload reinforcing detail sheets
| 29957942-5cb5-494b-a852-e27f1bfdbfb5 | checkpoint | Upload Photo of Reinforcing Stock Bundle Tags (Cast # Tracking)
| a306bc84-106c-439f-b159-91b89e8bccb9 | checkpoint | Upload Concrete test results
| c9532baa-2661-46a0-81b6-9e05e793d95f | checklist | 2. Standard with Aquron2000 |  | P
| 3af0ed91-1a12-48d6-a8f8-8c0d94327c3d | section | Precast Element Details
| 0d5daa81-d94e-4616-84ce-6d819a3e0693 | checkpoint | Concrete Details Complete
| 3a85f9d4-703c-55f7-9b57-850154b27ffe | textbox | Concrete Volume
| c8382481-315a-5d69-b033-00bfe99a280b | textbox | Concrete Strength
| 44df4941-b51a-5c4f-b1da-1c81d7e8811f | textbox | Enter Drawing Revision Number
| cbbe92d7-0e2f-55f3-bc1b-4274259dd7b5 | textbox | Cast Date
| 82807428-795d-4908-b30e-16add4baed73 | section | Reinforcing Yard Checks (Reo QA)
| 15df543a-6261-42b2-808e-30624be1003c | checkpoint | Operative on the reinforcing cutting line has uploaded clear photo of open stock bundle boar
| 6a432f5b-40b0-4358-96fc-bfe523f2e3ef | checkpoint | Cut and bent bars checked off against detail sheet
| 6c88ff88-bd04-4fbc-af87-8ced9cad3f5b | checkpoint | Perimeter bars and spacing marks confirmed
| e9e7a835-8e09-48cc-9bf6-f4af47e011fd | checkpoint | Cast in Items checked and marked on cage (Dross Ducts, Inserts Weld Plates)
| 82a7a611-592d-4544-8794-6da04b7e5ddd | checkpoint | Overall cage dimensions in plan checked and there will be sufficient concrete cover to edges
| d10b12dd-5a81-4dc6-8156-e909d18a7194 | checkpoint | Overall cage thickness checked and there will be sufficient cover to MF and TF
| 54c5301b-9ed2-47ec-8dfb-a6e809ad1ba3 | checkpoint | There is sufficient cover to rebates around openings or along edge forms
| 2002d92f-add1-4de1-916b-87c8c3a0eca7 | checkpoint | Weld plates can be fitted to cage in correct locations?
| 1ae09b2c-6b32-4da5-977f-db85e7f89f1b | checkpoint | Reinforcing details checked/highlighted off against shop drawing (upload photo)
| f60fafe9-b006-4b9a-96a0-df64a825b0f6 | section | Formwork Set Up Checks (Tables QA)
| 443a97be-3cbf-4341-873a-47e672c264c7 | checkpoint | Sides Straight & Magnets Fastened
| 568de151-9781-4959-afd6-41b5903bfce6 | checkpoint | Mould Face Clean
| 7d64f16f-4416-4c90-92d2-780e61232f90 | checkpoint | Length/Width/Thickness/Cutouts
| 2aebe6a9-c12e-449d-b9c0-1668625fef22 | checkpoint | Edge Details & Rebates
| 25d63464-79b5-4b8b-8e9c-a06025518391 | checkpoint | MF Weld plates in correct location and siliconed to table
| 04d564f0-6e3c-4f47-b513-898742360659 | section | Prepour Checks (Tables QA)
| 7d35586f-8a4b-4fcb-8875-30beb46d51d2 | checkpoint | Main Reinforcing
| 4e481b78-33cc-4123-b6f3-6312ead1bea6 | checkpoint | Starters
| b8559d72-a035-43c7-9567-5303c25a2e83 | checkpoint | Stirrups
| 7014fec5-99a0-49ba-b8fb-357d386aa585 | checkpoint | Lifters
| 260f757f-12db-463a-b474-896499452a70 | checkpoint | Mould Cleaned & Oiled
| 4b890473-b1a7-4c3b-80dc-6087a3a05646 | checkpoint | Tie wire Trimmed
| 2abea4b5-6d6e-4759-b9bf-8c8283b6cb81 | checkpoint | General Photos Attached
| 02a6f973-348c-487e-9599-f04a177b5d83 | checkpoint | Concrete Docket Attached
| 5f938220-45ed-4398-bc03-244528d68d6d | checkpoint | Shop Drawing Checked Off (attach photo)
| a057cf1e-23da-4f2f-9114-b73cec5e5ff2 | section | Post Pour (Table Supervisor)
| ca997259-066e-4475-bbd7-1dde1eef7efd | checkpoint | Confirm formwork has not shifted during placing of concrete
| 5a2b9d3f-41cf-42ef-9030-77d64866c9c6 | checkpoint | Face lifters placed in correct location
| 488d0deb-c0fc-491e-b88b-de7a137ce37c | checkpoint | Roughening Lines Correct
| c92f3d80-ce2f-4db7-8884-7faf173e1b0a | section | Demould Inspection (Yard QA)
| bac95f8e-cf57-43dc-adde-518a6f248c56 | checkpoint | Panel correctly labeled (check against shop drawing)
| a3eba977-f22d-4e9c-b47d-0c8691f8b8ea | checkpoint | Grout holes for Drossbach Ducts have been drilled (top and bottom)
| 277f257e-e4d4-4336-953f-96bf6a060971 | checkpoint | Bottom of Drossbach Duct is clear (any slurry/grout has been removed)
| 0bfdfc50-4e9b-4bc6-8cc0-5f6a5be8f406 | checkpoint | All lifters have been cleared/cleaned out (including top lifters for install)
| dbe2576f-fca6-4798-a37e-b7ea152107f6 | checkpoint | All Inserts have been exposed and nail plates removed (caps that came with Ancon fixings should be put back on)
| 1461a022-4a3c-499e-8ffa-f6873665fb42 | checkpoint | Stitch joints have been jet washed
| 17d0b46a-c24a-440e-838f-e230a569205c | checkpoint | MF roughening's jet washed
| 864d8a8a-0a4a-42f0-b853-cd00a783cb7d | checkpoint | NF chamfers and square edges rounded with cup stone
| 2bb34f40-b43f-432d-b6d3-bb78fcd74a81 | checkpoint | Weld plates cleaned (NF weld plates to be cleaned with cup stone)
| e46bddd3-c149-4771-8e2c-49ef868740da | checkpoint | Grade 300 starters bent up for transport (only bend starter down if transport height is increased by bending up)
| 5f6d402e-29ff-4e83-8243-47d545b6e27b | checkpoint | Grade 500 starters are straight
| e43d11ce-0752-4e30-9276-05601eef0884 | checkpoint | NF Quality acceptable (attach photo)
| 48ae86a5-fb44-4184-a054-f368f2531cc6 | checkpoint | MF Quality acceptable (attach photo)
| e45cc533-1903-4bd8-91db-611bdc3eade4 | checkpoint | Structural repairs required (if yes photograph before)
| c7596507-8e7f-4877-b407-d81759f11abd | checkpoint | Shop drawing checked off
| c19c76fe-0b9e-4233-8f1f-141d20da1e93 | checkpoint | Aquron2000 applied to Mould Face of Panel
| d6a6b1a2-61f5-499c-a32a-ef6557767030 | checkpoint | Upload photo of Batch no. for Aquron2000 applied to this panel
| 9f009d2e-39d5-4ef1-8039-f98384cc9e93 | section | Overall Panel Quality (Yard QA)
| 4986d13e-6244-4871-8b84-bf20b9c71151 | checkpoint | Overall Panel Quality Ratings Recorded Below
| 2ff8b1cb-7ac1-53df-af46-78eb6d1693e9 | note | The higher the number the better the quality
| 2c634f88-35d0-50a6-944e-55beebe44330 | note | e.g. "1" is unacceptable
| f555994b-e225-5071-87e6-61d4a819a6e5 | button | Vibrating Quality | 5 , 4 , 3 , 2 , 1
| 869a6493-be6c-565b-b276-f7c6dfec15cc | button | Trowelling Quality | 5 , 4 , 3 , 2 , 1
| 8a798ac1-df4f-54dc-8a03-dee910cd0530 | button | Silicone Quality | 5 , 4 , 3 , 2 , 1
| 30c0d8c2-31b5-5af4-9239-19f5b3ad476f | button | Chamfer Quality | 5 , 4 , 3 , 2 , 1
| 05f8b9dd-c82b-5037-b1a8-d55a9c3592fb | button | MF Quality | 5 , 4 , 3 , 2 , 1
| 5ed06998-d37e-4ae4-9da9-20c7c201c1db | section | Loading Out (Yard QA)
| 410ca20a-5c94-4256-9575-dd334e21776b | checkpoint | Load Docket Given to Driver
| b46c5ecb-24dc-4e79-a878-d3f206d09000 | checkpoint | Photo take of Panel on Truck
| e43f0833-e66e-4a54-9d52-95f5ef05c416 | checkpoint | No remedial work required on site
| e889270a-5643-4398-a04e-1e3cd1a34b63 | section | Test Results, Certificates and Documentation (Reo & Yard QA)
| ad32e840-80a9-4714-8d4a-82539d67487e | checkpoint | Upload reinforcing detail sheets
| 19a2f2db-d835-40e2-97a6-67c0eb10cf82 | checkpoint | Upload Photo of Reinforcing Stock Bundle Tags (Cast # Tracking)
| b21cbe19-abb3-4760-a152-648e03328ad8 | checkpoint | Upload Concrete test results
| 5c93fb5f-b61a-4357-8829-a2b817644768 | checklist | 3. LR WT2 Panel |  | 3. LR WT2 Panel
| 6f088471-5db4-478a-8d28-bf309b6a6bf1 | section | Precast Element Details
| 6e9a2455-9873-428b-ae69-0c70778ea1ae | checkpoint | Concrete Details Complete
| d36190de-c6c4-5076-83ae-e266b4aa0f17 | textbox | Concrete Volume
| ab5d60e3-3ec2-5eb0-9d08-0c330f3ca6b4 | textbox | Concrete Strength
| 5e2297eb-4354-5732-9668-aaf49961ae40 | textbox | Enter Drawing Revision Number
| 2fa8ac20-9f58-5315-a403-5f5bcc21d5db | textbox | Cast Date
| 4b6b42c8-324c-4998-886c-769bf6a964b3 | section | Reinforcing Yard Checks (Reo QA)
| 1cfa040a-5412-44c0-aa5a-edb08ef62baa | checkpoint | Operative on the reinforcing cutting line has uploaded clear photo of open stock bundle boar
| 3d593793-a7c7-40c6-a7d7-e276239582e3 | checkpoint | Cut and bent bars checked off against detail sheet
| 9e0412d0-965c-4290-8633-e7e6b352b71a | checkpoint | Perimeter bars and spacing marks confirmed
| f3959fa8-6b0a-4a8e-8039-3351e80160ad | checkpoint | Cast in Items checked and marked on cage (Dross Ducts, Inserts Weld Plates)
| f9eb675d-f8c0-489f-b070-34b74098efd3 | checkpoint | Overall cage dimensions in plan checked and there will be sufficient concrete cover to edges
| 7c2e024e-fdb4-4efd-82e0-1f25d2961284 | checkpoint | Overall cage thickness checked and there will be sufficient cover to MF and TF
| 84a23642-682d-4a7c-adb7-7fc42bfc126a | checkpoint | There is sufficient cover to rebates around openings or along edge forms
| 2bd72e81-121d-4972-96f5-3deab0acc852 | checkpoint | Weld plates can be fitted to cage in correct locations?
| bcedd380-12af-454a-8a05-97601f36a594 | checkpoint | Reinforcing details checked/highlighted off against shop drawing (upload photo)
| 6cdae6de-e05d-4289-bb05-dba79751c8a1 | section | Formwork Set Up Checks (Tables QA)
| 93143dff-4123-4ede-86c6-a32158df4654 | checkpoint | Sides Straight & Magnets Fastened
| 74878f7d-dd3b-4832-b0da-0db01909a29c | checkpoint | Mould Face Clean
| 2ca2f0b2-55ee-4d36-bb8f-8b732ba85a88 | checkpoint | Length/Width/Thickness/Cutouts
| 88f20329-3495-41c4-8a51-efc8dad893b3 | checkpoint | Edge Details & Rebates
| ac212024-7230-4b9a-b99d-3ea1105a0c38 | checkpoint | MF Weld plates in correct location and siliconed to table
| c858fa41-ca5b-4d0f-ba7b-a0f02f1454d3 | section | Prepour Checks (Tables QA)
| 95d9408d-a008-4c94-b975-9747871e89eb | checkpoint | Main Reinforcing
| bdac6b26-84f4-4764-8e9c-1b31275f74c7 | checkpoint | Starters
| 6feca183-f9e4-48bc-9452-ef2411204e3b | checkpoint | Stirrups
| 96f95bdf-c7a6-4289-8957-0c787d9bfe5b | checkpoint | Lifters
| fb31b4ef-87d6-420c-9599-268ac1f3987a | checkpoint | Mould Cleaned & Oiled
| d284b03e-6720-43fb-85f3-d37ddaec4931 | checkpoint | Tie wire Trimmed
| a1203515-40c1-48d9-a3cd-f7cefea5d610 | checkpoint | General Photos Attached
| 3e0483e6-6d34-4296-aa64-c5240b987c91 | checkpoint | Concrete Docket Attached
| e778187c-8b54-4705-8b14-0fbcdbc50392 | checkpoint | Shop Drawing Checked Off (attach photo)
| 4516c37b-f67b-4a64-9e8f-edbb7cccc460 | section | Post Pour (Table Supervisor)
| 6def30f3-6d78-4ce5-964f-cfabda6f5d03 | checkpoint | Confirm formwork has not shifted during placing of concrete
| 17f291a3-721d-43cb-8e5b-2cdd41a112c7 | checkpoint | Face lifters placed in correct location
| 5d27de29-2db8-4d62-9ce6-2449e5fdb579 | checkpoint | Roughening Lines Correct
| adee160f-226a-4b21-b385-9d902bcb46f7 | section | Demould Inspection (Yard QA)
| 42997e26-9829-4621-96b5-50f75262af6e | checkpoint | Panel correctly labeled (check against shop drawing)
| cd5926f9-7fa8-4253-815d-ab65123a2690 | checkpoint | Grout holes for Drossbach Ducts have been drilled (top and bottom)
| b95a575c-d0a6-4e00-bf4f-61e659040cb2 | checkpoint | Bottom of Drossbach Duct is clear (any slurry/grout has been removed)
| 843f8376-6696-4e61-a702-1d2eb4090faa | checkpoint | All lifters have been cleared/cleaned out (including top lifters for install)
| 8f35b262-69aa-4359-ac21-ed918c60b575 | checkpoint | All Inserts have been exposed and nail plates removed (caps that came with Ancon fixings should be put back on)
| 9b818bc7-5a6f-41fe-a6b7-684387085205 | checkpoint | Stitch joints have been jet washed
| dd902ac0-8622-4766-b886-275874b889f6 | checkpoint | MF roughening's jet washed
| 60432691-81d1-4d49-b718-1b436e509ae7 | checkpoint | NF chamfers and square edges rounded with cup stone
| c4086058-5c31-4a51-a714-687127fb3444 | checkpoint | Weld plates cleaned (NF weld plates to be cleaned with cup stone)
| ab62e6f5-834f-4c64-a77c-5419c6166088 | checkpoint | Grade 300 starters bent up for transport (only bend starter down if transport height is increased by bending up)
| 06bf7cfb-e3cb-4309-af04-a1e9bb855d57 | checkpoint | Grade 500 starters are straight
| e3633db2-8eee-41ca-ad8f-0d0726128d99 | checkpoint | NF Quality acceptable (attach photo)
| 711eccd1-49b0-457e-ad5a-fc1658304f7a | checkpoint | MF Quality acceptable (attach photo)
| 25071402-7fb7-4efb-9a1d-c490bbbc55d9 | checkpoint | Structural repairs required (if yes photograph before)
| d53f4229-a0f6-4441-b140-6956ecf7a051 | checkpoint | Shop drawing checked off
| d763b10a-d2d1-4a07-a0dc-afd36844a4ae | section | Panel Painting Checks (Yard Supervisor)
| 5f3ef837-c6e6-47dc-963d-abb4505abff3 | checkpoint | Panel MF Sprayed with Tiltwash and rinsed off with waterblaster (2 passes)
| 7ca30d9a-f496-44b9-9506-13cc931d2210 | checkpoint | Window opening inspected and concrete finish acceptable
| ff5ad1c6-97e1-4451-bf93-661f6ef5c957 | checkpoint | Large Pinholes or honey combing repaired with Sikadur UA (if required)
| aff4f0b4-820a-4694-9633-5a6d239dfa57 | checkpoint | Panel allowed to cure for 48hours before applying primer
| f9aaa4d5-8cbe-454e-be3d-b981a8743ab5 | checkpoint | Single coat of Dulux AcraTex Green Render Sealer applied (upload photo)
| 80680ddb-dac4-4e2f-bdc6-fa89e6175a8a | checkpoint | Allow sealer coat to dry for 4 hours before applying topcoat
| b509154a-84bb-40f5-940d-12ab6f664551 | checkpoint | 2 coats of Dulux AcraTex AcraShield Advance Matt topcoat (upload photo)
| fe5bacc4-9ad0-472b-86bb-d1012303b616 | checkpoint | Masking tape in window opening removed and edges of panel clear of any overspray
| c0188f1a-3da0-4996-a70a-47cdc1c56f07 | signoff | Window installer accepted quality of concrete opening
| 400c3274-5018-4d28-a284-b39f9d6d8ea1 | checkpoint | Confirmation
| 90a51107-ab38-4601-9f59-625ed62dd755 | signoff | Window installer confirmed they have completed their works and panel can delivered to site
| d8ae2582-7359-4b88-bf2e-ca9d2a347137 | section | Loading Out (Yard QA)
| 1e37e562-2ff6-4441-92db-39615c76e4ad | checkpoint | Load Docket Given to Driver
| 96d13520-b30a-46d1-a15b-9966dbcc69df | checkpoint | Photo take of Panel on Truck
| a337ab2f-bbf9-4077-b169-99b6f341fe76 | checkpoint | No remedial work required on site
| a22af8c2-c0f7-4efd-a3d3-6c1f3de88bef | section | Test Results, Certificates and Documentation (Reo & Yard QA)
| 4f629c74-fe0c-4526-9493-e1314c98ec86 | checkpoint | Upload reinforcing detail sheets
| 9a783d0c-df54-47b8-8ad4-525595c76adf | checkpoint | Upload Photo of Reinforcing Stock Bundle Tags (Cast # Tracking)
| d53cea49-063c-411f-ad33-a16528332da7 | checkpoint | Upload Concrete test results
| b724e883-46ad-4066-bbd6-7b76ba27a411 | checklist | 4. LR WT3 Panel |  | P
| d50a8d64-f42a-4db5-b00b-3607d2c2c06e | section | Precast Element Details
| 65b85a6f-9b67-48b7-bc9c-07b4c68cb279 | checkpoint | Concrete Details Complete
| f93de833-ccdc-5608-8629-2316fa7f600c | textbox | Concrete Volume
| 56b56db4-c506-5a41-af40-aff036996a3d | textbox | Concrete Strength
| 71a28364-61e6-5596-9258-cc7c6a059f71 | textbox | Enter Drawing Revision Number
| ca0a00f4-d2b5-5553-934b-5fb566b8821c | textbox | Cast Date
| 2eea5c2b-988c-49fd-a1a1-2184f840f926 | section | Reinforcing Yard Checks (Reo QA)
| 6aa62017-177a-49a9-b602-aac63163d958 | checkpoint | Operative on the reinforcing cutting line has uploaded clear photo of open stock bundle boar
| dab16392-35b2-4430-93c8-84582d427495 | checkpoint | Cut and bent bars checked off against detail sheet
| c87d5623-07e1-4a3a-8bff-1eb8f612c1f6 | checkpoint | Perimeter bars and spacing marks confirmed
| f36abc39-4276-4da4-8ff9-78f0b57af286 | checkpoint | Cast in Items checked and marked on cage (Dross Ducts, Inserts Weld Plates)
| 80fdf14f-f673-4f13-88e9-4631667290b3 | checkpoint | Overall cage dimensions in plan checked and there will be sufficient concrete cover to edges
| 21dbfe01-bcdb-47ed-9e1e-ce41e2379986 | checkpoint | Overall cage thickness checked and there will be sufficient cover to MF and TF
| 365be858-5d9b-4821-8ab1-b7839e899350 | checkpoint | There is sufficient cover to rebates around openings or along edge forms
| ca22ec0c-f64b-4f89-a8be-605c24dba9f1 | checkpoint | Weld plates can be fitted to cage in correct locations?
| 475dd75f-d023-44cd-a731-b873184a7b90 | checkpoint | Reinforcing details checked/highlighted off against shop drawing (upload photo)
| 3d2304b6-a071-4e25-8d11-6b04a7db2bc3 | section | Formwork Set Up Checks (Tables QA)
| 7d1d72d5-d3b9-4b10-bb5e-703a48945d74 | checkpoint | Sides Straight & Magnets Fastened
| 65c3dee1-1c73-44d1-adb4-b71fd464eff3 | checkpoint | Mould Face Clean
| 15976424-d03d-42b9-895a-b892e17e10e4 | checkpoint | Length/Width/Thickness/Cutouts
| 750bbf26-1471-4adc-9d70-6eddaf1b923b | checkpoint | Edge Details & Rebates
| d65eb75e-b297-48c5-8e07-66fd74f4e4c2 | checkpoint | MF Weld plates in correct location and siliconed to table
| 938ba8e7-c008-4d6b-83e7-dcd1572232c0 | section | Prepour Checks (Tables QA)
| 037c7b98-6806-4e63-b41d-08746a24ae4a | checkpoint | Main Reinforcing
| fb844be8-a2ff-4b95-afe5-e3114de6f815 | checkpoint | Starters
| 9c25e551-9e13-47ae-a999-f0aeabab3a0f | checkpoint | Stirrups
| 79701048-ec04-45ef-b37e-57f82e191a7b | checkpoint | Lifters
| 73384c8d-8264-49c4-8554-c6cc8ca43f48 | checkpoint | Mould Cleaned & Oiled
| 867a7f81-b555-4d55-914a-acd3754bb9a7 | checkpoint | Tie wire Trimmed
| 07849838-9a99-4424-9340-00e8c72e10b6 | checkpoint | General Photos Attached
| bc42d565-97da-49ad-998a-4ab978ee2f41 | checkpoint | Concrete Docket Attached
| b8aff650-fc59-4d7a-9e70-b5dc861c4c62 | checkpoint | Shop Drawing Checked Off (attach photo)
| 4e6ccdfc-8afd-4618-96b8-9db0e9d8df2c | section | Post Pour (Table Supervisor)
| 7515470f-9e12-4d1b-82f3-9cd28d6214f2 | checkpoint | Confirm formwork has not shifted during placing of concrete
| 9d6cef15-b237-44c9-919c-27805c00bb23 | checkpoint | Face lifters placed in correct location
| 24d944aa-177c-40ad-b4ff-dca6ba2e150c | checkpoint | Roughening Lines Correct
| 8325d04d-03ec-43ba-85b5-17649266397d | section | Demould Inspection (Yard QA)
| 15f0fed1-36ea-494a-a1ec-460dd0c1a81b | checkpoint | Panel correctly labeled (check against shop drawing)
| 4eec067d-b46a-43e3-983d-6ac1c56943ef | checkpoint | Grout holes for Drossbach Ducts have been drilled (top and bottom)
| a2b7bc2e-8679-475c-ad65-7c991bac6342 | checkpoint | Bottom of Drossbach Duct is clear (any slurry/grout has been removed)
| 49ac45ca-9b4b-44ad-afaa-b8805c878eee | checkpoint | All lifters have been cleared/cleaned out (including top lifters for install)
| b5875386-cb18-4732-815a-db0774dcf43f | checkpoint | All Inserts have been exposed and nail plates removed (caps that came with Ancon fixings should be put back on)
| a9143544-3c2b-426b-8cbc-a55cea1060dc | checkpoint | Stitch joints have been jet washed
| 8c25d55b-a3ea-43b4-a172-3cc622d1aa0c | checkpoint | MF roughening's jet washed
| 3b4dc1f8-770b-4842-bf37-a2f5554725b0 | checkpoint | NF chamfers and square edges rounded with cup stone
| 79e62c39-cec1-450d-872b-4142c70b3455 | checkpoint | Weld plates cleaned (NF weld plates to be cleaned with cup stone)
| 76bd40bd-4dbc-4f68-a4a8-6e3bdc63fa65 | checkpoint | Grade 300 starters bent up for transport (only bend starter down if transport height is increased by bending up)
| 8877fc6f-598a-428b-a26f-722f98707bd1 | checkpoint | Grade 500 starters are straight
| 1f308c9f-0fea-4327-8361-6f146fe133a8 | checkpoint | NF Quality acceptable (attach photo)
| 0e72cda3-ffe7-4754-85e0-d85e1a5eb587 | checkpoint | MF Quality acceptable (attach photo)
| e79d0926-519e-4ec9-b9be-3e89379a972f | checkpoint | Structural repairs required (if yes photograph before)
| 00481297-cd25-4982-a44c-cae53b69ec57 | checkpoint | Shop drawing checked off
| fb2ab45e-4f82-4ca9-a9f3-25d04fcb8fa5 | section | Panel Painting Checks (Yard Supervisor)
| 70446044-3882-4bc3-a235-9676ee9f289b | checkpoint | Panel MF Sprayed with Tiltwash and rinsed off with waterblaster (2 passes)
| 2a6cc8d9-0387-4612-816b-d2ed247becae | checkpoint | Window opening inspected and concrete finish acceptable
| 05bfac8b-4c1d-47b6-ae64-a820991b3088 | checkpoint | Large Pinholes or honey combing repaired with Sikadur UA (if required)
| 90148788-b82a-4ac0-b921-33c804eae774 | checkpoint | Ecotone colouring system applied as per quality plan
| b45bf808-b4c0-4230-bbae-94607fb1ceb2 | checkpoint | Masking tape in window opening removed and edges of panel clear of any overspray
Multiple signoffs are not allowed | 619ab959-3519-4208-9f6b-ab145baa2a3c | signoff | Window installer accepted quality of concrete opening
Multiple signoffs are not allowed | 0f434652-fe71-4eb1-bb55-31bfb52b4599 | signoff | Window installer confirmed they have completed their works and panel can delivered to site
| 0873e2ba-5b39-4b39-a886-d668e9fdc45d | section | Overall Panel Quality (Yard QA)
| 35b5ff2e-40e9-48a1-b583-c19cca553477 | checkpoint | Overall Panel Quality Ratings Recorded Below
| 89229089-abe6-556d-bcb8-02df20595fc2 | note | The higher the number the better the quality
| 3bacc4db-f3cf-5268-874b-d204448de3fc | note | e.g. "1" is unacceptable
| 5b5001e1-c681-5a8b-9851-93809a8aff02 | button | Vibrating Quality | 5 , 4 , 3 , 2 , 1
| 9cff5aa3-a33b-530a-88d9-2392fdcc67f9 | button | Trowelling Quality | 5 , 4 , 3 , 2 , 1
| 7eb9c059-7eb9-57df-89f8-d576c10a15f2 | button | Silicone Quality | 5 , 4 , 3 , 2 , 1
| f8d5cc93-b813-562b-9bbd-cfcb3ba1f551 | button | Chamfer Quality | 5 , 4 , 3 , 2 , 1
| 2c2070d3-5446-51e8-8925-3b63dbebaac6 | button | MF Quality | 5 , 4 , 3 , 2 , 1
| 8a0f5bcc-51f0-4431-9dbe-3b751f280f81 | section | Loading Out (Yard QA)
| c7d434d8-2d96-4f8e-a016-62692ed9c804 | checkpoint | Load Docket Given to Driver
| cdf7416b-3af7-4f4a-a649-27c4a72cff91 | checkpoint | Photo take of Panel on Truck
| ac290861-b72d-4d6b-910f-4909161ca741 | checkpoint | No remedial work required on site
| 07950d92-7d8b-4c72-8cb3-000353575e40 | section | Test Results, Certificates and Documentation (Reo & Yard QA)
| 18c48cbd-61d7-49e9-a5c8-223bb3b5baf7 | checkpoint | Upload reinforcing detail sheets
| 649b75c9-8a0c-423e-af85-5e49c1cc2813 | checkpoint | Upload Photo of Reinforcing Stock Bundle Tags (Cast # Tracking)
| 7eb796b1-08ee-4d6e-b922-1b858a23d03d | checkpoint | Upload Concrete test results
| 3a2edcf7-94ef-451e-b661-8c2c021a9af7 | checklist | Add Defect/Remedial |  | Remedial -
| e970f2e8-38be-47ea-88e8-55a317040604 | checkpoint | Defect Details Inputted
| 02fb74a6-9297-5b69-8d8f-5d0c48b9c66b | dropdown | What is the Defect | Chip in panel, Crack in the panel, Level of finish inadequate, Incorrect Location of Cast in Items, Missing Cast In Items, Other Remedial - Specify below
| 5643327d-d65b-5388-9530-86f7463e6f6b | textbox | Other Defect (specify here if applicable)
| 0a0c215a-1923-5c54-9bd7-a2a864f6723e | textbox | Defect Location on Panel (Attach Photo)
| 7152a2c6-2eb2-5247-8f3c-096388865e18 | textbox | Remedial Work Required
| 502296f5-6918-4b50-a34e-45b8d43935b1 | checkpoint | Panel Location Inputted
| 96be865a-2544-5cb4-9d0c-5574d44c5bb8 | textbox | Panel Location
| 98dc4c4e-edbc-4b97-8033-8b15d5166725 | checkpoint | NCR Raised if Required
| 883a5a98-2c88-4d02-aa0d-e0db0e558895 | checkpoint | Remedial completed - (Attach Photo)
| 496ad6f2-797a-4b17-a0c0-69cd3b3dcd4a | checklist | Compliance Documentation Checklist |  | Compliance Documentation
| f58889c0-5e6b-482f-bec0-0ae5a115ed21 | checkpoint | Concrete Test Results
| 066d13f7-4c78-53cf-ae07-c6288d05b188 | note | Pass once all test results for this project are attached
| 4fe06e26-34cc-58f5-876f-027f90ea4833 | textbox | Concrete test requirements for this project
| a40742db-3201-4a72-ac32-2faed3ed3e97 | checkpoint | Mill Certification
| 95c90d50-faae-57db-8f9a-9e8b3b1bada8 | note | Pass once all mill certs for this project are attached
| 75aa4f73-99ce-4d2a-a05b-d954d6eb38ed | checkpoint | PS1 Attached (if applicable)
| 49b1e850-1ca9-4741-8c28-ee80ef9b1a01 | checkpoint | PS3 Attached (if applicable)
| 2e7a2ce4-b667-435d-b89d-f639ced12998 | checkpoint | PS4 Attached (if applicable)
| b0a94f9c-8d3f-4a14-a6b3-95f2bb9efe13 | checklist | Demould Inspection |  | Demould Inspection
| cc713758-c7d1-4000-94a0-49771f36458f | section | Post Pour/Demould Inspection (Yard Manager)
| 570fd16c-c2c0-47b8-82ba-d7fe8f574853 | checkpoint | Mould Face Acceptable?
| 21acafad-a707-45c5-b33d-57431f8e4b8e | checkpoint | Trowel Face acceptable?
| be276187-75d3-4dd7-9792-8c817e0cc7ce | checkpoint | Item Labelled?
| 949b98e5-d84e-4eda-abf1-882f7821cb3f | checkpoint | Drossbachs cleaned out and clear?
| 3a946079-7e35-4cfb-b92e-ef247a29cfd7 | checkpoint | Top lifters are cleared out and eyes are free of concrete?
| 64edf7d7-0241-4bfb-b135-6ffb9ee7bfeb | checkpoint | Drossbachs drilled ?
| 73ef77bc-512d-4974-8e61-9384c0739d02 | checkpoint | Nail plates removed?
| 8c21555a-3f20-4971-a39d-2e9513cfb1ac | checkpoint | Jet washed?
| 3ed83de0-2c13-491f-b12d-ddb3518766e4 | checkpoint | Weld plates are cleaned and free of concrete?
| 363dbd71-56fc-4f5b-b879-25a2a10fbc48 | checkpoint | Starter bars bent for transportation?
| 49f08527-c22a-470b-b3a7-4cadc7089370 | checkpoint | Structural repair required?
| 3e28e816-1c9f-465c-a049-bbd09d29d034 | checkpoint | Chamfer Inspection
| f192b395-a8f0-4f6a-be06-f3dd0f917ff2 | checkpoint | Silicone Inspection
| 272b8afc-ded7-4634-8af4-56fedd48df35 | checkpoint | Honey combing from Vibrating
| be14bedc-6405-45e3-9788-10a3eb991fa4 | checkpoint | Final check with drawing
| e5b9e49d-353d-4f8a-986b-0e757185d91b | checklist | Drossbach Duct Grouting Records |  | Drossbach Duct Grouting Records
| ef35d6d4-762f-4cb4-b602-649c6b7d6ec4 | section | Project Details
| 7c0ad09a-44d5-4369-9dc2-172585ad2ad9 | checkpoint | Project Details
| 6799fd46-cc01-57ec-8710-0719df83db23 | textbox | Project Name:
| 8753bcc9-0acf-5d61-8d78-78c80eb6cccd | textbox | Stage:
| 216bed4e-91e8-5871-9e0e-a7c948764de8 | textbox | Grid/Panel Reference
| de9750c5-5a6e-537e-9846-3fdd3dd6d96a | textbox | Approved Grouting Material
| b84cb579-bd96-56b0-87df-71f5c07e6981 | date | Date Drypacked
| 308503df-3737-5363-a87a-dc1bfaae6df9 | date | Date Grouted
| cef5ee8c-06d8-4638-b421-1f4fb9d7ad2c | section | Area Grouted
| 455110f9-b320-430e-8028-9e23899d37d0 | checkpoint | Area Grouted
| 55154b88-2243-5a1f-a2b7-dc1a31c7325a | textbox | Total Panel Length
| 9529bf40-a26e-5d6a-bba0-26591f0e5377 | textbox | Average Shim Height
| f83606f1-028c-54e8-8316-bcef5164c4c6 | textbox | No. Drossbach Ducts
| 7bb0e31f-c2d8-5d5b-ab8f-18ac9beaae59 | textbox | Drossbach Duct Length
| d4f4d61e-a173-5549-9fea-4198ccc84dd5 | textbox | Anticipated No. Bags required
| 3dac75d5-734f-4348-a771-59bccfb04cbb | section | Quality Checks
| 80e58c16-c784-4466-bc51-9bd9bfaa6f3e | checkpoint | Foundation clean prior to drypacking
| e683829a-e85b-4be6-a159-611caad5d1a3 | checkpoint | Visual Inspection completed to confirm grout flowing from the top of all Drossbach ducts
| d8f1e123-f9e6-4ea8-922a-1731d0967afd | checkpoint | No. Bags Used for Dry packing
| bf508126-6b6f-48ad-ac50-fc40a915cfe0 | checkpoint | Grouting Material used
| 3fe5b0e7-507b-47b4-9efc-a5795e22ecd2 | checkpoint | No. Bags Used for Grouting
| 8af0b9f8-a202-42ad-8b79-d89c2a8e7291 | checkpoint | Grouting Supervisor name
| a489f28f-8086-4feb-a330-3a9e6898bfae | signoff | Sign off
| cb39f9e7-7e8f-4740-8ac4-ef68fc245ea4 | checklist | Job Details Checklist |  | Job Details
| 3d098030-e418-4675-b5b1-7520caf5ee77 | checkpoint | Project details entered below
| 8724734a-b967-59e4-b175-c5c6f1db0e60 | textbox | Job File Number
| 45b6015f-22e3-5b0c-8117-3a27221048ee | textbox | Project Name
| ef1b5d06-622a-5aca-84c2-8a00931e8d8a | textbox | Site Address
| 31c83e66-7544-5cd3-a918-a8f6baca03e9 | textbox | Main Contractor (e.g. Teak)
| b1590901-5990-5ddc-9dee-19725346ccbb | textbox | Main Contractor POC
| 04d29bad-dab1-5357-9860-e83c0c02444f | textbox | Structural Engineer
| 78611fa4-7a52-594c-8bc7-427229a97b3c | textbox | Architect
| d1596c44-971b-47e6-972c-f74679e99dc7 | checklist | Site Works Checklist |  | Site Works Checklist
| 48bfee1c-89f4-408e-b8a0-b08123875ca8 | section | Details
| 1905c0f6-38cc-4e88-8c72-a18a7d497f89 | checkpoint-no-value | Site Works
| a03baa4b-967b-501b-ba35-4d497c9286fb | date | Date when scoping document was created
| c8ba700a-6cb7-44d2-86f5-77752958011e | checkpoint | What is the Defect (Take photo of defect, highlight area of repair and add description where required on the photo or comment)
| a899a383-7128-44bd-9a4f-1dd61bc3f96a | checkpoint | Remedial required
| 39160c96-116b-554c-8509-f429477035e3 | tickbox | Grind
| 961ff29e-ea2b-5d97-a8d9-9bec355bfef5 | tickbox | Sand
| c8ba43f5-9762-54d3-bdd6-c5204340eb28 | tickbox | Fill
| 8bab69a8-499c-5194-b84e-d560dcc1c9b2 | tickbox | Drill
| 5bdad10c-6258-506f-95ae-57c35490065b | tickbox | Plaster
| 9a5726e5-8b82-5d9e-91fb-a7a60fda3257 | tickbox | Paint
| 6b49589a-8cd0-5ce0-8d3a-978103caff7a | tickbox | colour match
| e5a9b222-ab44-5017-ba18-f6d6d7f1ca6d | tickbox | Epoxy Reo
| f51f7521-70e4-5b0e-804a-9962fa2151be | dropdown | PHQ, Dayworks, | PHQ, Dayworks,
| 5768cdf8-29a6-4145-a522-0851ba9852c1 | checkpoint | NCR Raised if Required
| 606d7479-e242-471d-a2c5-006d3d19c570 | checkpoint | Remedial completed (Take photo to evidence)
| b65f91af-e11a-58b0-af01-eaa400f7b654 | date | Date remedial completed
| 95f18a3c-84d7-4ca9-9785-11e66380b797 | signoff | Remedial acceptable and signed off by client