## CHK-CIV-RSS Fill Installation
ConQA Team Notes:
Document Title: |  | CHK-013-CIV-SSB-RSS Walls-Fill Placement
Check list Description: |  | SSB RSS Walls-Fill Placement
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 2
Revision Date: |  | 18/3/2024
ITP created by: |  | Victor Mira
ITP approved for use by: |  | Victor Mira
Special Notes to ConQA Team : |  | To be Available for Station Street, Beaconsfield
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Soil reinforcement-Straps | 682.08 | Reinforcing elements shall be placed on top of the compacted fill material and connected to the wall panels. Any twists, kinks, sags or deviations in the reinforcing elements shall be removed prior to the placement of fill material on the reinforcing. | Visual | Each strap | IP | SE/PE | This Checklist
2 | Soil reinforcement-Straps | Installation manual | Correct number of reinforcing element shall be attached to each panel | Visual | Each panel | IP | SE/PE | This Checklist
3 | Soil reinforcements-Connections | IFC Drawings Schedule of lenghts | Grid Strips are to be installed at the back of each panel in correct length and to the correct anchors at the back of each panel - Bolts are to be snug tight. | Visual | Each Fill Layer | IP | SE/PE | This Checklist
4 | Soil reinforcements-Plan arrangement | IFC Drawings Arrangements: VR682.06 | Plan positions of Grid Strips are to be as IFC Drawings. - Grid Strips shall not overlapped | Visual | Each fill layer | IP | SE/PE | This Checklist
5 | Soil reinforcements-Plan arrangement | IFC Drawings Arrangements: VR682.06 | Plan positions of Grid Strips are to be as IFC Drawings. -RSS used in conjunction with a bridge abutment shall be independent of the bridge structure (i.e. Straps shall not cross pile cap boundary unless noted in IFC) | Visual | Where applicable | IP | SE/PE | This Checklist
6 | Soil reinforcements-vertical deviation | IFC Drawings | The vertical deviation of the soil reinforcement shall be within +1% upwards and -0.3% downwards of the soil reinforcement length, relative to the connection height. Avoid clash with drainage as directed in IFC Drawings. | Measure Survey | Each fill Layer | IP | Surveyoe/SE | This Checklist
7 | Fill placement-Protection of Straps | IFC Drawings | A minimum of 200mm select fill required to protect reinforcement elements before tracked machines or vehicles are permitted access over soil reinforcement as per dtp specification 682 and ensure stability of the top layer of reinforcement. | Measure | When applicable | IP | SE/PE | This Checklist
8 | Fill-Pacement | 204.10 | Fill layers to be spread and compacted in layers not exceeding a compacted thickness of 200mm All RSS fill layers to be spread from the back face of panel to tail of soil reinforcing straps | Measure Visual | Each fill layer | IP | PE/SE | This Checklist
9 | Select backfill-moisture content | IFC Drawings | Moisture content of the backfill shall be maintained evenly at all times. Moisture content shall be within 0% to -2% of the optimum moisture content. Any backfill material exceeding the optimum moisture content, must be allowed to dry | Measure | Each Fill Layer | IP | PE/SE | Attached Test Results
10 | Select backfil - placement | IFC Drawings | select bakfill shall be placed in accordance with Vicroads section 204 and compacted to 98% of standard proctor density. Compaction within 1 meter of the wall face shall be achieved by a light weight (Hand Operated) mechanical tamper roller or vibratory system. No large compaction equipment shall be allowed in this zon. Compaction beyond 1 meter of the wall face shall be in accordance with the table VR 204.111 | Measure | Each Fill Layer | HP* | PE/SE | This Checklist
11 | Select back fill-reduced frequency |  | After three consecutive lots of like material have achieved the specified requirement, the contractor may seek the superintendent's agreement to reduce the frequency of testing of subsequent lots to the minimum requirement specified in table 204.142: [Free Text]: Three Consecutive Lots tested to satisfy this requirement. | Documet review | Each Fill Layer | IP | Nominated Authority/PE | Referenced Lots in This Checklist
12 | Select Backfill-Testing frequency-acceptance | IFC Drawings VR 204.14 VR 682.16 | Testing frequency shall be in accordance with Vicroad Specification section 204.14 The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance. No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed Attach: Compaction test results | Measure | Each Fill Layer or every second layer as agreed | HP | Nominated Authority | Attached Test Results
13 | Select backfill -acceptance | VR 204.12 | All layers of fill shall be test rolled in accordance with VR 173. The contractor Shall provide for the superintendent to be present during all test rolling | Visual | Every Fill Layer | HP | Nominated Authority | This Checklist
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /