## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CHK-012-CIV-SSB-RSS Walls-Precast Panel installation | itp |  |  |  |  | CHK-012-CIV-SSB-RSS Walls-Precast Panel installation Rev 0
section | Details
checkpoint | Referenced Documentation
label | Document Title: CHK-012-CIV-SSB-RSS Walls-Precast Panel installation
label | ITP Description: SSB RSS Walls - Panel installation
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 18/3/2024
label | ITP created by: Victor Mira
label | ITP approved for use by: Victor Mira
checkpoint | 1. Panels-survey set out-Tolerance
label | REFERENCE: IFC Drawings VR 682.20
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Base course panels
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 2. Mark-up panel for construction team
label | REFERENCE: Construction Manual
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Mark number of strips per row on the back of each panel.
label | ○ Mark design locatoin (Wall number, row and column) as per elevation drawings on the back of each panel
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each panel
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 3. Panel installation
label | REFERENCE: IFC Drawing:, Schedules:
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: RSS Panels are to be installed as per IFC Drawings and specified schedule.
label | – Check for correct architectural pattern
label | – Check for Weephole Locations
label | – Check the 19mm nominal gap to be maintained
label | – Check the 1 in 40 slope is to be maintained
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each panel
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: WP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 4. Panel installation-Abutment interfaces
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: 20mm nominal gap between panels and Abutment wall is to be maintained
label | ○ Where nominated 125mm wide x 6mm thk hot dipped Galvanized plates fixed to abutment wall OR 250x6 Galvanised Folded Plate as per IFC drawings.
label | ○ 600mm wide BITAC tape installed on the joint
label | ○ Galvanised Plate, installed with M16x75mm long Gr.4.6/S
label | ○ For the slip joint location, spcing between panels to be min 25mm.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 5. Filter fabric -Installation
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Install Filter Fabric against all vertical and horizontal joints
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each course of panel installation
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 6. Drainage-Strip Drain
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Install 300mm wide vertical strip drain -at every vertical joint between panels in RSS wall.
label | ○ Ensure no gap is formed between strip drain and RSS panels.
label | ○ Strip Drain to be encapsulated by non-woven geotextile with minimum width of 500mm in accordance with VR 682
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each course of panel installation
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 7. Panel installation-Survey reference points
label | REFERENCE: VR 682.21
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: To ensure compliance with the tolerances specified in clause 682.20, the Contractor shall install stable and permanent survey reference points on a not more than 5 m (horizontal) by 2 m (vertical) grid covering the whole face of the RSS
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each course of panel installation
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor/SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 8. Traceability of precast units and records
label | REFERENCE: VR 620.09
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Unique ID of precast panel is recorded.
label | – ATTACH: marked-up elevation drawings or installation record with reference to panel ID
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each panel
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Attached marked-up drawing or installation record
date | Date Completed:
checkpoint | 9. Panels installation-Conformance Survey
label | REFERENCE: IFC Drawings VR 682.06, VR 682.17, VR 682.20
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
label | – Relative displacement of adjoining smooth panel faces shall not exceed ±15mm measured normal to face of the wall
label | – Local deviation of the wall face at any location with a 3m straight edge, shall not exceed 15mm
label | – Variation in gap width between facing panels shall not exceed 5mm per meter length and 10mm over the full lenght of the gap
label | – The wall level shall not deviate from the specified level by more than ±20mm
label | – The tolerance of position measured at the top of the wall face shall not excedd 5mm per 1m of wall height
label | – The verticality of the RSS wall facing shall lean backward at a minimum slope of 1(H) in 40 (V)
label | Attach: Survey Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Survey, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each course of panel installation
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Survey Report
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP