## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CHK-013-CIV-SSB-RSS Walls-Fill Placement | itp |  |  |  |  | CHK-013-CIV-SSB-RSS Walls-Fill Placement Rev 2
section | Details
checkpoint | Referenced Documentation
label | Document Title: CHK-013-CIV-SSB-RSS Walls-Fill Placement
label | ITP Description: SSB RSS Walls-Fill Placement
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 2
label | Revision Date: 18/3/2024
label | ITP created by: Victor Mira
label | ITP approved for use by: Victor Mira
checkpoint | 1. Soil reinforcement-Straps
label | REFERENCE: 682.08
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Reinforcing elements shall be placed on top of the compacted fill material and connected to the wall panels.
label | ○ Any twists, kinks, sags or deviations in the reinforcing elements shall be removed prior to the placement of fill material on the reinforcing.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each strap
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 2. Soil reinforcement-Straps
label | REFERENCE: Installation manual
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Correct number of reinforcing element shall be attached to each panel
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each panel
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 3. Soil reinforcements-Connections
label | REFERENCE: IFC Drawings, Schedule of lenghts
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Grid Strips are to be installed at the back of each panel in correct length and to the correct anchors at the back of each panel
label | ○ Bolts are to be snug tight.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Fill Layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 4. Soil reinforcements-Plan arrangement
label | REFERENCE: IFC Drawings Arrangements: VR682.06
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Plan positions of Grid Strips are to be as IFC Drawings.
label | ○ Grid Strips shall not overlapped
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each fill layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 5. Soil reinforcements-Plan arrangement
label | REFERENCE: IFC Drawings Arrangements: VR682.06
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Plan positions of Grid Strips are to be as IFC Drawings.
label | ○ RSS used in conjunction with a bridge abutment shall be independent of the bridge structure (i.e. Straps shall not cross pile cap boundary unless noted in IFC)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 6. Soil reinforcements-vertical deviation
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The vertical deviation of the soil reinforcement shall be within +1% upwards and -0.3% downwards of the soil reinforcement length, relative to the connection height.
label | ○ Avoid clash with drainage as directed in IFC Drawings.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Survey
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each fill Layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor/SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 7. Fill placement-Protection of Straps
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: A minimum of 200mm select fill required to protect reinforcement elements before tracked machines or vehicles are permitted access over soil reinforcement as per dtp specification 682 and ensure stability of the top layer of reinforcement.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: When applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 8. Fill-Pacement
label | REFERENCE: 204.10
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Fill layers to be spread and compacted in layers not exceeding a compacted thickness of 200mm
label | ○ All RSS fill layers to be spread from the back face of panel to tail of soil reinforcing straps
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each fill layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 9. Select backfill-moisture content
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Moisture content of the backfill shall be maintained evenly at all times. Moisture content shall be within 0% to -2% of the optimum moisture content. Any backfill material exceeding the optimum moisture content, must be allowed to dry
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Fill Layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Attached Test Results
date | Date Completed:
checkpoint | 10. Select backfil - placement
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: select backfill shall be placed in accordance with Vicroads section 204 and compacted to 98% of standard proctor density.
label | ○ Compaction within 1 meter of the wall face shall be achieved by a light weight (Hand Operated) mechanical tamper roller or vibratory system. No large compaction equipment shall be allowed in this zon. Compaction beyond 1 meter of the wall face shall be in accordance with the table VR 204.111
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Fill Layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 11. Select back fill-reduced frequency
label | ACCEPTANCE CRITERIA: After three consecutive lots of like material have achieved the specified requirement, the contractor may seek the superintendent's agreement to reduce the frequency of testing of subsequent lots to the minimum requirement specified in table 204.142:
text | Three Consecutive Lots tested to satisfy this requirement.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Fill Layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Referenced Lots in This Checklist
date | Date Completed:
checkpoint | 12. Select Backfill-Testing frequency-acceptance
label | REFERENCE: IFC Drawings VR 204.14, VR 682.16
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Testing frequency shall be in accordance with Vicroad Specification section 204.14
label | ○ The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance. No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed
label | Attach: Compaction test results
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Fill Layer or every second layer as agreed
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Attached Test Results
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13. Select backfill - acceptance
label | REFERENCE: VR 204.12
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All layers of fill shall be test rolled in accordance with VR 173. The contractor Shall provide for the superintendent to be present during all test rolling
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Every Fill Layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP