## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-144-CIV-SSB-RSS Wall Construction | itp |  |  |  |  | ITP-144-CIV-SSB-RSS Wall Construction Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-144-CIV-SSB-RSS Wall Construction
label | ITP Description: SSB-RSS Wall Construction
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): 144-CIV
label | Revision Number: 0
label | Revision Date: 18/3/2024
label | ITP created by: Victor Mira
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: VicRoads Section 682 November 2018
label | 1.2 Non Dependent
label | Reference: VicRoads Section 204 December 2015
label | 1.3 Non Dependent
label | Reference: IFC drawings
section | Preliminaries-Materials
checkpoint | 2.1 Concrete-Leveling Pad
label | REFERENCE: IFC drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: CONCRETE COMPRESSIVE STRENGTH GRADE MUST NOT BE LESS THAN N25 FOR LEVELLING COURSE AND BACKING BLOCKS;
textbox | Reference: Teambinder MA number:
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material approval
date | Date Completed:
checkpoint | 2.2 Select fill
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Select fill shall comply with the requirements of the RSS designer:
label | ○ UNIT WEIGHT: 22 ± 2 kN/m³
label | ○ INTERNAL FRICTION ANGLE ≥ 34.5°
label | Gradation:
label | ○ 150mm : 100% PASSING
label | ○ 37.5mm : 60 TO 100% PASSING
label | ○ 9.5mm : 25 TO 100% PASSING
label | ○ 2.36mm : 15 TO 100% PASSING
label | ○ 0.6mm : 10 TO 100% PASSING
label | ○ 0.075mm : 0 TO 15% PASSING
label | Electrochemical Properties:
label | ○ RESISTIVITY >1000 Ω-cm
label | ○ CHLORIDES <200 mg/kg
label | ○ SULPHATES <200 mg/kg
label | ○ ORGANIC CONTENT 0%
label | Structural Properties:
label | ○ COEFFICIENT OF UNIFORMITY ≥ 5
label | ○ LIQUID LIMIT ≤ 30%
label | ○ PLASTICITY INDEX ≤ 12
label | – The select backfill must meet the minimum requirements of Vicroads Type A filling
textbox | Reference: Material approval in Teambinder
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each material specification
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 Perforated Pipe-material
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Perforated plastic pipe perforations shall be a maximum width of 1.5mm and minimum length of 150mm per m2
textbox | Reference: Teambinder MA number:
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each wall
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Preliminaries-Documents
checkpoint | 3.1 RSS Panels
label | REFERENCE: IFC drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | i. Certificate of Compliance / Birth Certificate
label | ○ 1. Concrete strength;
label | ○ 2.Date of manufacture;
label | ○ 3.Unique Identification number;
label | ○ 4.Mass;
label | ○ 5.Confirmation of number, type and capacity of lifting inserts;
label | ○ 6.Quality assurance sign-off.
label | ii. Compressive strength test results
label | iii. Precast Lifting Design
label | iv. Pre-pour check sheet / ITP
label | v. Post-pour check sheet / ITP
label | vi. Covermeter check record
label | vii. Record of dimensional measurements
label | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder pre-cast supply Lot (don't attach it here)
textbox | Reference: Precast panels MDR Lot in TeamBinder:
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once for each type of panels
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Precast panels Birth certificates and MDR Lot
date | Date Completed:
section | Pre-Construction Activities
checkpoint | 4.1 Foundation
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The foundation material beneath the RSS fill shall be inspected on site by a qualified geotechnical Engineerto ensure that the soil conditions meet the assumed material properties:
label | ○ Effective friction angle: 28°
label | ○ Effective Cohession: 5 kPa
label | AN ARCADIS GEOTECHNICAL ENGINEER SHALL ASSESS FOUNDATION SOILS DURING CONSTRUCTION.
label | Attach: Geotechnical report/Certification
label | – – – – – – – – – – – – – – – – –
label | METHOD: Test, Document Review, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each retaining Wall
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Geotechnical Engineer
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP, Geotechnical report
date | Date Completed:
checkpoint | 4.2 Foundation
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Where the foundation material does not meet the assumed material parameters, the existing ground shall be replaced with VR Type A fill Compacted in accordance with VR 204
label | – Ground improvement works shall be keyed into surrounding material at minimum 200mm Bench width
label | – Ground improvement works shall extend beyond either side of bridge approach to detail show in IFC drawing
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each retaining wall
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Geotechnical Engineer
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.3 Foundation
label | REFERENCE: VR 204.12, VR 204.11
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: areas upon which fills are to be constructed shall be test rolled in accordance with VR 173
label | ○ No Fill shall be placed against or within 3 meters of a structure until the foundation for the fill has been reviewed by the superintendant
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each retaining Wall
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 Levelling Pad-Survey Set out
label | REFERENCE: IFC Drawings VR 682.20
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Survey activities to be undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the tables in IFC Drawings and Vicroads Specification
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each retaining Wall
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Construction / Installation Activities
checkpoint | Shape Arrays installation
label | REFERENCE: IFC Drawings MRP-087-C-ACD-DRG-10-BFD-CSF-3404
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Shape arraye are to be installed and mainatained as specified in Design package 10 notes:
label | ○ Shape arrays shall be installed horizontally across the full width of the embarkment prior to placement of the embankment and reinforced soil structure walls, in accordance with the manufacturer's instructions. Shape arrays shall be installed nominally 5m, 25m and 50m from both the north and south abutment face.
label | ○ Upload Shape array installation records.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each RSS Block
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Installation Documents
date | Date Completed:
checkpoint | 5.1 Form Levelling pad
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Form timber shutters to edge of levelling pad
label | – Levelling pad is a 500mm wide by 150mm thick unreinforced concrete footing
label | – The leveling course level shall NOT deviate from the specified level by mor than ±3mm.
label | – 20mm Nominal gap between levelling pad and adjacent ground beam is to be maintained
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.2 Leveling Pad Concrete Pour
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Concrete to be placed in accordance with 610.
label | Attach: Concrete Delivery Docket
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Concrete Pour record
date | Date Completed:
checkpoint | 5.3 Leveling Pad Concrete Testing
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Concrete testing for compressive strength shall be undertaken at the testing frequency specified in VicRoads Section 610.16 (b)
label | Attach: Concrete test report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Attach Concrete Test Report
date | Date Completed:
checkpoint | 5.4 Levelling Pad-Post Pour Survey-Levelling Course
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Levelling course level shall not deviate from the specified level by more than ±3mm
label | ○ Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each retaining Wall
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Surveyor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Attach Survey Report
date | Date Completed:
checkpoint | 5.5 Wall Panels Installation
label | REFERENCE: 682.17
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
label | ○ Refer to checklist for each course of panels
label | Attach: Lot map
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each course of facing panel
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Inspection record checklist: CHK-CIV-RSS Pre-cast panel installation
date | Date Completed:
checkpoint | 5.6 Drainage-base of the Wall
label | REFERENCE: IFC Drawings VR 702 MRP-087-C-ACD-DRG-10-BFD-CSW-3520
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: 300mm Wide Strip Drain along back of RSS Precast Panel at 2m c/c with 100mm clear distance from straps. Strop Drain to be encapsulated by Non-Woven Geotextile in accordance with DTP Section 682
label | ○ 100mm dia. perforated subsurface longitudinal drainage (1:100 Fall) 500mm nominal above existing surface level wrapped in geotextile and encased in free draining material.
label | ○ Refer to Precast Panel Installation Checklist for each course of panels.
label | Attach: Lot Maps
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each wall
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 5.7 Fill
label | REFERENCE: 682.16
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance. No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed.
label | ○ Refer to checklist for each fill layer
label | Attach: Lot map
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Test, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each layer of fill
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Inspection record checklist: CHK-CIV-RSS Fill installation
date | Date Completed:
checkpoint | 5.8 Panel installation-Settlement monitoring
label | REFERENCE: IFC Drawing MRP-087-C-ACD-DRG-10-BFD-CSF-3404
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: III. DURING FILL PLACEMENT - ONCE PER FORTNIGHT (OTHER PANELS).
label | II. DURING FILL PLACEMENT - TWICE PER WEEK (SHAPE ARRAYS AND BOTTOM ROW OF PANELS ONLY).
label | I. AT LEAST 2 WEEKLY BASELINE READINGS PRIOR TO PLACEMENT OF FILL MATERIAL.
label | ○ FREQUENCY SHOWN BELOW.
label | ○ SHAPE
label | – – – – – – – – – – – – – – – – –
label | METHOD: Survey, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: When applicable as instructed in IFC
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Surveyor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Survey Report
date | Date Completed:
section | Post-construction / Post-installation Activities
checkpoint | 6.1 As-built Survey
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances
label | Attach: Survey As-built / Survey Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Survey Report
date | Date Completed:
checkpoint | 6.2 Wall Post construction monitoring
label | REFERENCE: VR 682.20, VR 682.21
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The Contractor shall take measurements of the position of the RSS at the points defined in clause 682.20(a) to (f) at intervals not exceeding one month for the first six months immediately following completion of the RSS and at intervals not exceeding six months thereafter until the end of the Defects Liability Period.
label | (a) plan position shown on the drawings, at base of wall shall not exceed 15 mm;
label | (b) relative displacement of adjoining smooth panel faces shall not exceed 15 mm measured normal to face of wall;
label | (c) local deviation of the wall face measured at any location with a 3 m straight edge shall not exceed 15 mm;
label | (d) the tolerance on position measured at the top of the wall face shall not exceed 5 mm per 1 metre of wall height;
label | (e) the wall level shall not deviate from the specified level by more than 20 mm;
label | (f) variation in gap width between facing panels shall not exceed 5 mm per metre length and 10 mm over the full length of the gap.
label | The measurements shall be recorded in writing and reported to the Superintendent within two weeks of the survey.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Survey
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each wall
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
date | Date Completed:
checkpoint | 6.3 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP