## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | AA1 |  |  |  |  | Yes | AA1 | 00f5d5bc-029a-412f-a18a-fed2e42a398d
checkpoint-status |  |  | checkpoint | AA1.00 Obtain Access to Lot 8
checkpoint-status |  |  | checkpoint | AA1.01 Investigate Lot 8 for Internal Water Damage
checkpoint-status |  |  | checkpoint | AA1.02 Discuss Findings with Client
checkpoint-status |  |  | checkpoint | AA1.03 Raise Contract Variation if Required
checkpoint-status |  |  | checkpoint | AA1.04 Modify Program to include Contract Variation on Acceptance of Client
checklist-flat |  |  | checklist | BC212 |  |  |  |  | Yes | BC212 | 07274af5-cfd8-4179-b08e-b7e62b164c5c
checkpoint-status |  |  | checkpoint | BC212.00 Check to see if leaks continue
checkpoint-status |  |  | checkpoint | BC212.01 Evidence or Efflorescence Removed
checklist-flat |  |  | checklist | 112 |  |  |  |  | Yes | 112 | 07983aeb-8bb0-4884-993e-5eb3a16af61f
checkpoint-status |  |  | checkpoint | 112 Demolition & Removal of Existing Balcony Surface - 15M2
checkpoint-status |  |  | checkpoint | 112.01 Provide movement joints within the tile surface as required p/m2 - 15M2
checkpoint-status |  |  | checkpoint | 112.02 Apply First Membrane - 15M2
checkpoint-status |  |  | checkpoint | 112.03 Screed - 15M2
checkpoint-status |  |  | checkpoint | 112.04 Apply Second Membrane - 15M2
checkpoint-status |  |  | checkpoint | 112.05 Tiles Supplied - 15M2
checkpoint-status |  |  | checkpoint | 112.06 Tile & Grout balcony surface - 15M2
checkpoint-status |  |  | checkpoint | 112.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 112.08 Skirting Tile and Caulking as required - 18LM
checkpoint-status |  |  | checkpoint | 112.09 Remove any rubbish and clean area - 15M3
checklist-flat |  |  | checklist | 209.1 |  |  |  |  | Yes | 209.1 | 08dc7a70-f5cb-4c68-ad49-352378163985
checkpoint-status |  |  | checkpoint | 209.1 Remove moisture damaged section of the plasterboard ceiling - 16LM
checkpoint-status |  |  | checkpoint | 209.11 Inspect and replace water damaged timber members within the walls - T.B.A.T.B.A.
checkpoint-status |  |  | checkpoint | 209.12 Remove and replace moisture damage wall framing members - T.B.A.T.B.A.
checkpoint-status |  |  | checkpoint | 209.13 Supply and install new plasterboard where removed on the ceiling - 16LM
checkpoint-status |  |  | checkpoint | 209.14 Supply and install new skirting boards - 4LM
checkpoint-status |  |  | checkpoint | 209.15 Paint entire bedroom ceiling with a 3-coat paint system - 12LM
checkpoint-status |  |  | checkpoint | 209.16 Remove all rubbish created by repair work. - 1P
checklist-flat |  |  | checklist | 113 |  |  |  |  | Yes | 113 | 0b39c646-32c6-4a78-9437-679b3b0320b9
checkpoint-status |  |  | checkpoint | 113 Demolition & Removal of Existing Balcony Surface - 81M2
checkpoint-status |  |  | checkpoint | 113.01 Provide movement joints within the tile surface as required p/m2 - 81M2
checkpoint-status |  |  | checkpoint | 113.02 Apply First Membrane - 81M2
checkpoint-status |  |  | checkpoint | 113.03 Screed - 81M2
checkpoint-status |  |  | checkpoint | 113.04 Apply Second Membrane - 81M2
checkpoint-status |  |  | checkpoint | 113.05 Tiles Supplied - 81M2
checkpoint-status |  |  | checkpoint | 113.06 Tile & Grout balcony surface - 81M2
checkpoint-status |  |  | checkpoint | 113.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 113.08 Skirting Tile and Caulking as required - 98LM
checkpoint-status |  |  | checkpoint | 113.09 Remove any rubbish and clean area - 81M3
checklist-flat |  |  | checklist | 301 |  |  |  |  | Yes | 301 | 0f7c85cf-32e0-453b-99c9-fe4fa8f1b42e
checkpoint-status |  |  | checkpoint | 301 Demolition & Removal of Existing Balcony Surface - 0M2
checkpoint-status |  |  | checkpoint | 301.01 Provide movement joints within the tile surface as required p/m2 - 0M2
checkpoint-status |  |  | checkpoint | 301.02 Apply First Membrane - 0M2
checkpoint-status |  |  | checkpoint | 301.03 Screed - 0M2
checkpoint-status |  |  | checkpoint | 301.04 Apply Second Membrane - 0M2
checkpoint-status |  |  | checkpoint | 301.05 Tiles Supplied - 0M2
checkpoint-status |  |  | checkpoint | 301.06 Tile & Grout balcony surface - 0M2
checkpoint-status |  |  | checkpoint | 301.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 301.08 Skirting Tile and Caulking as required - 0LM
checkpoint-status |  |  | checkpoint | 301.09 Remove any rubbish and clean area - 0M3
checklist-flat |  |  | checklist | 1.1 |  |  |  |  | Yes | 1.1 | 106862f6-d475-471f-b48e-a650f90a0d00
checkpoint-status |  |  | checkpoint | 1.1 Remove moisture damaged skirting - 4LM
checkpoint-status |  |  | checkpoint | 1.11 Remove moisture damaged plaster board sheet - 4LM
checkpoint-status |  |  | checkpoint | 1.12 Supply and install new plasterboard - 4LM
checkpoint-status |  |  | checkpoint | 1.13 Supply and install new skirting boards - 4LM
checkpoint-status |  |  | checkpoint | 1.14 Paint new plasterwork and skirting with a 3-coat paint system - 8LM
checkpoint-status |  |  | checkpoint | 1.15 Remove all rubbish created by repair work. - 1P
checklist-flat |  |  | checklist | 8 |  |  |  |  | Yes | 8 | 11c69ad1-6d69-4e34-bdb0-2f01c9deebdc
checkpoint-status |  |  | checkpoint | 8 Demolition & Removal of Existing Balcony Surface - 12M2
checkpoint-status |  |  | checkpoint | 8.01 Provide movement joints within the tile surface as required p/m2 - 12M2
checkpoint-status |  |  | checkpoint | 8.02 Apply First Membrane - 12M2
checkpoint-status |  |  | checkpoint | 8.03 Screed - 12M2
checkpoint-status |  |  | checkpoint | 8.04 Apply Second Membrane - 12M2
checkpoint-status |  |  | checkpoint | 8.05 Tiles Supplied - 12M2
checkpoint-status |  |  | checkpoint | 8.06 Tile & Grout balcony surface - 12M2
checkpoint-status |  |  | checkpoint | 8.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 8.08 Skirting Tile and Caulking as required - 15LM
checkpoint-status |  |  | checkpoint | 8.09 Remove any rubbish and clean area - 12M3
checklist-flat |  |  | checklist | RC |  |  |  |  | Yes | RC | 14f26cc2-1116-4686-91e0-ee95067a541e
checkpoint-status |  |  | checkpoint | RC.00 New Box Gutter Installed & Connected to Existing DP's.
checkpoint-status |  |  | checkpoint | RC.01 New CB Capping to Perimeter of Building.
checkpoint-status |  |  | checkpoint | RC.02 Zincalume Patches Applied to Roof Sheet Dints.
checkpoint-status |  |  | checkpoint | RC.03 All Missing Slotted Vent Caps Replaced.
checkpoint-status |  |  | checkpoint | RC.04 Roof Plumber Assessment & Rectification of Side Entry Canopy Leak.
checkpoint-status |  |  | checkpoint | RC.05 Management, Documentation & Removal of all Redundant Roof Materials.
checkpoint-status |  |  | checkpoint | RC.06 Plasterer to Supply & Fit new Plasterboard Linings Where Removed.
checkpoint-status |  |  | checkpoint | RC.07 Painter to Patch Water Damaged Plaster within Side Entry Foyer.
checkpoint-status |  |  | checkpoint | RC.08 Painter to Paint Entire Foyer Ceiling - 1 undercoat and 2 topcoats, Colour to match the existing paintwork.
checkpoint-status |  |  | checkpoint | RC.09 Rubbish Removal of Builders Rubbish from Site.
checklist-flat |  |  | checklist | PB |  |  |  |  | Yes | PB | 1a32395e-45f1-4d20-b18c-8c0c7d458aeb
checkpoint-status |  |  | checkpoint | PB.00 APM PC Allowance to rectify Planter Boxes - 1A
checkpoint-status |  |  | checkpoint | PB.01 Remove soil from planter boxes and set aside - 40L
checkpoint-status |  |  | checkpoint | PB.02 Removal of existing failed waterproofing - 266L/M2
checkpoint-status |  |  | checkpoint | PB.03 Plumber to repair drain outlets if applicable - 4LM
checkpoint-status |  |  | checkpoint | PB.04 Apply first membrane - 266L/M2
checkpoint-status |  |  | checkpoint | PB.05 Apply second membrane - 266L/M2
checkpoint-status |  |  | checkpoint | PB.06 Reinstate soil - 40L
checkpoint-status |  |  | checkpoint | PB.07 Minders Landscaper - Remove & dispose of Tristaniopsis Luscious at front & R/H side planter boxes.
checkpoint-status |  |  | checkpoint | PB.08 Minders Landscaper - Plant 25 Magnolia (Teddy Bear) 40cm pots.
checkpoint-status |  |  | checkpoint | PB.09 Minders Landscaper - Install irrigation drip line and automated irrigation controllers.
checklist-flat |  |  | checklist | 9 |  |  |  |  | Yes | 9 | 218901cf-6ab5-4f4a-84cd-7550a4558b6e
checkpoint-status |  |  | checkpoint | 9 Demolition & Removal of Existing Balcony Surface - 45M2
checkpoint-status |  |  | checkpoint | 9.01 Provide movement joints within the tile surface as required p/m2 - 45M2
checkpoint-status |  |  | checkpoint | 9.02 Apply First Membrane - 45M2
checkpoint-status |  |  | checkpoint | 9.03 Screed - 45M2
checkpoint-status |  |  | checkpoint | 9.04 Apply Second Membrane - 45M2
checkpoint-status |  |  | checkpoint | 9.05 Tiles Supplied - 45M2
checkpoint-status |  |  | checkpoint | 9.06 Tile & Grout balcony surface - 45M2
checkpoint-status |  |  | checkpoint | 9.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 9.08 Skirting Tile and Caulking as required - 54LM
checkpoint-status |  |  | checkpoint | 9.09 Remove any rubbish and clean area - 45M3
checklist-flat |  |  | checklist | 104 |  |  |  |  | Yes | 104 | 25279833-515f-45b4-8367-c2b052260f8f
checkpoint-status |  |  | checkpoint | 104 Demolition & Removal of Existing Balcony Surface - 8M2
checkpoint-status |  |  | checkpoint | 104.01 Provide movement joints within the tile surface as required p/m2 - 8M2
checkpoint-status |  |  | checkpoint | 104.02 Apply First Membrane - 8M2
checkpoint-status |  |  | checkpoint | 104.03 Screed - 8M2
checkpoint-status |  |  | checkpoint | 104.04 Apply Second Membrane - 8M2
checkpoint-status |  |  | checkpoint | 104.05 Tiles Supplied - 8M2
checkpoint-status |  |  | checkpoint | 104.06 Tile & Grout balcony surface - 8M2
checkpoint-status |  |  | checkpoint | 104.07 Rendering of Internal Balaustrade as required (Including materials) - 1M2
checkpoint-status |  |  | checkpoint | 104.08 Painting of Internal Balaustrade as required (including materials) - 2M2
checkpoint-status |  |  | checkpoint | 104.09 Skirting Tile and Caulking as required - 10LM
checkpoint-status |  |  | checkpoint | 104.1 Remove any rubbish and clean area - 8M3
checklist-flat |  |  | checklist | CAHG |  |  |  |  | Yes | CAHG | 293be85f-9830-4f83-872f-ff97cdbc0ac7
checkpoint-status |  |  | checkpoint | CAHG.00 Fire Door Installation Completed
checkpoint-status |  |  | checkpoint | CAHG.01 Service Enclosure Electrical Penetrations Sealed
checkpoint-status |  |  | checkpoint | CAHG.02 Sensors Connected within Electrical Enclosure
checkpoint-status |  |  | checkpoint | CAHG.03 Debris Removed from Service Enclosure
checklist-flat |  |  | checklist | 6.1 |  |  |  |  | Yes | 6.1 | 295afb04-576d-4347-9856-963687b91daa
checkpoint-status |  |  | checkpoint | 6.1 Remove moisture damaged skirting - 4LM
checkpoint-status |  |  | checkpoint | 6.11 Remove moisture damaged plaster board sheet - 4LM
checkpoint-status |  |  | checkpoint | 6.12 Supply and install new plasterboard - 4LM
checkpoint-status |  |  | checkpoint | 6.13 Supply and install new skirting boards - 4LM
checkpoint-status |  |  | checkpoint | 6.14 Paint new plasterwork and skirting with a 3-coat paint system - 8LM
checkpoint-status |  |  | checkpoint | 6.15 Remove all rubbish created by repair work. - 1P
checklist-flat |  |  | checklist | 5.1 |  |  |  |  | Yes | 5.1 | 2e2e7a0a-e897-4832-9806-5d8c204236c2
checkpoint-status |  |  | checkpoint | 5.1 Remove moisture damaged skirting - 4LM
checkpoint-status |  |  | checkpoint | 5.11 Remove moisture damaged plaster board sheet - 4LM
checkpoint-status |  |  | checkpoint | 5.12 Supply and install new plasterboard - 4LM
checkpoint-status |  |  | checkpoint | 5.13 Supply and install new skirting boards - 4LM
checkpoint-status |  |  | checkpoint | 5.14 Paint new plasterwork and skirting with a 3-coat paint system - 8LM
checkpoint-status |  |  | checkpoint | 5.15 Remove all rubbish created by repair work. - 1P
checklist-flat |  |  | checklist | 102 |  |  |  |  | Yes | 102 | 2e378143-cbf6-4fd3-9a50-bce212492f0d
checkpoint-status |  |  | checkpoint | 102 Demolition & Removal of Existing Balcony Surface - 8M2
checkpoint-status |  |  | checkpoint | 102.01 Provide movement joints within the tile surface as required p/m2 - 8M2
checkpoint-status |  |  | checkpoint | 102.02 Apply First Membrane - 8M2
checkpoint-status |  |  | checkpoint | 102.03 Screed - 8M2
checkpoint-status |  |  | checkpoint | 102.04 Apply Second Membrane - 8M2
checkpoint-status |  |  | checkpoint | 102.05 Tiles Supplied - 8M2
checkpoint-status |  |  | checkpoint | 102.06 Tile & Grout balcony surface - 8M2
checkpoint-status |  |  | checkpoint | 102.07 Rendering of Internal Balaustrade as required (Including materials) - 1M2
checkpoint-status |  |  | checkpoint | 102.08 Painting of Internal Balaustrade as required (including materials) - 2M2
checkpoint-status |  |  | checkpoint | 102.09 Skirting Tile and Caulking as required - 10LM
checkpoint-status |  |  | checkpoint | 102.1 Remove any rubbish and clean area - 8M3
checklist-flat |  |  | checklist | BC207 |  |  |  |  | Yes | BC207 | 3678e38d-ef47-4a24-abed-8fb85b20cf5e
checkpoint-status |  |  | checkpoint | BC207.00 Check to see if leaks continue
checkpoint-status |  |  | checkpoint | BC207.01 Evidence or Efflorescence Removed
checklist-flat |  |  | checklist | 3 |  |  |  |  | Yes | 3 | 39695e3d-c537-439b-b716-5b222ff89209
checkpoint-status |  |  | checkpoint | 3 Demolition & Removal of Existing Balcony Surface - 37M2
checkpoint-status |  |  | checkpoint | 3.01 Provide movement joints within the tile surface as required p/m2 - 37M2
checkpoint-status |  |  | checkpoint | 3.02 Apply First Membrane - 37M2
checkpoint-status |  |  | checkpoint | 3.03 Screed - 37M2
checkpoint-status |  |  | checkpoint | 3.04 Apply Second Membrane - 37M2
checkpoint-status |  |  | checkpoint | 3.05 Tiles Supplied - 37M2
checkpoint-status |  |  | checkpoint | 3.06 Tile & Grout balcony surface - 37M2
checkpoint-status |  |  | checkpoint | 3.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 3.08 Skirting Tile and Caulking as required - 45LM
checkpoint-status |  |  | checkpoint | 3.09 Remove any rubbish and clean area - 37M3
checklist-flat |  |  | checklist | SSU |  |  |  |  | Yes | SSU | 3a0a42c6-60da-4925-9637-39c30bcf2b14
checkpoint-status |  |  | checkpoint | SSU.00 Set up Office
checkpoint-status |  |  | checkpoint | SSU.01 Set up Amenities
checkpoint-status |  |  | checkpoint | SSU.02 Set up First Aid
checkpoint-status |  |  | checkpoint | SSU.03 Set up Lock up Area in Basement
checkpoint-status |  |  | checkpoint | SSU.04 Set up Rubbish Removal Area
checklist-flat |  |  | checklist | 302.1 |  |  |  |  | Yes | 302.1 | 3a64e46e-1dae-4e56-9ae5-26da6fc5c773
checkpoint-status |  |  | checkpoint | 302.1 Remove moisture damaged skirting - 4LM
checkpoint-status |  |  | checkpoint | 302.11 Remove moisture damaged plasterboard - 4LM
checkpoint-status |  |  | checkpoint | 302.12 Supply and install new plasterboard - 4LM
checkpoint-status |  |  | checkpoint | 302.13 Supply and install new skirting boards - 4LM
checkpoint-status |  |  | checkpoint | 302.14 Paint new skirting with a 3 coat paint systern - paint entire surfaces for a consistent finish - 12LM
checkpoint-status |  |  | checkpoint | 302.15 Remove all rubbish created by repair work. - 1P
checklist-flat |  |  | checklist | 205 |  |  |  |  | Yes | 205 | 3a8a44bc-813b-478d-af3a-4b2aee6497ab
checkpoint-status |  |  | checkpoint | 205 Demolition & Removal of Existing Balcony Surface - 8M2
checkpoint-status |  |  | checkpoint | 205.01 Provide movement joints within the tile surface as required p/m2 - 8M2
checkpoint-status |  |  | checkpoint | 205.02 Apply First Membrane - 8M2
checkpoint-status |  |  | checkpoint | 205.03 Screed - 8M2
checkpoint-status |  |  | checkpoint | 205.04 Apply Second Membrane - 8M2
checkpoint-status |  |  | checkpoint | 205.05 Tiles Supplied - 8M2
checkpoint-status |  |  | checkpoint | 205.06 Tile & Grout balcony surface - 8M2
checkpoint-status |  |  | checkpoint | 205.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 205.08 Skirting Tile and Caulking as required - 10LM
checkpoint-status |  |  | checkpoint | 205.09 Remove any rubbish and clean area - 8M3
checklist-flat |  |  | checklist | 109 |  |  |  |  | Yes | 109 | 3d420a2a-9ebd-4b1f-acc0-5bf622601116
checkpoint-status |  |  | checkpoint | 109 Demolition & Removal of Existing Balcony Surface - 0M2
checkpoint-status |  |  | checkpoint | 109.01 Provide movement joints within the tile surface as required p/m2 - 0M2
checkpoint-status |  |  | checkpoint | 109.02 Apply First Membrane - 0M2
checkpoint-status |  |  | checkpoint | 109.03 Screed - 0M2
checkpoint-status |  |  | checkpoint | 109.04 Apply Second Membrane - 0M2
checkpoint-status |  |  | checkpoint | 109.05 Tiles Supplied - 0M2
checkpoint-status |  |  | checkpoint | 109.06 Tile & Grout balcony surface - 0M2
checkpoint-status |  |  | checkpoint | 109.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 109.08 Skirting Tile and Caulking as required - 0LM
checkpoint-status |  |  | checkpoint | 109.09 Remove any rubbish and clean area - 0M3
checklist-flat |  |  | checklist | 211 |  |  |  |  | Yes | 211 | 40f238e4-9404-49c2-9974-d5adad3da7f7
checkpoint-status |  |  | checkpoint | 211 Demolition & Removal of Existing Balcony Surface - 15M2
checkpoint-status |  |  | checkpoint | 211.01 Provide movement joints within the tile surface as required p/m2 - 15M2
checkpoint-status |  |  | checkpoint | 211.02 Apply First Membrane - 15M2
checkpoint-status |  |  | checkpoint | 211.03 Screed - 15M2
checkpoint-status |  |  | checkpoint | 211.04 Apply Second Membrane - 15M2
checkpoint-status |  |  | checkpoint | 211.05 Tiles Supplied - 15M2
checkpoint-status |  |  | checkpoint | 211.06 Tile & Grout balcony surface - 15M2
checkpoint-status |  |  | checkpoint | 211.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 211.08 Skirting Tile and Caulking as required - 18LM
checkpoint-status |  |  | checkpoint | 211.09 Remove any rubbish and clean area - 15M3
checklist-flat |  |  | checklist | CAH3 |  |  |  |  | Yes | CAH3 | 4c9097d5-1bc2-49aa-96b4-15bed2e51661
checkpoint-status |  |  | checkpoint | CAH3.00 Fire Door Installation Completed
checkpoint-status |  |  | checkpoint | CAH3.01 Service Enclosure Electrical Penetrations Sealed
checkpoint-status |  |  | checkpoint | CAH3.02 Sensors Connected within Electrical Enclosure
checkpoint-status |  |  | checkpoint | CAH3.03 Debris Removed from Service Enclosure
checklist-flat |  |  | checklist | 206.1 |  |  |  |  | Yes | 206.1 | 4d1bcf68-0aba-4e29-817f-c25201591af5
checkpoint-status |  |  | checkpoint | 206.11 Remove moisture damaged skirting - 8LM
checkpoint-status |  |  | checkpoint | 206.12 Remove moisture damaged plasterboard - 18LM
checkpoint-status |  |  | checkpoint | 206.13 Inspect for water damaged timber members within the walls - T.B.A.T.B.A.
checkpoint-status |  |  | checkpoint | 206.14 Replace water damaged timber members within the walls - T.B.A.T.B.A.
checkpoint-status |  |  | checkpoint | 206.15 Replace water damaged plasterboard - 18LM
checkpoint-status |  |  | checkpoint | 206.16 Replace water damaged skirting boards - 8LM
checkpoint-status |  |  | checkpoint | 206.17 Paint new plasterwork and skirting with a 3 coat paint system - 24LM
checkpoint-status |  |  | checkpoint | 206.18 Remove all rubbish created by repair work. - 1P
checklist-flat |  |  | checklist | 7.1 |  |  |  |  | Yes | 7.1 | 4dee1de1-8c4d-407a-9ac1-79578b74407a
checkpoint-status |  |  | checkpoint | 7.1 Remove moisture damaged skirting - 4LM
checkpoint-status |  |  | checkpoint | 7.11 Supply and install new skirting boards - 4LM
checkpoint-status |  |  | checkpoint | 7.12 Paint new plasterwork and skirting with a 3-coat paint system - 4LM
checkpoint-status |  |  | checkpoint | 7.13 Remove all rubbish created by repair work. - 1P
checklist-flat |  |  | checklist | 207 |  |  |  |  | Yes | 207 | 4ee7fa81-78d5-4fbd-a73a-4caa09654464
checkpoint-status |  |  | checkpoint | 207 Demolition & Removal of Existing Balcony Surface - 0M2
checkpoint-status |  |  | checkpoint | 207.01 Provide movement joints within the tile surface as required p/m2 - 0M2
checkpoint-status |  |  | checkpoint | 207.02 Apply First Membrane - 0M2
checkpoint-status |  |  | checkpoint | 207.03 Screed - 0M2
checkpoint-status |  |  | checkpoint | 207.04 Apply Second Membrane - 0M2
checkpoint-status |  |  | checkpoint | 207.05 Tiles Supplied - 0M2
checkpoint-status |  |  | checkpoint | 207.06 Tile & Grout balcony surface - 0M2
checkpoint-status |  |  | checkpoint | 207.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 207.08 Skirting Tile and Caulking as required - 0LM
checkpoint-status |  |  | checkpoint | 207.09 Remove any rubbish and clean area - 0M3
checklist-flat |  |  | checklist | Variations |  |  |  |  | Yes | _Add Variations | 50f61b11-ae11-4059-905b-38c8892e649a
checkpoint-status |  |  | checkpoint | Confirm area and location
checkpoint-status |  |  | checkpoint | Confirm task
checkpoint-status |  |  | checkpoint | Confirm measurement / hours / materials
checkpoint-status |  |  | checkpoint | CLIENTS ASSESSMENT
checklist-flat |  |  | checklist | 2.1 |  |  |  |  | Yes | 2.1 | 51f1adf6-d1f0-4960-80a6-ba5b227234e4
checkpoint-status |  |  | checkpoint | 2.1 Remove moisture damaged skirting - 4LM
checkpoint-status |  |  | checkpoint | 2.11 Remove moisture damaged plaster board sheet - 4LM
checkpoint-status |  |  | checkpoint | 2.12 Supply and install new plasterboard - 4LM
checkpoint-status |  |  | checkpoint | 2.13 Supply and install new skirting boards - 4LM
checkpoint-status |  |  | checkpoint | 2.14 Paint new plasterwork and skirting with a 3-coat paint system - 8LM
checkpoint-status |  |  | checkpoint | 2.15 Remove all rubbish created by repair work. - 1P
checklist-flat |  |  | checklist | WSE |  |  |  |  | Yes | WSE | 53b0003c-343f-4f98-9a9f-2c13e2e21d80
checkpoint-status |  |  | checkpoint | WSE.00 Tactile Installation Front Entry
checkpoint-status |  |  | checkpoint | WSE.01 Tactile Installation Side Entry
checkpoint-status |  |  | checkpoint | WSE.02 Handrail Installation for Front Steps
checklist-flat |  |  | checklist | Document Upload |  |  |  |  | Yes | Document Upload | 5a53333c-a1fd-4dfa-abd0-2f1433ee7b8a
checkpoint-no-status |  |  | checkpoint | Document uploaded below
checklist-flat |  |  | checklist | 303 |  |  |  |  | Yes | 303 | 5efd1607-1b28-4ce5-a05b-17e047de2415
checkpoint-status |  |  | checkpoint | 303 Demolition & Removal of Existing Balcony Surface - 22M2
checkpoint-status |  |  | checkpoint | 303.01 Provide movement joints within the tile surface as required p/m2 - 22M2
checkpoint-status |  |  | checkpoint | 303.02 Apply First Membrane - 22M2
checkpoint-status |  |  | checkpoint | 303.03 Supply Acoustic Rubber Underlay - 22M2
checkpoint-status |  |  | checkpoint | 303.04 Fitting Accoustic Rubber Underlay - 22M2
checkpoint-status |  |  | checkpoint | 303.05 Screed - 22M2
checkpoint-status |  |  | checkpoint | 303.06 Apply Second Membrane - 22M2
checkpoint-status |  |  | checkpoint | 303.07 Tiles Supplied - 22M2
checkpoint-status |  |  | checkpoint | 303.08 Tile & Grout balcony surface - 22M2
checkpoint-status |  |  | checkpoint | 303.09 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 303.1 Skirting Tile and Caulking as required - 27LM
checkpoint-status |  |  | checkpoint | 303.11 Remove any rubbish and clean area - 22M3
checklist-flat |  |  | checklist | 105 |  |  |  |  | Yes | 105 | 5f65a136-371a-438d-aa2d-384f19847e54
checkpoint-status |  |  | checkpoint | 105 Demolition & Removal of Existing Balcony Surface - 8M2
checkpoint-status |  |  | checkpoint | 105.01 Provide movement joints within the tile surface as required p/m2 - 8M2
checkpoint-status |  |  | checkpoint | 105.02 Apply First Membrane - 8M2
checkpoint-status |  |  | checkpoint | 105.03 Screed - 8M2
checkpoint-status |  |  | checkpoint | 105.04 Apply Second Membrane - 8M2
checkpoint-status |  |  | checkpoint | 105.05 Tiles Supplied - 8M2
checkpoint-status |  |  | checkpoint | 105.06 Tile & Grout balcony surface - 8M2
checkpoint-status |  |  | checkpoint | 105.07 Rendering of Internal Balaustrade as required (Including materials) - 1M2
checkpoint-status |  |  | checkpoint | 105.08 Painting of Internal Balaustrade as required (including materials) - 2M2
checkpoint-status |  |  | checkpoint | 105.09 Skirting Tile and Caulking as required - 10LM
checkpoint-status |  |  | checkpoint | 105.1 Remove any rubbish and clean area - 8M3
checklist-flat |  |  | checklist | 306.1 |  |  |  |  | Yes | 306.1 | 63c9d949-6179-4bf1-baed-fa2b1a51dae9
checkpoint-status |  |  | checkpoint | 306.1 Skirting Tile and Caulking as required - 77LM
checkpoint-status |  |  | checkpoint | 306.11 Remove any rubbish and clean area - 64M3
checkpoint-status |  |  | checkpoint | 306.12 Remove moisture damaged skirting - 4LM
checkpoint-status |  |  | checkpoint | 306.13 Supply and install new skirting boards - 4LM
checkpoint-status |  |  | checkpoint | 306.14 Paint new skirting with a 3 coat paint systern - paint entire surfaces for a consistent finish - 8LM
checkpoint-status |  |  | checkpoint | 306.15 Remove all rubbish created by repair work. - 1P
checklist-flat |  |  | checklist | 301.1 |  |  |  |  | Yes | 301.1 | 64c1f028-c980-4b30-932f-0c048b498bf6
checkpoint-status |  |  | checkpoint | 301.1 Remove moisture damaged skirting - 4LM
checkpoint-status |  |  | checkpoint | 301.11 Supply and install new skirting boards - 4LM
checkpoint-status |  |  | checkpoint | 301.12 Paint new skirting with a 3 coat paint systern - 4LM
checkpoint-status |  |  | checkpoint | 301.13 Remove all rubbish created by repair work. - 1P
checklist-flat |  |  | checklist | 202 |  |  |  |  | Yes | 202 | 64c4c48a-b6d3-4e9e-98d1-6f6c56dc38fb
checkpoint-status |  |  | checkpoint | 202 Demolition & Removal of Existing Balcony Surface - 0M2
checkpoint-status |  |  | checkpoint | 202.01 Provide movement joints within the tile surface as required p/m2 - 0M2
checkpoint-status |  |  | checkpoint | 202.02 Apply First Membrane - 0M2
checkpoint-status |  |  | checkpoint | 202.03 Screed - 0M2
checkpoint-status |  |  | checkpoint | 202.04 Apply Second Membrane - 0M2
checkpoint-status |  |  | checkpoint | 202.05 Tiles Supplied - 0M2
checkpoint-status |  |  | checkpoint | 202.06 Tile & Grout balcony surface - 0M2
checkpoint-status |  |  | checkpoint | 202.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 202.08 Skirting Tile and Caulking as required - 0LM
checkpoint-status |  |  | checkpoint | 202.09 Remove any rubbish and clean area - 0M3
checklist-flat |  |  | checklist | 103 |  |  |  |  | Yes | 103 | 6646d11c-061a-429a-a768-0e220722c59c
checkpoint-status |  |  | checkpoint | 103 Demolition & Removal of Existing Balcony Surface - 0M2
checkpoint-status |  |  | checkpoint | 103.01 Provide movement joints within the tile surface as required p/m2 - 0M2
checkpoint-status |  |  | checkpoint | 103.02 Apply First Membrane - 0M2
checkpoint-status |  |  | checkpoint | 103.03 Screed - 0M2
checkpoint-status |  |  | checkpoint | 103.04 Apply Second Membrane - 0M2
checkpoint-status |  |  | checkpoint | 103.05 Tiles Supplied - 0M2
checkpoint-status |  |  | checkpoint | 103.06 Tile & Grout balcony surface - 0M2
checkpoint-status |  |  | checkpoint | 103.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 103.08 Painting of Internal Balaustrade as required (including materials) - 0M2
checkpoint-status |  |  | checkpoint | 103.09 Skirting Tile and Caulking as required - 0LM
checkpoint-status |  |  | checkpoint | 103.1 Remove any rubbish and clean area - 0M3
checklist-flat |  |  | checklist | 108 |  |  |  |  | Yes | 108 | 670a4595-3619-4189-924b-b728f0c283e2
checkpoint-status |  |  | checkpoint | 108 Demolition & Removal of Existing Balcony Surface - 9M2
checkpoint-status |  |  | checkpoint | 108.01 Provide movement joints within the tile surface as required p/m2 - 9M2
checkpoint-status |  |  | checkpoint | 108.02 Apply First Membrane - 9M2
checkpoint-status |  |  | checkpoint | 108.03 Screed - 9M2
checkpoint-status |  |  | checkpoint | 108.04 Apply Second Membrane - 9M2
checkpoint-status |  |  | checkpoint | 108.05 Tiles Supplied - 9M2
checkpoint-status |  |  | checkpoint | 108.06 Tile & Grout balcony surface - 9M2
checkpoint-status |  |  | checkpoint | 108.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 108.08 Skirting Tile and Caulking as required - 11LM
checkpoint-status |  |  | checkpoint | 108.09 Remove any rubbish and clean area - 9M3
checklist-flat |  |  | checklist | 7 |  |  |  |  | Yes | 7 | 6cbbd0e2-7d00-4307-adf9-3dc58774674d
checkpoint-status |  |  | checkpoint | 7 Demolition & Removal of Existing Balcony Surface - 14M2
checkpoint-status |  |  | checkpoint | 7.01 Provide movement joints within the tile surface as required p/m2 - 14M2
checkpoint-status |  |  | checkpoint | 7.02 Apply First Membrane - 14M2
checkpoint-status |  |  | checkpoint | 7.03 Screed - 14M2
checkpoint-status |  |  | checkpoint | 7.04 Apply Second Membrane - 14M2
checkpoint-status |  |  | checkpoint | 7.05 Tiles Supplied - 14M2
checkpoint-status |  |  | checkpoint | 7.06 Tile & Grout balcony surface - 14M2
checkpoint-status |  |  | checkpoint | 7.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 7.08 Skirting Tile and Caulking as required - 17LM
checkpoint-status |  |  | checkpoint | 7.09 Remove any rubbish and clean area - 14M3
checklist-flat |  |  | checklist | 6 |  |  |  |  | Yes | 6 | 702584d3-d603-40e2-91fd-e2d4dfdf2681
checkpoint-status |  |  | checkpoint | 6 Demolition & Removal of Existing Balcony Surface - 29M2
checkpoint-status |  |  | checkpoint | 6.01 Provide movement joints within the tile surface as required p/m2 - 29M2
checkpoint-status |  |  | checkpoint | 6.02 Apply First Membrane - 29M2
checkpoint-status |  |  | checkpoint | 6.03 Screed - 29M2
checkpoint-status |  |  | checkpoint | 6.04 Apply Second Membrane - 29M2
checkpoint-status |  |  | checkpoint | 6.05 Tiles Supplied - 29M2
checkpoint-status |  |  | checkpoint | 6.06 Tile & Grout balcony surface - 29M2
checkpoint-status |  |  | checkpoint | 6.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 6.08 Skirting Tile and Caulking as required - 35LM
checkpoint-status |  |  | checkpoint | 6.09 Remove any rubbish and clean area - 29M3
checklist-flat |  |  | checklist | 302 |  |  |  |  | Yes | 302 | 70ecb3d2-9ac6-4562-bc9a-a293ff893b77
checkpoint-status |  |  | checkpoint | 302 Demolition & Removal of Existing Balcony Surface - 0M2
checkpoint-status |  |  | checkpoint | 302.01 Provide movement joints within the tile surface as required p/m2 - 0M2
checkpoint-status |  |  | checkpoint | 302.02 Apply First Membrane - 0M2
checkpoint-status |  |  | checkpoint | 302.03 Screed - 0M2
checkpoint-status |  |  | checkpoint | 302.04 Apply Second Membrane - 0M2
checkpoint-status |  |  | checkpoint | 302.05 Tiles Supplied - 0M2
checkpoint-status |  |  | checkpoint | 302.06 Tile & Grout balcony surface - 0M2
checkpoint-status |  |  | checkpoint | 302.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 302.08 Skirting Tile and Caulking as required - 0LM
checkpoint-status |  |  | checkpoint | 302.09 Remove any rubbish and clean area - 0M3
checklist-flat |  |  | checklist | 104.1 |  |  |  |  | Yes | 104.1 | 77ee8b32-1fb5-4f6a-b560-d80b798128f1
checkpoint-status |  |  | checkpoint | 104.11 Remove moisture damaged skirting - 4LM
checkpoint-status |  |  | checkpoint | 104.12 Supply and install new skirting boards - 4LM
checkpoint-status |  |  | checkpoint | 104.13 Paint new skirting with a 3 coat paint system - 4LM
checkpoint-status |  |  | checkpoint | 104.14 Remove all rubbish created by repair work. - 1P
checklist-flat |  |  | checklist | 212 |  |  |  |  | Yes | 212 | 7aafb5f1-b089-4d76-a0cd-96408a2a1d93
checkpoint-status |  |  | checkpoint | 212 Demolition & Removal of Existing Balcony Surface - 15M2
checkpoint-status |  |  | checkpoint | 212.01 Provide movement joints within the tile surface as required p/m2 - 15M2
checkpoint-status |  |  | checkpoint | 212.02 Apply First Membrane - 15M2
checkpoint-status |  |  | checkpoint | 212.03 Screed - 15M2
checkpoint-status |  |  | checkpoint | 212.04 Apply Second Membrane - 15M2
checkpoint-status |  |  | checkpoint | 212.05 Tiles Supplied - 15M2
checkpoint-status |  |  | checkpoint | 212.06 Tile & Grout balcony surface - 15M2
checkpoint-status |  |  | checkpoint | 212.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 212.08 Skirting Tile and Caulking as required - 18LM
checkpoint-status |  |  | checkpoint | 212.09 Remove any rubbish and clean area - 15M3
checklist-flat |  |  | checklist | 307 |  |  |  |  | Yes | 307 | 7e0856de-567e-4ef5-8eed-0075d0e7d7e6
checkpoint-status |  |  | checkpoint | 307 Demolition & Removal of Existing Balcony Surface - 39M2
checkpoint-status |  |  | checkpoint | 307.01 Provide movement joints within the tile surface as required p/m2 - 39M2
checkpoint-status |  |  | checkpoint | 307.02 Apply First Membrane - 39M2
checkpoint-status |  |  | checkpoint | 307.03 Supply Acoustic Rubber Underlay - 29M2
checkpoint-status |  |  | checkpoint | 307.04 Fitting Accoustic Rubber Underlay - 39M2
checkpoint-status |  |  | checkpoint | 307.05 Screed - 39M2
checkpoint-status |  |  | checkpoint | 307.06 Apply Second Membrane - 39M2
checkpoint-status |  |  | checkpoint | 307.07 Tiles Supplied - 39M2
checkpoint-status |  |  | checkpoint | 307.08 Tile & Grout balcony surface - 39M2
checkpoint-status |  |  | checkpoint | 307.09 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 307.1 Skirting Tile and Caulking as required - 47LM
checkpoint-status |  |  | checkpoint | 307.11 Remove any rubbish and clean area - 39M3
checklist-flat |  |  | checklist | 2 |  |  |  |  | Yes | 2 | 7ef9d376-50d2-45a3-9571-6ccf8711aa69
checkpoint-status |  |  | checkpoint | 2 Demolition & Removal of Existing Balcony Surface - 37M2
checkpoint-status |  |  | checkpoint | 2.01 Provide movement joints within the tile surface as required p/m2 - 37M2
checkpoint-status |  |  | checkpoint | 2.02 Apply First Membrane - 37M2
checkpoint-status |  |  | checkpoint | 2.03 Screed - 37M2
checkpoint-status |  |  | checkpoint | 2.04 Apply Second Membrane - 37M2
checkpoint-status |  |  | checkpoint | 2.05 Tiles Supplied - 37M2
checkpoint-status |  |  | checkpoint | 2.06 Tile & Grout balcony surface - 37M2
checkpoint-status |  |  | checkpoint | 2.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 2.08 Skirting Tile and Caulking as required - 45LM
checkpoint-status |  |  | checkpoint | 2.09 Remove any rubbish and clean area - 37M3
checklist-flat |  |  | checklist | 14.1 |  |  |  |  | Yes | 14.1 | 7fca750a-bf9d-4903-a1ab-444190e94050
checkpoint-status |  |  | checkpoint | 14.10 Remove all skirting boards, architraves and door frame in bedroom 1 - 16LM
checkpoint-status |  |  | checkpoint | 14.11 Remove all the bottom section of plasterboard linings at the horizontal joint within bedroom 1 & 2 - 16LM
checkpoint-status |  |  | checkpoint | 14.12 Remove carpets within the bedrooms 1 & 2 - 16LM
checkpoint-status |  |  | checkpoint | 14.13 Isolate and disconnect the wall mounted GPO's at the base of each wall where the plaster lining is to be removed - 2L
checkpoint-status |  |  | checkpoint | 14.14 Remove all debris and dispose into bins - 6L
checkpoint-status |  |  | checkpoint | 14.15 Inspect and replace water damaged timber members within the walls - T.B.A.T.B.A.
checkpoint-status |  |  | checkpoint | 14.16 Supply and install new plasterboard linings to the internal walls were removed - 32LM
checkpoint-status |  |  | checkpoint | 14.17 Supply and install new skirting boards - 16LM
checkpoint-status |  |  | checkpoint | 14.18 Paint all internal areas 1 undercoat and 2 top­ coats to all walls and woodwork - Paint colour to match the existing - 32LM
checkpoint-status |  |  | checkpoint | 14.19 Reconnect GPO's when work is completed - 4L
checkpoint-status |  |  | checkpoint | 14.20 Lay new carpets to bedrooms 1 & 2 - 16LM
checklist-flat |  |  | checklist | 111 |  |  |  |  | Yes | 111 | 80384af7-2345-41a2-bdec-39f7075f9404
checkpoint-status |  |  | checkpoint | 111 Demolition & Removal of Existing Balcony Surface - 0M2
checkpoint-status |  |  | checkpoint | 111.01 Provide movement joints within the tile surface as required p/m2 - 0M2
checkpoint-status |  |  | checkpoint | 111.02 Apply First Membrane - 0M2
checkpoint-status |  |  | checkpoint | 111.03 Screed - 0M2
checkpoint-status |  |  | checkpoint | 111.04 Apply Second Membrane - 0M2
checkpoint-status |  |  | checkpoint | 111.05 Tiles Supplied - 0M2
checkpoint-status |  |  | checkpoint | 111.06 Tile & Grout balcony surface - 0M2
checkpoint-status |  |  | checkpoint | 111.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 111.08 Skirting Tile and Caulking as required - 0LM
checkpoint-status |  |  | checkpoint | 111.09 Remove any rubbish and clean area - 0M3
checklist-flat |  |  | checklist | BC213 |  |  |  |  | Yes | BC213 | 80ab6a8a-a321-47d7-8418-26ebf2efaf5e
checkpoint-status |  |  | checkpoint | BC213.00 Check to see if leaks continue
checkpoint-status |  |  | checkpoint | BC213.01 Evidence or Efflorescence Removed
checklist-flat |  |  | checklist | CAH2 |  |  |  |  | Yes | CAH2 | 80e5b447-28a0-4e1f-a0e4-d51f58a1e842
checkpoint-status |  |  | checkpoint | CAH2.00 Fire Door Installation Completed
checkpoint-status |  |  | checkpoint | CAH2.01 Service Enclosure Electrical Penetrations Sealed
checkpoint-status |  |  | checkpoint | CAH2.02 Sensors Connected within Electrical Enclosure
checkpoint-status |  |  | checkpoint | CAH2.03 Debris Removed from Service Enclosure
checklist-flat |  |  | checklist | 309 |  |  |  |  | Yes | 309 | 816ef54a-9dcc-467d-b9f2-23ddb6e46dc9
checkpoint-status |  |  | checkpoint | 309 Demolition & Removal of Existing Balcony Surface - 87M2
checkpoint-status |  |  | checkpoint | 309.01 Provide movement joints within the tile surface as required p/m2 - 87M2
checkpoint-status |  |  | checkpoint | 309.02 Apply First Membrane - 87M2
checkpoint-status |  |  | checkpoint | 309.03 Supply Acoustic Rubber Underlay - 87M2
checkpoint-status |  |  | checkpoint | 309.04 Fitting Accoustic Rubber Underlay - 87M2
checkpoint-status |  |  | checkpoint | 309.05 Screed - 87M2
checkpoint-status |  |  | checkpoint | 309.06 Apply Second Membrane - 87M2
checkpoint-status |  |  | checkpoint | 309.07 Tiles Supplied - 87M2
checkpoint-status |  |  | checkpoint | 309.08 Tile & Grout balcony surface - 87M2
checkpoint-status |  |  | checkpoint | 309.09 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 309.1 Skirting Tile and Caulking as required - 105LM
checkpoint-status |  |  | checkpoint | 309.11 Remove any rubbish and clean area - 87M3
checklist-flat |  |  | checklist | 9.1 |  |  |  |  | Yes | 9.1 | 89fbeb78-81b2-48ad-8c2a-94a6b82e3c19
checkpoint-status |  |  | checkpoint | 9.1 Remove moisture damaged skirting - 4LM
checkpoint-status |  |  | checkpoint | 9.11 Supply and install new skirting boards - 4LM
checkpoint-status |  |  | checkpoint | 9.12 Paint new plasterwork and skirting with a 3-coat paint system - 4LM
checkpoint-status |  |  | checkpoint | 9.13 Remove all rubbish created by repair work. - 1P
checklist-flat |  |  | checklist | 305.1 |  |  |  |  | Yes | 305.1 | 8d19eb5e-9751-477e-b99c-89118ebd21e8
checkpoint-status |  |  | checkpoint | 305.1 Skirting Tile and Caulking as required - 42LM
checkpoint-status |  |  | checkpoint | 305.11 Remove any rubbish and clean area - 35M3
checkpoint-status |  |  | checkpoint | 305.12 Remove the skirting board and bottom section of the plaster within the bedroom 1 & 3 - 16LM
checkpoint-status |  |  | checkpoint | 305.13 Remove delaminated section of all parquetry flooring in each room - 8LM
checkpoint-status |  |  | checkpoint | 305.14 Dispose of all debris - 16LM
checkpoint-status |  |  | checkpoint | 305.15 Supply and install new plasterboard linings where removed - 8LM
checkpoint-status |  |  | checkpoint | 305.16 Supply and install new timber parquetry flooring to each room - 23M
checkpoint-status |  |  | checkpoint | 305.17 Fill, sand and polish parquetry timber flooring within entire bedroom 1 & 3. - 1LM2
checkpoint-status |  |  | checkpoint | 305.18 Supply and install new skirting boards where removed. - 16LM
checkpoint-status |  |  | checkpoint | 305.19 Paint all walls and woodwork as required - 1 undercoat and 2 top coats colour to match existing paintwork - 12LM
checkpoint-status |  |  | checkpoint | 305.2 Remove all rubbish created by repair work. - 1P
checklist-flat |  |  | checklist | 203 |  |  |  |  | Yes | 203 | 8d5717cb-d1d7-4c61-bdd2-86164da2387b
checkpoint-status |  |  | checkpoint | 203 Demolition & Removal of Existing Balcony Surface - 8M2
checkpoint-status |  |  | checkpoint | 203.01 Provide movement joints within the tile surface as required p/m2 - 8M2
checkpoint-status |  |  | checkpoint | 203.02 Apply First Membrane - 8M2
checkpoint-status |  |  | checkpoint | 203.03 Screed - 8M2
checkpoint-status |  |  | checkpoint | 203.04 Apply Second Membrane - 8M2
checkpoint-status |  |  | checkpoint | 203.05 Tiles Supplied - 8M2
checkpoint-status |  |  | checkpoint | 203.06 Tile & Grout balcony surface - 8M2
checkpoint-status |  |  | checkpoint | 203.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 203.08 Skirting Tile and Caulking as required - 10LM
checkpoint-status |  |  | checkpoint | 203.09 Remove any rubbish and clean area - 8M3
checklist-flat |  |  | checklist | 305 |  |  |  |  | Yes | 305 | 8f50774d-8d20-4524-82c4-3fb4ff7bc214
checkpoint-status |  |  | checkpoint | 305 Demolition & Removal of Existing Balcony Surface - 35M2
checkpoint-status |  |  | checkpoint | 305.01 Provide movement joints within the tile surface as required p/m2 - 35M2
checkpoint-status |  |  | checkpoint | 305.02 Apply First Membrane - 35M2
checkpoint-status |  |  | checkpoint | 305.03 Supply Acoustic Rubber Underlay - 35M2
checkpoint-status |  |  | checkpoint | 305.04 Fitting Accoustic Rubber Underlay - 35M2
checkpoint-status |  |  | checkpoint | 305.05 Screed - 35M2
checkpoint-status |  |  | checkpoint | 305.06 Apply Second Membrane - 35M2
checkpoint-status |  |  | checkpoint | 305.07 Tiles Supplied - 35M2
checkpoint-status |  |  | checkpoint | 305.08 Tile & Grout balcony surface - 35M2
checkpoint-status |  |  | checkpoint | 305.09 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checklist-flat |  |  | checklist | 11 |  |  |  |  | Yes | 11 | 94ba98fa-6583-443d-b3e0-f981aabb584d
checkpoint-status |  |  | checkpoint | 11 Demolition & Removal of Existing Balcony Surface - 36M2
checkpoint-status |  |  | checkpoint | 11.01 Provide movement joints within the tile surface as required p/m2 - 36M2
checkpoint-status |  |  | checkpoint | 11.02 Apply First Membrane - 36M2
checkpoint-status |  |  | checkpoint | 11.03 Screed - 36M2
checkpoint-status |  |  | checkpoint | 11.04 Apply Second Membrane - 36M2
checkpoint-status |  |  | checkpoint | 11.05 Tiles Supplied - 36M2
checkpoint-status |  |  | checkpoint | 11.06 Tile & Grout balcony surface - 36M2
checkpoint-status |  |  | checkpoint | 11.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 11.08 Skirting Tile and Caulking as required - 44LM
checkpoint-status |  |  | checkpoint | 11.09 Remove any rubbish and clean area - 36M3
checklist-flat |  |  | checklist | 206 |  |  |  |  | Yes | 206 | 99070d99-d2f5-436c-b3cb-023c1c4bf813
checkpoint-status |  |  | checkpoint | 206 Demolition & Removal of Existing Balcony Surface - 13M2
checkpoint-status |  |  | checkpoint | 206.01 Provide movement joints within the tile surface as required p/m2 - 13M2
checkpoint-status |  |  | checkpoint | 206.02 Apply First Membrane - 13M2
checkpoint-status |  |  | checkpoint | 206.03 Screed - 13M2
checkpoint-status |  |  | checkpoint | 206.04 Apply Second Membrane - 13M2
checkpoint-status |  |  | checkpoint | 206.05 Tiles Supplied - 13M2
checkpoint-status |  |  | checkpoint | 206.06 Tile & Grout balcony surface - 13M2
checkpoint-status |  |  | checkpoint | 206.07 Rendering of Internal Balaustrade as required (Including materials) - 1M2
checkpoint-status |  |  | checkpoint | 206.08 Painting of Internal Balaustrade as required (including materials) - 2M2
checkpoint-status |  |  | checkpoint | 206.09 Skirting Tile and Caulking as required - 16LM
checkpoint-status |  |  | checkpoint | 206.1 Remove any rubbish and clean area - 13M3
checklist-flat |  |  | checklist | BCCI |  |  |  |  | Yes | BCCI | 9cb9d762-0fc1-4469-af39-25be740120d4
checkpoint-status |  |  | checkpoint | BCCI.00 Plumbing work in Basement Complete (Plumber x 2 x 1 day)
checkpoint-status |  |  | checkpoint | BCCI.01 Electrician work in Basement Complete (Electrician x 1 x 1 Day)
checkpoint-status |  |  | checkpoint | BCCI.02 Labourer Removed Rubbish
checkpoint-status |  |  | checkpoint | BCCI.03 Commercial Clean Required and Completed
checklist-flat |  |  | checklist | 201 |  |  |  |  | Yes | 201 | 9f31b200-be3d-4bca-b790-d13254bbbb51
checkpoint-status |  |  | checkpoint | 201 Demolition & Removal of Existing Balcony Surface - 21M2
checkpoint-status |  |  | checkpoint | 201.01 Provide movement joints within the tile surface as required p/m2 - 21M2
checkpoint-status |  |  | checkpoint | 201.02 Apply First Membrane - 21M2
checkpoint-status |  |  | checkpoint | 201.03 Screed - 21M2
checkpoint-status |  |  | checkpoint | 201.04 Apply Second Membrane - 21M2
checkpoint-status |  |  | checkpoint | 201.05 Tiles Supplied - 21M2
checkpoint-status |  |  | checkpoint | 201.06 Tile & Grout balcony surface - 21M2
checkpoint-status |  |  | checkpoint | 201.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 201.08 Skirting Tile and Caulking as required - 26LM
checkpoint-status |  |  | checkpoint | 201.09 Remove any rubbish and clean area - 21M3
checklist-flat |  |  | checklist | 204 |  |  |  |  | Yes | 204 | 9f78453a-9fee-42a1-8a0d-c5830c2c4555
checkpoint-status |  |  | checkpoint | 204 Demolition & Removal of Existing Balcony Surface - 8M2
checkpoint-status |  |  | checkpoint | 204.01 Provide movement joints within the tile surface as required p/m2 - 8M2
checkpoint-status |  |  | checkpoint | 204.02 Apply First Membrane - 8M2
checkpoint-status |  |  | checkpoint | 204.03 Screed - 8M2
checkpoint-status |  |  | checkpoint | 204.04 Apply Second Membrane - 8M2
checkpoint-status |  |  | checkpoint | 204.05 Tiles Supplied - 8M2
checkpoint-status |  |  | checkpoint | 204.06 Tile & Grout balcony surface - 8M2
checkpoint-status |  |  | checkpoint | 204.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 204.08 Skirting Tile and Caulking as required - 10LM
checkpoint-status |  |  | checkpoint | 204.09 Remove any rubbish and clean area - 8M3
checklist-flat |  |  | checklist | 210 |  |  |  |  | Yes | 210 | a0f6518d-0d67-4679-ad21-375665389fef
checkpoint-status |  |  | checkpoint | 210 Demolition & Removal of Existing Balcony Surface - 12M2
checkpoint-status |  |  | checkpoint | 210.01 Provide movement joints within the tile surface as required p/m2 - 12M2
checkpoint-status |  |  | checkpoint | 210.02 Apply First Membrane - 12M2
checkpoint-status |  |  | checkpoint | 210.03 Screed - 12M2
checkpoint-status |  |  | checkpoint | 210.04 Apply Second Membrane - 12M2
checkpoint-status |  |  | checkpoint | 210.05 Tiles Supplied - 12M2
checkpoint-status |  |  | checkpoint | 210.06 Tile & Grout balcony surface - 12M2
checkpoint-status |  |  | checkpoint | 210.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 210.08 Skirting Tile and Caulking as required - 15LM
checkpoint-status |  |  | checkpoint | 210.09 Remove any rubbish and clean area - 12M3
checklist-flat |  |  | checklist | 1 |  |  |  |  | Yes | 1 | a367e1e7-80bd-4604-a73b-c605c5e95fba
checkpoint-status |  |  | checkpoint | 1 Demolition & Removal of Existing Balcony Surface - 35M2
checkpoint-status |  |  | checkpoint | 1.01 Provide movement joints within the tile surface as required p/m2 - 35M2
checkpoint-status |  |  | checkpoint | 1.02 Apply First Membrane - 35M2
checkpoint-status |  |  | checkpoint | 1.03 Screed - 35M2
checkpoint-status |  |  | checkpoint | 1.04 Apply Second Membrane - 35M2
checkpoint-status |  |  | checkpoint | 1.05 Tiles Supplied - 35M2
checkpoint-status |  |  | checkpoint | 1.06 Tile & Grout balcony surface - 35M2
checkpoint-status |  |  | checkpoint | 1.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 1.08 Skirting Tile and Caulking as required - 42LM
checkpoint-status |  |  | checkpoint | 1.09 Remove any rubbish and clean area - 1A
checklist-flat |  |  | checklist | 13 |  |  |  |  | Yes | 13 | a82f4653-d477-4349-970e-94a1a3559888
checkpoint-status |  |  | checkpoint | 13 Demolition & Removal of Existing Balcony Surface - 0M2
checkpoint-status |  |  | checkpoint | 13.01 Provide movement joints within the tile surface as required p/m2 - 0M2
checkpoint-status |  |  | checkpoint | 13.02 Apply First Membrane - 0M2
checkpoint-status |  |  | checkpoint | 13.03 Screed - 0M2
checkpoint-status |  |  | checkpoint | 13.04 Apply Second Membrane - 0M2
checkpoint-status |  |  | checkpoint | 13.05 Tiles Supplied - 0M2
checkpoint-status |  |  | checkpoint | 13.06 Tile & Grout balcony surface - 0M2
checkpoint-status |  |  | checkpoint | 13.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 13.08 Skirting Tile and Caulking as required - 0LM
checkpoint-status |  |  | checkpoint | 13.09 Remove any rubbish and clean area - 0M3
checklist-flat |  |  | checklist | 107.1 |  |  |  |  | Yes | 107.1 | ad69a0e3-8c63-4975-901d-39dc2e8346e3
checkpoint-status |  |  | checkpoint | 107.1 Remove moisture damaged skirting - 8LM
checkpoint-status |  |  | checkpoint | 107.11 Remove moisture damaged plaster board sheet - 18LM
checkpoint-status |  |  | checkpoint | 107.12 Inspect and replace water damaged timber members within the walls - T.B.A.T.B.A.
checkpoint-status |  |  | checkpoint | 107.13 Isolate and disconnect the wall mounted GPO's at the base of each wall where the plaster lining is to be removed - 2L
checkpoint-status |  |  | checkpoint | 107.14 Remove all debris and dispose into bins - 8L
checkpoint-status |  |  | checkpoint | 107.15 Inspect and replace water damaged timber members within the walls - T.B.A.T.B.A.
checkpoint-status |  |  | checkpoint | 107.16 Supply and install new plasterboard linings to the internal walls where removed - 18LM
checkpoint-status |  |  | checkpoint | 107.17 Supply and install new skirting boards - 8LM
checkpoint-status |  |  | checkpoint | 107.18 Paint all repaired internal surfaces with 1 undercoat and 2 top­ coats - Paint colour to match the existing. - 24LM
checkpoint-status |  |  | checkpoint | 107.19 Remove all rubbish created by repair work. - 1P
checklist-flat |  |  | checklist | 10 |  |  |  |  | Yes | 10 | af9c70c6-bb3a-4bf3-a51e-11656fe06368
checkpoint-status |  |  | checkpoint | 10 Demolition & Removal of Existing Balcony Surface - 66M2
checkpoint-status |  |  | checkpoint | 10.01 Provide movement joints within the tile surface as required p/m2 - 66M2
checkpoint-status |  |  | checkpoint | 10.02 Apply First Membrane - 66M2
checkpoint-status |  |  | checkpoint | 10.03 Screed - 66M2
checkpoint-status |  |  | checkpoint | 10.04 Apply Second Membrane - 66M2
checkpoint-status |  |  | checkpoint | 10.05 Tiles Supplied - 66M2
checkpoint-status |  |  | checkpoint | 10.06 Tile & Grout balcony surface - 66M2
checkpoint-status |  |  | checkpoint | 10.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 10.08 Skirting Tile and Caulking as required - 80LM
checkpoint-status |  |  | checkpoint | 10.09 Remove any rubbish and clean area - 66M3
checklist-flat |  |  | checklist | 101.1 |  |  |  |  | Yes | 101.1 | b294d031-c0a8-41bd-80c2-c69ffc88cb86
checkpoint-status |  |  | checkpoint | 101.11 Remove water damaged skirting boards - 4lm
checkpoint-status |  |  | checkpoint | 101.12 Supply and install new skirting boards - 4LM
checkpoint-status |  |  | checkpoint | 101.13 Paint new skirting with a 3 coat paint system. - 4LM
checkpoint-status |  |  | checkpoint | 101.14 Remove all rubbish created by repair work. - 1P
checklist-flat |  |  | checklist | SCE |  |  |  |  | Yes | SCE | b7dbd943-b825-4211-9ab8-4c66ff76dd1d
checkpoint-status |  |  | checkpoint | SCE.00 Dismantle Lock up and Clean Area in Basement
checkpoint-status |  |  | checkpoint | SCE.01 Clean Lock up Area in Basement
checkpoint-status |  |  | checkpoint | SCE.02 Dismantle/ Remove Amenities
checkpoint-status |  |  | checkpoint | SCE.03 Clean Amenities Area
checkpoint-status |  |  | checkpoint | SCE.04 Dismantle Site Office
checkpoint-status |  |  | checkpoint | SCE.05 Clean Site Office Area
checkpoint-status |  |  | checkpoint | SCE.06 Dismantle Rubbish Removal Area
checkpoint-status |  |  | checkpoint | SCE.07 Clean up Rubbish Removal Area
checkpoint-status |  |  | checkpoint | SCE.08 Have Bin Removed
checkpoint-status |  |  | checkpoint | SCE.09 Exit Site
checklist-flat |  |  | checklist | 202.1 |  |  |  |  | Yes | 202.1 | b9f95af1-3f90-4a87-bdb3-7e66e09c5a26
checkpoint-status |  |  | checkpoint | 202.1 Remove moisture damaged skirting - 4LM
checkpoint-status |  |  | checkpoint | 202.11 Supply and install new skirting boards - 4LM
checkpoint-status |  |  | checkpoint | 202.12 Paint new skirting with a 3 coat paint systern - 4LM
checkpoint-status |  |  | checkpoint | 202.13 Remove all rubbish created by repair work. - 1P
checklist-flat |  |  | checklist | 107 |  |  |  |  | Yes | 107 | ba070831-d7dd-4dd9-8bf6-f3d87f706fce
checkpoint-status |  |  | checkpoint | 107 Demolition & Removal of Existing Balcony Surface - 12M2
checkpoint-status |  |  | checkpoint | 107.01 Provide movement joints within the tile surface as required p/m2 - 12M2
checkpoint-status |  |  | checkpoint | 107.02 Apply First Membrane - 12M2
checkpoint-status |  |  | checkpoint | 107.03 Screed - 12M2
checkpoint-status |  |  | checkpoint | 107.04 Apply Second Membrane - 12M2
checkpoint-status |  |  | checkpoint | 107.05 Tiles Supplied - 12M2
checkpoint-status |  |  | checkpoint | 107.06 Tile & Grout balcony surface - 12M2
checkpoint-status |  |  | checkpoint | 107.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 107.08 Skirting Tile and Caulking as required - 15LM
checkpoint-status |  |  | checkpoint | 107.09 Remove any rubbish and clean area - 12M3
checklist-flat |  |  | checklist | CAH1 |  |  |  |  | Yes | CAH1 | bb54e747-8724-451d-a16e-23e205e43cc6
checkpoint-status |  |  | checkpoint | CAH1.00 Fire Door Installation Completed
checkpoint-status |  |  | checkpoint | CAH1.01 Service Enclosure Electrical Penetrations Sealed
checkpoint-status |  |  | checkpoint | CAH1.02 Sensors Connected within Electrical Enclosure
checkpoint-status |  |  | checkpoint | CAH1.03 Debris Removed from Service Enclosure
checklist-flat |  |  | checklist | 110 |  |  |  |  | Yes | 110 | bcea57ea-fb9a-4930-b180-5aadfbe0ce7d
checkpoint-status |  |  | checkpoint | 110 Demolition & Removal of Existing Balcony Surface - 0M2
checkpoint-status |  |  | checkpoint | 110.01 Provide movement joints within the tile surface as required p/m2 - 0M2
checkpoint-status |  |  | checkpoint | 110.02 Apply First Membrane - 0M2
checkpoint-status |  |  | checkpoint | 110.03 Screed - 0M2
checkpoint-status |  |  | checkpoint | 110.04 Apply Second Membrane - 0M2
checkpoint-status |  |  | checkpoint | 110.05 Tiles Supplied - 0M2
checkpoint-status |  |  | checkpoint | 110.06 Tile & Grout balcony surface - 0M2
checkpoint-status |  |  | checkpoint | 110.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 110.08 Skirting Tile and Caulking as required - 0LM
checkpoint-status |  |  | checkpoint | 110.09 Remove any rubbish and clean area - 0M3
checklist-flat |  |  | checklist | 5 |  |  |  |  | Yes | 5 | bd6c46bc-118f-400e-b6aa-55e9da3d8d67
checkpoint-status |  |  | checkpoint | 5 Demolition & Removal of Existing Balcony Surface - 37M2
checkpoint-status |  |  | checkpoint | 5.01 Provide movement joints within the tile surface as required p/m2 - 37M2
checkpoint-status |  |  | checkpoint | 5.02 Apply First Membrane - 37M2
checkpoint-status |  |  | checkpoint | 5.03 Screed - 37M2
checkpoint-status |  |  | checkpoint | 5.04 Apply Second Membrane - 37M2
checkpoint-status |  |  | checkpoint | 5.05 Tiles Supplied - 37M2
checkpoint-status |  |  | checkpoint | 5.06 Tile & Grout balcony surface - 37M2
checkpoint-status |  |  | checkpoint | 5.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 5.08 Skirting Tile and Caulking as required - 45LM
checkpoint-status |  |  | checkpoint | 5.09 Remove any rubbish and clean area - 37M3
checklist-flat |  |  | checklist | 205.1 |  |  |  |  | Yes | 205.1 | c41ecd59-dab9-4003-b059-b0af76e9d8f5
checkpoint-status |  |  | checkpoint | 205.1 Remove moisture damaged section of the plasterboard ceiling - 16LM
checkpoint-status |  |  | checkpoint | 205.11 Inspect and replace water damaged timber members within the walls - T.B.A.T.B.A.
checkpoint-status |  |  | checkpoint | 205.12 Remove and replace moisture damage wall framing members - 4LM
checkpoint-status |  |  | checkpoint | 205.13 Supply and install new plasterboard where removed on the ceiling - 16LM
checkpoint-status |  |  | checkpoint | 205.14 Paint entire bedroom ceiling with a 3-coat paint system - 12LM
checkpoint-status |  |  | checkpoint | 205.15 Remove all rubbish created by repair work. - 1P
checklist-flat |  |  | checklist | 12 |  |  |  |  | Yes | 12 | c507cb8f-6058-4fec-99be-0b223561ff7b
checkpoint-status |  |  | checkpoint | 12 Demolition & Removal of Existing Balcony Surface - 66M2
checkpoint-status |  |  | checkpoint | 12.01 Provide movement joints within the tile surface as required p/m2 - 66M2
checkpoint-status |  |  | checkpoint | 12.02 Apply First Membrane - 66M2
checkpoint-status |  |  | checkpoint | 12.03 Screed - 66M2
checkpoint-status |  |  | checkpoint | 12.04 Apply Second Membrane - 66M2
checkpoint-status |  |  | checkpoint | 12.05 Tiles Supplied - 66M2
checkpoint-status |  |  | checkpoint | 12.06 Tile & Grout balcony surface - 66M2
checkpoint-status |  |  | checkpoint | 12.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 12.08 Skirting Tile and Caulking as required - 80LM
checkpoint-status |  |  | checkpoint | 12.09 Remove any rubbish and clean area - 66M3
checklist-flat |  |  | checklist | BCSSF |  |  |  |  | Yes | BCSSF | c9062efd-d524-47e6-81b6-4283811048b0
checkpoint-status |  |  | checkpoint | BCSSF.00 Check to see if leaks continue
checkpoint-status |  |  | checkpoint | BCSSF.01 Evidence or Efflorescence Removed
checklist-flat |  |  | checklist | 213 |  |  |  |  | Yes | 213 | d396f2d8-2803-426a-9c99-6c89147f4c8b
checkpoint-status |  |  | checkpoint | 213 Demolition & Removal of Existing Balcony Surface - 81M2
checkpoint-status |  |  | checkpoint | 213.01 Provide movement joints within the tile surface as required p/m2 - 81M2
checkpoint-status |  |  | checkpoint | 213.02 Apply First Membrane - 81M2
checkpoint-status |  |  | checkpoint | 213.03 Screed - 81M2
checkpoint-status |  |  | checkpoint | 213.04 Apply Second Membrane - 81M2
checkpoint-status |  |  | checkpoint | 213.05 Tiles Supplied - 81M2
checkpoint-status |  |  | checkpoint | 213.06 Tile & Grout balcony surface - 81M2
checkpoint-status |  |  | checkpoint | 213.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 213.08 Skirting Tile and Caulking as required - 98LM
checkpoint-status |  |  | checkpoint | 213.09 Remove any rubbish and clean area - 81M3
checklist-flat |  |  | checklist | 212.1 |  |  |  |  | Yes | 212.1 | d552922e-f3d7-4609-a998-dcfa22c057df
checkpoint-status |  |  | checkpoint | 212.1 Remove moisture damaged skirting - 4LM
checkpoint-status |  |  | checkpoint | 212.11 Supply and install new skirting boards - 4LM
checkpoint-status |  |  | checkpoint | 212.12 Paint new skirting with a 3 coat paint systern - 4LM
checkpoint-status |  |  | checkpoint | 212.13 Remove all rubbish created by repair work. - 1P
checklist-flat |  |  | checklist | 304 |  |  |  |  | Yes | 304 | de3c825a-6eca-4452-9a5f-71250d71a312
checkpoint-status |  |  | checkpoint | 304 Demolition & Removal of Existing Balcony Surface - 20M2
checkpoint-status |  |  | checkpoint | 304.01 Provide movement joints within the tile surface as required p/m2 - 20M2
checkpoint-status |  |  | checkpoint | 304.02 Apply First Membrane - 20M2
checkpoint-status |  |  | checkpoint | 304.03 Supply Acoustic Rubber Underlay - 20M2
checkpoint-status |  |  | checkpoint | 304.04 Fitting Accoustic Rubber Underlay - 20M2
checkpoint-status |  |  | checkpoint | 304.05 Screed - 20M2
checkpoint-status |  |  | checkpoint | 304.06 Apply Second Membrane - 20M2
checkpoint-status |  |  | checkpoint | 304.07 Tiles Supplied - 20M2
checkpoint-status |  |  | checkpoint | 304.08 Tile & Grout balcony surface - 20M2
checkpoint-status |  |  | checkpoint | 304.09 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checklist-flat |  |  | checklist | 106.1 |  |  |  |  | Yes | 106.1 | eb44830a-91ab-40c5-a0d7-0a1572164985
checkpoint-status |  |  | checkpoint | 106.11 Remove moisture damaged skirting - 5LM
checkpoint-status |  |  | checkpoint | 106.12 Remove moisture damaged plaster board sheet - 16LM
checkpoint-status |  |  | checkpoint | 106.13 Supply and install new plasterboard - 16LM
checkpoint-status |  |  | checkpoint | 106.14 Supply and install new skirting boards - 5LM
checkpoint-status |  |  | checkpoint | 106.15 Paint new plasterwork and skirting with a 3-coat paint system - 16LM
checkpoint-status |  |  | checkpoint | 106.16 Remove all rubbish created by repair work. - 1P
checklist-flat |  |  | checklist | 304.1 |  |  |  |  | Yes | 304.1 | eb59c47b-40ed-4537-a58c-77a90a617a4f
checkpoint-status |  |  | checkpoint | 304.1 Skirting Tile and Caulking as required - 24LM
checkpoint-status |  |  | checkpoint | 304.11 Remove any rubbish and clean area - 20M3
checkpoint-status |  |  | checkpoint | 304.12 Remove the moisture damaged skirting adjacent to the window in the dining area - 9LM
checkpoint-status |  |  | checkpoint | 304.13 Remove the moisture damaged flooring adjacent to the window in the dining area - 23LM
checkpoint-status |  |  | checkpoint | 304.14 Dispose of all debris - 1P
checkpoint-status |  |  | checkpoint | 304.15 Supply and install new flooring where removed - profile and finish to match the existing flooring - 23LM
checkpoint-status |  |  | checkpoint | 304.16 Supply and install new skirting boards where removed. - 9LM
checkpoint-status |  |  | checkpoint | 304.17 Paint all new skirting with a 3-coat paint system - colour to match the existing - 8LM
checkpoint-status |  |  | checkpoint | 304.18 Remove all rubbish created by repair work. - 1P
checklist-flat |  |  | checklist | 308 |  |  |  |  | Yes | 308 | eb5e064b-5f0f-4b41-b2ef-65546441faf0
checkpoint-status |  |  | checkpoint | 308 Demolition & Removal of Existing Balcony Surface - 37M2
checkpoint-status |  |  | checkpoint | 308.01 Provide movement joints within the tile surface as required p/m2 - 37M2
checkpoint-status |  |  | checkpoint | 308.02 Apply First Membrane - 37M2
checkpoint-status |  |  | checkpoint | 308.03 Supply Acoustic Rubber Underlay - 37M2
checkpoint-status |  |  | checkpoint | 308.04 Fitting Accoustic Rubber Underlay - 37M2
checkpoint-status |  |  | checkpoint | 308.05 Screed - 37M2
checkpoint-status |  |  | checkpoint | 308.06 Apply Second Membrane - 37M2
checkpoint-status |  |  | checkpoint | 308.07 Tiles Supplied - 37M2
checkpoint-status |  |  | checkpoint | 308.08 Tile & Grout balcony surface - 37M2
checkpoint-status |  |  | checkpoint | 308.09 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 308.1 Skirting Tile and Caulking as required - 45LM
checkpoint-status |  |  | checkpoint | 308.11 Remove any rubbish and clean area - 37M3
checklist-flat |  |  | checklist | 14 |  |  |  |  | Yes | 14 | eb7cc565-73ff-442d-9d60-f28a384bd4ef
checkpoint-status |  |  | checkpoint | 14 Demolition & Removal of Existing Balcony Surface - 81M2
checkpoint-status |  |  | checkpoint | 14.01 Provide movement joints within the tile surface as required p/m2 - 81M2
checkpoint-status |  |  | checkpoint | 14.02 Apply First Membrane - 81M2
checkpoint-status |  |  | checkpoint | 14.03 Screed - 81M2
checkpoint-status |  |  | checkpoint | 14.04 Apply Second Membrane - 81M2
checkpoint-status |  |  | checkpoint | 14.05 Tiles Supplied - 81M2
checkpoint-status |  |  | checkpoint | 14.06 Tile & Grout balcony surface - 81M2
checkpoint-status |  |  | checkpoint | 14.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 14.08 Skirting Tile and Caulking as required - 98LM
checkpoint-status |  |  | checkpoint | 14.09 Remove any rubbish and clean area - 81M3
checklist-flat |  |  | checklist | 208 |  |  |  |  | Yes | 208 | eba7c6d7-5414-478b-843b-cf6fac5abfff
checkpoint-status |  |  | checkpoint | 208 Demolition & Removal of Existing Balcony Surface - 0M2
checkpoint-status |  |  | checkpoint | 208.01 Provide movement joints within the tile surface as required p/m2 - 0M2
checkpoint-status |  |  | checkpoint | 208.02 Apply First Membrane - 0M2
checkpoint-status |  |  | checkpoint | 208.03 Screed - 0M2
checkpoint-status |  |  | checkpoint | 208.04 Apply Second Membrane - 0M2
checkpoint-status |  |  | checkpoint | 208.05 Tiles Supplied - 0M2
checkpoint-status |  |  | checkpoint | 208.06 Tile & Grout balcony surface - 0M2
checkpoint-status |  |  | checkpoint | 208.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 208.08 Skirting Tile and Caulking as required - 0LM
checkpoint-status |  |  | checkpoint | 208.09 Remove any rubbish and clean area - 0M3
checklist-flat |  |  | checklist | 4 |  |  |  |  | Yes | 4 | ec73bc0b-ae6a-4c4c-b1b0-95844979248c
checkpoint-status |  |  | checkpoint | 4 Demolition & Removal of Existing Balcony Surface - 16M2
checkpoint-status |  |  | checkpoint | 4.01 Provide movement joints within the tile surface as required p/m2 - 16M2
checkpoint-status |  |  | checkpoint | 4.02 Apply First Membrane - 16M2
checkpoint-status |  |  | checkpoint | 4.03 Screed - 16M2
checkpoint-status |  |  | checkpoint | 4.04 Apply Second Membrane - 16M2
checkpoint-status |  |  | checkpoint | 4.05 Tiles Supplied - 16M2
checkpoint-status |  |  | checkpoint | 4.06 Tile & Grout balcony surface - 16M2
checkpoint-status |  |  | checkpoint | 4.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 4.08 Skirting Tile and Caulking as required - 20LM
checkpoint-status |  |  | checkpoint | 4.09 Remove any rubbish and clean area - 16M3
checklist-flat |  |  | checklist | BC011 |  |  |  |  | Yes | BC011 | ed5da0ef-1bcc-4f30-b4c3-1d2143d4c458
checkpoint-status |  |  | checkpoint | BC011.00 Check to see if leaks continue
checkpoint-status |  |  | checkpoint | BC011.01 Evidence or Efflorescence Removed
checklist-flat |  |  | checklist | 209 |  |  |  |  | Yes | 209 | f1f1da04-644f-4e2f-a76e-5d2b774995db
checkpoint-status |  |  | checkpoint | 209 Demolition & Removal of Existing Balcony Surface - 15M2
checkpoint-status |  |  | checkpoint | 209.01 Provide movement joints within the tile surface as required p/m2 - 15M2
checkpoint-status |  |  | checkpoint | 209.02 Apply First Membrane - 15M2
checkpoint-status |  |  | checkpoint | 209.03 Screed - 15M2
checkpoint-status |  |  | checkpoint | 209.04 Apply Second Membrane - 15M2
checkpoint-status |  |  | checkpoint | 209.05 Tiles Supplied - 15M2
checkpoint-status |  |  | checkpoint | 209.06 Tile & Grout balcony surface - 15M2
checkpoint-status |  |  | checkpoint | 209.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint-status |  |  | checkpoint | 209.08 Skirting Tile and Caulking as required - 18LM
checkpoint-status |  |  | checkpoint | 209.09 Remove any rubbish and clean area - 15M3
checklist-flat |  |  | checklist | 108.1 |  |  |  |  | Yes | 108.1 | f2358e10-152a-4992-bc24-9f0d3af38667
checkpoint-status |  |  | checkpoint | 108.1 Sand and fill skirting below the window sill in the living area - 8LM
checkpoint-status |  |  | checkpoint | 108.11 Paint all repaired internal surfaces with 1 undercoat and 2 top­ coats - Paint colour to match the existing. - 8LM
checkpoint-status |  |  | checkpoint | 108.12 Remove all rubbish created by repair work. - 1P
checklist-flat |  |  | checklist | 213.1 |  |  |  |  | Yes | 213.1 | f4b359e0-1314-4fae-b41a-ab00673f6e70
checkpoint-status |  |  | checkpoint | 213.1 Remove the luminaries and exhaust fans on the bathroom ceiling and set aside - 2L
checkpoint-status |  |  | checkpoint | 213.11 Remove the existing shower screen and set aside - 2L
checkpoint-status |  |  | checkpoint | 213.12 Plumber to remove the existing laundry trough and set aside - 1L
checkpoint-status |  |  | checkpoint | 213.13 Remove the ceiling in the bathroom - 2L
checkpoint-status |  |  | checkpoint | 213.14 Remove the moisture damage wall linings adjacent to the laundry trough - 16L
checkpoint-status |  |  | checkpoint | 213.15 Inspect wall framing members for moisture damage - T.B.A.T.B.A.
checkpoint-status |  |  | checkpoint | 213.16 Remove and replace moisture damage framing members - T.B.A.T.B.A.
checkpoint-status |  |  | checkpoint | 213.17 Remove the moisture damaged skirting in the hallway cupboard - 3LM
checkpoint-status |  |  | checkpoint | 213.18 Remove the moisture damaged skirting in the living room under the window - 16LM
checkpoint-status |  |  | checkpoint | 213.19 Provide mould remediation to area where mould is identified - 1A
checkpoint-status |  |  | checkpoint | 213.2 Supply and install new plasterboard where removed on the ceiling - T.B.A.LM
checkpoint-status |  |  | checkpoint | 213.21 Supply and install new plasterboard on the wall in the bathroom - 16LM
checkpoint-status |  |  | checkpoint | 213.22 Supply and install new skirting in the hallway cupboard - 3LM
checkpoint-status |  |  | checkpoint | 213.23 Supply and install new skirting in the living room - 16LM
checkpoint-status |  |  | checkpoint | 213.24 Supply and install skirting tile in the bathroom where removed from wall surface - T.B.A.LM
checkpoint-status |  |  | checkpoint | 213.25 Paint entire bathroom ceiling with a 3-coat paint system to provide a consistent surface finish - 24LM
checkpoint-status |  |  | checkpoint | 213.26 Paint all new skirting with a 3-coat paint system - colour to match the existing - 19LM
checkpoint-status |  |  | checkpoint | 213.27 Plumber to reinstate laundry trough - 1LM
checkpoint-status |  |  | checkpoint | 213.28 Reinstall luminaries & exhaust fans - 4L
checkpoint-status |  |  | checkpoint | 213.29 Reinstall shower screen - 1L
checkpoint-status |  |  | checkpoint | 213.3 Remove all rubbish created by repair work. - 1P
checklist-flat |  |  | checklist | 101 |  |  |  |  | Yes | 101 | f4f8bacb-59b5-4019-b6ab-1544d873c2cc
checkpoint-status |  |  | checkpoint | 101 Demolition & Removal of Existing Balcony Surface - 21M2
checkpoint-status |  |  | checkpoint | 101.01 Provide movement joints within the tile surface as required p/m2 - 21M2
checkpoint-status |  |  | checkpoint | 101.02 Apply First Membrane - 21M2
checkpoint-status |  |  | checkpoint | 101.03 Screed - 21M2
checkpoint-status |  |  | checkpoint | 101.04 Apply Second Membrane - 21M2
checkpoint-status |  |  | checkpoint | 101.05 Tiles Supplied - 21M2
checkpoint-status |  |  | checkpoint | 101.06 Tile & Grout balcony surface - 21M2
checkpoint-status |  |  | checkpoint | 101.07 Rendering of Internal Balaustrade as required (Including materials) - 1M2
checkpoint-status |  |  | checkpoint | 101.08 Painting of Internal Balaustrade as required (including materials) - 2M2
checkpoint-status |  |  | checkpoint | 101.09 Skirting Tile and Caulking as required - 26LM
checkpoint-status |  |  | checkpoint | 101.1 Remove any rubbish and clean area - 21M3
checklist-flat |  |  | checklist | 306 |  |  |  |  | Yes | 306 | ff6fdb2d-a86b-4e32-9608-5e6d935a5ed7
checkpoint-status |  |  | checkpoint | 306 Demolition & Removal of Existing Balcony Surface - 64M2
checkpoint-status |  |  | checkpoint | 306.01 Provide movement joints within the tile surface as required p/m2 - 64M2
checkpoint-status |  |  | checkpoint | 306.02 Apply First Membrane - 64M2
checkpoint-status |  |  | checkpoint | 306.03 Supply Acoustic Rubber Underlay - 64M2
checkpoint-status |  |  | checkpoint | 306.04 Fitting Accoustic Rubber Underlay - 64M2
checkpoint-status |  |  | checkpoint | 306.05 Screed - 64M2
checkpoint-status |  |  | checkpoint | 306.06 Apply Second Membrane - 64M2
checkpoint-status |  |  | checkpoint | 306.07 Tiles Supplied - 64M2
checkpoint-status |  |  | checkpoint | 306.08 Tile & Grout balcony surface - 64M2
checkpoint-status |  |  | checkpoint | 306.09 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checklist-flat |  |  | checklist | 106 |  |  |  |  | Yes | 106 | ffbb13c6-1b15-48a7-971b-b551f85a8699
checkpoint-status |  |  | checkpoint | 106 Demolition & Removal of Existing Balcony Surface - 13M2
checkpoint-status |  |  | checkpoint | 106.01 Provide movement joints within the tile surface as required p/m2 - 13M2
checkpoint-status |  |  | checkpoint | 106.02 Apply First Membrane - 13M2
checkpoint-status |  |  | checkpoint | 106.03 Screed - 13M2
checkpoint-status |  |  | checkpoint | 106.04 Apply Second Membrane - 13M2
checkpoint-status |  |  | checkpoint | 106.05 Tiles Supplied - 13M2
checkpoint-status |  |  | checkpoint | 106.06 Tile & Grout balcony surface - 13M2
checkpoint-status |  |  | checkpoint | 106.07 Rendering of Internal Balaustrade as required (Including materials) - 1M2
checkpoint-status |  |  | checkpoint | 106.08 Painting of Internal Balaustrade as required (including materials) - 2M2
checkpoint-status |  |  | checkpoint | 106.09 Skirting Tile and Caulking as required - 16LM
checkpoint-status |  |  | checkpoint | 106.1 Remove any rubbish and clean area - 13M3