## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Walls - ITP (V.231121) |  |  |  |  | Yes | Walls - ITP (V.231121) | 0103c489-fb51-4a73-9b20-ea72ed550e18
checkpoint-status |  |  | checkpoint | Safety induction
label | dbfd2340-62ff-5671-a713-ec3befa8493f |  | note | Reference: Spec / Std - BUILT site safety induction and relevant SWMS
label | ef5f5282-e6f1-5abf-b3fb-42143ec3f4b5 |  | note | Acceptance Criteria - Signature
label | ee8a2407-b627-59d5-9c65-62261cd37dc7 |  | note | Frequency - Prior to commence
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | f9a78d6e-6bc7-5757-9dac-eee9db320c54 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | ca52328b-c93b-5930-8ac2-6db1fb58673a |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | ff39ba37-e408-53f8-9baa-2111d75130e9 |  | button | Verifying records attached below - Induction register, safety file | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check concrete strength (required)
label | 3b1e798a-1478-5291-894f-974081a9a221 |  | note | Reference: Spec / Std - Refer to relevant IFC Structural Drawings
label | 2046c5b1-00be-56fc-a02c-16f6842aff99 |  | note | Acceptance Criteria - Minimum strength requirement - 32/40 MPa unless noted otherwise. (refer to Structural Drawings for details) . Mix to be pre-approved by BUILT.
label | bbfc415b-cf16-5124-963d-e652c56b7a44 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | e0c09745-4b07-593e-a6be-4924aebcc14e |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | c48d7f85-8aa2-5ed9-a5dc-6f81e8af578e |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check for conforming concrete slab below
label | fcbb63f3-f39a-5592-9d68-928c6b8865d8 |  | note | Reference: Spec / Std - Superintendent nominated personnel to inspect prior to pouring of slab on ground
label | 1faa9a95-7cf8-5c65-9c3b-eef18bec230e |  | note | Acceptance Criteria - Construction Joint (between Slab and Column) shall be free of Standing water, debris, oils, objectionable coatings and fragments.
label | 7b85d5af-6e72-5f0d-a490-87bcb4139c36 |  | note | The Slab area is to be scabbled at CJ and starter bars to protrude as specified on IFC Structural Drawings
label | ac158327-6c2e-54b9-bedb-1f6eee0d482c |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 822c7430-2a7b-5208-8ed8-1dd947fcecf5 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 561a566d-861f-55a2-9d84-ff537cd65f06 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 809d10cc-fe48-5f3c-8921-bb180a18884f |  | button | Verifying records attached below - Quality Assurance for slab below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check Pre Pour Inspection Checklist signed off
text | 42c05de0-2ddf-59a5-a6fe-7086c6a74676 |  | textbox | Site Conditions Pour Day
label | 7c64d755-9c5e-55be-ba9e-caf8d23688a9 |  | note | Reference: Spec / Std - AS 3600
label | e144ca43-be4e-55ed-b6c8-dd568f1302ac |  | note | Acceptance Criteria - Concrete not placed when temperature below 5oC or greater than 35oC (refer to 'Slab on Ground - Prepour Checklist').
label | 22508cf0-54f0-5d7d-8397-20952f2e2dbd |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 2355e2c2-286f-50e7-b66f-eb7dd02d0e7b |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | a00173ad-5cf0-5955-95f8-dc604c206965 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | eb6443a5-938d-5258-91ba-772f2e98842f |  | button | Verifying records attached below - Checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Setting out
label | 38389568-d4a7-5578-8108-e006dca9b611 |  | note | Reference: Spec / Std - To comply with relevant IFC Architectural Drawings
label | 3425cf35-4a57-5351-af4a-0bf0b827b873 |  | note | Acceptance Criteria - Conforming as per Slab on Ground Prepour Checklist
label | 941b30df-3b2b-5784-ad5f-876261104b1b |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | f0032d79-7ae6-5c6a-b78f-4e7005e92113 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 8daf6f7e-067f-58b8-b02e-e9f3543fc64a |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 279718f9-45cb-5fc7-aaed-679866cf8f5b |  | button | Verifying records attached below - Checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Formwork
label | c2239800-a234-5eb9-a2a5-a3837ce00961 |  | note | Reference: Spec / Std - AS 3600
label | d654df8c-55b2-5aa9-a164-d0ec5312da4d |  | note | Acceptance Criteria - Conforming as per Slab on Ground Prepour Checklist.
label | 0cb12c40-3dab-5c4d-9ba9-40d55be38618 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 3f3e3d72-4c26-5e58-b8b4-c85dc199173a |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | dfaba2b3-17df-5bdf-8a27-677fb562656a |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 1b67284b-08b6-565e-95f7-e772f0032766 |  | button | Verifying records attached below - Checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Penetrations
label | 767b34dd-d20b-5e01-8775-a356da4b5fa7 |  | note | Reference: Spec / Std - To comply with relevant IFC Architectural Drawings
label | e716af74-d317-5855-9214-e9f9c20d0f43 |  | note | Acceptance Criteria - BUILT to sign-off that services have been installed in-ground conforming as per Walls Checklist
label | e454ea07-b2e1-5a45-94cf-9d9b4e1f2c7e |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | b2357d32-7f25-5233-8269-44a4c2a29940 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 943ea599-a545-58de-b890-f38ae6ecbe0b |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 551721e9-7842-53eb-8234-04bf2e795e11 |  | button | Verifying records attached below - Checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Reinforcement
label | 59002193-4dfb-5c0b-8242-b95772c2110f |  | note | Reference: Spec / Std - AS 3600 / approved relevant IFC Structural Drawings / inspection
label | f745f1ac-e6aa-5f34-97e7-d61be3e374c8 |  | note | Acceptance Criteria - Conforming as per Slab on Ground Prepour Checklist
label | 013c9a41-753b-5ce5-912f-8cd5362f768e |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | fae27c4f-89d9-5e5c-8bf1-100f020fc2d3 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 4d8e398f-715d-526e-93f9-12d0c5cf3abb |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 21f30af8-b957-53ce-8edf-a4facadac9b7 |  | button | Verifying records attached below - Engineers Sign Off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Pre-pour inspection by Symal Structures and BUILT.
label | de366ae2-e75c-5305-9f14-6c624048f1ed |  | note | Acceptance Criteria - Prior to placement of concrete to slab on ground, a pre-pour inspection is to be carried out by Symal Structures and BUILT
label | ee1a3d35-e7af-5468-9217-87908dbab820 |  | note | A minimum notification time of 24 hours is required before the scheduled pour
label | 38f5aa41-93e1-5a1c-8ccb-9d95180eeac4 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | d73cc353-ae8e-5b07-ab52-66c8cd3ccef3 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 28417074-9534-514d-99e2-b209eca025e4 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | ec02f6aa-80ff-5b60-8971-4f66f2b118bd |  | button | Verifying records attached below - Engineer to sign-off prior to placement of concrete | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | In-situ Column Services (where applicable)
label | b308a629-1f74-55fb-9295-147f81283251 |  | note | Acceptance Criteria - Conforming as per Column Pre-Pour Checklist
label | 96069cbd-f391-5596-a931-5ef707fd8744 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 2e223aa8-7788-50a9-b60a-c788b47126f0 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 921a7161-3617-585a-bbf1-c167669957b5 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | cae2ae70-93d9-584e-b711-1e909b34f4ce |  | button | Verifying records attached below - Symal Structures/HMB signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Concrete placement and consolidation, delivery monitoring - check concrete type, check aggregate
label | 6b235727-c57d-527f-be3e-facae4022c2a |  | note | Reference: Spec / Std - AS 3600 and construction specification
label | 786846a3-d653-54a1-b62f-dc097a2098bb |  | note | Acceptance Criteria - Concrete shall not be used if it is more than 1.5 hours old, concrete shall be placed in a continuous flow without high velocity to alleviate segregation.
label | 8a4f4349-879a-5f9d-b1e8-eb6dd3b7abf7 |  | note | Concrete shall be consolidated, ensuring density. Duration of vibration will be as evidences by the cessation of large bubbles rising to the surface
label | 887b2afe-c92b-5734-8de1-3c64fae41609 |  | note | Frequency - During pour
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 314c6a8d-c983-54c3-a491-e861212485ef |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 9f94c03c-c1b5-5370-8c93-52c6dda41b92 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 5cbf2269-352b-5257-9055-45df86985814 |  | button | Verifying records attached below - Delivery dockets, slump tests cylinder records, Prepour Checklist | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Sampling and testing of concrete
label | ec2f74f5-10a1-5b55-8a7d-86b1c857441c |  | note | Reference: Spec / Std - AS 3600, AS 1012, construction specifications and Slab on Ground Prepour Checklist
label | d7ab5113-7feb-5470-b7df-a1469e4f8a1d |  | note | Acceptance Criteria - Concrete testing to be in accordance with minimum requirements set out in the concrete specifications,
label | e3a0b46f-15d6-562f-8e7a-0c9cbee93902 |  | note | the relevant Australian Standards and conforming as per Slab on Ground Prepour Checklist
label | 07d9a53c-adf6-5177-a0ae-881a8636447d |  | note | Frequency - During pour
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | a4319e52-8ab5-54fe-b0cd-ce9c582dbb3d |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | f4ce8498-62cb-5418-bfd9-0a90117088c3 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | edc0bcb9-9cac-57ba-857e-e5aaac96186c |  | button | Verifying records attached below - Concrete test results submitted for each lot | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Stripping time
label | 057a3c6b-1ce4-567d-939f-8396e28409d5 |  | note | Reference: Spec / Std - AS3600, Clause 19.6.2
label | 1a5e8c02-258b-5ddf-b511-2936f57df063 |  | note | Acceptance Criteria - Formwork that is stripped at less than 18 hours after casting,
label | dc1f0193-8553-5b42-806e-7533c450ed4d |  | note | shall ensure that extra care will be exercised to avoid surface damage during stripping
label | 1cef3e6f-91bc-574c-981d-96749c3780f5 |  | note | Frequency - After Pour
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 6b887a94-3893-583c-87f4-f8f708cff619 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | e85cb75c-6c87-532d-9830-3b594e27a346 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Finishes
label | ba95700e-fdb1-5a03-b142-c6eeccdad63b |  | note | Reference: Spec / Std - As per specifications and Slab on Ground Prepour Checklist
label | 8abac33b-5b76-5da0-b6ee-9f55e5215ee4 |  | note | Acceptance Criteria - Concrete finishes to conform with specifications and Slab on Ground Prepour Checklist
label | 354f29d9-0712-5127-bcee-3d20105ba232 |  | note | Frequency - After pour
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | c6e5bfa5-bd2f-5817-ab8a-5a49c8d2d2d3 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 350ed17c-a496-56bb-9da4-39eec391b9be |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 0b336e86-8994-5e0c-b508-2128d74de8b3 |  | button | Verifying records attached below - Visual inspection / survey (if required) | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Precast Panels - Post-Installation Checklist (V.241121) |  |  |  |  | Yes | Precast Panels - Post-Installation Checklist (V.241121) | 03fa18fa-5901-4639-9c5b-725b473386fa
checkpoint-status |  |  | checkpoint | Horizontal Joints Installed as per Structural Documentation, including grout, backing rods etc
checkpoint-status |  |  | checkpoint | Stitch Plates Supplied as per IFC Shop Drawings & Structural Documentation
checkpoint-status |  |  | checkpoint | Panel to Panel Stitch/ Connection Plates Welded as per Structural Documentation
checkpoint-status |  |  | checkpoint | Welds have been reviewed by Independent Welding Inspector and Reports issued to Built
checkpoint-status |  |  | checkpoint | Vertical Joints installed as per Structural Documentation, including caulk, backing and rods etc
checkpoint-status |  |  | checkpoint | Connection Plate Pockets have been patched with specified or approved product.
checkpoint-status |  |  | checkpoint | Internal Caulking installed with specified or approved Fire Rated product as per structural documentation
checkpoint-status |  |  | checkpoint | Grout Tubes filled and finished with approved/appropriate product
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | e63df4d8-b1ce-58f4-b397-448ee14ab965 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | f5f00c22-f8ae-56cf-9cfb-0df3fd5d7061 |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 5b263db8-11cd-59aa-9445-7f6f50c5de66 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Columns - Post-pour Checklist (V.231121) |  |  |  |  | Yes | Columns - Post-pour Checklist (V.231121) | 07495c93-39ab-4ef2-867e-6284d5efe302
checkpoint-status |  |  | checkpoint | 1 Immersion Vibrator to be situated and used for duration of pour.
label | 9d1b79d0-3273-5099-b3c9-f4e640962bbb |  | note | A minimum of one vibrator must be used at all times while the pour is in operation
label | 57287e73-f6c4-5e68-8421-1f1fb50b1ceb |  | note | These vibrators are to be a minimum of 5 metres long to ensure the full column height is reached
checkpoint-status |  |  | checkpoint | Competent concreters will be used to vibrate the concrete using the immersion vibrators, ensuring full compaction is achieved
checkpoint-status |  |  | checkpoint | Has concrete been finished to correct RL
checkpoint-status |  |  | checkpoint | Visual check on columns once stripped to ensure no cracking has occurred
checkpoint-status |  |  | checkpoint | Visual check on columns once stripped to ensure that there are no boney concrete areas due to lack of vibration
checkpoint-status |  |  | checkpoint | Ensure patching to columns has been undertaken for any defect areas that are visible
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | df937b42-5869-5cad-90f1-a5549533674e |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 266be9c3-040f-588a-9866-2c5f3abbb1d3 |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 85314954-238e-5db5-bc5f-be6dd056f9bc |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Conventional Stairs - ITP (V.231121) |  |  |  |  | Yes | Conventional Stairs - ITP (V.231121) | 16926e22-a36e-428f-aefe-5bbb71003044
checkpoint-status |  |  | checkpoint | Safety induction
label | 6f5776fd-0c0a-5eab-9fc2-c097e4d90240 |  | note | Reference: Spec / Std - BUILT site safety induction and relevant SWMS
label | fac4035c-4ad9-59ae-90f1-4da40476a805 |  | note | Acceptance Criteria - Signature
label | 060c5e56-6172-54c9-be7b-b191591a1c2e |  | note | Frequency - Prior to commence
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 99499af4-072f-58bc-90c6-54b5a79fbb77 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | d41babbc-d53d-5f3e-afea-30ab9001bace |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 66b1710f-55d3-575b-8ba9-b4aab3c60863 |  | button | Verifying records attached below - Induction register, safety file | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check concrete strength (required)
label | 7cb2ab08-4bb8-5b2a-980a-e1eee1ef913f |  | note | Reference: Spec / Std - Refer to relevant IFC Structural Drawings
label | d28bc777-9cc9-5bc0-ab23-f4b2e5be8cee |  | note | Acceptance Criteria - Minimum strength requirement - 32/40 MPa unless noted otherwise. (refer to Structural Drawings for details) . Mix to be pre-approved by BUILT.
label | d53c8f89-00fa-5db3-ac3f-7dcf7ad0e6b2 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 7bc67815-fa89-55e1-95f1-d4383103bfa4 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 4b4800dc-f579-52d5-89dd-b0b873a09a10 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check for conforming concrete slab below
label | 144d49ce-8f1f-5d19-aac3-673aa5713213 |  | note | Reference: Spec / Std - Superintendent nominated personnel to inspect prior to pouring of slab on ground
label | 7337da4c-ebfa-5023-816e-3d0a1f01c340 |  | note | Acceptance Criteria - Construction Joint (between Slab and Column) shall be free of Standing water, debris, oils, objectionable coatings and fragments.
label | a82e1d51-f01c-573e-ac2e-83f4614e95e5 |  | note | The Slab area is to be scabbled at CJ and starter bars to protrude as specified on IFC Structural Drawings
label | 4c1199bc-f960-50ef-925e-531f0cd8636b |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | a0ba51de-3c8d-5f06-8dea-e52430fe351b |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 82ba495b-7f46-5f01-bfb5-0f67e7413300 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | f9117265-9247-5816-afb8-9f6058bb0948 |  | button | Verifying records attached below - Quality Assurance for slab below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check Pre Pour Inspection Checklist signed off
text | 15d57fa6-27c2-523e-af30-062e5bd3ee81 |  | textbox | Site Conditions Pour Day
label | 9018a8a2-fca4-5aeb-9ced-7acb4c66df5b |  | note | Reference: Spec / Std - AS 3600
label | f7c6f9b1-f271-58c0-85e2-bd710c222998 |  | note | Acceptance Criteria - Concrete not placed when temperature below 5oC or greater than 35oC (refer to 'Slab on Ground - Prepour Checklist').
label | 8a291356-4524-5b79-9b6c-e644ea3141f2 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 69c25bd7-d036-582a-a8b3-f60fbcd9e022 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 141bc746-e9f4-5244-b85b-065d4172a47b |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 8ccbf269-cd2c-50ff-b93e-314345b4cfc0 |  | button | Verifying records attached below - Checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Setting out
label | bc7058bf-de6d-5978-8962-7c9c653d3753 |  | note | Reference: Spec / Std - To comply with relevant IFC Architectural Drawings
label | cdf2c135-5c36-5eb4-802e-bb9bca44cb81 |  | note | Acceptance Criteria - Conforming as per Slab on Ground Prepour Checklist
label | a2606b27-d032-5ac7-b6ac-361c39f5b35f |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 88a9d7ae-108e-5008-9776-a68339c516b7 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 80213e2e-2365-5a78-9f97-01dd7d4e83b3 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | d43fb507-9f43-5fd0-832d-5bfb961349ef |  | button | Verifying records attached below - Checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Formwork
label | eaf0edbc-e782-52f8-beb4-ad01be2214cd |  | note | Reference: Spec / Std - AS 3600
label | 9066baaf-d7da-5fa3-a2dc-64e44dbd2ddf |  | note | Acceptance Criteria - Conforming as per Slab on Ground Prepour Checklist.
label | 6345d7d4-2912-5fe0-a991-770a089db65d |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | a867d5f8-e007-576f-a7e7-ccc86719d4cb |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 20380d89-c952-5887-af37-50bac9bfd566 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 02a0db74-3cb0-5a8a-b205-8759cb0c3d8c |  | button | Verifying records attached below - Checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Reinforcement
label | f3fccc52-fd9e-50af-be24-34e7deb99c5a |  | note | Reference: Spec / Std - AS 3600 / approved relevant IFC Structural Drawings / inspection
label | 18078a42-b670-5740-bf77-72c6dfbba70d |  | note | Acceptance Criteria - Conforming as per Slab on Ground Prepour Checklist
label | 98a5c084-c984-53d1-8d11-537d9042ae81 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 01b44a61-6cdb-5394-9aa8-cd948a7011ee |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 1d64fe62-f553-5542-bc4b-5045fb3d04dd |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | fdf09a7e-4a8e-5051-9b1c-d3b5147429e0 |  | button | Verifying records attached below - Engineers Sign Off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Pre-pour inspection by Symal Structures and BUILT.
label | b7c3b9b5-c3e4-57f3-b5eb-5d18174bec56 |  | note | Acceptance Criteria - Prior to placement of concrete to slab on ground, a pre-pour inspection is to be carried out by Symal Structures and BUILT
label | e11fd6fb-ae98-53bb-bde3-629e5d7513c6 |  | note | A minimum notification time of 24 hours is required before the scheduled pour
label | 5358a44c-df2d-5cdd-a47c-610d67ce0e36 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 6fa10b27-ed64-57f0-bd80-e8fd67d82aba |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | c0daa2c8-2092-5b2b-bd68-0ae1a8bd6996 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 817f2d2d-858d-5ada-9b18-1535082f2493 |  | button | Verifying records attached below - Engineer to sign-off prior to placement of concrete | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Concrete placement and consolidation, delivery monitoring - check concrete type, check aggregate
label | 68551a8f-8ffc-5ea8-baf7-a93f98f1b2f5 |  | note | Reference: Spec / Std - AS 3600 and construction specification
label | cad6c5b0-92e1-57e1-a643-e5c33c99c380 |  | note | Acceptance Criteria - Concrete shall not be used if it is more than 1.5 hours old, concrete shall be placed in a continuous flow without high velocity to alleviate segregation.
label | 57504261-be9e-5036-b93c-6e814eaeefe7 |  | note | Concrete shall be consolidated, ensuring density. Duration of vibration will be as evidences by the cessation of large bubbles rising to the surface
label | 1e0d3433-f04c-5404-aaf1-bd539e573288 |  | note | Frequency - During pour
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | f4adee08-d631-51e8-bf9e-ae7f8da8d68e |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | cfac900e-542f-5def-9ce5-b4601f013e9c |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 2f4b4c0f-bdb3-5d4c-88b8-acb2ef909c05 |  | button | Verifying records attached below - Delivery dockets, slump tests cylinder records, Prepour Checklist | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Sampling and testing of concrete
label | 8c83ee40-ba96-5dec-9728-be1c9e683334 |  | note | Reference: Spec / Std - AS 3600, AS 1012, construction specifications and Slab on Ground Prepour Checklist
label | eecd7f9b-9b14-5281-be1b-6a22f1f81850 |  | note | Acceptance Criteria - Concrete testing to be in accordance with minimum requirements set out in the concrete specifications,
label | bf5739a2-1a78-5ca6-8bd8-efed4e90645f |  | note | the relevant Australian Standards and conforming as per Slab on Ground Prepour Checklist
label | 9a7036d5-4275-5db3-9cb8-a66d62e4c10f |  | note | Frequency - During pour
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 86d41c5d-7c20-5456-9331-d3d79c8f3e0c |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 3820e94d-27e6-5de3-86af-41cc0978ad34 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | c7e1c1a5-2f11-5857-b36d-b4c10afe8ec4 |  | button | Verifying records attached below - Concrete test results submitted for each lot | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Finishes
label | 325871cf-8d3b-5573-a915-e1e3b65ad691 |  | note | Reference: Spec / Std - As per specifications and Slab on Ground Prepour Checklist
label | 7ea199f9-8378-5da4-8763-4ca03db05278 |  | note | Acceptance Criteria - Concrete finishes to conform with specifications and Slab on Ground Prepour Checklist
label | ed76ffff-540a-5853-9beb-3773538cd671 |  | note | Frequency - After pour
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 80f11d0d-4c4a-5b30-b831-ec7be426e6a1 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 30c70ee9-d014-5a2a-880f-01d79915402f |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 693ef1ca-f815-5528-83e7-bc7022af990c |  | button | Verifying records attached below - Visual inspection / survey (if required) | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Precast Columns - Installation Checklist (V.221121) |  |  |  |  | Yes | Precast Columns - Installation Checklist (V.221121) | 29a71038-7656-49db-9a59-c73be8385a01
checkpoint-status |  |  | checkpoint | Work area is clear of any overhead hazards. For example leads
label | 4727a154-77aa-5be0-b039-e3a9a5da64e7 |  | note | Any issues please attach comments/photos below
checkpoint-status |  |  | checkpoint | Dimensions - pass once entered
text | adc1f0b3-5f07-5d36-b2ac-b083a2349c29 |  | textbox | Width (mm)
text | 5613dd70-5e0e-5621-9b41-4a9305e6d1c4 |  | textbox | Length (mm)
checkpoint-status |  |  | checkpoint | Base clear of debris
checkpoint-status |  |  | checkpoint | Grout tubes unobstructed and clear of debris
checkpoint-status |  |  | checkpoint | Grout tubes
text | a8807f92-80ed-53d2-b2a7-c4e673564cd4 |  | textbox | Diameter (mm)
text | 27703a53-cef6-512b-96a8-e745115c4812 |  | textbox | Quantity
text | 1b5d5bfc-501d-58d2-bee2-ef998cdc4c7a |  | textbox | Height (mm)
checkpoint-status |  |  | checkpoint | Dowel bars
text | c473954b-7dad-5287-add6-e00744412548 |  | textbox | Diameter (mm)
text | a350ea6c-bcba-52e3-89c3-47b99d262f17 |  | textbox | Height (mm)
checkpoint-status |  |  | checkpoint | Mid span grout volume
text | eb4d5559-26f3-58f2-8805-9e10c638a0ce |  | textbox | Expected (L)
checkpoint-status |  |  | checkpoint | Packer height not greater than 40mm
button | 614e960c-7698-530f-b18b-a5c228aad935 | DataPoint is missing 'button' values | button | Is additional packing is required, If yes Ensure Grouting Team is notified to install additional grout (IF REQUIRED)
label | c15029dc-e3e7-5754-ba76-d9df66f48695 |  | note | Photos to be attached below - Showing Shim packer completed with panel number noted on the floor (Use builders pencil or the like)
checklist-flat |  |  | checklist | Suspended Slab - ITP (V.231121) |  |  |  |  | Yes | Suspended Slab - ITP (V.231121) | 3994cb98-a486-4253-864e-1c22f2fbfd92
checkpoint-status |  |  | checkpoint | Safety induction
label | 3fb0ba29-fd01-573d-9ec5-9a98ceb287fb |  | note | Reference: Spec / Std - BUILT site safety induction and relevant SWMS
label | 7e96c17d-326a-52fc-b4c3-d0abb0c6e9b7 |  | note | Acceptance Criteria - Signature
label | 38c4ce26-409e-5c90-882c-9155f2e63169 |  | note | Frequency - Prior to commence
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 1d683788-f7f2-5758-9d0f-dbe86b682862 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | f247feb1-a426-5a09-be26-d33bcfb276be |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 8a43c06b-b1ff-572f-941d-43675b43fff7 |  | button | Verifying records attached below - Induction register, safety file | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check concrete strength (required)
label | 95c81a6a-0dd6-501d-a756-4115d307f12d |  | note | Reference: Spec / Std - Refer to relevant IFC Structural Drawings
label | 1c1458a3-0f8d-5907-ba3a-a4572fb913c9 |  | note | Acceptance Criteria - Minimum strength requirement - 32/40 MPa unless noted otherwise. (refer to Structural Drawings for details) . Mix to be pre-approved by BUILT.
label | e5721cb7-0de2-5286-b20b-225e70703c09 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 06feb4a9-407f-56e1-ac06-1dd71dff5a37 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 29ce1b97-f302-5710-81f8-f3dcec1d4f9d |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check for conforming column lot (under)
label | 2ff7f2bd-4e2c-5f73-8491-7b38393a1806 |  | note | Reference: Spec / Std - Superintendent nominated personnel to inspect prior to pouring of suspended slab
label | 87769380-db7a-5fc3-b894-1d509acccfef |  | note | Acceptance Criteria - Construction joint (between column and suspended slab) shall be free of standing water, debris, oils, objectionable coatings and fragments
label | 3b1c14c2-1cb5-530c-8172-0887077e680c |  | note | The top of column is to be scabbled at CJ and starter bars to protrude as specified on IFC Structural Drawings
label | c044782b-a6b9-53de-8d28-338d6340e440 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 510dda7b-9fe9-5dd3-b00b-08abce009459 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 2c31d1c8-8665-5639-8627-6fcd0b20fb8d |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 20fc03ef-40ca-5948-8ae2-0a2bc3809f07 |  | button | Verifying records attached below - Quality Assurance for columns (under) | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check pre-pour inspection checklist signed off
text | 900cf48a-71cb-5681-973d-2946f42ce228 |  | textbox | site conditions pour day
label | 66ff08f5-d3f5-5844-806f-a96926906a88 |  | note | Reference: Spec / Std - AS3600
label | 8fa6d6ba-ae18-513a-8cbd-ed920b6ff860 |  | note | Acceptance Criteria - Concrete not placed when temperature below 5oC or greater than 35oC (refer to 'Suspended Slab - Prepour Checklist')
label | d97ac47d-136c-5d49-ae67-7f78fa4e4828 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | c0bcc80a-8c4c-5a1f-aa93-e5de75b09fa1 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | c634df00-8fe1-5033-83f5-0266205f3de5 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 6c9867f3-18f3-52d2-8dc1-bfc629a3cefd |  | button | Verifying records attached below - Checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Setting out
label | b094e711-ce1d-59c4-8fe5-69156fe9d089 |  | note | Reference: Spec / Std - To comply with relevant IFC Architectural Drawings
label | 58bac18b-46d2-559b-acab-a6e856497483 |  | note | Acceptance Criteria - Conforming as per suspended slab pre-pour checklist
label | 89d6540f-8b68-5310-a908-05367b684908 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | fa102e2d-5dfd-5d0f-a43e-fba0ad2a919e |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 631e568c-90c4-5bd2-b253-fcf81a51a911 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | d00be27a-138f-59e2-a2f7-7e906a130c87 |  | button | Verifying records attached below - Checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Formwork
label | 6153bacb-ffa3-58c0-bd2f-87a62130d556 |  | note | Reference: Spec / Std - AS3600
label | 132b92fc-454c-5652-b7a0-aca1e11c584f |  | note | Acceptance Criteria - Conforming as per suspended slab pre-pour checklist
label | 77043166-d9bc-51bd-a582-c25d93a911ad |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 16a779a7-4ab5-5747-b251-95a454be63d1 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 69848b70-714b-57ac-a18c-f6c663dd4e1c |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 643550ee-ae8e-5706-8b59-be1b79632fc1 |  | button | Verifying records attached below - Checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Penetrations
label | a040e859-b72a-592b-81da-11e2a7e56675 |  | note | Reference: Spec / Std - To comply with relevant IFC Architectural Drawings
label | 8ffc067d-386f-5106-ac81-95006b8eb510 |  | note | Acceptance Criteria - BUILT to sign-off that services have been installed. Conforming as per suspended slab pre-pour checklist
label | cb65a74e-8078-5ac9-ba9d-9f22b7d416ce |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 53bfe722-33a2-57a4-bcbc-39f57499d597 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 83d9e027-b840-5e22-b33d-14b49128c256 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 240197a6-f51c-5d56-9ddd-f348bf86e24a |  | button | Verifying records attached below - Checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Reinforcement
label | 16c17076-aa0e-56b7-a690-c407a7d608e1 |  | note | Reference: Spec / Std - AS 3600 / approved relevant IFC Structural Drawings / inspection
label | 9f51a60b-0c99-5386-bcb4-ab371bb9a786 |  | note | Acceptance Criteria - Conforming as per suspended slab pre-pour checklist
label | 281b692d-0ddc-53f6-a9dd-37f8dc143133 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 2e9f546f-334b-5264-823b-17e2079fa8f1 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 7ad21c85-1672-5652-a688-be05a4a81694 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | c2d5ea65-64f2-518f-91eb-cb52b0583197 |  | button | Verifying records attached below - Engineers sign off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Pre-pour inspection by Symal Structures and BUILT
label | cbe530b0-e8b6-541c-a704-84b2d813f4d1 |  | note | Acceptance Criteria - Prior to placement of concrete to suspended slab, a pre-pour inspection is to be carried out by Symal Structures and BUILT
label | 4d634744-de68-5300-8401-49fafef99b09 |  | note | A minimum notification time of 24 hours is required before the scheduled pour
label | 6fdd3b52-2149-5d4d-8668-4be263019508 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 7c0305ad-704a-5e9a-ac2e-f4bc91547801 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | d360534c-05ea-5a8c-842a-0d19b5fb006c |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | d32f19fc-3ced-57e0-8ec5-27ba80abc786 |  | button | Verifying records attached below - Engineer to sign-off prior to placement of concrete | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Post-tensioning
label | e0415f05-1e70-5df3-af2b-a48fb8dc4a71 |  | note | Reference: Spec / Std - Refer to relevant IFC Structural Drawings and suspended slab pre-pour checklist
label | 1f9aeeb3-75ab-52e8-bcf0-0701bd789a13 |  | note | Acceptance Criteria - Conforming as per suspended slab pre-pour checklist
label | 0ecdf529-d93b-512d-b252-7e9b3cb66a50 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | df8e5322-46f5-5a5f-b07a-0b17d14d4744 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 5db4dfc6-68b4-5a2c-bc82-4a43e6138c5f |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 42a01ccc-4716-5b20-a239-306d8e340961 |  | button | Verifying records attached below - Checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Concrete placement and consolidation, delivery monitoring - check concrete type, check aggregate
label | 30614cb4-1894-54f2-a12c-500706ef4717 |  | note | Reference: Spec / Std - AS3600 and construction specification
label | e0916d47-af86-52e3-9c39-80ab924abbd8 |  | note | Acceptance Criteria - Concrete shall not be used if it is more than 1.5 hours old, concrete shall be placed in a continuous flow without high velocity to alleviate segregation.
label | 82502a10-aca8-558e-a830-6459464426d4 |  | note | Concrete shall be consolidated, ensuring density. Duration of vibration will be as evidences by the cessation of large bubbles rising to the surface
label | fd4ec1f2-f1ca-5a7e-aeb9-1f949af000d5 |  | note | Frequency - During pour
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 9c1d3ce2-0c2e-53ae-ae48-6d8f79e8dc15 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 9ead80e2-be28-5fa1-913a-8093cd975dba |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | ce5dbaab-a645-5bce-834c-0fdcb1a102a2 |  | button | Verifying records attached below - Delivery dockets, slump tests cylinder records, pre-pour checklist | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Sampling and testing of concrete
label | a9e3ae13-fbb2-516e-95fb-962e93bdff68 |  | note | Reference: Spec / Std - AS3600, AS1012, construction specifications and suspended slab pre-pour checklist
label | 12fa05de-1d09-5de2-b667-4b32fb6b362a |  | note | Acceptance Criteria - Concrete testing to be in accordance with minimum requirements set out in the concrete specifications,
label | d14f5acb-bd6d-52da-8d04-23894cc15a42 |  | note | the relevant Australian Standards and conforming as per suspended slab pre-pour checklist
label | f1218990-66d2-5c9e-834d-68b541d90712 |  | note | Frequency - During pour
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | cd526dda-dcd1-5c8e-af8d-168daa344131 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | a5a14170-cf28-5730-8db6-b3e23803aad1 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | e9c5fee6-3a78-5e84-9f7e-593459070dc3 |  | button | Verifying records attached below - Concrete test results submitted for each lot | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Stripping time
label | 16e123c8-0854-5c60-a472-2798dd53a9d3 |  | note | Acceptance Criteria - Formwork stripping not to take place until PT Slab is completely stressed and grouted which is 4 days after pour and grout in the tendons is a minimum of 2 days old
label | 72029759-88f8-5444-bfd4-c12afdd3fa62 |  | note | Frequency - After pour
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | ea184ec7-714e-5ead-b435-574bcb256b58 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 4a68fa0d-8e1e-5c03-8ba1-4b72a81fb699 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 2c41a562-fafc-5dac-8d62-bb1e0c89d640 |  | button | Verifying records attached below - PT extensions report | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Finishes
label | 8ffbc7f3-9856-5fc6-ac4b-cc0b3a526476 |  | note | Reference: Spec / Std - As per specifications and suspended slab pre-pour checklist
label | b6462d95-5bb9-57fc-9414-6102fa7afa5a |  | note | Acceptance Criteria - Concrete finishes to conform with specifications and suspended slab pre-pour checklist
label | 001a14f6-8126-5efc-8c56-18c2b2c39908 |  | note | Frequency - During pour
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 4721516b-4a66-5c54-ab9d-192ecdcc63f9 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | c3cb453b-e4c2-5ac1-ae8a-712f4a563e2f |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 442b59fe-7b33-5a1b-83fc-1f343a9b2cb8 |  | button | Verifying records attached below - Visual inspection / survey (if required) | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Floor Handover Checklist (V.221121) |  |  |  |  | Yes | Floor Handover Checklist (V.221121) | 3f08d1af-612d-4052-a867-b78f351050cb
checkpoint-status |  |  | checkpoint | All service penetrations are covered
checkpoint-status |  |  | checkpoint | Handrails installed correctly (If part of scope)
checkpoint-status |  |  | checkpoint | All Symal Structures material has been removed from the level (if loading bay is installed)
checkpoint-status |  |  | checkpoint | Sofit inspection confirms stripping completed 100% (including all fillet)
checkpoint-status |  |  | checkpoint | All Symal Structures waste has been disposed in bins (if available)
checkpoint-status |  |  | checkpoint | All PT pockets have been filled and grinded
checkpoint-status |  |  | checkpoint | All prop penetrations have been filled and grinded
checkpoint-status |  |  | checkpoint | Caulking is complete (if required)
checkpoint-status |  |  | checkpoint | Patching complete (if required)
checkpoint-status |  |  | checkpoint | Floors grinded general (if required)
checkpoint-status |  |  | checkpoint | Symal Structures sub-contractors work completed
checkpoint-status |  |  | checkpoint | All Symal Structures sub-contractors material removed from level
checkpoint-status |  |  | checkpoint | All Symal Structures subcontractors waste has been disposed in bins (if available)
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | fe1d7bd8-4345-5927-986b-dc0bb2d864c4 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | be97014c-90d1-585a-bf05-a3254fd63a5b |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | b6f09d77-bada-5cdb-96ef-9e954476d5b2 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Precast Panels - Installation Checklist (V.241121) |  |  |  |  | Yes | Precast Panels - Installation Checklist (V.241121) | 462998ff-9eea-496f-b7f1-7f5979b8b450
checkpoint-status |  |  | checkpoint | Work area is clear of any overhead hazards. For example leads
label | 0f7c5c23-079f-5124-8655-23820f44d981 |  | note | Any issues please attach comments/photos below
checkpoint-status |  |  | checkpoint | Setting out is done as per Precast marking plan
checkpoint-status |  |  | checkpoint | Dry mix Grout/ Mortar has been placed bottom of the panel along the perimeter as per specifications
checkpoint-status |  |  | checkpoint | Liquid Grout Poured into Grout tubes under the slab
checkpoint-status |  |  | checkpoint | Liquid Grout Poured into Grout tubes in the panel. For sleeve connections , specified grouts should be used and appropriate pump should be used
checkpoint-status |  |  | checkpoint | Bracing has been done as per design
checkpoint-status |  |  | checkpoint | Final alignment has been checked for acceptance
checkpoint-status |  |  | checkpoint | Anchors properly tighten on the floor and on panel. Torque register updated
checkpoint-status |  |  | checkpoint | Approval - Pass once below completed
checklist-sectioned |  |  | checklist | Slab on Ground (V.231121) |  |  |  |  | Yes | Slab on Ground (V.231121) | 472a3af7-dea0-4c65-8979-5edee38fbbc2
checkpoint-group |  |  | section | Setout
checkpoint-status |  |  | checkpoint | Safety Induction/Documentation complete - Lend Lease Project Induction & relevant SWMS communicated
checkpoint-status |  |  | checkpoint | Latest IFC drawings checked & referenced
text | f898c0d0-4fc3-5f1a-b0d6-50c6b59d2499 |  | textbox | Drawing & Revision # (or Attach photo below)
text | 042bb26e-5bd2-57c3-a0cc-966415a1377f |  | textbox | Concrete Strength (mPa)
checkpoint-status |  |  | checkpoint | Tolerance - Specification and Australian Standards
checkpoint-status |  |  | checkpoint | All cast-in's in place (pipe block outs, peno's etc)
checkpoint-status |  |  | checkpoint | RLs checked & Correct
text | 67ef772b-ba99-5525-a89b-47b40a190570 |  | textbox | RL. (Top of pour)
label | 4e2f318d-92af-5b74-9cff-dc558c7b0fab |  | note | RL varies accordingly in sections of works. Refer to Architectural Drawings
checkpoint-group |  |  | section | Foundation
checkpoint-status |  |  | checkpoint | Ensure minimum coverage attained as per relevant cover notes and specifications
checkpoint-status |  |  | checkpoint | Approval from Geotechnical Engineer, or nominated personnel
checkpoint-status |  |  | checkpoint | Compliance with Geotechnical Engineer Report
checkpoint-status |  |  | checkpoint | Compacted sand lines and levels/concrete blinding
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | All in-ground services have been installed and in the correct location
checkpoint-status |  |  | checkpoint | Ensure formwork for stop ends has suitable 'stripping oil' applied. (chipboard)
checkpoint-status |  |  | checkpoint | Diamond dowel lengths and spacing correct. IF required
checkpoint-status |  |  | checkpoint | Ensure all cast-in elements are positioned, fixed, level, plumb
checkpoint-status |  |  | checkpoint | All penetrations are installed and in correct location
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | All reinforcement to be placed in accordance with the IFC structural drawings and AS 1302
checkpoint-status |  |  | checkpoint | Reinforcement securely fixed in place
checkpoint-status |  |  | checkpoint | Where reinforcement has been tack welded (yet approved by Lend Lease), it must conform to AS 1554.3:2002
checkpoint-status |  |  | checkpoint | Bar spacing correct
checkpoint-status |  |  | checkpoint | Correct bar diameter
checkpoint-status |  |  | checkpoint | Correct splice lengths
checkpoint-status |  |  | checkpoint | Correct concrete cover
checkpoint-status |  |  | checkpoint | Bar chair location and spacing
checkpoint-status |  |  | checkpoint | Starter bars comply with size and spacing for column over
checkpoint-group |  |  | section | Pre-Pour
checkpoint-status |  |  | checkpoint | Pour area cleaned before pour - to ensure free of standing Water, debris, oils, objectionable coatings & fragments. (Refer specification)
checkpoint-status |  |  | checkpoint | Concrete strength for Slab on Ground to be at 32MPa or unless noted otherwise
checkpoint-status |  |  | checkpoint | Reinforcement fixed in place
checkpoint-status |  |  | checkpoint | Prepour outstanding items list signed off and completed
checkpoint-status |  |  | checkpoint | Ensure temperatures when pouring are within acceptable criteria (between 5ºC and 35ºC)
checkpoint-status |  |  | checkpoint | Tester ordered: 0 - 50m3 - 1 batch of tests or there off. 50-100m3 - 2 batch of tests or there off
checkpoint-status |  |  | checkpoint | Placement method confirmed
select | a75dd669-ef2a-5d72-b932-611cd3fdcb68 |  | dropdown | Method | Chute, Kibble, Pump
checkpoint-status |  |  | checkpoint | Concrete vibration to be completed with use of vibrator motor (minimum requirement of 300rpm)
checkpoint-status |  |  | checkpoint | Tester Required for Structural Elements as noted in AS 1012
checkpoint-status |  |  | checkpoint | Approval to Pour - Pass once below completed
button | cd08050c-921d-5505-965f-c78d2c1b233c |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | 761b80aa-fdf4-5066-8077-7a7d5422e1e6 |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-group |  |  | section | Placement & Finish
checkpoint-status |  |  | checkpoint | One immersion Vibrator is to be situated on the site and used for duration of pour, this must be used at all times while the pump or kibble is in operation
checkpoint-status |  |  | checkpoint | Competent concreters will be used to vibrate the concrete using the immersion vibrators, ensuring full compaction is achieved
checkpoint-status |  |  | checkpoint | Concrete is to be finished to correct RL
checkpoint-status |  |  | checkpoint | Check finish to ensure that there is no slab over. Refer Architectural drawings
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | 997f8a5d-3c03-5906-9910-8a1ac0d74974 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 1c0fbb6b-04bf-52c8-9607-fe4607acb67b |  | note | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 0a8ee212-c98b-5106-91e2-c0e6df2da634 |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | 154bef59-272f-572b-a618-f7ab87bffb4a |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Precast Columns - Post-Installation Checklist (V.221121) |  |  |  |  | Yes | Precast Columns - Post-Installation Checklist (V.221121) | 4a9e90f1-c6d2-45d7-9001-dfbf3294a12d
checkpoint-status |  |  | checkpoint | Precast installed in correct location as per drawing
checkpoint-status |  |  | checkpoint | Fixings installed and torqued as per manufactures specifications
checkpoint-status |  |  | checkpoint | Braces installed as per engineers design
checkpoint-status |  |  | checkpoint | Braces installed between 45 and 60 degrees
checkpoint-status |  |  | checkpoint | Tolerance - Specification and Australian Standards
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | dd2d94b5-1fcf-5d11-972d-b2a3297438e2 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 8d29779e-99b8-5a12-9b04-766f2ae6ba0b |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 08ee38b1-86ea-5943-a5fa-854832c40f8f |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-sectioned |  |  | checklist | Columns - Pre-pour Checklist (V.231121) |  |  |  |  | Yes | Columns - Pre-pour Checklist (V.231121) | 4da5f175-225d-4564-b6f7-eab0ddf398d7
checkpoint-group |  |  | section | Setout
checkpoint-status |  |  | checkpoint | Tolerance - specification and Australian Standards
checkpoint-status |  |  | checkpoint | All cast-in's in place (pipe block outs, peno's etc)
checkpoint-status |  |  | checkpoint | RL (top of pour) - (RL varies accordingly in sections of works). Refer to Architectural Drawings
checkpoint-group |  |  | section | Foundation
checkpoint-status |  |  | checkpoint | Ensure minimum coverage attained as per relevant cover notes and specifications
checkpoint-status |  |  | checkpoint | Approval from Geotechnical Engineer, or nominated personnel
checkpoint-status |  |  | checkpoint | Approval of QA for footings under
checkpoint-status |  |  | checkpoint | Compliance with 'Geotechnical Engineer Report'
checkpoint-status |  |  | checkpoint | Compliance with ITP001 Footings
checkpoint-status |  |  | checkpoint | Compacted sand lines and levels
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | All in-ground services have been installed and in the correct location
checkpoint-status |  |  | checkpoint | Ensure formwork for stop ends has suitable 'stripping oil' applied
checkpoint-status |  |  | checkpoint | Diamond dowel lengths and spacing correct
checkpoint-status |  |  | checkpoint | Ensure all cast-in elements are positioned, fixed, level, plumb
checkpoint-status |  |  | checkpoint | All penetrations are installed and in correct location
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | All reinforcement to be placed in accordance with the IFC Structural Drawings and AS1302
checkpoint-status |  |  | checkpoint | Reinforcement securely fixed in place
checkpoint-status |  |  | checkpoint | Where reinforcement has been tack welded (yet approved by Head Contractor), it must conform to AS1554.3-2002
checkpoint-status |  |  | checkpoint | Bar spacing correct
checkpoint-status |  |  | checkpoint | Correct bar diameter
checkpoint-status |  |  | checkpoint | Correct splice lengths
checkpoint-status |  |  | checkpoint | Correct concrete cover
checkpoint-status |  |  | checkpoint | Bar chair location and spacing
checkpoint-status |  |  | checkpoint | Starter bars comply with size and spacing for column over
checkpoint-group |  |  | section | W/Shop
checkpoint-status |  |  | checkpoint | Allowance for water-stop in all joints as specified in Structural Drawings
checkpoint-status |  |  | checkpoint | Ensure water-stop is securely fastened to construction joints (where applicable)
checkpoint-group |  |  | section | Pre-pour
checkpoint-status |  |  | checkpoint | Pour area cleaned before pour - to ensure free of standing water, debris, oils, objectionable coatings and fragments (refer specification)
checkpoint-status |  |  | checkpoint | Concrete strength for Slab on Ground to be at 32MPa or unless noted otherwise
checkpoint-status |  |  | checkpoint | Reinforcement fixed in place
checkpoint-status |  |  | checkpoint | Pre-pour outstanding items list signed off and completed
checkpoint-status |  |  | checkpoint | Ensure temperatures when pouring are within acceptable criteria (between 5ºC and 35ºC)
checkpoint-status |  |  | checkpoint | Tester ordered 0 - 50m3 - 1 batch of tests or there of, 50-100m3 - 2 batch of tests or there of
checkpoint-status |  |  | checkpoint | Placing of concrete (method) - Chute, Kibble or Pump
checkpoint-status |  |  | checkpoint | Concrete vibration to be completed with use of vibrator motor (minimum requirement of 300rpm)
checkpoint-status |  |  | checkpoint | Tester required for structural elements as noted in AS1012
checkpoint-group |  |  | section | Sign-off
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | da6a0b5d-09ff-5675-8ca3-59d9932edb94 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | c0bcf4ff-3694-559d-b00f-695971642582 |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 7addff6e-4514-55b0-9c97-d6323725fc06 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-group |  |  | section | Placement
checkpoint-status |  |  | checkpoint | All concrete work shall be carried out in accordance with the AS3600
checkpoint-status |  |  | checkpoint | One immersion Vibrator is to be situated on the site and used for duration of pour, this must be used at all times while the pump or kibble is in operation
checkpoint-status |  |  | checkpoint | Competent concreters will be used to vibrate the concrete using the immersion vibrators, ensuring full compaction is achieved
checkpoint-status |  |  | checkpoint | Concrete is to be finished to correct RL
checkpoint-group |  |  | section | Sign-off
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | c9fc8bd3-4c8d-5062-b8f2-6f9e0f355c72 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 3683f245-2feb-5354-b093-5896e71b02bb |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 71652843-92b2-5eb3-a756-34e31181e097 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-sectioned |  |  | checklist | Walls - Pre-pour Checklist (V.231121) |  |  |  |  | Yes | Walls - Pre-pour Checklist (V.231121) | 542fa017-8e69-4182-a200-4cedc537bfa5
checkpoint-group |  |  | section | Setout
checkpoint-status |  |  | checkpoint | Tolerance - specification and Australian Standards
checkpoint-status |  |  | checkpoint | RL (top of pour) - (RL varies accordingly in sections of works). Refer to Architectural Drawings
checkpoint-status |  |  | checkpoint | Set out of all conventional stairs. Refer to Architectural Drawings
checkpoint-group |  |  | section | Existing Conditions
checkpoint-status |  |  | checkpoint | Approval of QA for slab under
checkpoint-status |  |  | checkpoint | Compliance with ITP of slab below
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | All in-situ stair services have been installed and in correct location
checkpoint-status |  |  | checkpoint | Ensure stairs are in correct position, all dimensions and spacing between flights are as per Structural drawings and Architectural drawings
checkpoint-status |  |  | checkpoint | Ensure formwork has suitable 'stripping oil' applied
checkpoint-status |  |  | checkpoint | All penetrations are installed and in correct location
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | All reinforcement to be placed in accordance with the IFC structural drawings
checkpoint-status |  |  | checkpoint | Where reinforcement has been tack welded (get approved by Head Contractor), it must conform to AS1554.3-2002
checkpoint-status |  |  | checkpoint | Bar spacing correct
checkpoint-status |  |  | checkpoint | Correct bar diameter
checkpoint-status |  |  | checkpoint | Correct splice lengths through construction joints
checkpoint-status |  |  | checkpoint | Correct concrete cover
checkpoint-status |  |  | checkpoint | Bar chair location and spacing
checkpoint-status |  |  | checkpoint | Starter bars comply with size and spacing for elements over
checkpoint-group |  |  | section | Waterstop
checkpoint-status |  |  | checkpoint | All cast-in terms as specified and in correct location
checkpoint-status |  |  | checkpoint | Ensure water-stop is securely fastened to construction joints (where applicable)
checkpoint-group |  |  | section | Pre-pour
checkpoint-status |  |  | checkpoint | Pour area cleaned before pour - to ensure free of standing water, debris, oils, objectionable coatings and fragments (refer specification)
checkpoint-status |  |  | checkpoint | Concrete strength for Walls to be as documented in Structural Drawings
checkpoint-status |  |  | checkpoint | Reinforcement fixed in place
checkpoint-status |  |  | checkpoint | Prepour outstanding items list signed off and completed
checkpoint-status |  |  | checkpoint | Ensure temperatures when pouring are within acceptable criteria (between 5ºC and 35ºC)
checkpoint-status |  |  | checkpoint | Tester ordered 0 - 50m3 - 1 batch of tests or there of, 50-100m3 - 2 batch of tests or there of
button | e7c22fcf-32e9-521e-95ec-f1a66ebe89ac |  | button | Placing of concrete (method) | Chute, Kibble, Pump
checkpoint-status |  |  | checkpoint | Concrete vibration to be completed with use of vibrator motor (minimum requirement of 300rpm)
checkpoint-status |  |  | checkpoint | Tester required for structural elements as noted in AS1012
checkpoint-group |  |  | section | Sign-off
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | 74275667-7955-536d-a557-1581ab60ea87 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | efda82bc-33fb-5f44-80b7-0a7142fb052d |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 2ca67265-e10a-5391-87aa-0e601a0f0263 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-group |  |  | section | Placement
checkpoint-status |  |  | checkpoint | All concrete work shall be carried out in accordance with the AS3600
checkpoint-status |  |  | checkpoint | A minimum of one vibrator must be used at all times while concrete is in operation
label | a741c2dd-9117-5e5c-8320-a102685e0b78 |  | note | These vibrators are to be no less than 5 metres long to ensure full compaction is reached
checkpoint-status |  |  | checkpoint | Competent concreters will be used to vibrate the concrete using the immersion vibrators, ensuring full compaction is achieved
checkpoint-status |  |  | checkpoint | Concrete is to be finished to correct RL
checkpoint-status |  |  | checkpoint | Ensure class finish has been complete as per relevant project specifications
label | e3b055c5-4d65-5c52-adaa-566f71ef5365 |  | note | Refer Scope Specification - Concrete Finish and in reference with AS3600 and AS3610
checkpoint-group |  |  | section | Sign-off
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | d8d7fdd4-dfb6-502d-91d6-c06f4b86fb8d |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | cfaac8f7-601e-5b52-8995-0d01735bb3ae |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | e4b8b505-6931-58b0-81b5-8283f2bb28a1 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-sectioned |  |  | checklist | Conventional Stairs - Pre-pour Checklist (V.231121) |  |  |  |  | Yes | Conventional Stairs - Pre-pour Checklist (V.231121) | 55ef7a3b-646e-4c63-aeb6-1ae0734d13d5
checkpoint-group |  |  | section | Check setting out for
checkpoint-status |  |  | checkpoint | Tolerance - specification and Australian Standards
checkpoint-status |  |  | checkpoint | RL (top of pour) - (RL varies accordingly in sections of works). Refer to Architectural Drawings, Structural
checkpoint-status |  |  | checkpoint | Set out of all conventional stairs. Refer to Architectural Drawings
checkpoint-group |  |  | section | Check existing slab conditions for
checkpoint-status |  |  | checkpoint | Approval of QA for slab under
checkpoint-status |  |  | checkpoint | Compliance with ITP of slab below
checkpoint-group |  |  | section | Check formwork for
checkpoint-status |  |  | checkpoint | All in-situ stair services have been installed and in correct location
checkpoint-status |  |  | checkpoint | Ensure stairs are in correct position, all dimensions and spacing between flights are as per Structural drawings and Architectural drawings
checkpoint-group |  |  | section | Check reinforcement for
checkpoint-status |  |  | checkpoint | All reinforcement to be placed in accordance with the IFC Structural Drawings
checkpoint-status |  |  | checkpoint | Reinforcement securely fixed in place
checkpoint-status |  |  | checkpoint | Where reinforcement has been tack welded (yet approved by Head Contractor), it must conform to AS1554.3-2002
checkpoint-status |  |  | checkpoint | Where bars have been drilled and epoxied into precast panels, ensure embedment and projection are correct
checkpoint-status |  |  | checkpoint | Bar spacing correct
checkpoint-status |  |  | checkpoint | Correct bar diameter
checkpoint-status |  |  | checkpoint | Correct splice lengths through construction joints
checkpoint-status |  |  | checkpoint | Correct concrete cover
checkpoint-group |  |  | section | Check preparation for pour
checkpoint-status |  |  | checkpoint | Pour area cleaned before pour - to ensure free of standing water, debris, oils, objectionable coatings and fragments (refer specification)
checkpoint-status |  |  | checkpoint | Any flat surface concrete areas on precast rebate for landings, needs to be scabbled to exposed concrete aggregate
checkpoint-status |  |  | checkpoint | Concrete strength for Conventional Stairs to be 32MPa unless noted otherwise
checkpoint-status |  |  | checkpoint | Reinforcement fixed in place
checkpoint-status |  |  | checkpoint | Prepour outstanding items list signed off and completed
checkpoint-status |  |  | checkpoint | Ensure temperatures when pouring are within acceptable criteria (between 5ºC and 35ºC)
checkpoint-status |  |  | checkpoint | Tester ordered 0 - 50m3 - 1 batch of tests or there of, 50-100m3 - 2 batch of tests or there of
checkpoint-status |  |  | checkpoint | Placing of concrete (method) - Chute, Kibble or Pump
checkpoint-status |  |  | checkpoint | Concrete vibration to be completed with use of vibrator motor (minimum requirement of 300rpm)
checkpoint-status |  |  | checkpoint | Tester Required for structural elements as noted in AS1012
checkpoint-group |  |  | section | Sign-off
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | d852385d-2a72-59f3-a5c0-2389c9aa1d28 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | df9f3732-1572-5a9c-98bd-806b5b78636d |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 67122bad-2143-532f-867f-224fa3bbb06c |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-group |  |  | section | Placement of concrete
checkpoint-status |  |  | checkpoint | All concrete work shall be carried out in accordance with the AS3600
checkpoint-status |  |  | checkpoint | A minimum of one vibrator must be used at all times while concrete is in operation
label | 3976dd06-3688-5d4c-9e70-e3ce8e4a6a49 |  | note | These vibrators are to be no less than 5 metres long to ensure full compaction is reached
checkpoint-status |  |  | checkpoint | Competent concreters will be used to vibrate the concrete using the immersion vibrators, ensuring full compaction is achieved
checkpoint-status |  |  | checkpoint | Concrete is to be finished to correct RL
checkpoint-status |  |  | checkpoint | Ensure class finish has been complete as per relevant project specifications
label | 2a508c86-365d-514d-9c42-d292b174d8a3 |  | note | Refer Scope Specification - Concrete Finish and in reference with AS3600 and AS3610
checkpoint-group |  |  | section | Sign-off
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | 3b85afed-35a2-5d5f-a07c-a0930b9a3a38 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 92791fd1-6663-5741-935c-2ef679d9dd5e |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | c00a7702-8c15-5726-8af3-18dcddef636a |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-sectioned |  |  | checklist | Suspended Formwork - Pre-strip Checklist (V.231121) |  |  |  |  | Yes | Suspended Formwork - Pre-strip Checklist (V.231121) | 5ac97fb0-d3b0-4b27-bc95-693701523175
checkpoint-group |  |  | section | Confirmation required for the following
checkpoint-status |  |  | checkpoint | SWMS considers credible hazards for task
checkpoint-status |  |  | checkpoint | Concrete has reached the minimum strength as per AS3600 or engineering specifications, which ever the greater
label | 3a312720-f4aa-5612-8a39-9dd20b2af566 |  | note | Attach documentation
checkpoint-status |  |  | checkpoint | Post Tensioning (P.T) is complete, stress results and sign off by P.T contractor received
label | 34613007-705f-5999-9aae-68d29279f094 |  | note | Attach documentation
checkpoint-status |  |  | checkpoint | Grout is complete to all P.T ducting
label | 6310d618-7ff0-575a-a5af-e39423f09be2 |  | note | Attach documentation
checkpoint-status |  |  | checkpoint | P.T grout has reached required strength as per engineering / P.T contractor specifications
label | 71bdd65f-735a-511a-b18d-fe79a1f3fa38 |  | note | Attach documentation
checkpoint-status |  |  | checkpoint | Panel props have been signed off for removal
label | 042e6adc-ea9c-58c6-a9be-33bfca74a2c3 |  | note | Attach documentation
checkpoint-status |  |  | checkpoint | Are any permits required by the PC for the task
checkpoint-group |  |  | section | Pre-stripping work area set up
checkpoint-status |  |  | checkpoint | Re-route of site egress and access established
checkpoint-status |  |  | checkpoint | Barricade and signage erected to prohibit unauthorised entry to stripping area
checkpoint-status |  |  | checkpoint | Guarding or penetration covers have been installed to slab above
checkpoint-status |  |  | checkpoint | Perimeter Screen Catch Decks mechanically secured back to structure to prevent materials falling with all gaps fully covered
checkpoint-status |  |  | checkpoint | Penetrations covered (working level)
checkpoint-status |  |  | checkpoint | Drop zone areas have been established for areas below (stripping near a live edge)
checkpoint-status |  |  | checkpoint | All workers who will undertake task have read understood and signed SWMS for task
checkpoint-status |  |  | checkpoint | (If required) permit(s) have been approved by the PC and all workers completing the task have read, understood and have sign on to the permit
label | 6a638a5d-f730-534b-9b57-c61db1ca5b13 |  | note | Attach documentation
checkpoint-group |  |  | section | Sign-off
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | 86ab99d9-5890-52d8-8d3a-126517fe5573 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 6be3ea17-8174-5695-85aa-48c19211bbad |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 0c938ff9-de8a-54c8-9996-e602b35708fb |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Loading Bay Back Propping Checklist (V.221121) |  |  |  |  | Yes | Loading Bay Back Propping Checklist (V.221121) | 6d4e0756-6635-4b4c-b524-f6b2e8ddc80a
checkpoint-status |  |  | checkpoint | 2x Props (Peri MP350 / Alshor / Titan No 2.) installed either side underneath loading bay support beams. Total of 4 props per floor
checkpoint-status |  |  | checkpoint | Props installed underneath loading bay for at least two floors
checkpoint-status |  |  | checkpoint | Preston Hire Props installed as per drawings. Rear props fixed to the slab above and front props left approximately 20mm below underside of slab above
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | a6e24b02-5bd9-5d03-b752-c57e17031968 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 1f25ffac-8de1-5e22-a27f-bd6e71b8cbb5 |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 6ab16f8c-d16f-5b70-abc8-d69a03d97d4c |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-sectioned |  |  | checklist | Columns - Pre-pour Checklist (V.231121) |  |  |  |  | Yes | Columns - Pre-pour Checklist (V.231121) | 741a7b41-f5dc-4e7c-b485-cb3dbcd22db8
checkpoint-group |  |  | section | Setout
checkpoint-status |  |  | checkpoint | Tolerance - specification and Australian Standards
checkpoint-status |  |  | checkpoint | Set out of all Columns. Refer to Architectural Drawings
checkpoint-status |  |  | checkpoint | RL (top of pour) - (RL varies accordingly in sections of works). Refer to Architectural Drawings
checkpoint-group |  |  | section | Existing Conditions
checkpoint-status |  |  | checkpoint | Approval of QA for footings / slab below
checkpoint-status |  |  | checkpoint | Compliance with Slab on Ground and Suspended Slabs
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | All in-situ column services have been installed and in correct location
checkpoint-status |  |  | checkpoint | Where column has been stick built, ensure Formwork Engineer has inspected and signed off column prior to any placement of concrete
checkpoint-status |  |  | checkpoint | Ensure formwork has suitable 'stripping oil' applied prior to standing up column body
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | All reinforcement to be placed in accordance with the IFC Structural Drawings and AS1302
checkpoint-status |  |  | checkpoint | Where reinforcement has been tack welded (get approved by Head Contractor), it must conform to AS1554.3-2002
checkpoint-status |  |  | checkpoint | Reinforcement securely fixed in place
checkpoint-status |  |  | checkpoint | Bar spacing correct
checkpoint-status |  |  | checkpoint | Correct bar diameter
checkpoint-status |  |  | checkpoint | Correct splice lengths
checkpoint-status |  |  | checkpoint | Correct concrete cover
checkpoint-group |  |  | section | Pre-pour
checkpoint-status |  |  | checkpoint | Pour area cleaned before pour - to ensure free of standing water, debris, oils, objectionable coatings and fragments. (Refer specification)
checkpoint-status |  |  | checkpoint | Concrete strength for Columns are in accordance with structural drawings
checkpoint-status |  |  | checkpoint | Reinforcement fixed in place
checkpoint-status |  |  | checkpoint | Pre-pour outstanding items list signed off and completed
checkpoint-status |  |  | checkpoint | Ensure temperatures when pouring are within acceptable criteria (between 5ºC and 35ºC)
checkpoint-status |  |  | checkpoint | Tester ordered 0 - 50m3 - 1 batch of tests or there of, 50-100m3 - 2 batch of tests or there of
checkpoint-status |  |  | checkpoint | Placing of concrete (method) - Chute, Kibble or Pump
checkpoint-status |  |  | checkpoint | Concrete vibration to be completed with use of vibrator motor (minimum requirement of 300rpm)
checkpoint-status |  |  | checkpoint | Tester Required for Structural Elements as noted in AS1012
checkpoint-group |  |  | section | Sign-off
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | d2e8b68c-e155-561b-abdd-0bcd9a4087d5 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 3ab797f0-7fdd-5ac2-aba7-714b9ce4b4e6 |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 42ead2b5-9b0b-5dd4-b73e-82487844a682 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-group |  |  | section | Placement
checkpoint-status |  |  | checkpoint | All concrete work shall be carried out in accordance with the AS3600
checkpoint-status |  |  | checkpoint | A minimum of one vibrator must be used at all times while concrete is in operation. These vibrators are to be no less then 5 metres long to ensure full column height is reached
checkpoint-status |  |  | checkpoint | Competent concreters will be used to vibrate the concrete using the immersion vibrators, ensuring full compaction is achieved
checkpoint-status |  |  | checkpoint | Concrete is to be finished to correct RL
checkpoint-status |  |  | checkpoint | Ensure class finish has been complete as per relevant project specifications (Refer Scope Specification - Concrete Finish) and in reference with AS3600 and AS3610)
checkpoint-group |  |  | section | Sign-off
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | 043f8c2f-7c47-57e4-9a67-bf9fe12aac61 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | d7f74b99-77cd-5030-a466-625552af283e |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 4426d004-321b-5fc1-8b2c-1bf148eae9b6 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-sectioned |  |  | checklist | Suspended Slab - Pre-pour Checklist (V.231121) |  |  |  |  | Yes | Suspended Slab - Pre-pour Checklist (V.231121) | 7d8ac319-d1a0-4808-bdb0-c6b185ac3f74
checkpoint-group |  |  | section | Setout
checkpoint-status |  |  | checkpoint | Tolerance - specification and Australian Standards
checkpoint-status |  |  | checkpoint | RL (top of pour) - (RL varies accordingly in sections of works). Refer to Architectural Drawings
checkpoint-status |  |  | checkpoint | Check for all penetrations (set-out and location). Refer to Architectural Drawings, Structural
checkpoint-group |  |  | section | Existing Conditions
checkpoint-status |  |  | checkpoint | Approval of QA for columns under
checkpoint-status |  |  | checkpoint | Approval of Symal Structures design compliance Inspection Report for column under
checkpoint-status |  |  | checkpoint | Compliance with Columns ITP
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | All in-situ slab services have been installed and in correct location
checkpoint-status |  |  | checkpoint | Ensure all beam and slab depths are correct and are carried out as per IFC Structural Drawings
checkpoint-status |  |  | checkpoint | Ensure formwork at stop ends has suitable 'stripping oil' applied
checkpoint-status |  |  | checkpoint | All penetrations are installed and in correct location. Cross check both Structural and Architectural Drawings - enter #'s below
text | f3072336-a143-59a6-ad6a-0ec34e82184e |  | textbox | Structural #
text | e75f58b1-5025-56d9-8730-599b4a63e841 |  | textbox | Architectural #
checkpoint-status |  |  | checkpoint | Ensure bondek has correct lap and is securely fastened
checkpoint-status |  |  | checkpoint | Ensure bondek has a minimum 25mm overlap from edge of formwork
checkpoint-status |  |  | checkpoint | All frames, bases and formwork tables to be correctly aligned (frames vertical)
checkpoint-status |  |  | checkpoint | Ensure that formwork (frames, bases, tables, etc) have been inspected and signed off by a formwork designer prior to any pour of a suspended slab
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | All reinforcement to be placed in accordance with IFC post tension drawings
checkpoint-status |  |  | checkpoint | Reinforcement securely fixed in place
checkpoint-status |  |  | checkpoint | Where reinforcement has been tack welded (get approved by Head Contractor), it must conform to AS1554.3-2002
checkpoint-status |  |  | checkpoint | Bar spacing correct
checkpoint-status |  |  | checkpoint | Correct bar diameter
checkpoint-status |  |  | checkpoint | Correct splice lengths
checkpoint-status |  |  | checkpoint | Correct concrete cover
checkpoint-status |  |  | checkpoint | Bar chair location and spacing
checkpoint-status |  |  | checkpoint | Starter bars comply with size and spacing for column over
checkpoint-status |  |  | checkpoint | All Post Tensioning to be placed in accordance with the IFC Structural Drawings
checkpoint-status |  |  | checkpoint | P.T. ducts, fixing and strands securely fixed in place
checkpoint-status |  |  | checkpoint | P.T. spacing correct
checkpoint-status |  |  | checkpoint | Correct P.T. sizes used
checkpoint-status |  |  | checkpoint | Correct duct level in concrete
checkpoint-status |  |  | checkpoint | Bar chair location and spacing
checkpoint-group |  |  | section | Pre-pour
checkpoint-status |  |  | checkpoint | Pour area cleaned before pour - to ensure free of standing water, debris, oils, objectionable coatings and fragments. (Refer specification)
checkpoint-status |  |  | checkpoint | Confirm RL for slab - pass once entered drawing # and RL below
text | b548313a-3e29-571a-bb07-8f47c1dcc142 |  | textbox | Drawing #
text | 821d2df3-e35c-5842-a8de-8bc2db2aed8c |  | textbox | RL
checkpoint-status |  |  | checkpoint | Confirm correct RL for wet areas - pass once details entered below
text | f7beec54-15e7-5d95-a948-7049e58ccc51 |  | textbox | Drawing #
text | 459da4d7-0814-5639-96de-0e900230fcb1 |  | textbox | RL falls to waste (top)
text | b1623da7-41b3-5a8b-a4e2-14f86567eea9 |  | textbox | to (low)
checkpoint-status |  |  | checkpoint | Confirm correct RL for balconies - pass once details entered below
text | 8e22a8a2-c8ba-5007-97b2-6a50114c2eb4 |  | textbox | Drawing #
text | 2cff57b5-ecca-5bb3-9882-2bca2124a136 |  | textbox | RL falls to waste (top)
text | e6689575-66bc-5cff-a048-a123a79aaaae |  | textbox | to (low)
checkpoint-status |  |  | checkpoint | Concrete strength for Suspended Slabs to be at 32 / 40 MPa or unless noted otherwise
checkpoint-status |  |  | checkpoint | Reinforcement fixed in place
checkpoint-status |  |  | checkpoint | Post tensioning fixed and in place
checkpoint-status |  |  | checkpoint | Pre-pour outstanding items list signed off and completed
checkpoint-status |  |  | checkpoint | Ensure temperatures when pouring are within acceptable criteria (between 5ºC and 35ºC)
checkpoint-status |  |  | checkpoint | Tester ordered 0 - 50m3 - 1 batch of tests or there of, 50-100m3 - 2 batch of tests or there of
checkpoint-status |  |  | checkpoint | Placing of concrete (method) - Chute, Kibble or Pump
checkpoint-status |  |  | checkpoint | Concrete vibration to be completed with use of vibrator motor (minimum requirement of 300rpm)
checkpoint-status |  |  | checkpoint | Tester required for structural elements as noted in AS1012
checkpoint-group |  |  | section | Sign-off
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | b8b14ef4-4e86-5a99-a003-4e7e285990bb |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 016fcbae-e77a-52f5-a39e-c528da89021c |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 756c031c-56f2-5070-8ab7-a1c578ad9a90 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-group |  |  | section | Placement
checkpoint-status |  |  | checkpoint | All concrete work shall be carried out in accordance with the AS3600
checkpoint-status |  |  | checkpoint | A minimum of one vibrator must be used at all times while concrete is in operation. These vibrators are to be no less then 5 metres long to ensure full column height is reached
checkpoint-status |  |  | checkpoint | One Immersion Vibrator is to be situated on the site and used for duration of pour, this must be used at all times while the pump or kibble is in operation
checkpoint-status |  |  | checkpoint | Competent concreters will be used to vibrate the concrete using the immersion vibrators, ensuring full compaction is achieved
checkpoint-status |  |  | checkpoint | Concrete is to be finished to correct RL
checkpoint-group |  |  | section | Sign-off
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | 12962f8e-e747-531a-925b-55bcf08bcdfb |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | c480dc98-09b4-5647-b1dd-3bdb5cb66886 |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 2affb9bf-6208-5234-96ec-86b800ea96ed |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | False Formwork Handover Checklist (V.221121) |  |  |  |  | Yes | False Formwork Handover Checklist (V.221121) | 874ba757-c4fd-4dd2-b94b-36174845afda
checkpoint-status |  |  | checkpoint | All penetrations are covered and secured
checkpoint-status |  |  | checkpoint | Handrail system is installed correctly
checkpoint-status |  |  | checkpoint | All Symal Structures waste has been disposed of in bins
checkpoint-status |  |  | checkpoint | Temporary formwork structure is completed as per engineers design
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | 564bf14f-3566-52ce-82eb-8831a1cae732 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 2947f31e-a3d1-59f2-8229-ceb948cde919 |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | ba03b938-fd42-539d-ac79-2ee07591f61f |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Footings - ITP (V.231121) |  |  |  |  | Yes | Footings - ITP (V.231121) | 881e2e16-55aa-4177-84d9-55a34988c1f7
checkpoint-status |  |  | checkpoint | Safety induction
label | 6ba217c9-3c1b-56ce-a61f-06feac94c878 |  | note | Reference: Spec / Std - BUILT site safety induction and relevant SWMS
label | c20ed187-24f3-594c-ad6a-13b9de75401f |  | note | Acceptance Criteria - signature
label | 57eea7d3-ed58-5161-b71d-c8dcb105448c |  | note | Frequency - prior to commence
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 4ece3b0e-bcb7-58c7-a08d-c350c8c54417 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | f9542e56-e2e1-5fbe-ad4a-6de110319c4c |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 0b224f1d-8431-5dd2-9dbb-686711f0f9a1 |  | button | Verifying records attached below - induction register, safety file | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check concrete strength required
label | d3d9ed40-6647-5b9e-a8f8-83c0784ab445 |  | note | Reference: Spec / Std - Refer to relevant IFC Structural Drawings
label | 2ef48d93-b9fe-5f2e-8159-7e41824199a5 |  | note | Acceptance Criteria - Minimum strength requirement - 25 / 32 / 40 MPa (Refer Structural Drawing for details). Mix to be pre-approved by BUILT)
label | 55e46699-fc11-5bea-8d49-751da61823b6 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 35bead42-c59c-5bef-9e35-757cf11df366 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 979e8d3c-1076-5073-b958-016e33ff1e01 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | dde237ff-8d52-5586-af8f-df96bcbabe26 |  | button | Verifying records attached below - Concrete Dockets | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check sub-grade conditions
label | f21319d3-f9dd-5a66-943c-582c6ebc7815 |  | note | Reference: Spec / Std - Superintendent Nominated personnel to inspect prior to pouring of blinding
label | 5f560015-ffa9-5baa-bbff-047ed544f88c |  | note | head of each pile trimmed to required cut-off level.
label | 326988e7-a74e-5263-90ef-9b341837d434 |  | note | Any flat surface concrete areas of pile caps should be scabbled at the CJ and starter bars to protrude as specified on IFC Structural Drawing
label | a5519a18-6a4c-56cf-8f07-184fff43e5ad |  | note | Acceptance Criteria - Foundations shall be free of Standing Water, debris, oils, objectionable coatings & fragments
label | 4bd7d309-6fea-5246-9424-d2a051a02900 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 80ce7334-5340-568e-87f5-13fd4bfd1c41 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 37ceb174-4f8a-50d4-8786-fc7a3815a1b1 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 287765c3-ef77-5e00-b6a3-c9c8ff71d083 |  | button | Verifying records attached below - geotechnical engineer report | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check pre-pour inspection checklist signed off and site conditions pour day
label | 3622dc01-ad35-5788-81fc-f31c1318f370 |  | note | Reference: Spec / Std - AS 3600
label | fbe65e2a-fd8c-5793-b9b4-b056ee9f84f4 |  | note | Acceptance Criteria - Concrete not placed when temperature below 5oC or greater than 35oC (refer to 'Blinding - Pre-Pour Checklist')
label | 147dd8f0-b814-52b2-97d0-85ff1547ad78 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 154c6f36-cee4-53a9-a34e-2886e5788ceb |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 92182006-826f-570b-90c2-c83c7a00e5be |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 56dd9da2-50ed-55ec-8587-896406659371 |  | button | Verifying records attached below - checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Setting out
label | 2fe8d222-4870-5aa2-99ca-dcdbd8e0c48f |  | note | Reference: Spec / Std - To comply with relevant IFC Architectural Drawings
label | 69747c23-22bb-50dd-93c0-abd182cf7288 |  | note | Acceptance Criteria - Conforming as per Footings Pre-pour Checklist
label | 471f2b3b-ba0a-54fb-8e8f-3b49c44f03a5 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | b2556162-084c-5cfd-ba7b-029779408d0c |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 55a72434-bfa8-59f4-807a-0c2cd5b1ce76 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 5aeef152-4f3c-5875-92d9-ddb345fa1ea9 |  | button | Verifying records attached below - Checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Pile breakdown
label | ba3bd119-eac9-5951-8a28-fe2d9f003b40 |  | note | Acceptance Criteria - Refer to Structural Drawings
label | 3f42443a-bf01-59f3-8451-df03192bea7e |  | note | Frequency - Pile broken down to 50mm below lower pad level and reinforcement bars cut off 100mm below top of pile cap level
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 74411a47-00df-59c2-9434-a2b31a73984e |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | cafd657f-711d-5b3f-9866-113e18cef109 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 0bdb6a0a-2086-5e06-8767-2683fa26bad4 |  | button | Verifying records attached below - Pre pour checklist | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Concrete placement and Consolidation, Delivery Monitoring - Check Concrete Type, Check aggregate
label | c4b8691b-f60c-5998-9a57-9d9ee68eebba |  | note | Reference: Spec / Std - AS3600 and Construction Specification
label | 4fe92f3a-d5df-5ca6-aaa4-0f38936a1022 |  | note | Acceptance Criteria - Concrete shall not be used if it is more than 1.5 hours old, Concrete shall be placed in a continuous flow without high velocity to alleviate segregation.
label | 97199137-8a58-559c-98a1-c0d754e48b85 |  | note | Acceptance Criteria - Concrete shall be consolidated, ensuring density. Duration of vibration will be as evidences by the cessation of large bubbles rising to the surface
label | 314b11aa-0611-58cb-8fef-a47954fc62c4 |  | note | Frequency - During pour
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 2dc55c3d-930f-56b2-b7c1-a4a88c8f56bc |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | fc3d8111-f2f9-58e0-ba6e-cd4e2e9ba772 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 9e679ea9-d282-5d47-939a-0ba80fd4ad91 |  | button | Verifying records attached below - delivery dockets, slump tests cylinder records, pre-pour checklist | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Sampling and testing of concrete
label | 9a43e831-5c68-534d-9a29-2f41d5aaf520 |  | note | Reference: Spec / Std - AS3600, AS1012, construction specifications and footings pre-pour checklist
label | d9d505bb-0138-5feb-bfe5-22cddf2254cd |  | note | Acceptance Criteria - Concrete testing to be in accordance with minimum requirements set out in the:
label | 70f1baf0-9705-5653-bef8-84841a37eb9c |  | note | Concrete specifications, the relevant Australian Standards and conforming as per footings pre-pour checklist
label | 2b5442fc-1337-54fe-94eb-11fcdb3c8388 |  | note | Frequency - During pour
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 1f4586e2-ad63-50df-8b0e-bc35552af2d0 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | f51e901e-70f3-58a5-89ef-302a97f0a2c1 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | ebc87e73-da90-5f5e-a4cc-592f0f37e781 |  | button | Verifying records attached below - Concrete test results submitted for each lot | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Finishes
label | 5a93e6fc-d8f4-5e21-9a2b-3a7a3330c1f2 |  | note | Reference: Spec / Std - As per specifications and footings pre-pour checklist
label | cb5f217f-791d-58be-9eb4-b68c44146c62 |  | note | Acceptance Criteria - Concrete finishes to conform with specifications and footings pre-pour checklist
label | 34e0cd78-df6b-5785-8ba3-970ad2a6e2c1 |  | note | Frequency - after pour
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 2f2eb65b-cccc-57e6-8d3e-7a646671f752 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 6b959c69-28ed-5d5b-bf35-06b5b7cb1e2c |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 430f9660-92bc-50ed-a121-8e39f969b5ab |  | button | Verifying records attached below - visual inspection / survey (if required) | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Precast Columns - Mid Span Grouting Checklist (V.221121) |  |  |  |  | Yes | Precast Columns - Mid Span Grouting Checklist (V.221121) | 92091a8b-aecd-435f-87b0-5839a0a45991
checkpoint-status |  |  | checkpoint | Precast column no.
checkpoint-status |  |  | checkpoint | Engineer column no.
checkpoint-status |  |  | checkpoint | Dimensions - pass once entered
text | afbbad17-a367-582f-ac2f-80ee61810e76 |  | textbox | Width (mm)
text | 946c4f93-f813-52c5-8f1d-93ef6a8b0c3a |  | textbox | Length (mm)
checkpoint-status |  |  | checkpoint | Base clear of debris
checkpoint-status |  |  | checkpoint | Grout tubes unobstructed and clear of debris
checkpoint-status |  |  | checkpoint | Gap between base and slab (mm) - pass once entered below
text | 32ebeac5-bed5-572e-a0c7-7e05dec330de |  | textbox | Gap (mm)
checkpoint-status |  |  | checkpoint | Grout tubes
text | cc9a0ceb-ff13-5004-b58b-73d6493a4105 |  | textbox | Diameter (mm)
text | dfcda9d4-ddc7-5a1d-8589-30c705662da0 |  | textbox | Quantity
text | 4fdf71d4-22dc-5949-939f-b3c2bb7c09a3 |  | textbox | Height (mm)
checkpoint-status |  |  | checkpoint | Mid span grout volume
text | a9b7ddcb-98be-535c-b149-358914d6f7ff |  | textbox | Expected (L)
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | d0ae1259-1907-5440-af41-94e913cd99c4 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 8fea2077-429c-5dd4-8a7e-5807f62ee895 |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | b603e0bd-d437-5c6d-bc35-7e3b063effe5 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-sectioned |  |  | checklist | Blinding - Pre-Pour Checklist (V.191121) |  |  |  |  | Yes | Blinding - Pre-Pour Checklist (V.191121) | 953066c0-bccb-41ee-b402-8ef38f3280f9
checkpoint-group |  |  | section | Setout
checkpoint-status |  |  | checkpoint | Tolerance - Specification and Australian Standards
checkpoint-status |  |  | checkpoint | Footings shall be in accordance with AS2159 and with the project specifications
checkpoint-status |  |  | checkpoint | Refer to the IFC drawings for footing sizes and design loads
checkpoint-status |  |  | checkpoint | RL (top of blinding) - (RL varies accordingly in sections of works)
text | 18750ad2-1fc7-5e03-b166-71a7d87ea7d0 |  | textbox | RL
checkpoint-group |  |  | section | Foundation
checkpoint-status |  |  | checkpoint | Approval from Geotechnical Engineer, or nominated personnel
label | 57290f04-6209-58df-b5a8-d947c2020bf2 |  | note | Engineer SVR attached below as applicable
checkpoint-status |  |  | checkpoint | Compliance with 'Geotechnical Engineer Report
checkpoint-status |  |  | checkpoint | Ensure minimum coverage attained as per relevant cover notes and specifications
checkpoint-group |  |  | section | Pre-Pour
checkpoint-status |  |  | checkpoint | Ensure concrete strength for blinding is in accordance with Structural Drawing
text | 0f5668cb-d249-59cb-8e23-a36392300609 |  | textbox | Concrete Mpa
checkpoint-status |  |  | checkpoint | Pour area cleaned before pour
label | bc98d144-7aaa-5b53-b4f2-54e4f9adb702 |  | note | To ensure free of standing water, debris, oils, objectionable coatings and fragments. (Refer specification)
checkpoint-status |  |  | checkpoint | Prepour outstanding items list signed off and completed
checkpoint-status |  |  | checkpoint | Ensure temperatures when pouring are within acceptable criteria
label | e4ad2bf9-68a4-58d6-a2e9-ca668e495257 |  | note | Between 5ºC and 35ºC
checkpoint-status |  |  | checkpoint | Placing of concrete (method) confirmed
select | 73786e0c-ea84-520c-9b16-8d4af9687065 |  | dropdown | Method | Chute, Kibble, Pump
checkpoint-status |  |  | checkpoint | HOLD POINT - Approval to Pour
button | 579ffaf7-39ef-5c8c-91d9-92130b61ff23 |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 8644a436-d4f4-5a01-99de-138070399cb8 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-group |  |  | section | Concrete Placement & Post-Pour Sign-Off
checkpoint-status |  |  | checkpoint | All concrete work shall be carried out in accordance with the AS3600
checkpoint-status |  |  | checkpoint | Concrete is to be finished to correct RL
text | 9579d0ec-a34c-54dc-ae7e-45734524bb54 |  | textbox | RL
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | c6707b7d-d863-55af-872a-d32b7d989e57 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
text | d016f3ba-9390-5b5b-8777-6e9464b08406 |  | textbox | If needed add m3 of concrete used
button | a9022dce-9531-5b9d-af2f-d9c41b2f5de3 |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 84242396-b820-5a64-914e-60a2e717970a |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Spandrel Panel Propping Checklist (V.221121) |  |  |  |  | Yes | Spandrel Panel Propping Checklist (V.221121) | 9f43b7ef-e98c-40cd-ba0f-8139acffce8e
checkpoint-status |  |  | checkpoint | Frames and props installed as per drawings
checkpoint-status |  |  | checkpoint | Bearers and joists installed as per drawings
checkpoint-status |  |  | checkpoint | Acrow props with reverse pin installed correctly
checkpoint-status |  |  | checkpoint | Acrow props fixed to slab using 1 No 12 x 100mm PBI SCREW BOLT or equivalent and nailed to bearers
checkpoint-status |  |  | checkpoint | Omni precast spandrel support brackets installed at max 3000 C/C. Minimum 2 brackets per panel, and minimum 3 brackets if panel exceeds 6m
checkpoint-status |  |  | checkpoint | Brackets tied to formwork as per drawings detail
checkpoint-status |  |  | checkpoint | Timber kickers installed on formwork to restrain panels at base
checkpoint-status |  |  | checkpoint | Handrail system installed correctly
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | 4400d129-7569-5078-8e0d-aa58a1854e1b |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | bebec080-9369-59a1-80d2-974667828ead |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | baeaeb5b-9fc3-5ff6-8705-1d4264bfec35 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Blinding - ITP (V.221121) |  |  |  |  | Yes | Blinding - ITP (V.221121) | ab72bb7d-dab5-4e9d-bc84-8638ebe78e92
checkpoint-status |  |  | checkpoint | Safety induction
label | 29167858-8bca-5291-81fe-6d3524050428 |  | note | Reference: Spec / Std - BUILT site safety induction and relevant SWMS
label | 6551295c-d6c5-514e-874b-c1aa417dbfdd |  | note | Acceptance Criteria - signature
label | 472e6558-a636-538e-8e84-d06c6c228c6e |  | note | Frequency - prior to commence
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 2a7dbb2f-fea3-5ce1-8b0c-b9bfa9f50514 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | e8566a63-20dd-56ee-8970-beff5923b9d9 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 88672694-1ef2-5b23-919a-759bf8264512 |  | button | Verifying records attached below - induction register, safety file | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check concrete strength required
label | 4daa3b51-3204-5544-8e5d-9cfc0ad50d68 |  | note | Reference: Spec / Std - Refer to relevant IFC Structural Drawings
label | dfacb595-b4ce-5ce6-b473-c173f9369616 |  | note | Acceptance Criteria - Minimum strength requirement - 25 / 32 / 40 MPa (Refer Structural Drawing for details). Mix to be pre-approved by BUILT)
label | 1dbba50d-2751-5dd5-be2c-d96ac9c1b09e |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | f5613806-931a-50df-bcc3-8d1b122ec33b |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 8da4537b-8b8c-5f58-a695-3eb008e22fc1 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 399fd138-ef36-5464-af6a-2c20adf050a6 |  | button | Verifying records attached below - Concrete Dockets | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check sub-grade conditions
label | 07a427ad-e7bb-5381-b846-984dd5c4fae0 |  | note | Reference: Spec / Std - Superintendent Nominated personnel to inspect prior to pouring of blinding
label | 54fe269b-ef62-54cd-86fd-2e619ea1f144 |  | note | Acceptance Criteria - Foundations shall be free of Standing Water, debris, oils, objectionable coatings & fragments
label | c556f377-4a84-58f3-bbda-f7f658f564a5 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 16a1d8db-ce0c-556d-9e65-f23139fe00a2 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | e8d6f463-b6de-5a43-9afe-453dec3f3436 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 56e8b868-5b34-530f-b2b6-1e14270f56c0 |  | button | Verifying records attached below - geotechnical engineer report | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check pre-pour inspection checklist signed off and site conditions pour day
label | dd68da07-ebb2-515a-8eb3-e54e4d1a9b7f |  | note | Reference: Spec / Std - AS 3600
label | aa6c9d13-15c5-5ad8-865e-a13d3bae1a3c |  | note | Acceptance Criteria - Concrete not placed when temperature below 5oC or greater than 35oC (refer to 'Blinding - Pre-Pour Checklist')
label | 88e485e8-2d81-5304-9328-d2298274e22c |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | ecaee340-f066-5beb-8c73-a96fb92af7d5 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | cbe63e0b-d61a-557c-ad47-fa9faed44281 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | dabd2e70-c912-5dd8-86d4-2f74e0882c0b |  | button | Verifying records attached below - checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Setting out
label | a82b2599-f31b-50f1-b984-81849b7353aa |  | note | Reference: Spec / Std - To comply with relevant IFC Architectural Drawings
label | fa4759a0-2ee9-5952-9af9-18a4eca3d565 |  | note | Acceptance Criteria - Conforming as per Blinding Pre-Pour Checklist
label | d8747f10-ef65-5afb-93d5-26a97e6219e8 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 93bc2ace-5593-5457-87e4-b2e2f9217736 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 6a378a2f-aabf-5d74-b964-32dd24675f9e |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 4de13e76-dcb5-52ad-afee-f41ad5da79c9 |  | button | Verifying records attached below - checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Pre-pour inspection
label | 465de17f-f4dc-55a8-9c02-eb49b1f63c87 |  | note | Acceptance Criteria - Prior to placement of concrete, pre-pour inspection is to be carried out by BUILT. A minimum notification time of 24 hours is required before the scheduled pour.
label | e90ab302-77da-53ed-a54c-c6a8bd43ff5d |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 5c8b2b83-26e1-5fad-8913-e8b453fe3448 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 165b6b64-e305-5d5c-9a25-ebb8f2e9fb1d |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | b2829910-337c-56ba-98f5-8daf791de721 |  | button | Verifying records attached below - Engineer to sign off prior to placement of concrete | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Concrete placement and Consolidation, Delivery Monitoring - Check Concrete Type, Check aggregate
label | 9916fe07-ea7c-54fa-a97e-398e6677fe82 |  | note | Reference: Spec / Std - AS3600 and Construction Specification
label | aa9aeaa9-027a-5dc1-8768-90a7bd0a1201 |  | note | Acceptance Criteria - Concrete shall not be used if it is more than 1.5 hours old, Concrete shall be placed in a continuous flow without high velocity to alleviate segregation.
label | b81c8f66-b20e-57e0-a440-feebed6f2023 |  | note | Acceptance Criteria - Concrete shall be consolidated, ensuring density. Duration of vibration will be as evidences by the cessation of large bubbles rising to the surface
label | f367f6f2-3e6d-5214-bab0-ab1a408e117e |  | note | Frequency - During pour
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 49af2147-6045-51d4-aa24-8f754f8b615c |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | bfeca341-d7ba-5774-a18b-a9be242b0d48 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 347d157c-bb99-5b5d-a56b-5016c42e290d |  | button | Verifying records attached below - Delivery dockets, slump tests cylinder records, Pre-Pour Checklist | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Slab On Ground - ITP (V.231121) |  |  |  |  | Yes | Slab On Ground - ITP (V.231121) | ac32d7b8-d93d-4081-8d16-983745dbbee1
checkpoint-status |  |  | checkpoint | Safety induction
label | 7e772a99-67d5-5585-803c-fef65e5a067c |  | note | Reference: Spec / Std - BUILT site safety induction and relevant SWMS
label | 4fc2e2dd-64cb-55b8-a02b-a9849f3c50be |  | note | Acceptance Criteria - Signature
label | 0f9f1b06-63ca-560c-a2c4-0f2310e8fe94 |  | note | Frequency - Prior to commence
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 1942a0c5-0c6e-5f45-ab82-b00df7102fc5 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 04e5b85a-dd56-5f66-b4c7-81d403d3a51f |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 86140903-ea89-5095-9789-5eaf23f7b43d |  | button | Verifying records attached below - Induction register, safety file | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check concrete strength (required)
label | 420d3a39-65b0-5842-ae2d-429ac85bbc24 |  | note | Reference: Spec / Std - Refer to relevant IFC Structural Drawings
label | 201c85cc-813a-54af-ada8-9db8a4e9bed7 |  | note | Acceptance Criteria - Minimum strength requirement - 32/40 MPa unless noted otherwise. (refer to Structural Drawings for details) . Mix to be pre-approved by BUILT.
label | 53507cc4-2789-5e8a-9eaa-3f61e5f7ea95 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | fe829191-5491-5386-bafc-0c1c8096ba76 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 13cc8a5b-fd72-54ba-9abe-3f9e20a63a31 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check sub-grade conditions
label | 41cd06ba-81f4-57bc-8d39-2812399b18e1 |  | note | Reference: Spec / Std - Superintendent nominated personnel to inspect prior to pouring of slab on ground
label | b54a6f5b-c04f-5132-8628-17e30aa7bb67 |  | note | Acceptance Criteria - Foundation shall be free of standing water, debris, oils, objectionable coatings and fragments.
label | 7513a762-a914-5e26-bb0a-5004635f01f0 |  | note | 1 layer of 0.2 Polythene to be founded on 150mm of either no fines concrete or crushed rock.
label | 22768269-c590-5e24-9a16-014354746c09 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 0387bbca-88cc-5d30-bb32-e1389468c7a0 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 67c97f46-2b00-59ba-95fc-fa79628e6314 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 4682eefd-c724-5179-9cfb-93395293e9e9 |  | button | Verifying records attached below - Geotechnical Engineer report | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check sub-grade layers completed and placed to correct RL
label | 17436bfd-d1b2-5c40-9ce8-588613e599c9 |  | note | Reference: Spec / Std - Thickness dependant on quality of founding material
label | 9c72dcc8-aef0-5c20-a576-12375eaa608f |  | note | Acceptance Criteria - Survey conducted by Symal Structures. ITP from the Civil contractors
label | e7079ba0-e3d2-5184-8d4a-02df263a6f97 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 4caee9e8-a58b-5012-bff2-0c0be0278cd0 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 1360a72a-d3f8-523a-8e3f-4819de0e7f19 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | e31bebad-71e8-53a4-bfd0-1af1ae592de1 |  | button | Verifying records attached below - Survey report, checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check Pre Pour Inspection Checklist signed off
text | 3bb06370-5bff-5ca6-a701-2210d36d0393 |  | textbox | Site Conditions Pour Day
label | 7a41f330-be3e-5b8c-9751-8b99580c1995 |  | note | Reference: Spec / Std - AS 3600
label | 366491e9-aff7-5363-b9ff-6035c9dacc21 |  | note | Acceptance Criteria - Concrete not placed when temperature below 5oC or greater than 35oC (refer to 'Slab on Ground - Prepour Checklist').
label | 34310d70-552e-5d95-8afe-34eb3165be24 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | d5244074-7e33-5269-a190-95623096b48b |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 516d86d3-e79d-5cc4-b89f-9b6cccbcaf46 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | d0e0a994-df51-5386-b360-000d94b0ada5 |  | button | Verifying records attached below - Checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Setting out
label | 29f8aae7-4938-545c-93f4-d486c4879db3 |  | note | Reference: Spec / Std - To comply with relevant IFC Architectural Drawings
label | cd429925-590b-5474-87c6-838d32c2afaf |  | note | Acceptance Criteria - Conforming as per Slab on Ground Prepour Checklist
label | 28173294-5392-570b-8c12-a963fcaf2116 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 306de6a7-8c23-5409-8865-e5ae14be1537 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 60036796-5c8d-55c5-ba65-7468bf64e046 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 6336e155-8dd4-5c78-b2d6-a36c12970ddd |  | button | Verifying records attached below - Checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Formwork
label | 4e179573-028e-5df5-a779-af78efa50484 |  | note | Reference: Spec / Std - AS 3600
label | ed7bc9b6-54a4-5a7b-ac20-7a7977fc45d2 |  | note | Acceptance Criteria - Conforming as per Slab on Ground Prepour Checklist.
label | e4ac9f9e-d54a-57e2-be91-ce41c9d2a8b1 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 2df2637c-d0c8-5962-bbf6-c7a790e35b24 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 5487d902-ef51-5c70-8b27-0e7eb521e026 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | a75bb5d8-da0a-5d38-b344-23ad2274485d |  | button | Verifying records attached below - Checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Penetrations
label | 1a630c90-263b-586c-ba14-ecb86cdcbdf6 |  | note | Reference: Spec / Std - To comply with relevant IFC Architectural Drawings
label | eff9ba07-743e-5e29-a930-0b0fd35f0e74 |  | note | Acceptance Criteria - BUILT to sign-off that services have been installed. Conforming as per Suspended Slab Checklist
label | 990f6c51-27ff-58b2-9376-9d097b764209 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 594f46af-2c18-57cb-bb38-b1219d02834d |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | feb80fd4-51b8-5bb9-aaf6-27b409d20fe6 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | c3f6d35e-120a-54e1-8b28-168e47a854c7 |  | button | Verifying records attached below - Checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Reinforcement
label | 2039473c-e3f7-59b7-8321-657f975a1809 |  | note | Reference: Spec / Std - AS 3600 / approved relevant IFC Structural Drawings / inspection
label | 1da672bd-53f0-58bb-9ce7-84aad8a018ab |  | note | Acceptance Criteria - Conforming as per Slab on Ground Prepour Checklist
label | 0fc1ef6d-82b0-5b44-b44f-fd19e71587c0 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 21ccf4e1-fbe8-5281-9cd4-6503d841930c |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | e7592973-2c48-5ed1-9121-7f199d227a49 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 09ded617-7d81-5c70-9892-e244ca72b15b |  | button | Verifying records attached below - Engineers Sign Off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Pre-pour inspection by Symal Structures and BUILT.
label | 31aef8d6-1a44-54f1-b570-2e868c4c3d36 |  | note | Acceptance Criteria - Prior to placement of concrete to slab on ground, a pre-pour inspection is to be carried out by Symal Structures and BUILT
label | 9546e7fe-200a-56bd-84ff-415425d3394d |  | note | A minimum notification time of 24 hours is required before the scheduled pour
label | 9bbf5ece-f7dc-591e-9d55-3976d7cf9dad |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | d12f2304-cf84-5c7f-b1ba-24ec8860a540 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | a1c67f5a-a46e-55ea-80b6-823f50ca3b44 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 331e98b4-c490-56b6-ad2c-6c4ecf6e4b31 |  | button | Verifying records attached below - Engineer to sign-off prior to placement of concrete | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Concrete placement and consolidation, delivery monitoring - check concrete type, check aggregate
label | be0fa3f2-3358-5392-a3cb-3265b699b234 |  | note | Reference: Spec / Std - AS 3600 and construction specification
label | 834dd0bd-54f6-584a-b9fd-bc47797cf383 |  | note | Acceptance Criteria - Concrete shall not be used if it is more than 1.5 hours old, concrete shall be placed in a continuous flow without high velocity to alleviate segregation.
label | af225a4a-36ef-563f-84af-4fa11ae9e56d |  | note | Concrete shall be consolidated, ensuring density. Duration of vibration will be as evidences by the cessation of large bubbles rising to the surface
label | 7a532af7-0121-521a-afd3-2320bebb2d13 |  | note | Frequency - During pour
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | d4bd0ae3-e8f9-5992-8acb-f3962f9f1bc7 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | f84955d1-a507-5496-a58c-bed99c14596e |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 909d0d8d-db48-53f3-98d5-7a76041ab4c5 |  | button | Verifying records attached below - Delivery dockets, slump tests cylinder records, Prepour Checklist | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Sampling and testing of concrete
label | 120504d6-a55b-5175-bd70-f81ca774eacb |  | note | Reference: Spec / Std - AS 3600, AS 1012, construction specifications and Slab on Ground Prepour Checklist
label | 81b97f1e-f836-54a1-a211-523b761ca97d |  | note | Acceptance Criteria - Concrete testing to be in accordance with minimum requirements set out in the concrete specifications,
label | 53b8d089-bf5e-5a35-9246-0212a26a03f5 |  | note | the relevant Australian Standards and conforming as per Slab on Ground Prepour Checklist
label | a59128c5-cc08-5c43-8600-fc648c450cde |  | note | Frequency - During pour
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 3791d47d-2c4e-5f5c-ab52-08072c7cdf48 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | caa93a1b-15f4-5e6b-bafe-d38748feafac |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | cceb6f49-7bbc-5fb3-b70e-e46b44926e40 |  | button | Verifying records attached below - Concrete test results submitted for each lot | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Finishes
label | cc23f110-4c98-57e6-9207-ef6fd4df94c6 |  | note | Reference: Spec / Std - As per specifications and Slab on Ground Prepour Checklist
label | 7b52c56a-e4eb-5234-83f8-6873b9c2f6a2 |  | note | Acceptance Criteria - Concrete finishes to conform with specifications and Slab on Ground Prepour Checklist
label | 2f0d0f6b-2b65-5713-a448-2fe7eeea581a |  | note | Frequency - After pour
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | d2e0e981-e2a6-5f99-bca8-203eec930f97 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | db46dba1-f2bc-5dd8-b053-0ee297b64afc |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | fc5622f1-b927-54a3-99e5-8d9e6297377e |  | button | Verifying records attached below - Visual inspection / survey (if required) | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Precast Prop Removal Checklist (V.201121) |  |  |  |  | Yes | Precast Prop Removal Checklist (V.201121) | b393ccc6-47ca-4ec7-8fc8-2998adea3c2e
checkpoint-status |  |  | checkpoint | SWMS considers credible hazards for task
checkpoint-status |  |  | checkpoint | Concrete to connecting panel has been completed
checkpoint-status |  |  | checkpoint | Connecting concrete slabs to be fully stressed prior
checkpoint-status |  |  | checkpoint | Vertical dowel bars have been fully grouted and cured
checkpoint-status |  |  | checkpoint | Grouting of sleeves if applicable completed minimum 7 days prior
label | 22b01fe3-c86f-5ca1-972f-b9ca8dfcb2ec |  | note | Attach documentation below
checkpoint-status |  |  | checkpoint | All stitch plates if applicable have been fully welded and inspected
label | 1468f949-0c33-5662-a7b8-60d3591ffc5c |  | note | Attach documentation below
checkpoint-status |  |  | checkpoint | Engineers sign-off for removal of precast panel prop
label | 83ae1609-98e6-50ef-810a-1464374f43aa |  | note | Attach documentation below
checkpoint-status |  |  | checkpoint | Are any permits required by the PC for the task
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | 4a5516fb-d40b-5944-a180-5edfb6b7fbbf |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 68aded1c-752f-52ab-ba33-e137670c9d19 |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 8bbb5339-daba-5517-8355-3d748e6eaf4c |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Precast Columns - Pre-Installation Checklist (V.221121) |  |  |  |  | Yes | Precast Columns - Pre-Installation Checklist (V.221121) | b715c635-23b5-4ce9-9faf-379cc9ee8855
checkpoint-status |  |  | checkpoint | Set-out of all columns. Refer to latest IFC Architectural drawings
text | 71bcae03-6420-5661-b107-35174ea710b7 |  | textbox | Drawing & Revision # (or Attach photo below)
checkpoint-status |  |  | checkpoint | Work area is clear of any overhead hazards. For example leads
label | 14b1468f-c97c-570a-8bfa-920029f37880 |  | note | Any issues please attach comments/photos below
boolean | fe78dc77-f566-5d5d-a81c-3231b545857b |  | tickbox | Exclusion zone established, delineated and sign posted
boolean | de03c341-4dd6-5729-b9a0-86aa0c1c5642 |  | tickbox | All trip hazards are removed from work area
label | 52ef059f-f02d-5942-bcf6-a2a3674adc6c |  | note | Attach Photos/Comments below if any issues & Send report to Builder
checkpoint-status |  |  | checkpoint | Documentation provider - pass once entered below
text | b451922f-0c78-5888-b8e1-7e7df5ff4ec0 |  | textbox | Documentation provider
checkpoint-status |  |  | checkpoint | Birth certificates received
checkpoint-status |  |  | checkpoint | Lifting certificates received
checkpoint-status |  |  | checkpoint | Strong backs installed as per drawings
checkpoint-status |  |  | checkpoint | Rigging Equipment test and tag current
checkpoint-status |  |  | checkpoint | Crane lifting capacity SWL not exceeded to complete installation of precast
checkpoint-status |  |  | checkpoint | Installation crew hold current relevant competencies for task
checkpoint-status |  |  | checkpoint | Correct braces delivered to site
checkpoint-status |  |  | checkpoint | Braces are in serviceable condition
checkpoint-status |  |  | checkpoint | Approved structural grout available
checklist-flat |  |  | checklist | Precast Panels - Pre-Installation Checklist (V.241121) |  |  |  |  | Yes | Precast Panels - Pre-Installation Checklist (V.241121) | ba0ac496-c99d-44ac-b651-26ed4f136e20
checkpoint-status |  |  | checkpoint | Set-out of all panels. Refer to latest IFC Architectural drawings
text | 8b3f341d-f910-591e-a3dc-41d2e29014aa |  | textbox | Drawing & Revision # (or Attach photo below)
checkpoint-status |  |  | checkpoint | Work area is clear of any overhead hazards. For example leads
label | df5c8ada-46df-5c89-9fe0-5f7677582a72 |  | note | Any issues please attach comments/photos below
boolean | c62edece-3f5f-57e6-a160-e67a4b485a26 |  | tickbox | Exclusion zone established, delineated and sign posted
boolean | 276a7a9c-6aa0-5e65-a8be-1589f7b0ef68 |  | tickbox | All trip hazards are removed from work area
label | 4b8e9e4d-c33d-5142-8526-910ff759172a |  | note | Attach Photos/Comments below if any issues & Send report to Builder
checkpoint-status |  |  | checkpoint | Documentation - pass once all checked
text | 0a7f8094-ec8e-5df5-956a-13ccc2162254 |  | textbox | Documentation provider
boolean | 8960c1f4-75ec-5842-a914-845ec1a40536 |  | tickbox | Birth certificates received
boolean | ac61b00b-d527-5328-b35d-ca5c28ebb492 |  | tickbox | Lifting certificates received
checkpoint-status |  |  | checkpoint | Strong backs installed as per drawings
checkpoint-status |  |  | checkpoint | Rigging Equipment test and tag current
checkpoint-status |  |  | checkpoint | Crane lifting capacity SWL not exceeded to complete installation of precast
checkpoint-status |  |  | checkpoint | Installation crew hold current relevant competencies for task
checkpoint-status |  |  | checkpoint | Correct braces delivered to site
checkpoint-status |  |  | checkpoint | Braces are in serviceable condition
checkpoint-status |  |  | checkpoint | Approved structural grout available
checkpoint-status |  |  | checkpoint | Safety signs to be in place, Working area should be covered from barricades to control others to access
checkpoint-status |  |  | checkpoint | Check concrete strengths
checkpoint-status |  |  | checkpoint | Reinforcement - Starter Bars installed as per documentation
label | 4dc2647b-ceab-5113-b173-7f24a4918ad3 |  | note | Type of Rebar-Carbon Steel Rebar/ Epoxy-Coated Rebar/ Galvanized Rebar/ Glass-Fiber-ReinforcedPolymer/ Stainless Steel Rebar
checkpoint-status |  |  | checkpoint | Grout Tubes - Material and diameter installed as per pre cast shop drawings
checkpoint-status |  |  | checkpoint | Grout delivered to site as per specifications, required quantity, relevant equipments and Grout expiry date to check
checkpoint-status |  |  | checkpoint | Panel to Panel Alignment correct and connection plate bolted to enable welding to commence
checkpoint-status |  |  | checkpoint | Bracing, locks, PBI bolts as specified in Bracing design have been delivered to location
checkpoint-status |  |  | checkpoint | Shim Packers/ Spacers & Donuts have been installed where necessary to enable grouting of horizontal joints to commence
checklist-flat |  |  | checklist | Columns - ITP (V.231121) |  |  |  |  | Yes | Columns - ITP (V.231121) | cba27934-2fb7-4e5b-a06d-68f2f3d37706
checkpoint-status |  |  | checkpoint | Safety induction
label | 25ffd713-7e90-52bf-ba48-a3172ea14c25 |  | note | Reference: Spec / Std - BUILT site safety induction and relevant SWMS
label | 72132a33-95bb-5e66-816d-66682e226900 |  | note | Acceptance Criteria - Signature
label | c0f29c1f-9c8a-5086-92b6-61270a02fbc0 |  | note | Frequency - Prior to commence
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | f384518a-214a-5578-b816-5d75748ac334 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 5085815a-f955-57ac-a693-d4cdd9e312a8 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | cb214784-68b4-5f4a-8a47-d4a738cfe96e |  | button | Verifying records attached below - Induction register, safety file | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check concrete strength (required)
label | af982aa5-ade9-5ae4-87d5-ae2df6c92115 |  | note | Reference: Spec / Std - Refer to relevant IFC Structural Drawings
label | 349982c9-dfdd-5655-bafa-5ceeeb70c88a |  | note | Acceptance Criteria - Minimum strength requirement - 32/40 MPa unless noted otherwise. (refer to Structural Drawings for details) . Mix to be pre-approved by BUILT.
label | 3702fd8d-e911-5810-b2f4-b8b8b3cbb6e2 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 461c193d-5bd2-5f40-89bb-76f0a9fde34e |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 0fd77877-0bc5-5cb6-8f96-35cee7d8225f |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check for conforming concrete slab below
label | 841ab7fc-86d6-5515-ac30-0e3ae3a61fd4 |  | note | Reference: Spec / Std - Superintendent nominated personnel to inspect prior to pouring of slab on ground
label | 7bbb42cf-f8d6-5e21-b372-13b94f093e66 |  | note | Acceptance Criteria - Construction Joint (between Slab and Column) shall be free of Standing water, debris, oils, objectionable coatings and fragments.
label | ad8ce765-0458-5410-be6f-11e86cc933e9 |  | note | The Slab area is to be scabbled at CJ and starter bars to protrude as specified on IFC Structural Drawings
label | 83b7a11c-a45a-5c8f-b485-bb91c793962d |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 67762127-d049-5d24-af5a-ecc4ce436edc |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 76c336a1-f7dd-5d2e-a146-cb7935951f72 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 6c838197-8953-577d-b473-33b72d1ab32c |  | button | Verifying records attached below - Quality Assurance for slab below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check Pre Pour Inspection Checklist signed off
text | 89e7f02d-4dfa-5082-8a92-f514deeed68a |  | textbox | Site Conditions Pour Day
label | 58f530a4-cf44-54b4-a624-d3e667d0218f |  | note | Reference: Spec / Std - AS 3600
label | 2adefeb9-077b-53b5-ade9-ef0b31d3e2c2 |  | note | Acceptance Criteria - Concrete not placed when temperature below 5oC or greater than 35oC (refer to 'Slab on Ground - Prepour Checklist').
label | 290ada7e-8f46-5b2d-bcae-844d4d76439e |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | fb4fe961-92c8-53d8-a14a-a53f1669af4c |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 37c8ea1c-df96-5a48-9aa3-aba94ee6c20d |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | a9a9b66e-486d-557d-8a72-8c025c85ad51 |  | button | Verifying records attached below - Checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Setting out
label | 3c77bb65-3754-53f0-8e1e-56beae1c8391 |  | note | Reference: Spec / Std - To comply with relevant IFC Architectural Drawings
label | ec184254-e264-58da-9f7e-d5700c7c0f54 |  | note | Acceptance Criteria - Conforming as per Slab on Ground Prepour Checklist
label | bc510748-179b-5a58-b8f9-c2abdeedb173 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | ab4a1b8e-598a-590a-b74f-6eeebe48fe1f |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | caf97b8a-f882-5439-8cc3-99d22bc5285f |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 109ca195-d171-524a-b6ad-3e52c9e2f8e9 |  | button | Verifying records attached below - Checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Formwork
label | 31dce392-a6d9-5f85-b7df-71f40c7942fc |  | note | Reference: Spec / Std - AS 3600
label | fbaada9a-eb29-5e25-a71f-8b73f4093aae |  | note | Acceptance Criteria - Conforming as per Slab on Ground Prepour Checklist.
label | 9ac7e9c8-bc5f-5d95-befa-8d6e8b7b5db6 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 6af8e67e-0f10-5598-893b-54c226338e59 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 41f81003-7725-5f4c-92ce-7ccbdee4cc72 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | ec2feb91-8f24-5404-9981-0ee5e9457030 |  | button | Verifying records attached below - Checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Reinforcement
label | ed45a095-6d96-5d58-b06a-8b6c31a87f56 |  | note | Reference: Spec / Std - AS 3600 / approved relevant IFC Structural Drawings / inspection
label | 44b61fb2-a986-53e4-b636-764709bd486e |  | note | Acceptance Criteria - Conforming as per Slab on Ground Prepour Checklist
label | 91ae07b9-4d84-5569-980d-f2546a7a3ee3 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | b2a3c360-663e-5f46-85d5-03e9755805c4 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 8255cc65-aa47-5c01-9da2-54d4363bc4ea |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | e5ba2bd8-1eb8-51d2-9f31-9853f41f0415 |  | button | Verifying records attached below - Engineers Sign Off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Pre-pour inspection by Symal Structures and BUILT.
label | 890bdfcc-cf11-5e44-b6ac-71783cded8dc |  | note | Acceptance Criteria - Prior to placement of concrete to slab on ground, a pre-pour inspection is to be carried out by Symal Structures and BUILT
label | 2bf894ed-b03a-54c1-867d-9699f6a77491 |  | note | A minimum notification time of 24 hours is required before the scheduled pour
label | 488887c2-1ce0-5d68-8d4e-41c5ee47c65d |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 0952fe35-25d9-5635-a2a7-0f52efe77328 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | d65ca908-44d3-53b4-bf3f-8e41258a515c |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | c14260d3-deab-5456-bb58-e9990b0a528e |  | button | Verifying records attached below - Engineer to sign-off prior to placement of concrete | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | In-situ Column Services (where applicable)
label | 4bfbfe9e-f0c7-5b2b-9294-4cf50bc16ae1 |  | note | Acceptance Criteria - Conforming as per Column Pre-Pour Checklist
label | e2dc5001-7fa7-5cc6-8ebb-89bbbdd0fdb7 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 9d6b5b9f-a38f-5296-ad81-ad63bf773801 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | d737f407-bd39-5a82-b1ba-74ce0b289b39 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | ea4a1665-b407-55e0-918d-a88a661984c1 |  | button | Verifying records attached below - Symal Structures/HMB signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Concrete placement and consolidation, delivery monitoring - check concrete type, check aggregate
label | cfebd0ce-7f86-521f-a7c4-2240e50a7aa1 |  | note | Reference: Spec / Std - AS 3600 and construction specification
label | b392fdd6-24e9-5544-9807-4f77eee85efd |  | note | Acceptance Criteria - Concrete shall not be used if it is more than 1.5 hours old, concrete shall be placed in a continuous flow without high velocity to alleviate segregation.
label | c3441cb7-5827-5ba5-92c0-361e9c577c5a |  | note | Concrete shall be consolidated, ensuring density. Duration of vibration will be as evidences by the cessation of large bubbles rising to the surface
label | 0afcf0ef-5e1c-5951-b629-cc95523dba1c |  | note | Frequency - During pour
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 530f0a32-af4f-5d58-8a26-71b01e9483ce |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 87aa1be0-8318-579f-bf8e-d1d44959c497 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 44d242ad-e331-535e-ab4b-dd8ed536c933 |  | button | Verifying records attached below - Delivery dockets, slump tests cylinder records, Prepour Checklist | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Sampling and testing of concrete
label | 995788be-060e-58d4-b93d-1a1e4762d425 |  | note | Reference: Spec / Std - AS 3600, AS 1012, construction specifications and Slab on Ground Prepour Checklist
label | 423007ef-06f9-5717-8827-9229942a2c8f |  | note | Acceptance Criteria - Concrete testing to be in accordance with minimum requirements set out in the concrete specifications,
label | 97f2c04f-79ef-5b6e-aab2-d5d86a17a318 |  | note | the relevant Australian Standards and conforming as per Slab on Ground Prepour Checklist
label | d9b152f3-7c68-529d-bc7f-764b15d5a3dc |  | note | Frequency - During pour
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | ce1444a6-85bd-582c-bef0-50b026c0e192 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 9ab1d36e-9607-55e6-b2d6-c8a50d251a9a |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 9ae24866-5ee6-5505-9321-98836c0e2457 |  | button | Verifying records attached below - Concrete test results submitted for each lot | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Stripping time
label | 47cc5d46-674d-5c7a-9cc9-5a1ddf4ad1fe |  | note | Reference: Spec / Std - AS3600, Clause 19.6.2
label | 347787c1-9808-5fad-8009-a7e3839d85cc |  | note | Acceptance Criteria - Formwork that is stripped at less than 18 hours after casting,
label | 18022050-e750-5f6d-ba6f-66cf779a0396 |  | note | shall ensure that extra care will be exercised to avoid surface damage during stripping
label | 838d1440-ed42-54fe-a014-76072d1f4931 |  | note | Frequency - After Pour
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 762d5332-780f-5890-a184-08cad78b2aed |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | bc18cc25-25ec-5a0d-8091-2084980b6195 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Finishes
label | 34ff5ffd-b39a-56b1-933e-236c0b22410b |  | note | Reference: Spec / Std - As per specifications and Slab on Ground Prepour Checklist
label | 16425c25-e161-5f84-a192-faf92a2112cf |  | note | Acceptance Criteria - Concrete finishes to conform with specifications and Slab on Ground Prepour Checklist
label | a3384fdc-75e1-52fa-b112-8c062aea8e75 |  | note | Frequency - After pour
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | b39e2b1d-ac13-5b47-833d-a7c4420ab1ec |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 30f84a4e-72c7-51a6-9156-c912273aea61 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | b4c749a8-0709-58a4-9aa3-b81e3a2b9163 |  | button | Verifying records attached below - Visual inspection / survey (if required) | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Stairmaster - ITP (V.231121) |  |  |  |  | Yes | Stairmaster - ITP (V.231121) | ce5af240-c3a0-441a-9495-f09f489a15e7
checkpoint-status |  |  | checkpoint | Safety induction
label | 293f2c88-efc7-5b20-b778-85238c9fd79c |  | note | Reference: Spec / Std - BUILT site safety induction and relevant SWMS
label | 392cdb4e-018f-5d95-b193-5eb4483092e4 |  | note | Acceptance Criteria - Signature
label | d36014ab-fb59-521e-ace3-312f2e50c9e6 |  | note | Frequency - Prior to commence
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 9dabf5d8-e8b5-54ee-b68e-985a464fed2e |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 2c5f4195-006a-57f9-9d57-374b5c932e02 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 3ab7de3a-8f27-5727-8e1b-e512fa01f7c6 |  | button | Verifying records attached below - Induction register, safety file | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check concrete strength (required)
label | ff5278f9-dae8-5658-832b-b84aa80b13a1 |  | note | Reference: Spec / Std - Refer to relevant IFC Structural Drawings
label | 62c4d2de-f990-5f11-80c8-fb311c1bee32 |  | note | Acceptance Criteria - Minimum strength requirement - 32/40 MPa unless noted otherwise. (refer to Structural Drawings for details) . Mix to be pre-approved by BUILT.
label | b1009970-559e-50d4-8ac0-ccaa70c41cb4 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 26560047-3258-5dde-982b-e053d259348a |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 097b85a2-ba4e-538a-a7de-c4c836b4debe |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check for conforming concrete slab below
label | d28cfbb0-aed5-5be4-8a21-c9c851a23f5b |  | note | Reference: Spec / Std - Superintendent nominated personnel to inspect prior to pouring of slab on ground
label | 56c5d651-41c9-5614-a167-f9a119dcaa66 |  | note | Acceptance Criteria - Construction Joint (between Slab and Column) shall be free of Standing water, debris, oils, objectionable coatings and fragments.
label | 44844142-c778-54ea-8d1d-c5812f65460d |  | note | The Slab area is to be scabbled at CJ and starter bars to protrude as specified on IFC Structural Drawings
label | eb1092ba-0ebe-5794-9577-8f2841049e6c |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 93e5d8e0-6bd5-50c7-b647-d48c6afa4da2 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | faa1b561-92d6-56cc-98da-eb858d17f11a |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 4bf2cab9-78ed-54c6-9e73-d9a89019578c |  | button | Verifying records attached below - Quality Assurance for slab below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Check Pre Pour Inspection Checklist signed off
text | 4734669e-5f43-5110-a948-cf554323be92 |  | textbox | Site Conditions Pour Day
label | d201168b-bb00-5ca6-924f-374129f81654 |  | note | Reference: Spec / Std - AS 3600
label | b139c68c-7729-5a61-b5b9-150ca52c256e |  | note | Acceptance Criteria - Concrete not placed when temperature below 5oC or greater than 35oC (refer to 'Slab on Ground - Prepour Checklist').
label | 4698eea5-9fb4-5171-b635-2a8726d42ded |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | a5755a96-8858-54d5-9326-c74617a60fc4 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | b81bad4c-4da4-5e0e-ac5c-374521ee7665 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | a1be2416-e184-5f63-ab3c-263f10988232 |  | button | Verifying records attached below - Checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Setting out
label | 4bca16ed-d43c-5762-bf9c-0f453bc542f4 |  | note | Reference: Spec / Std - To comply with relevant IFC Architectural Drawings
label | 19caa15d-5284-5723-b7e9-6c7c358c7d86 |  | note | Acceptance Criteria - Conforming as per Slab on Ground Prepour Checklist
label | 4d04ea2c-ac79-5000-a844-03b86073fc64 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | WITNESS POINT - Signature by Symal Structures and Builders Site Coordinator
button | 28839a5c-905b-52b0-b2f5-6ba72de7671e |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | e8980f25-4651-5de4-a637-fc466f5c8231 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 41c18100-5f36-5aae-b5a0-ba5e4af45835 |  | button | Verifying records attached below - Checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Formwork
label | c2f67b91-aa3d-59be-9cc3-1145ddffb282 |  | note | Reference: Spec / Std - AS 3600
label | 79bd9513-04c9-50e2-b7b5-879f70caa1e5 |  | note | Acceptance Criteria - Conforming as per Slab on Ground Prepour Checklist.
label | b35ebc3f-7d70-5d3d-a99f-f747e52ad7f3 |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 62b91aa1-d42f-586f-bb4b-961c63e6bd17 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | a3158de9-bde6-5a5c-8d76-35c270d501cf |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 7d08d8d8-5d52-537d-85c1-f30fdb0dc07d |  | button | Verifying records attached below - Checklist signed off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Reinforcement
label | 949ec0de-01f7-56fd-b4a6-4575874142ce |  | note | Reference: Spec / Std - AS 3600 / approved relevant IFC Structural Drawings / inspection
label | 9e6aac82-23d0-5254-a506-989a48a774f3 |  | note | Acceptance Criteria - Conforming as per Slab on Ground Prepour Checklist
label | cda5a296-8a31-51e3-83af-4623de1c164d |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | de1834ee-85b0-58a7-badf-262096286751 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | e6cc1b06-7edb-5f3a-b259-e3583ebfb462 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 574c8f2f-3c0c-54c3-9947-30c51a0bbc8a |  | button | Verifying records attached below - Engineers Sign Off | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Pre-pour inspection by Symal Structures and BUILT.
label | 980706c9-920f-5cee-9a56-8bbcca569d8c |  | note | Acceptance Criteria - Prior to placement of concrete to slab on ground, a pre-pour inspection is to be carried out by Symal Structures and BUILT
label | 3fb33803-230e-5544-8f26-bd9e76112137 |  | note | A minimum notification time of 24 hours is required before the scheduled pour
label | 534eca12-5d54-5cc1-846b-6111918a727f |  | note | Frequency - Prior to pouring
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | e55ee459-d68c-58fc-832a-a59463e91ade |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 94d8deee-e651-5e29-bcad-35899f863d35 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | c5d38da4-d07a-5a36-bab2-a3fd3a7a40da |  | button | Verifying records attached below - Engineer to sign-off prior to placement of concrete | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Concrete placement and consolidation, delivery monitoring - check concrete type, check aggregate
label | f11394c1-2503-508b-8e98-6e3cedddfcef |  | note | Reference: Spec / Std - AS 3600 and construction specification
label | a75dddb3-3a50-5467-94a5-2dbf9a7d00ea |  | note | Acceptance Criteria - Concrete shall not be used if it is more than 1.5 hours old, concrete shall be placed in a continuous flow without high velocity to alleviate segregation.
label | ab6c72f9-29c4-5e2b-825b-4b684c080259 |  | note | Concrete shall be consolidated, ensuring density. Duration of vibration will be as evidences by the cessation of large bubbles rising to the surface
label | 49db82c0-ebd8-5b58-9d16-b117f42f1852 |  | note | Frequency - During pour
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | c0b76683-025a-590a-8ec1-ea9f9adef38e |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | d1ba9fe2-2ddf-5686-8b09-0d8ecbc9b5bb |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | e89ab79b-8d9e-54e4-bca7-64e1f561a229 |  | button | Verifying records attached below - Delivery dockets, slump tests cylinder records, Prepour Checklist | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Sampling and testing of concrete
label | 47e9bb4e-2cb2-5e08-983a-13e10af65050 |  | note | Reference: Spec / Std - AS 3600, AS 1012, construction specifications and Slab on Ground Prepour Checklist
label | 322b0121-c455-5ee7-a2c5-191eba22217a |  | note | Acceptance Criteria - Concrete testing to be in accordance with minimum requirements set out in the concrete specifications,
label | 98a0c039-6b10-5670-a77f-90d645d1db52 |  | note | the relevant Australian Standards and conforming as per Slab on Ground Prepour Checklist
label | 3e4f6c34-bf05-5794-9eed-c3bbaa08c773 |  | note | Frequency - During pour
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 2ad7dc4c-d91e-5731-9d58-2cd318d471bc |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | b32e4b14-853b-5b0f-b090-b564ba5e7f86 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | 923acfba-d3ec-5367-8cf2-071cf0365667 |  | button | Verifying records attached below - Concrete test results submitted for each lot | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-status |  |  | checkpoint | Finishes
label | a988e7ca-f173-5ae4-a97c-3ff5dbd34255 |  | note | Reference: Spec / Std - As per specifications and Slab on Ground Prepour Checklist
label | 1106374d-f6cf-50dd-b5b2-350a2b5ca2cd |  | note | Acceptance Criteria - Concrete finishes to conform with specifications and Slab on Ground Prepour Checklist
label | 4043a79b-2b9d-565f-9f71-d236a04c1ecc |  | note | Frequency - After pour
checkpoint-status |  |  | checkpoint | HOLD POINT - Signature by Symal Structures and Builders Site Coordinator
button | 53c213d1-ea18-5e0e-958d-ebb0b4f810c0 |  | button | Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 675d9415-e747-5813-9ada-c3fc18dde379 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
button | e863c995-a2ff-5372-b435-69f6a611b556 |  | button | Verifying records attached below - Visual inspection / survey (if required) | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-sectioned |  |  | checklist | Stairmaster - Pre-pour Checklist (V.231121) |  |  |  |  | Yes | Stairmaster - Pre-pour Checklist (V.231121) | d8feede4-32e9-475f-b121-6b158b958c88
checkpoint-group |  |  | section | Check setting out for
checkpoint-status |  |  | checkpoint | Tolerance - specification and Australian Standards
checkpoint-status |  |  | checkpoint | RL (top of pur) - (RL to the top of last riser) refer to Architectural Drawings
checkpoint-status |  |  | checkpoint | Set out of all Stairmasters. Refer to Architectural Drawings
checkpoint-group |  |  | section | Check existing conditions for
checkpoint-status |  |  | checkpoint | Approval of QA for slab under
checkpoint-status |  |  | checkpoint | Compliance with ITP of slab below
checkpoint-group |  |  | section | Check formwork for
checkpoint-status |  |  | checkpoint | All in-situ stair services have been installed and in correct location
checkpoint-status |  |  | checkpoint | Ensure Stairmasters shop drawings have been approved by CCL prior to any installation of Stairmasters
checkpoint-status |  |  | checkpoint | Formwork has been properly formed as per designed computations by Formwork Engineer
checkpoint-status |  |  | checkpoint | Ensure Stairmasters are in correct position
checkpoint-status |  |  | checkpoint | All dimensions and spacing between flights are as per Stairmaster shop drawings and Architectural Drawings
checkpoint-group |  |  | section | Check reinforcement for
checkpoint-status |  |  | checkpoint | All reinforcement to be placed in accordance with the IFC structural drawings
checkpoint-status |  |  | checkpoint | Reinforcement securely fixed in place
checkpoint-status |  |  | checkpoint | Where reinforcement has been tack welded (yet approved by Head Contractor), it must conform to AS1554.3-2002
checkpoint-status |  |  | checkpoint | Where bars have been drilled and epoxied into precast panels, ensure embedment and projection are correct
checkpoint-status |  |  | checkpoint | Bar spacing correct
checkpoint-status |  |  | checkpoint | Correct bar diameter
checkpoint-status |  |  | checkpoint | Correct splice lengths through construction joints
checkpoint-status |  |  | checkpoint | Correct concrete cover
checkpoint-group |  |  | section | Check preparation for pour
checkpoint-status |  |  | checkpoint | Pour area cleaned before pour - to ensure free of standing water, debris, oils, objectionable coatings and fragments (refer specification)
checkpoint-status |  |  | checkpoint | Any flat surface concrete areas on precast rebate for landings, need to be scabbled to exposed concrete aggregate
checkpoint-status |  |  | checkpoint | Concrete strength for Stairmasters to be 32MPa unless noted otherwise
checkpoint-status |  |  | checkpoint | Reinforcement fixed in place
checkpoint-status |  |  | checkpoint | Prepour outstanding items list signed off and completed
checkpoint-status |  |  | checkpoint | Ensure temperatures when pouring are within acceptable criteria (between 5ºC and 35ºC)
checkpoint-status |  |  | checkpoint | Tester ordered 0 - 50m3 - 1 batch of tests or there of, 50-100m3 - 2 batch of tests or there of
checkpoint-status |  |  | checkpoint | Placing of concrete (method) - Chute, Kibble or Pump
checkpoint-status |  |  | checkpoint | Concrete vibration to be completed with use of vibrator motor (minimum requirement of 300rpm)
checkpoint-status |  |  | checkpoint | Tester Required for structural elements as noted in AS1012
checkpoint-group |  |  | section | Sign-off
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | 70b1821f-0fd4-5152-b9dd-f98f488f6c7b |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 50465b9b-372a-50e3-87cc-f58633714670 |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | b7563d83-e67f-5dfc-82a1-07f464da17f5 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-group |  |  | section | Placement of concrete
checkpoint-status |  |  | checkpoint | All concrete work shall be carried out in accordance with the AS3600
checkpoint-status |  |  | checkpoint | A minimum of one vibrator must be used at all times while concrete is in operation
label | fd3bf075-b226-584b-b022-7897ae145465 |  | note | These vibrators are to be no less than 5 metres long to ensure full compaction is reached
checkpoint-status |  |  | checkpoint | Competent concreters will be used to vibrate the concrete using the immersion vibrators, ensuring full compaction is achieved
checkpoint-status |  |  | checkpoint | Concrete is to be finished to correct RL
checkpoint-status |  |  | checkpoint | Ensure class finish has been complete as per relevant project specifications
label | c4383276-0eb3-549f-b512-12308b6781c6 |  | note | Refer Scope Specification - Concrete Finish and in reference with AS3600 and AS3610
checkpoint-group |  |  | section | Sign-off
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | a8608191-9513-5e55-8072-971f3471198f |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | a9b9c706-06cb-5146-a21a-9756541078f9 |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 8b54436c-4786-550d-94de-214da963b912 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-sectioned |  |  | checklist | Footing - Pre-pour checklist (V.231121) |  |  |  |  | Yes | Footing - Pre-pour checklist (V.231121) | f3a97a75-2964-46b7-9b3e-f1df6fda2ad1
checkpoint-group |  |  | section | Setout
checkpoint-status |  |  | checkpoint | Tolerance - Specification and Australian Standards
checkpoint-status |  |  | checkpoint | Piles and footings shall be in accordance with AS2159 and with the project specifications
checkpoint-status |  |  | checkpoint | Refer to the IFC drawings for footing sizes and design loads.
checkpoint-status |  |  | checkpoint | RL. (top of pile cap / footing) - (RL varies accordingly in sections of works)
checkpoint-status |  |  | checkpoint | Set-out of all pile caps and footings
checkpoint-group |  |  | section | Foundation
checkpoint-status |  |  | checkpoint | Approval from Geotechnical Engineer, or nominated personnel
checkpoint-status |  |  | checkpoint | Compliance with 'Geotechnical Engineer Report
checkpoint-status |  |  | checkpoint | Ensure minimum coverage attained as per relevant cover notes and specifications
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | All reinforcement to be placed in accordance with the IFC structural drawings
checkpoint-status |  |  | checkpoint | Bar spacing correct
checkpoint-status |  |  | checkpoint | Correct bar diameter
checkpoint-status |  |  | checkpoint | Correct splice / lap lengths
checkpoint-status |  |  | checkpoint | Correct concrete cover
checkpoint-status |  |  | checkpoint | Bar chair location and spacing
checkpoint-group |  |  | section | Pre-pour
checkpoint-status |  |  | checkpoint | Ensure concrete strength for Footings and pile caps are in accordance with Structural Drawing
checkpoint-status |  |  | checkpoint | Pour area cleaned before pour - to ensure free of standing Water, debris, oils, objectionable coatings and fragments. (Refer specification)
checkpoint-status |  |  | checkpoint | Reinforcement fixed in place
checkpoint-status |  |  | checkpoint | Pre-pour outstanding items list signed off and completed
checkpoint-status |  |  | checkpoint | Ensure temperatures when pouring are within acceptable criteria (between 5ºC and 35ºC)
checkpoint-status |  |  | checkpoint | Tester ordered 0 - 50m3 - 1 batch of tests or there of, 50-100m3 - 2 batch of tests or there of
checkpoint-status |  |  | checkpoint | Placing of concrete (method) - Chute, Kibble or Pump
checkpoint-status |  |  | checkpoint | Concrete vibration to be completed with use of vibrator motor (minimum requirement of 300rpm)
checkpoint-status |  |  | checkpoint | Tester Required for Structural Elements as noted in AS1012
checkpoint-group |  |  | section | Sign-off
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | 78688f1c-c101-500b-a7d0-bbb96d25ebf4 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | f574884e-ad51-5a7d-809f-8c84b2f7f675 |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 1ed26544-3a11-520d-83d8-8629930ae226 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-group |  |  | section | Placement
checkpoint-status |  |  | checkpoint | All concrete work shall be carried out in accordance with the AS3600
checkpoint-status |  |  | checkpoint | One Immersion Vibrator is to be situated on the site and used for duration of pour, this must be used at all times while the pump or kibble is in operation
checkpoint-status |  |  | checkpoint | Competent concreters will be used to vibrate the concrete using the immersion vibrators, ensuring full compaction is achieved
checkpoint-status |  |  | checkpoint | Concrete is to be finished to correct RL
checkpoint-group |  |  | section | Sign-off
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | a1c272be-33ed-5cfc-bdbf-754c2f3f7109 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 38afee68-aa01-5f82-b2a2-464697aaee83 |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 3547d391-08a3-5ada-a900-b5a629ff852a |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Pre and Post Stripping Checklist (V.221121) |  |  |  |  | Yes | Pre and Post Stripping Checklist (V.221121) | fc7ab1ea-534b-4491-b9ae-0b5dbaddff72
checkpoint-status |  |  | checkpoint | All service penetrations are covered
checkpoint-status |  |  | checkpoint | Handrails installed correctly (if part of scope)
checkpoint-status |  |  | checkpoint | All Symal Structures material has been removed from the level (if loading bay is installed)
checkpoint-status |  |  | checkpoint | Sofit inspection confirms stripping completed 100% (including all fillet)
checkpoint-status |  |  | checkpoint | All Symal Structures waste has been disposed in bins (if available)
checkpoint-status |  |  | checkpoint | All PT pockets have been filled and grinded
checkpoint-status |  |  | checkpoint | All prop penetrations have been filled and grinded
checkpoint-status |  |  | checkpoint | Caulking is complete (if required)
checkpoint-status |  |  | checkpoint | Patching complete (if required)
checkpoint-status |  |  | checkpoint | Floors grinded general (if required)
checkpoint-status |  |  | checkpoint | Symal Structures sub-contractors work completed
checkpoint-status |  |  | checkpoint | All Symal Structures sub-contractors material removed from level
checkpoint-status |  |  | checkpoint | All Symal Structures subcontractors waste has been disposed in bins (if available)
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | 01170ddf-418b-5ef0-bdc3-c3d9e4f26bbb |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 8a325943-d680-5db4-8423-91e27e90e98b |  | button | HOLD POINT - Signature by Builders Site Coordinator attached below or Requested | Yes, No
button | 66612ba0-4126-530c-bd8d-566f881afbc7 |  | button | Symal Structures Signature Sign-Off attached below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off