## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Precast - Install Checklist (GAC - V.211021) |  |  |  |  | Yes | Precast - Install Checklist (GAC - V.211021) | 0e5c4d2c-24da-48f0-8bf3-99010a068ece
checkpoint-group |  |  | section | Details & Procedure
checkpoint-status |  |  | checkpoint | Safety Induction/Documentation complete - Lend Lease Project Induction & relevant SWMS communicated
checkpoint-status |  |  | checkpoint | Latest IFC drawings checked & referenced
text | f5e74645-5bec-5f7b-9d01-6b33de71eb35 |  | textbox | Drawing & Revision # (or Attach photo below)
text | 903a6517-75f9-5587-adaf-33b6d96914ea |  | textbox | Grout Strength
checkpoint-status |  |  | checkpoint | Column/Panel # confirmed and referenced
text | ee631745-3f26-5316-af84-0e9489a327dd |  | textbox | Column/Panel No.
checkpoint-status |  |  | checkpoint | Check for Birth Certificate, Compliances
checkpoint-status |  |  | checkpoint | Checked Lifting Certificates
checkpoint-status |  |  | checkpoint | Check Bracing design accepted by Lendlease
checkpoint-status |  |  | checkpoint | Check approved precast drawing
checkpoint-status |  |  | checkpoint | Check concrete test reports of slab/wall that precast sitting on
text | c601e7fa-b578-53da-b670-7e7dccf86ab9 |  | textbox | Concrete Strength (mPa)
checkpoint-status |  |  | checkpoint | Grouting Procedure/ Grouting Product approved by Engineer/Lendlease
checkpoint-status |  |  | checkpoint | Welding Procedure, Type & Size approved by Engineer (Sub Contractor to Weld)
checkpoint-group |  |  | section | Pre-Installation
checkpoint-status |  |  | checkpoint | Safety signs to be in place, Working area should be covered from barricades to control others to access
checkpoint-status |  |  | checkpoint | Check for concrete strength of loading slab/wall- 20Mpa required for PBI bolt anchors and 10Mpa required for Early aged anchors
checkpoint-status |  |  | checkpoint | Check for concrete strength of precast panels. Min 25Mpa for lifting or refer precast drawing
checkpoint-status |  |  | checkpoint | Reinforcement- Starter Bars installed as per documentation
label | 1ee887b8-74a5-5d33-b01c-e6e5b2ba727f |  | note | Type of Rebar-Carbon Steel Rebar/ Epoxy-Coated Rebar/ Galvanized Rebar/ Glass-Fiber-ReinforcedPolymer/ Stainless Steel Rebar
checkpoint-status |  |  | checkpoint | Grout Tubes - Material and diameter installed as per pre cast shop drawings
checkpoint-status |  |  | checkpoint | Grout material (TDS) and Methods approved by Lendlease
checkpoint-status |  |  | checkpoint | Grout delivered to site as per specifications, required quantity, relevant equipments and Grout expiry date to check
checkpoint-status |  |  | checkpoint | Panel to Panel Alignment correct and connection plate bolted to enable welding to commence
checkpoint-status |  |  | checkpoint | Bracing, locks, PBI bolts as specified in Bracing design have been delivered to location
checkpoint-status |  |  | checkpoint | Shim Packers/ Spacers & Donuts have been installed where necessary to enable grouting of horizontal joints to commence
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Setting out is done as per Precast marking plan
checkpoint-status |  |  | checkpoint | Dry mix Grout/ Mortar has been placed bottom of the panel along the perimeter as per specifications
checkpoint-status |  |  | checkpoint | Liquid Grout Poured into Grout tubes under the slab
checkpoint-status |  |  | checkpoint | Liquid Grout Poured into Grout tubes in the panel. For sleeve connections , specified grouts should be used and appropriate pump should be used
checkpoint-status |  |  | checkpoint | Bracing has been done as per design
checkpoint-status |  |  | checkpoint | Final alignment has been checked for acceptance
checkpoint-status |  |  | checkpoint | Anchors properly tighten on the floor and on panel. Torque register updated
checkpoint-status |  |  | checkpoint | Approval - Pass once below completed
button | 269d04bf-edf1-53e6-a474-87d9db113785 |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | 6c031f4d-18f3-5c6a-94ca-a16632d9ccc1 |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-group |  |  | section | Post-Installation
checkpoint-status |  |  | checkpoint | Horizontal Joints Installed as per Structural Documentation, including grout, backing rods etc
checkpoint-status |  |  | checkpoint | Stitch Plates Supplied as per IFC Shop Drawings & Structural Documentation
checkpoint-status |  |  | checkpoint | Panel to Panel Stitch/ Connection Plates Welded as per Structural Documentation
checkpoint-status |  |  | checkpoint | Welds have been reviewed by Independent Welding Inspector and Reports issued to Lendlease
checkpoint-status |  |  | checkpoint | Vertical Joints installed as per Structural Documentation, including caulk, backing and rods etc
checkpoint-status |  |  | checkpoint | Connection Plate Pockets have been patched with specified or approved product.
checkpoint-status |  |  | checkpoint | Internal Caulking installed with specified or approved Fire Rated product as per structural documentation
checkpoint-status |  |  | checkpoint | Grout Tubes filled and finished with approved/appropriate product
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
label | 33dbddc0-5a4c-5a10-9c83-ce5a771d61b1 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 7d858f98-635b-50b8-bfca-1f7ceddbd341 |  | note | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 1faa2168-9b9e-57ba-9723-628248eab393 |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | 6079c7a8-0c53-517f-a469-f4b1370420f8 |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Overall - Precast - Install Checklist (GAC - V.211021) |  |  |  |  | Yes | Overall - Precast - Install Checklist (GAC - V.211021) | 11a3ce8d-f156-4bd1-92ee-0eed38968604
checkpoint-status |  |  | checkpoint | Safety Induction/Documentation complete - Lend Lease Project Induction & relevant SWMS communicated
checkpoint-status |  |  | checkpoint | Latest IFC drawings checked & referenced
text | ecf60c2a-aa40-5682-a35f-582703c8dc25 |  | textbox | Drawing & Revision # (or Attach photo below)
checkpoint-status |  |  | checkpoint | Panel # confirmed and referenced
text | dfa34bd0-ec42-5679-b5b2-17dbf13c9d71 |  | textbox | Panel No.
checkpoint-status |  |  | checkpoint | Panel is installed to correct R.L
label | 384253fc-2847-53c0-a225-ecb3cf9e32dc |  | note | "+/- 5mm"
checkpoint-status |  |  | checkpoint | Panel has been setout by surveyor
checkpoint-status |  |  | checkpoint | Panel is facing correct way for elevation
checkpoint-status |  |  | checkpoint | Panel is level and installed correctly
label | 6214f1da-1b54-5cd8-9ae5-9f46f164e51b |  | note | Ma 40mm of shims
checkpoint-status |  |  | checkpoint | Was the panel damaged in transport
label | 419d415b-5969-565d-a98d-7c4f7d273cce |  | note | Attach photos below
checkpoint-status |  |  | checkpoint | Are there any concerns regarding this panel moving forward - Comment/photo below
checkpoint-status |  |  | checkpoint | Are Strong Backs attached to Panel which require removal post install
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
label | 3fe31c14-9a8d-5715-a38d-fc353605d472 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | bd172140-781e-5663-b019-07cb214b069a |  | note | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | a27ef39b-f9c0-5310-b18b-cc75a18046fd |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | a1541825-529e-598e-b1e9-e6033dda4f67 |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Floor Handover Checklist (GAC - V.211021) |  |  |  |  | Yes | Floor Handover Checklist (GAC - V.211021) | 20564859-731f-45fc-8606-4ee1a59175c1
checkpoint-status |  |  | checkpoint | Safety Induction/Documentation complete - Lend Lease Project Induction & relevant SWMS communicated
checkpoint-status |  |  | checkpoint | Latest IFC drawings checked & referenced
text | 7b174ca6-b200-5fe7-85d2-a7e5ebcbea45 |  | textbox | Drawing & Revision # (or Attach photo below)
checkpoint-status |  |  | checkpoint | All service penetrations are covered
checkpoint-status |  |  | checkpoint | Handrails installed correctly (If part of scope)
checkpoint-status |  |  | checkpoint | All Conset material has been removed from the level (if loading bay is installed)
checkpoint-status |  |  | checkpoint | Sofit inspection confirms stripping completed 100% (including all fillet)
checkpoint-status |  |  | checkpoint | All Symal waste has been disposed in bins (if available)
checkpoint-status |  |  | checkpoint | All PT pockets have been filled and grinded
checkpoint-status |  |  | checkpoint | All prop penetrations have been filled and grinded
checkpoint-status |  |  | checkpoint | Caulking is complete (if required)
checkpoint-status |  |  | checkpoint | Patching complete (if required)
checkpoint-status |  |  | checkpoint | Floors grinded general (if required)
checkpoint-status |  |  | checkpoint | Symal sub-contractors works completed
checkpoint-status |  |  | checkpoint | All Symal sub-contractors material removed from level
checkpoint-status |  |  | checkpoint | All Symal subcontractors waste has been disposed in bins (if available)
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
label | b615963f-cff2-5606-b835-d161352378f2 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 85be2e52-8f17-50f2-bce2-ca671432c9cd |  | note | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 7bda6a55-ef73-5586-acfb-c0cdbde33d68 |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | df7a4df3-c1a3-5013-b60e-86d91fb6bee6 |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | "Precast" - Setout Checklist (GAC - V.211021) |  |  |  |  | Yes | "Precast" - Setout Checklist (GAC - V.211021) | 356a097e-5dd5-47b4-b3e4-07bebf2729b4
checkpoint-status |  |  | checkpoint | Safety Induction/Documentation complete - Lend Lease Project Induction & relevant SWMS communicated
checkpoint-status |  |  | checkpoint | Latest IFC drawings checked & referenced
text | f519611c-490c-5afe-82b5-a617e3598eb6 |  | textbox | Drawing & Revision # (or Attach photo below)
checkpoint-status |  |  | checkpoint | Setout completed
text | 5ace541c-830d-50d9-8b24-026f2ddc5d5b |  | textbox | Setout By
text | 93ca1722-ef7c-5cc8-b66a-4a64f3449c90 |  | textbox | Date setout
label | 6f630aa6-e0cf-58e9-ab7b-84b8c8ed623b |  | note | NOTE: NCR MUST BE RAISED BY SITE ENGINEER WHEN ANSWERING- "NO" TO QUESTION 1-4
checkpoint-status |  |  | checkpoint | Panel # confirmed and referenced
text | ac1ee68e-d7c1-5bc8-9cfb-e8db74926af0 |  | textbox | Panel No.
checkpoint-status |  |  | checkpoint | Panel has been shot at the correct R.L
checkpoint-status |  |  | checkpoint | Panel has been setout by surveyor
checkpoint-status |  |  | checkpoint | All steps in panel match the slab or panel below
checkpoint-status |  |  | checkpoint | All bars are correct height. diameter and location
checkpoint-status |  |  | checkpoint | There is nothing overhead, or in the way of panel being installed
checkpoint-status |  |  | checkpoint | All ferrules are in place and panel can be propped
label | 74853049-2f7d-54a8-9853-1a187ebadb0d |  | note | The install area is clear and safe to begin install
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
label | 1f4807e4-a54b-5140-939f-cd1b1b11b540 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 88832354-a767-5ba1-a607-473798a1b3f0 |  | note | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | df277760-0a91-5004-a6ba-5141620b7dab |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | 2a8754ec-ac56-537f-b2b9-a6c829afecad |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Precast - Post-Install Sign Off Checklist (GAC - V.101221) |  |  |  |  | Yes | Precast - Post-Install Sign Off Checklist (GAC - V.101221) | 3b8f30f1-2d6f-4574-9653-391fa9ad55e1
checkpoint-status |  |  | checkpoint | Horizontal Joints Installed as per Structural Documentation, including grout, backing rods etc
checkpoint-status |  |  | checkpoint | Stitch Plates Supplied as per IFC Shop Drawings & Structural Documentation
checkpoint-status |  |  | checkpoint | Panel to Panel Stitch/ Connection Plates Welded as per Structural Documentation
checkpoint-status |  |  | checkpoint | Welds have been reviewed by Independent Welding Inspector and Reports issued to Lendlease
checkpoint-status |  |  | checkpoint | Vertical Joints installed as per Structural Documentation, including caulk, backing and rods etc
checkpoint-status |  |  | checkpoint | Connection Plate Pockets have been patched with specified or approved product.
checkpoint-status |  |  | checkpoint | Internal Caulking installed with specified or approved Fire Rated product as per structural documentation
checkpoint-status |  |  | checkpoint | Grout Tubes filled and finished with approved/appropriate product
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
label | 7751f03d-e31a-53de-b32f-8cd22f91f160 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | a639faf9-6210-57f7-a26e-fd4d1d99149a |  | note | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 9e01302d-5084-56ab-ae42-52ad7bca4a9a |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | 1344cb3e-543b-5c77-ab93-0f38e0ef8566 |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-sectioned |  |  | checklist | ITP-001 - BLINDING - PREPOUR CHECKLIST (GAC - V.211021) |  |  |  |  | Yes | ITP-001 - BLINDING - PREPOUR CHECKLIST (GAC - V.211021) | 5a70ffd5-6053-4be9-8fc6-84df81fe8018
checkpoint-group |  |  | section | Setout
checkpoint-status |  |  | checkpoint | Safety Induction/Documentation complete - Lend Lease Project Induction & relevant SWMS communicated
checkpoint-status |  |  | checkpoint | Latest IFC drawings checked & referenced
text | 245eae35-a0d8-5ca5-9d8e-043cea77f6bf |  | textbox | Drawing & Revision # (or Attach photo below)
text | 2c0bdebd-145f-550e-983c-825bda8396be |  | textbox | Concrete Strength (mPa)
checkpoint-status |  |  | checkpoint | Tolerance - Specification and Australian Standards
checkpoint-status |  |  | checkpoint | Footings shall be in accordance with AS2159 and with the project specifications
checkpoint-status |  |  | checkpoint | Refer to the IFC drawings for footing sizes and design loads
checkpoint-status |  |  | checkpoint | RLs checked & Correct
text | 1156bfae-a77e-5ad3-b756-087fcf483bd8 |  | textbox | RL. (Top of blinding)
label | c18d90c9-30e9-5f6f-b922-f2011f341fa3 |  | note | RL varies accordingly in sections of works
checkpoint-group |  |  | section | Foundation
checkpoint-status |  |  | checkpoint | Approval from Geotechnical Engineer, or nominated personnel
checkpoint-status |  |  | checkpoint | Compliance with Geotechnical Engineer Report
checkpoint-status |  |  | checkpoint | Ensure minimum coverage attained as per relevant cover notes and specifications
checkpoint-group |  |  | section | Pre-Pour
checkpoint-status |  |  | checkpoint | Ensure concrete strength for blinding is in accordance with Structural Drawing
text | 81250739-01b3-5a3b-a617-bf1aa99d6d11 |  | textbox | Concrete Strength (mPa)
checkpoint-status |  |  | checkpoint | Pour area cleaned before pour - to ensure free of standing Water, debris, oils, objectionable coatings & fragments. (Refer specification)
checkpoint-status |  |  | checkpoint | Prepour outstanding items list signed off and completed
checkpoint-status |  |  | checkpoint | Ensure temperatures when pouring are within acceptable criteria (between 5ºC and 35ºC)
checkpoint-status |  |  | checkpoint | Placement method confirmed
select | ddf679f4-f5e2-59a8-a5b4-80a7d6c962da |  | dropdown | Method | Chute, Kibble, Pump
checkpoint-status |  |  | checkpoint | Approval to Pour - Pass once below completed
button | 5e6ecc13-72d7-58e6-bed9-d76ede7e299a |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | d0174964-0dfe-5f9c-b510-ba8325883309 |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-group |  |  | section | Placement
checkpoint-status |  |  | checkpoint | All concrete work shall be carried out in accordance with the AS3600
checkpoint-status |  |  | checkpoint | Concrete is to be finished to correct RL
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | 0b3af41c-34da-532f-863f-e1858e60ecb8 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | fce879eb-d22a-58fd-9834-e5b743d1deaf |  | note | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 17799153-8805-5713-b9da-2bef4b4e07a8 |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | 741a030c-8746-526e-989c-52fc2c334fdc |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Composite Slab Handover (V.140222) |  |  |  |  | Yes | Composite Slab Handover (V.140222) | 5ab5ee29-2fcb-476f-93f5-df89eb907570
checkpoint-status |  |  | checkpoint | Confirmation base (bondeck) has been installed to correct levels – asbuilt.
checkpoint-status |  |  | checkpoint | Confirmation area is safe to access – stretcher and secondary access in place, any required edge support installed, back propping has been considered/completed
checkpoint-status |  |  | checkpoint | Confirmation edge protection is installed/compliant
checkpoint-status |  |  | checkpoint | Confirmation area is clean/free of debris
checklist-flat |  |  | checklist | Precast Torque Register (GAC - V.211021) |  |  |  |  | Yes | Precast Torque Register (GAC - V.211021) | 5dcd5a5d-0f7f-43ee-b6d6-afa1083026a0
checkpoint-status |  |  | checkpoint | Safety Induction/Documentation complete - Lend Lease Project Induction & relevant SWMS communicated
checkpoint-status |  |  | checkpoint | Latest IFC drawings checked & referenced
text | 6be0565f-7173-59ae-bd41-5c7e11a29974 |  | textbox | Drawing & Revision # (or Attach photo below)
checkpoint-status |  |  | checkpoint | Panel # confirmed and referenced
text | 8b6dc1ad-28db-5ef2-ac71-6ea714f2a54a |  | textbox | Panel No.
text | 6363930c-5fe2-5281-8b60-5e0c3dcbdffc |  | textbox | Install date
checkpoint-status |  |  | checkpoint | Initial Torque
text | babce269-82fe-5271-b487-31dde8e5b6dd |  | textbox | Torque (base)
text | 66ff9062-5393-59af-8d06-a00a8113054c |  | textbox | Torque (panel)
checkpoint-status |  |  | checkpoint | 24hr Torque
text | 352dcdb9-4d0b-53f7-8f16-3993b7959d0f |  | textbox | Torque (base) 24hr
text | f858fb5b-8b0c-5ddb-8325-a0479f78c59e |  | textbox | Torque (panel) 24hr
checkpoint-status |  |  | checkpoint | 72hr Torque
text | c2fbd1b7-df63-5839-84b3-f3005a81b88a |  | textbox | Torque (base) 72hr
text | b3a93db6-6484-5f79-80bf-5a16361fcf77 |  | textbox | Torque (panel) 72hr
checkpoint-status |  |  | checkpoint | Torque # confirmed and referenced
text | e999ab7e-e049-55b5-958b-cc08dff885de |  | textbox | Torque Number
checkpoint-status |  |  | checkpoint | All Symal sub-contractors material removed from level
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
label | 08fc5a44-978d-50ea-aad1-c50b4bd142b9 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 8d640f2d-a13a-502e-af15-ec56acd2cbb7 |  | button | Symal Structures Signature Sign-Off added below | Yes, No
checklist-sectioned |  |  | checklist | ITP-005 - Walls (GAC - V.211021) |  |  |  |  | Yes | ITP-005 - Walls (GAC - V.211021) | 62b5850f-9141-4d6b-8eb9-ae27bd21127b
checkpoint-group |  |  | section | Setout
checkpoint-status |  |  | checkpoint | Safety Induction/Documentation complete - Lend Lease Project Induction & relevant SWMS communicated
checkpoint-status |  |  | checkpoint | Latest IFC drawings checked & referenced
text | 02557bdb-64f6-52d8-b1d8-fda10ae10fb0 |  | textbox | Drawing & Revision # (or Attach photo below)
text | ec9e1a20-5e21-5871-9819-5e8977c57456 |  | textbox | Concrete Strength (mPa)
checkpoint-status |  |  | checkpoint | Tolerance - Specification and Australian Standards
checkpoint-status |  |  | checkpoint | RLs checked & Correct
text | dbb563f2-4ba8-5a1d-8157-e3347d38c6a6 |  | textbox | RL. (Top of pour)
label | 8966d2ef-d4aa-553a-a506-82d190fc8c97 |  | note | RL varies accordingly in sections of works. Refer to Architectural Drawings
checkpoint-status |  |  | checkpoint | Check for all penetrations (set-out and location). Refer Architectural, Structural
checkpoint-status |  |  | checkpoint | Set-out of all walls. Refer to Architectural drawings
checkpoint-status |  |  | checkpoint | Approval of QA for slab under
checkpoint-status |  |  | checkpoint | Compliance with ITP of slab below
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | All in-situ wall services have been installed and in correct location
checkpoint-status |  |  | checkpoint | Shutters are scraped, cleaned and in satisfactory condition prior to each use
checkpoint-status |  |  | checkpoint | Ensure formwork has suitable 'stripping oil' applied
checkpoint-status |  |  | checkpoint | All penetrations are installed and in correct location
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | All reinforcement to be placed in accordance with the IFC structural drawings
checkpoint-status |  |  | checkpoint | Reinforcement securely fixed in place
checkpoint-status |  |  | checkpoint | Where reinforcement has been tack welded (yet approved by Lend Lease), it must conform to AS 1554.3:2002
checkpoint-status |  |  | checkpoint | Bar spacing correct
checkpoint-status |  |  | checkpoint | Correct bar diameter
checkpoint-status |  |  | checkpoint | Correct splice lengths through construction joints
checkpoint-status |  |  | checkpoint | Correct concrete cover
checkpoint-status |  |  | checkpoint | Bar chair location and spacing
checkpoint-status |  |  | checkpoint | Starter bars comply with size and spacing for elements over
checkpoint-group |  |  | section | Water Stop
checkpoint-status |  |  | checkpoint | All cast-in terms as specified and in correct location
checkpoint-status |  |  | checkpoint | Ensure water-stop is securely fastened to construction joints. (Where applicable)
checkpoint-group |  |  | section | Pre-Pour
checkpoint-status |  |  | checkpoint | Pour area cleaned before pour - to ensure free of standing Water, debris, oils, objectionable coatings & fragments. (Refer specification)
checkpoint-status |  |  | checkpoint | Concrete strength for walls are in accordance with structural drawings
checkpoint-status |  |  | checkpoint | Reinforcement fixed in place
checkpoint-status |  |  | checkpoint | Prepour outstanding items list signed off and completed
checkpoint-status |  |  | checkpoint | Ensure temperatures when pouring are within acceptable criteria (between 5ºC and 35ºC)
checkpoint-status |  |  | checkpoint | Tester ordered: 0 - 50m3 - 1 batch of tests or there off. 50-100m3 - 2 batch of tests or there off
checkpoint-status |  |  | checkpoint | Placement method confirmed
select | 7853e44f-ce3b-52a1-ae25-a921e123f52d |  | dropdown | Method | Chute, Kibble, Pump
checkpoint-status |  |  | checkpoint | Concrete vibration to be completed with use of vibrator motor (minimum requirement of 300rpm)
checkpoint-status |  |  | checkpoint | Tester Required for Structural Elements as noted in AS 1012
checkpoint-status |  |  | checkpoint | Approval to Pour - Pass once below completed
button | 21c55e4f-5989-5a0f-aa30-a7ce75e1311e |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | b282ff55-811c-555b-bb6b-85154ab3f152 |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-group |  |  | section | Placement
checkpoint-status |  |  | checkpoint | All concrete work shall be carried out in accordance with the AS 3600
checkpoint-status |  |  | checkpoint | A minimum of one vibrator must be used at all times while concrete is in operation
label | b5e585ec-9a4a-5e1d-aa5b-f905939b85fc |  | note | These vibrators are to be no less than 5 metres long to ensure full compaction is reached
checkpoint-status |  |  | checkpoint | Competent concreters will be used to vibrate the concrete using the immersion vibrators, ensuring full compaction is achieved
checkpoint-status |  |  | checkpoint | Concrete is to be finished to correct RL
checkpoint-status |  |  | checkpoint | Ensure class finish has been complete as per relevant project specifications
label | 9de98d14-ffef-5009-af07-4e53bf978a71 |  | note | (Refer Scope Specification - Concrete Finish) and in reference with AS3600 and AS3610)
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | 3291bc60-ee22-5c25-8b57-a4a6c9bc62c1 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 077ef247-4752-508f-bb17-af5a6cb54dea |  | note | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 5f46da33-3cbf-5c38-8639-815d9fdc4662 |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | 7333cba3-d59d-5d13-9cba-521e7adac91f |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Concrete Pour Record (GAC - V.211021) |  |  |  |  | Yes | Concrete Pour Record (GAC - V.211021) | 6b496951-fa8a-41a4-ac08-0df48b293829
checkpoint-status |  |  | checkpoint | Concrete delivery dockets uploaded
label | 52f8e1c0-6483-5889-bb9e-149ef6a69d1f |  | note | Pdf reports received from concrete supplier
label | 5380282d-628f-55dd-a95e-7fa13c491bd7 |  | note | Ensure naming convention of checklist is accurate
checklist-sectioned |  |  | checklist | ITP-003 - Suspended Slabs (GAC - V.211021) |  |  |  |  | Yes | ITP-003 - Suspended Slabs (GAC - V.211021) | 7cf56593-11ae-4f82-89ae-e018d003c665
checkpoint-group |  |  | section | Setout
checkpoint-status |  |  | checkpoint | Safety Induction/Documentation complete - Lend Lease Project Induction & relevant SWMS communicated
checkpoint-status |  |  | checkpoint | Latest IFC drawings checked & referenced
text | d10ad670-1357-550d-8780-46dab8d0f363 |  | textbox | Drawing & Revision # (or Attach photo below)
text | 5594124a-6d38-57e8-8d22-026554d442b3 |  | textbox | Concrete Strength (mPa)
checkpoint-status |  |  | checkpoint | Tolerance - Specification and Australian Standards
checkpoint-status |  |  | checkpoint | RLs checked & Correct
text | fcb0a9cd-c54e-5453-9f49-1cba790eb1c7 |  | textbox | RL. (Top of pour)
label | af7e36b8-e695-50f9-9235-fb7bbf68db68 |  | note | RL varies accordingly in sections of works. Refer to Architectural Drawings
checkpoint-status |  |  | checkpoint | Check for all penetrations (set-out and location). Refer Architectural, Structural
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | All in-situ slab services have been installed and in correct location
checkpoint-status |  |  | checkpoint | Ensure all beam and slab depths are correct and are carried out as per IFC structural drawings
checkpoint-status |  |  | checkpoint | Ensure formwork at stop ends has suitable 'stripping oil' applied
checkpoint-status |  |  | checkpoint | Ensure bondek has correct lap and is securely fastened
checkpoint-status |  |  | checkpoint | Ensure bondek has a minimum 25mm overlap from edge of formwork
checkpoint-status |  |  | checkpoint | All frames, bases and formwork tables to be correctly aligned (frames vertical)
checkpoint-status |  |  | checkpoint | Ensure that formwork (frames, bases, tables, etc) have been inspected and signed off by a formwork designer prior to any pour of a suspended slab
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | All reinforcement to be placed in accordance with the IFC post tension drawings
checkpoint-status |  |  | checkpoint | Reinforcement securely fixed in place
checkpoint-status |  |  | checkpoint | Where reinforcement has been tack welded (yet approved by Lend Lease), it must conform to AS 1554.3:2002
checkpoint-status |  |  | checkpoint | Bar spacing correct
checkpoint-status |  |  | checkpoint | Correct bar diameter
checkpoint-status |  |  | checkpoint | Correct splice lengths
checkpoint-status |  |  | checkpoint | Correct concrete cover
checkpoint-status |  |  | checkpoint | Bar chair location and spacing
checkpoint-status |  |  | checkpoint | Starter bars comply with size and spacing for column over
checkpoint-group |  |  | section | Post-Tensioning
checkpoint-status |  |  | checkpoint | All Post Tensioning to be placed in accordance with the IFC structural drawings
checkpoint-status |  |  | checkpoint | P.T. ducts, fixing and strands securely fixed in place
checkpoint-status |  |  | checkpoint | P.T. spacing correct
checkpoint-status |  |  | checkpoint | Correct P.T. sizes used
checkpoint-status |  |  | checkpoint | Correct duct level in concrete
checkpoint-status |  |  | checkpoint | Bar chair location and spacing
checkpoint-group |  |  | section | Pre-Pour
checkpoint-status |  |  | checkpoint | Pour area cleaned before pour - to ensure free of standing Water, debris, oils, objectionable coatings & fragments. (Refer specification)
checkpoint-status |  |  | checkpoint | Concrete strength for Slab on Ground to be at 32/40MPa or unless noted otherwise
checkpoint-status |  |  | checkpoint | Reinforcement fixed in place
checkpoint-status |  |  | checkpoint | Prepour outstanding items list signed off and completed
checkpoint-status |  |  | checkpoint | Ensure temperatures when pouring are within acceptable criteria (between 5ºC and 35ºC)
checkpoint-status |  |  | checkpoint | Tester ordered: 0 - 50m3 - 1 batch of tests or there off. 50-100m3 - 2 batch of tests or there off
checkpoint-status |  |  | checkpoint | Placement method confirmed
select | c81c6c74-e675-5471-85dd-c9e52a7f3988 |  | dropdown | Method | Chute, Kibble, Pump
checkpoint-status |  |  | checkpoint | Concrete vibration to be completed with use of vibrator motor (minimum requirement of 300rpm)
checkpoint-status |  |  | checkpoint | Tester Required for Structural Elements as noted in AS 1012
checkpoint-status |  |  | checkpoint | Approval to Pour - Pass once below completed
button | 1b86dcf0-7ac3-5b4e-bdd6-716f9253d3d2 |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | 36c35e35-ba68-58ce-a0c1-0135d5e9579f |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-group |  |  | section | Placement & Finish
checkpoint-status |  |  | checkpoint | All concrete work shall be carried out in accordance with the AS 3600
checkpoint-status |  |  | checkpoint | A minimum of one vibrator must be used at all times while concrete is in operation
label | 4cda2803-b7c4-5b90-b336-fed4f9f77ced |  | note | These vibrators are to be no less than 5 metres long to ensure full compaction is reached
checkpoint-status |  |  | checkpoint | Competent concreters will be used to vibrate the concrete using the immersion vibrators, ensuring full compaction is achieved
checkpoint-status |  |  | checkpoint | Concrete is to be finished to correct RL or slope
checkpoint-status |  |  | checkpoint | Check finish to ensure that there is no slab over. Refer Architectural drawings
checkpoint-status |  |  | checkpoint | Please ensure concrete finishing method is to the correct drawings, materials schedule and specifications
checkpoint-status |  |  | checkpoint | If there is no slab over has the class finish been complete as per relevant project specifications
label | 2b5986c3-30ed-516f-b530-30073f3d1082 |  | note | (Refer relevant specification) and in reference with AS3600 and AS3610
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | 27c571c3-45ff-5243-ae09-8ed0eacf3485 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 542c2ef6-88ae-5686-a05e-a5701747a650 |  | note | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 09a878a9-8f2f-5004-9d3d-38e737dcc6a1 |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | baf86553-e7a8-580f-83fd-b8606117b10a |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-sectioned |  |  | checklist | ITP-002 - Slab on Ground (GAC - V.211021) |  |  |  |  | Yes | ITP-002 - Slab on Ground (GAC - V.211021) | 8e759ba0-698a-48f3-9f9a-44556039a296
checkpoint-group |  |  | section | Setout
checkpoint-status |  |  | checkpoint | Safety Induction/Documentation complete - Lend Lease Project Induction & relevant SWMS communicated
checkpoint-status |  |  | checkpoint | Latest IFC drawings checked & referenced
text | e4fda671-afde-5ea0-af01-83d8edc3cad3 |  | textbox | Drawing & Revision # (or Attach photo below)
text | add6dad0-f438-5f9a-a5c7-bdc35b8feaa6 |  | textbox | Concrete Strength (mPa)
checkpoint-status |  |  | checkpoint | Tolerance - Specification and Australian Standards
checkpoint-status |  |  | checkpoint | All cast-in's in place (pipe block outs, peno's etc)
checkpoint-status |  |  | checkpoint | RLs checked & Correct
text | 67ae13a3-10dd-5bba-9879-c53dbb61f0cd |  | textbox | RL. (Top of pour)
label | 7b16fdeb-1fb3-55e1-9d96-bfd767facdd4 |  | note | RL varies accordingly in sections of works. Refer to Architectural Drawings
checkpoint-group |  |  | section | Foundation
checkpoint-status |  |  | checkpoint | Ensure minimum coverage attained as per relevant cover notes and specifications
checkpoint-status |  |  | checkpoint | Approval from Geotechnical Engineer, or nominated personnel
checkpoint-status |  |  | checkpoint | Compliance with Geotechnical Engineer Report
checkpoint-status |  |  | checkpoint | Compacted sand lines and levels/concrete blinding
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | All in-ground services have been installed and in the correct location
checkpoint-status |  |  | checkpoint | Ensure formwork for stop ends has suitable 'stripping oil' applied. (chipboard)
checkpoint-status |  |  | checkpoint | Diamond dowel lengths and spacing correct. IF required
checkpoint-status |  |  | checkpoint | Ensure all cast-in elements are positioned, fixed, level, plumb
checkpoint-status |  |  | checkpoint | All penetrations are installed and in correct location
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | All reinforcement to be placed in accordance with the IFC structural drawings and AS 1302
checkpoint-status |  |  | checkpoint | Reinforcement securely fixed in place
checkpoint-status |  |  | checkpoint | Where reinforcement has been tack welded (yet approved by Lend Lease), it must conform to AS 1554.3:2002
checkpoint-status |  |  | checkpoint | Bar spacing correct
checkpoint-status |  |  | checkpoint | Correct bar diameter
checkpoint-status |  |  | checkpoint | Correct splice lengths
checkpoint-status |  |  | checkpoint | Correct concrete cover
checkpoint-status |  |  | checkpoint | Bar chair location and spacing
checkpoint-status |  |  | checkpoint | Starter bars comply with size and spacing for column over
checkpoint-group |  |  | section | Pre-Pour
checkpoint-status |  |  | checkpoint | Pour area cleaned before pour - to ensure free of standing Water, debris, oils, objectionable coatings & fragments. (Refer specification)
checkpoint-status |  |  | checkpoint | Concrete strength for Slab on Ground to be at 32MPa or unless noted otherwise
checkpoint-status |  |  | checkpoint | Reinforcement fixed in place
checkpoint-status |  |  | checkpoint | Prepour outstanding items list signed off and completed
checkpoint-status |  |  | checkpoint | Ensure temperatures when pouring are within acceptable criteria (between 5ºC and 35ºC)
checkpoint-status |  |  | checkpoint | Tester ordered: 0 - 50m3 - 1 batch of tests or there off. 50-100m3 - 2 batch of tests or there off
checkpoint-status |  |  | checkpoint | Placement method confirmed
select | 7da4eca8-b728-5bfb-a0b5-b3baba31a05f |  | dropdown | Method | Chute, Kibble, Pump
checkpoint-status |  |  | checkpoint | Concrete vibration to be completed with use of vibrator motor (minimum requirement of 300rpm)
checkpoint-status |  |  | checkpoint | Tester Required for Structural Elements as noted in AS 1012
checkpoint-status |  |  | checkpoint | Approval to Pour - Pass once below completed
button | 24c50ed5-b628-5d95-aff7-21cc142ace54 |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | d9b971aa-064a-5f38-a108-686eb131de83 |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-group |  |  | section | Placement & Finish
checkpoint-status |  |  | checkpoint | One immersion Vibrator is to be situated on the site and used for duration of pour, this must be used at all times while the pump or kibble is in operation
checkpoint-status |  |  | checkpoint | Competent concreters will be used to vibrate the concrete using the immersion vibrators, ensuring full compaction is achieved
checkpoint-status |  |  | checkpoint | Concrete is to be finished to correct RL
checkpoint-status |  |  | checkpoint | Check finish to ensure that there is no slab over. Refer Architectural drawings
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | ca9e56ac-e7ec-5c06-8a0e-065b6be0cbdf |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 54f62b23-a0ba-57b9-9749-ccf508001b95 |  | note | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 3ae1de3a-4727-53ae-8705-27ca447f04a7 |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | e0f9d1b5-4f2b-5931-8f4f-6f6554cb7a47 |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-sectioned |  |  | checklist | Suspended Formwork Pre-Strip Checklist (GAC - V.211021) |  |  |  |  | Yes | Suspended Formwork Pre-Strip Checklist (GAC - V.211021) | 91399494-07fb-409e-ab9a-8bae7b200d6d
checkpoint-group |  |  | section | Details & Procedure
checkpoint-status |  |  | checkpoint | Safety Induction/Documentation complete - Lend Lease Project Induction & relevant SWMS communicated
checkpoint-status |  |  | checkpoint | Latest IFC drawings checked & referenced
text | b318868d-e48b-54b3-9d44-d5e7c6b96749 |  | textbox | Drawing & Revision # (or Attach photo below)
text | 1b756d90-9331-50f5-af8e-f5d15049766a |  | textbox | Date poured
checkpoint-group |  |  | section | Pre-Strip Requirements
checkpoint-status |  |  | checkpoint | SWMS considers credible hazards for task in line with Project Risk Assessment
checkpoint-status |  |  | checkpoint | Concrete has reached the minimum strength as per AS 3600 or engineering specifications which ever the greater
label | 14c9ed54-f90a-5059-97a2-da3200c560b0 |  | note | Attach documentation below
checkpoint-status |  |  | checkpoint | Post tensioning (P.T) is complete, stress results and sign off by SRG received
label | a1bfc8c9-ecbf-575c-a236-8dd1d4e2790d |  | note | Attach documentation below
checkpoint-status |  |  | checkpoint | Grout is complete to all P.T ducting
label | c37d4179-5c1c-5df0-aefb-ed2766ee1883 |  | note | Attach documentation below
checkpoint-status |  |  | checkpoint | P.T grout has reached required strength as per engineering/SRG Specifications
label | 9087296d-bb06-50ba-9be7-afb4ca103afc |  | note | Attach documentation below
checkpoint-status |  |  | checkpoint | Panel props have been signed off for removal
label | ccaaf20f-cb55-5490-8721-96f72b8a8a24 |  | note | Attach documentation below
checkpoint-status |  |  | checkpoint | Are any permits required by LLB for the task
checkpoint-group |  |  | section | Strip Formwork
checkpoint-status |  |  | checkpoint | Re-route of site egress and access established and communicated
checkpoint-status |  |  | checkpoint | Barricade and signage erected to prohibit unathorised entry to stripping area
checkpoint-status |  |  | checkpoint | Guarding or penetration covers have been installed to slab above
checkpoint-status |  |  | checkpoint | Penetrations covered (working level)
checkpoint-status |  |  | checkpoint | Drop zone areas have been established for areas below (stripping near a live edge)
checkpoint-status |  |  | checkpoint | All workers who will undertake task have read understood and signed SWMS for task
checkpoint-status |  |  | checkpoint | If Required - Permit(s) have been approved by Lend Lease and all workers completing the task have read, understood and signed the permit
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
label | 731e98e4-d8ec-51ea-a201-3880784d0fe8 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 546ed6c4-a410-5553-b785-074c4ad24aba |  | note | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 9a174921-2912-569f-a97c-0b42b086cafd |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | 39ab92ca-b276-5560-a0a7-6b2e32f57f4e |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-sectioned |  |  | checklist | ITP-006 - Conventional Stairs - Pre-pour (GAC - V.211021) |  |  |  |  | Yes | ITP-006 - Conventional Stairs - Pre-pour (GAC - V.211021) | 9cd36ca6-fbf8-4d89-8e07-36896cf7b142
checkpoint-group |  |  | section | Setout
checkpoint-status |  |  | checkpoint | Safety Induction/Documentation complete - Lend Lease Project Induction & relevant SWMS communicated
checkpoint-status |  |  | checkpoint | Latest IFC drawings checked & referenced
text | 9f702b76-fc06-5026-a9f8-054a3038a099 |  | textbox | Drawing & Revision # (or Attach photo below)
text | 1fd57504-ee53-5e9d-b4c2-49a8b3d53cbc |  | textbox | Concrete Strength (mPa)
checkpoint-status |  |  | checkpoint | Tolerance - Specification and Australian Standards
checkpoint-status |  |  | checkpoint | RLs checked & Correct
text | 143fdc42-4e37-58b9-b582-d9ba743cf5c5 |  | textbox | RL. (Top of pour)
label | 242d1ec7-19f7-5c75-b975-04a16cfd0ba5 |  | note | RL varies accordingly in sections of works. Refer to Architectural Drawings
checkpoint-status |  |  | checkpoint | Set-out of all conventional stairs. Refer to Architectural drawings
checkpoint-status |  |  | checkpoint | Approval of QA for slab under
checkpoint-status |  |  | checkpoint | Compliance with ITP of slab below
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | All in-situ stair services have been installed and in correct location
checkpoint-status |  |  | checkpoint | Ensure stairs are in correct position, all dimensions and spacing between flights are as per Structural drawings and Architectural drawings
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | All reinforcement to be placed in accordance with the IFC structural drawings
checkpoint-status |  |  | checkpoint | Reinforcement securely fixed in place
checkpoint-status |  |  | checkpoint | Where reinforcement has been tack welded (yet approved by Lend Lease), it must conform to AS 1554.3:2002
checkpoint-status |  |  | checkpoint | Where bars have been drilled and epoxied into precast panels, ensure embedment and projection are correct
checkpoint-status |  |  | checkpoint | Bar spacing correct
checkpoint-status |  |  | checkpoint | Correct bar diameter
checkpoint-status |  |  | checkpoint | Correct splice lengths through construction joints
checkpoint-status |  |  | checkpoint | Correct concrete cover
checkpoint-group |  |  | section | Pre-Pour
checkpoint-status |  |  | checkpoint | Pour area cleaned before pour - to ensure free of standing Water, debris, oils, objectionable coatings & fragments. (Refer specification)
checkpoint-status |  |  | checkpoint | Any flat surface concrete areas on precast rebate for landings, needs to be scabbled to exposed concrete aggregate
checkpoint-status |  |  | checkpoint | Concrete strength for Conventional Stairs to be 32MPa unless noted otherwise
checkpoint-status |  |  | checkpoint | Reinforcement fixed in place
checkpoint-status |  |  | checkpoint | Prepour outstanding items list signed off and completed
checkpoint-status |  |  | checkpoint | Ensure temperatures when pouring are within acceptable criteria (between 5ºC and 35ºC)
checkpoint-status |  |  | checkpoint | Tester ordered: 0 - 50m3 - 1 batch of tests or there off. 50-100m3 - 2 batch of tests or there off
checkpoint-status |  |  | checkpoint | Placement method confirmed
select | 8dee8606-6804-5965-a139-84ddb4b99bce |  | dropdown | Method | Chute, Kibble, Pump
checkpoint-status |  |  | checkpoint | Concrete vibration to be completed with use of vibrator motor (minimum requirement of 300rpm)
checkpoint-status |  |  | checkpoint | Tester Required for Structural Elements as noted in AS 1012
checkpoint-status |  |  | checkpoint | Approval to Pour - Pass once below completed
button | 743c9409-e58f-553e-a623-6a57994a192c |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | 407a6d59-c0e9-53ed-95d1-76bd9f0e822f |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-group |  |  | section | Placement
checkpoint-status |  |  | checkpoint | A minimum of one vibrator must be used at all times while concrete is in operation
label | 666c1b80-945b-5050-90b3-59af344e525a |  | note | These vibrators are to be no less than 5 metres long to ensure full compaction is reached
checkpoint-status |  |  | checkpoint | Competent concreters will be used to vibrate the concrete using the immersion vibrators, ensuring full compaction is achieved
checkpoint-status |  |  | checkpoint | Concrete is to be finished to correct RL
checkpoint-status |  |  | checkpoint | All concrete work shall be carried out in accordance with the AS3600
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | d62f582a-000d-54c3-a419-41e786a3bd52 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | f93017a3-caa9-504f-8fda-5c46c7e99d21 |  | note | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | a0665b1c-88e2-5152-b858-a9694293d98f |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | 9df3ed5e-24ca-54bf-b9b0-b5518bda1eb2 |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-sectioned |  |  | checklist | Precast - Details & Pre-Install Checklist (GAC - V.101221) |  |  |  |  | Yes | Precast - Details & Pre-Install Checklist (GAC - V.101221) | 9e8c23bd-9b73-4964-b5cc-3e8a79bd289f
checkpoint-group |  |  | section | Details & Procedure
checkpoint-status |  |  | checkpoint | Safety Induction/Documentation complete - Lend Lease Project Induction & relevant SWMS communicated
checkpoint-status |  |  | checkpoint | Latest IFC drawings checked & referenced
text | d424b4a6-a57f-53a4-bf7d-acb8f5400104 |  | textbox | Drawing & Revision # (or Attach photo below)
text | c9bef3b9-7f60-532c-8c2a-82f2d2bec518 |  | textbox | Grout Strength
checkpoint-status |  |  | checkpoint | Column/Panel # confirmed and referenced
text | b7ea17d3-309f-51b1-84a2-ff42d994f8f3 |  | textbox | Column/Panel No.
checkpoint-status |  |  | checkpoint | Check for Birth Certificate, Compliances
checkpoint-status |  |  | checkpoint | Checked Lifting Certificates
checkpoint-status |  |  | checkpoint | Check Bracing design accepted by Lendlease
checkpoint-status |  |  | checkpoint | Check approved precast drawing
checkpoint-status |  |  | checkpoint | Check concrete test reports of slab/wall that precast sitting on
text | 309ebc68-4f1b-5ed4-8d1a-774cb822dbbd |  | textbox | Concrete Strength (mPa)
checkpoint-status |  |  | checkpoint | Grouting Procedure/ Grouting Product approved by Engineer/Lendlease
checkpoint-status |  |  | checkpoint | Welding Procedure, Type & Size approved by Engineer (Sub Contractor to Weld)
checkpoint-group |  |  | section | Pre-Installation
checkpoint-status |  |  | checkpoint | Safety signs to be in place, Working area should be covered from barricades to control others to access
checkpoint-status |  |  | checkpoint | Check for concrete strength of loading slab/wall- 20Mpa required for PBI bolt anchors and 10Mpa required for Early aged anchors
checkpoint-status |  |  | checkpoint | Check for concrete strength of precast panels. Min 25Mpa for lifting or refer precast drawing
checkpoint-status |  |  | checkpoint | Reinforcement- Starter Bars installed as per documentation
label | a10aacdf-8288-50fa-91cd-d4229b6c9abd |  | note | Type of Rebar-Carbon Steel Rebar/ Epoxy-Coated Rebar/ Galvanized Rebar/ Glass-Fiber-ReinforcedPolymer/ Stainless Steel Rebar
checkpoint-status |  |  | checkpoint | Grout Tubes - Material and diameter installed as per precast shop drawings
checkpoint-status |  |  | checkpoint | Grout material (TDS) and Methods approved by Lendlease
checkpoint-status |  |  | checkpoint | Grout delivered to site as per specifications, required quantity, relevant equipments and Grout expiry date to check
checkpoint-status |  |  | checkpoint | Panel to Panel Alignment correct and connection plate bolted to enable welding to commence
checkpoint-status |  |  | checkpoint | Bracing, locks, PBI bolts as specified in Bracing design have been delivered to location
checkpoint-status |  |  | checkpoint | Shim Packers/ Spacers & Donuts have been installed where necessary to enable grouting of horizontal joints to commence
checklist-sectioned |  |  | checklist | ITP-004.1 - Columns Postpour (GAC - V.211021) |  |  |  |  | Yes | ITP-004.1 - Columns Postpour (GAC - V.211021) | a6923981-1a71-45d0-bfaf-fdfb29ba1929
checkpoint-group |  |  | section | Setout
checkpoint-status |  |  | checkpoint | Safety Induction/Documentation complete - Lend Lease Project Induction & relevant SWMS communicated
checkpoint-status |  |  | checkpoint | Latest IFC drawings checked & referenced
text | 6320fc18-66db-5fff-9b46-d6e695a39b51 |  | textbox | Drawing & Revision # (or Attach photo below)
text | 01d7ace0-8a59-50a6-a7cd-05c4110e36f2 |  | textbox | Concrete Strength (mPa)
checkpoint-status |  |  | checkpoint | Tolerance - Specification and Australian Standards
checkpoint-group |  |  | section | Placement & Finish
checkpoint-status |  |  | checkpoint | Immersion Vibrator to be situated and used for duration of pour
checkpoint-status |  |  | checkpoint | A minimum of one vibrator must be used at all times while concrete is in operation
label | 7fa6ce7b-c6be-54cc-b0b9-368dfe0c842b |  | note | These vibrators are to be no less than 5 metres long to ensure full compaction is reached
checkpoint-status |  |  | checkpoint | Competent concreters will be used to vibrate the concrete using the immersion vibrators, ensuring full compaction is achieved
checkpoint-status |  |  | checkpoint | Has concrete been finished to correct RL
checkpoint-status |  |  | checkpoint | Visual check on columns once stripped to ensure no cracking has occurred
checkpoint-status |  |  | checkpoint | Visual check on columns once stripped to ensure that there are no boney concrete areas due to lack of vibration
checkpoint-status |  |  | checkpoint | Ensure patching to columns has been undertaken for any defect areas that are visible
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | efd894e8-060b-59b2-aaef-8677209823f9 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 61aa34b1-484b-59d0-a4e1-d0b99a575d33 |  | note | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | f64b88b4-d34b-5193-97dd-9d8bcf905e02 |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | 36dc5bd3-3ba8-5e32-ab53-3ad7223f1f65 |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Precast - Pre-pour Checklist (GAC - V.211021) |  |  |  |  | Yes | Precast - Pre-pour Checklist (GAC - V.211021) | a906518b-1ad6-4e57-b61b-08216f382aef
checkpoint-status |  |  | checkpoint | Safety Induction/Documentation complete - Lend Lease Project Induction & relevant SWMS communicated
checkpoint-status |  |  | checkpoint | Latest IFC drawings checked & referenced
text | d16ae703-4b7e-5b02-b513-5b46ca165eec |  | textbox | Drawing & Revision # (or Attach photo below)
checkpoint-status |  |  | checkpoint | Panel # confirmed and referenced
text | 31e87c7b-1849-5da8-ba7a-c4834fe86c71 |  | textbox | Panel No.
checkpoint-status |  |  | checkpoint | Panel faces all lined up flush
checkpoint-status |  |  | checkpoint | Panel in the correct position
checkpoint-status |  |  | checkpoint | All ferrules installed for the new panels
checkpoint-status |  |  | checkpoint | All grout tubes and new bars installed
label | f2e96abe-e38d-5f1d-9a3f-1e007ec5f9af |  | note | All PT pockets 600mm away from precast & ferrules
checkpoint-status |  |  | checkpoint | Was the panel damaged in transport
label | 332924ec-2488-5001-b04f-d29fb65301f9 |  | note | Attach photos below
checkpoint-status |  |  | checkpoint | Are there any concerns regarding this panel moving forward - Comment/photo below
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
label | 95ab3a12-fee6-5ce8-8b45-0993c6ec6a86 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 9c2a8e4c-e0ce-594a-a420-24c2435f6704 |  | note | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | aa39ee68-e524-58f4-9090-6be2a3e99e8c |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | 1b5bf548-6b2e-5250-9ec0-a52c9ddc2229 |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Removal or Precast panel Props Checklist (GAC - V.211021) |  |  |  |  | Yes | Removal or Precast panel Props Checklist (GAC - V.211021) | bee8dd96-7579-486e-a549-139ef16ffa69
checkpoint-status |  |  | checkpoint | Safety Induction/Documentation complete - Lend Lease Project Induction & relevant SWMS communicated
checkpoint-status |  |  | checkpoint | Latest IFC drawings checked & referenced
text | 28c5d8c0-d380-53dd-9113-dbf1d7da2d33 |  | textbox | Drawing & Revision # (or Attach photo below)
text | bcd02ac7-0f81-5d79-b471-c8a7254bbd90 |  | textbox | Date poured
checkpoint-status |  |  | checkpoint | SWMS considers credible hazards for task in accordance with Risk Register
checkpoint-status |  |  | checkpoint | Concrete to connecting panel has been completed
checkpoint-status |  |  | checkpoint | Connecting concrete slabs to be fully stressed prior
checkpoint-status |  |  | checkpoint | Vertical dowel bars have been fully grouted and cured
checkpoint-status |  |  | checkpoint | Temporary formwork structure is completed as per engineers design
checkpoint-status |  |  | checkpoint | Grouting of sleeves if applicable completed minimum 7 days prior
label | 947d763c-0fa4-5422-80a3-aba3a699b449 |  | note | Attach documentation below
checkpoint-status |  |  | checkpoint | All stitch plates if applicable have been fully welded and inspected
label | 5df12f25-d071-5bd5-abe4-6e611c152d2d |  | note | Attach documentation below
checkpoint-status |  |  | checkpoint | Engineers sign-off for removal of precast panel prop
label | 6f519023-ad98-5caf-8f52-1c33941b3ca4 |  | note | Attach documentation below
checkpoint-status |  |  | checkpoint | Are any permits required by Lend Lease for the task
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
label | 4b0558f4-da1a-54cc-bb0a-119620166a4e |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | c4bd768f-fb81-5440-943b-1d7a4724c261 |  | note | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | d752ec8c-4ac7-5454-85fb-848e8b481676 |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | b5077a68-ac37-5abf-ac1a-803cbc547bf4 |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | False Formwork Handover Checklist (GAC - V.211021) |  |  |  |  | Yes | False Formwork Handover Checklist (GAC - V.211021) | caf0e98a-8fc0-43eb-bcbc-c9111229dd39
checkpoint-status |  |  | checkpoint | Safety Induction/Documentation complete - Lend Lease Project Induction & relevant SWMS communicated
checkpoint-status |  |  | checkpoint | Latest IFC drawings checked & referenced
text | ba4c7b85-7df6-5f55-991e-f4e56390b72c |  | textbox | Drawing & Revision # (or Attach photo below)
checkpoint-status |  |  | checkpoint | All penetrations are covered and secured
checkpoint-status |  |  | checkpoint | Handrail system is installed correctly
checkpoint-status |  |  | checkpoint | All Symal waste has been disposed in bins
checkpoint-status |  |  | checkpoint | Independent sign off conducted by competent person
checkpoint-status |  |  | checkpoint | Temporary formwork structure is completed as per engineers design
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
label | 0a2c54aa-d0f7-567e-856e-12464f668611 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | b873b4ef-c1b0-5f74-9d03-85695de65e52 |  | note | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | d329e38b-725e-5e80-a12e-d1f0d9c5cf19 |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | abafc4cd-415d-53ae-982f-b485abc69851 |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-sectioned |  |  | checklist | ITP-004 - Columns Pre-pour (GAC - V.211021) |  |  |  |  | Yes | ITP-004 - Columns Pre-pour (GAC - V.211021) | dff9fabc-a8c0-4f12-a89a-bc2e9beddb38
checkpoint-group |  |  | section | Setout
checkpoint-status |  |  | checkpoint | Safety Induction/Documentation complete - Lend Lease Project Induction & relevant SWMS communicated
checkpoint-status |  |  | checkpoint | Latest IFC drawings checked & referenced
text | 47f614c4-21a4-538c-8729-c7dade8f95c0 |  | textbox | Drawing & Revision # (or Attach photo below)
text | 186064e3-9468-5abf-956a-e541fceff911 |  | textbox | Concrete Strength (mPa)
checkpoint-status |  |  | checkpoint | Tolerance - Specification and Australian Standards
checkpoint-status |  |  | checkpoint | Set-out of all columns. Refer to Architectural drawings
checkpoint-status |  |  | checkpoint | RLs checked & Correct
text | 57662863-4eeb-59ce-9f18-85d8ee361a72 |  | textbox | RL. (Top of pour)
label | 682dace4-845e-5650-afc4-88e3418527e2 |  | note | RL varies accordingly in sections of works. Refer to Architectural Drawings
checkpoint-status |  |  | checkpoint | Approval of QA for footings/slab below
checkpoint-status |  |  | checkpoint | Compliance with Slab on Ground and Suspended Slabs
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | All in-situ column services have been installed and in correct location
checkpoint-status |  |  | checkpoint | Where column has been stick built, ensure Formwork Engineer has inspected and signed off column prior to any placement of concrete
checkpoint-status |  |  | checkpoint | Ensure formwork at stop ends has suitable 'stripping oil' applied prior to standing up column box/ply
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | All reinforcement to be placed in accordance with the IFC structural drawings and AS 1302
checkpoint-status |  |  | checkpoint | Reinforcement securely fixed in place
checkpoint-status |  |  | checkpoint | Where reinforcement has been tack welded (yet approved by Lend Lease), it must conform to AS 1554.3:2002
checkpoint-status |  |  | checkpoint | Reinforcement securely fixed in place
checkpoint-status |  |  | checkpoint | Bar spacing correct
checkpoint-status |  |  | checkpoint | Correct bar diameter
checkpoint-status |  |  | checkpoint | Correct splice lengths
checkpoint-status |  |  | checkpoint | Correct concrete cover
checkpoint-group |  |  | section | Pre-Pour
checkpoint-status |  |  | checkpoint | Pour area cleaned before pour - to ensure free of standing Water, debris, oils, objectionable coatings & fragments. (Refer specification)
checkpoint-status |  |  | checkpoint | Concrete strength for Columns are in accordance with structural drawings
checkpoint-status |  |  | checkpoint | Reinforcement fixed in place
checkpoint-status |  |  | checkpoint | Prepour outstanding items list signed off and completed
checkpoint-status |  |  | checkpoint | Ensure temperatures when pouring are within acceptable criteria (between 5ºC and 35ºC)
checkpoint-status |  |  | checkpoint | Tester ordered: 0 - 50m3 - 1 batch of tests or there off. 50-100m3 - 2 batch of tests or there off
checkpoint-status |  |  | checkpoint | Placement method confirmed
select | d38381f8-ab84-5d8f-94fd-9988402277eb |  | dropdown | Method | Chute, Kibble, Pump
checkpoint-status |  |  | checkpoint | Concrete vibration to be completed with use of vibrator motor (minimum requirement of 300rpm)
checkpoint-status |  |  | checkpoint | Tester Required for Structural Elements as noted in AS 1012
checkpoint-status |  |  | checkpoint | Approval to Pour - Pass once below completed
button | 7ad31d17-8bb7-5907-95d5-b763e2756d59 |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | 2e1b62dd-651a-586c-93de-186854fdace4 |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checkpoint-group |  |  | section | Placement
checkpoint-status |  |  | checkpoint | All concrete work shall be carried out in accordance with the AS 3600
checkpoint-status |  |  | checkpoint | A minimum of one vibrator must be used at all times while concrete is in operation
label | e7348d13-7e9a-558b-a2c1-69da2616c8e3 |  | note | These vibrators are to be no less than 5 metres long to ensure full compaction is reached
checkpoint-status |  |  | checkpoint | Competent concreters will be used to vibrate the concrete using the immersion vibrators, ensuring full compaction is achieved
checkpoint-status |  |  | checkpoint | Concrete is to be finished to correct RL
checkpoint-status |  |  | checkpoint | Ensure class finish has been complete as per relevant project specifications
label | 75ab6e62-de6a-5c8d-9291-07fa32cfd00b |  | note | (Refer Scope Specification - Concrete Finish) and in reference with AS3600 and AS3610)
checkpoint-status |  |  | checkpoint | Concrete Work(s) completed to specification/drawings & Area left clean/tidy
label | e293f89b-e316-5b63-b59a-6c39c599a9c1 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 047502e6-1500-5d93-ac80-18c6479645d5 |  | note | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 2c60bb73-207f-5730-b423-c3a8f40ccc1d |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | 14eb1514-52f5-5ed8-a76c-217084211d9b |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off
checklist-flat |  |  | checklist | Precast - Install Checklist (GAC - V.101221) |  |  |  |  | Yes | Precast - Install Checklist (GAC - V.101221) | e9299f38-09c8-453d-b548-f42304e927fb
checkpoint-status |  |  | checkpoint | Setting out is done as per Precast marking plan
checkpoint-status |  |  | checkpoint | Dry mix Grout/ Mortar has been placed bottom of the panel along the perimeter as per specifications
checkpoint-status |  |  | checkpoint | Liquid Grout Poured into Grout tubes under the slab
checkpoint-status |  |  | checkpoint | Liquid Grout Poured into Grout tubes in the panel. For sleeve connections , specified grouts should be used and appropriate pump should be used
checkpoint-status |  |  | checkpoint | Bracing has been done as per design
checkpoint-status |  |  | checkpoint | Final alignment has been checked for acceptance
checkpoint-status |  |  | checkpoint | Anchors properly tighten on the floor and on panel. Torque register updated
checkpoint-status |  |  | checkpoint | Approval - Pass once below completed
button | 197c3ceb-2317-56af-9965-4abe21fff570 |  | button | HOLD POINT - Signature by Builders Site Coordinator | Yes, No
button | 99d60f9c-dc63-5ba4-b109-e2acaadde44b |  | button | Symal Structures Signature Sign-Off added below | Yes, No
holdpoint |  |  | signoff | Request Builder Sign-Off