## COMBINED_ITPs
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-ITP-001 - Subgrade (Rev A) | [5 empty] | SYM-ITP-001 - Subgrade (Rev A)
section | 1.0 Preliminaries
checkpoint | 1.1 - Determine lot size
label | Ref docs: Lot map
label | Acceptance criteria:
textbox | • What is the lot size? |  |  | m2
label | • Maximum lot size = 1 days production or 4000m2
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Lot map
holdpoint | WITNESS POINT
checkpoint | 1.2 - Survey set-out
label | Ref docs: VR Clause 204.03 (a)
label | Acceptance criteria:
button | • Has the work area been set out for line and level? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
holdpoint | HOLD POINT
checkpoint | 1.3 - Excavation material classification
label | Ref docs:
label | • VR Clause
label | • 204.06 (c)
label | • 204.04 (b)
label | Acceptance criteria:
button | • Has the material being excavated been inspected with category agreed upon by Superintendent? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Imported material test report
label | • CYP Material Approval
holdpoint | HOLD POINT
checkpoint | 1.4 - Fill material classification
label | Ref docs:
label | • VR Clause 204.06 (c)
label | • 204.04 (b)
label | • IFC Drawings
label | Acceptance criteria:
button | • Has the material to be used been approved by CYP D&C JV? | Yes,No,N/A
label | Freq: Per material
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Imported material test report
label | • CYP Material Approval
holdpoint | HOLD POINT
checkpoint | 1.5 - Water management
label | Ref docs: VR Clause 204.06 (b)
label | Acceptance criteria:
button | • Where necessary, have batters been rounded and catch drains constructed to allow for potential surface runoff during the course of excavation? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: PE
checkpoint | 1.6 - Stage/ Zone
label | Ref docs: Site Layout
label | Acceptance criteria:
label | • 1A / 1B/ 1C/ 1D / 1E / 1F / 1G / 2A / 2B / 2C / 2D / 2E / 2F / 2G / 3A / 3B / 3C / 4A / 4B / 4C / 5A / 5B / 5D / 6A / 6B
textbox | Stage
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Lot map
checkpoint-no-status | Is the area in cut / fill / both?
label | If in cut proceed to step 2.0 and strike out section 3.0.
label | If in fill please strike out section 2.0 and proceed to section 3.0
label | If in both proceed to step 2.0 as well as section 3.0
section | 2.0 Bulk earthworks - cut
checkpoint | 2.1 - Subgrade preparation
label | Ref docs: VR Clause 204.06
label | Acceptance criteria:
button | • Has the cut surface been trimmed to an even surface free from lose material? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Site photos
holdpoint | WITNESS POINT
checkpoint | 2.2 - Groundwater/ seepage (if applicable)
label | Ref docs: VR Clause 204.06 (h)
label | Acceptance criteria:
label | • If groundwater or seepage is encountered, notify the Superintendent and create a course of proposed action.
label | • Submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
button | • Approval to proceed? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Dewatering permit (if applicable)
holdpoint | WITNESS POINT
checkpoint | 2.3 - Treatment of Cut
label | Ref docs:
label | • VR Clause
label | • 204.06 (e)(ii)
label | • 204.10 (b)
label | • 204.12
label | Acceptance criteria:
label | • The in-situ material shall be ripped to a minimum depth of 150 mm, loosened and broken down to a maximum particle size of 50 mm. Any rocks or boulders larger than 50 mm shall be removed and any resulting depression shall be backfilled with approved material and such backfilling together with the loosened material shall be reworked and compacted as specified to the Cut Floor Level in preparation for test rolling.
button | • Has all of the above been completed? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
holdpoint | WITNESS POINT
checkpoint | 2.4 - Compaction
label | Ref docs:
label | • VR Clause
label | • 204.13
label | • 204.13 (b)
label | • 204.15
label | • 173.04
label | Acceptance criteria:
label | • Compaction Scale B, CBR and Swell Testing per lot (3 tests per lot).
button | • Has the subgrade been adequately compacted achieving a mean value density ratio of 98% Standard? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Test reports
holdpoint | HOLD POINT
checkpoint | 2.5 - Test Rolling of prepared subgrade
label | Ref docs: VR Clause 173.03
label | Acceptance criteria:
button | • Does the layer withstand test rolling without visible deformation or springing? | Yes,No,N/A
label | • If ‘no’ please see below.
label | • If ‘yes’ please proceed
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Proof roll report
holdpoint | HOLD POINT
checkpoint | 2.6 - Identification of soft wet or unstable material
label | Ref docs: VR Clause 204.07
label | Acceptance criteria:
textbox | • What quantity of soft, wet or unstable material is present? |  |  | m3
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Survey report of area
checkpoint | 2.7 - Treatment of unsuitable material
label | Ref docs: VR Clause 204.07(d)
label | Acceptance criteria:
button | • Has rectification process been submitted to the Superintendent for review? | Yes,No,N/A
textbox | • What was the rectification process used?
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Rectification process
holdpoint | HOLD POINT
checkpoint | 2.8 - Maintenance of Cut Floor Level
label | Ref docs:
label | • VR Clause
label | • 204.15
label | • 204.03
label | Acceptance criteria:
label | • Visual inspection to confirm that surface is a smooth, hard, tightly bound surface, free from depressions capable of holding water.
label | • Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of optimum moisture content prior to the placement of any pavement layer.
button | • Has all of the above been completed? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Site photos
holdpoint | WITNESS POINT
section | 3.0 Bulk earthworks - fill
checkpoint | 3.1 - Stripped surface - test rolling (If applicable)
label | Ref docs:
label | • VR Clause
label | • 173.03
label | • 204.10
label | Acceptance criteria:
button | • Does the stripped surface to be filled withstand test rolling without visible deformation or springing? | Yes,No,N/A
label | • If ‘no’ please see below.
label | • If ‘yes’ please proceed to item 3.2
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Material report
label | • Proof roll report
holdpoint | HOLD POINT
checkpoint | 3.2 - Identification of soft wet or unstable material
label | Ref docs: VR Clause 204.07
label | Acceptance criteria:
textbox | • What quantity of soft, wet or unstable material is present? |  |  | m3
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Survey report of area
checkpoint | 3.3 - Treatment of unsuitable material
label | Ref docs: VR Clause 204.07(d)
label | Acceptance criteria:
button | • Has rectification process been submitted to the Superintendent for review? | Yes,No,N/A
textbox | • What was the rectification process used?
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Rectification process
holdpoint | HOLD POINT
checkpoint | 3.4 - Preparation of surface
label | Ref docs: VR Clause 204.13(B)
label | Acceptance criteria:
button | • Has adequate water been added to the stripped surface to ensure adhesion to the next layer? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
checkpoint | 3.5 - Fill Placement
label | Ref docs: VR Clause 204.10
label | Acceptance criteria:
button | • Has fill been placed in maximum 200mm compacted layer thickness? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • As built report
checkpoint | 3.6 - Moisture
label | Ref docs: VR Clause 204.13(B)
label | Acceptance criteria:
button | • Has the material maintained at optimum moisture content (>80%), with additional water being added if required during compaction? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Test reports
holdpoint | WITNESS POINT
checkpoint | 3.7 - Compaction
label | Ref docs: VR Clause 204.13
label | Acceptance criteria:
label | • Compaction Scale B (6 tests per lot)
button | • Has the layer been adequately compacted achieving a mean value density ratio of 98% Standard? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Test reports
holdpoint | WITNESS POINT
checkpoint | 3.8 - Material properties testing
label | Ref docs:
label | • VR Clause
label | • 204.04
label | • Table 204.041
label | • 204.14
label | Acceptance criteria:
label | • Has the material properties testing (CBR / Swell / Grading / PI / LL / Permeability) been undertaken for the first lot of material placement and satisfies the VicRoads requirements as per Table 204.041?
button | • If the first lot of each fill satisfies the specified post compaction requirements, every second lot of like material and work will be tested | Yes,No,N/A
label | Freq: Per material
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Test reports
holdpoint | HOLD POINT
checkpoint | 3.9 - Fill layer – test rolling
label | Ref docs:
label | • VR Clause
label | • 173.03
label | • 204.10
label | Acceptance criteria:
button | • Does the layer withstand test rolling without visible deformation or springing? | Yes,No,N/A
label | • If ‘no’ please see below
label | • If ‘yes’ please proceed to fill construction
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Proof roll report
holdpoint | HOLD POINT
checkpoint | 3.10 - Identification of soft wet or unstable material
label | Ref docs: VR Clause 204.07
label | Acceptance criteria:
textbox | • What quantity of soft, wet or unstable material is present? |  |  | m3
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Survey report of area
checkpoint | 3.11 - Treatment of unsuitable material
label | Ref docs: VR Clause 204.07(d)
label | Acceptance criteria:
button | • Has rectification process been submitted to the Superintendent for review? | Yes,No,N/A
textbox | • What was the rectification process used?
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Rectification process
holdpoint | HOLD POINT
section | 4.0 Conformance check
checkpoint | 4.1 - Width and alignment
label | Ref docs:
label | • VR Clause
label | • 204.03
label | • IFC drawings
label | Acceptance criteria:
button | • Has the pavement been constructed at the correct width and alignment as detailed in the construction drawings? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • As built report
holdpoint | WITNESS POINT
checkpoint | 4.2 - Subgrade level and shape
label | Ref docs:
label | • VR Clause
label | • 204.03
label | • IFC drawings
label | Acceptance criteria:
label | • Has the prepared subgrade been surveyed in accordance with and verifying specified requirements?
button | • Mean Range: +5mm to -25mm Standard Deviation: Maximum 15mm | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • As built report
holdpoint | WITNESS POINT
checkpoint | 4.3 - Test Reports
label | Ref docs: VR Clause 204.14
label | Acceptance criteria:
button | • All Test reports received and reviewed. | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • NATA Endorsed Test Reports
holdpoint | WITNESS POINT
checkpoint | 4.4 - Product non-conformance
label | Acceptance criteria:
button | • All Product Non-Conformance(s) recorded and closed (if applicable) | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Completed NCR form
holdpoint | WITNESS POINT
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot
checklist | SYM-ITP-002 - Flexible Pavements (Rev A) | [5 empty] | SYM-ITP-002 - Flexible Pavements (Rev A)
section | 1.0 Preliminaries
checkpoint | 1.1 - Survey Set-out
label | Ref docs: IFC Drawings
label | Acceptance criteria:
button | • Has the work area been set out for line and level? | Yes,No,N/A
label | Freq: Prior to start of Works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
holdpoint | HOLD POINT
checkpoint | 1.2 - Conformance of Previous layer
label | Ref docs: VR Clause 304.04
label | Acceptance criteria:
label | • Has the previous layer passed acceptance criteria?
button | • Approval to proceed? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Survey Conformance Certificate
label | • ITP & Test Reports
holdpoint | HOLD POINT
checkpoint | 1.3 - Material classification and source
label | Ref docs:
label | • VR Clause 304.03
label | • 811
label | • 812
label | • IFC Drawings
label | Acceptance criteria:
button | • Is the correct material being used? | Class 2,Class 3,CTCR
button | • Has the material to be used been approved for use (Material certificates to be provided)? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • CYP D&C JV Materials Approval
holdpoint | HOLD POINT
checkpoint | 1.4 - Determine lot size
label | Ref docs: VR Clause 304.111
label | Acceptance criteria:
textbox | • What is the lot size? |  |  | m2
label | • Maximum lot size = 1 days production or 4000m2
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Lot map
holdpoint | HOLD POINT
section | 2.0 Pavement Construction
checkpoint | 2.1 - Layer classification
label | Ref docs:
label | • VR Clause 304
label | • IFC Drawings
label | Acceptance criteria:
button | • Is the pavement intended to be Lower Subbase or Upper Subbase? | Lower subbase,Subbase,Base
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
checkpoint | 2.2 - Construction - Jointing
label | Ref docs: VR Clause 304.07
label | Acceptance criteria:
label | • Transverse - Offset by not less than 2 m to any underlying pavement layers.
label | • Longitudinal - Offset by not less than 150 mm to any underlying pavement layers. Located within 300 mm of the traffic lane lines or within 300 mm of the centre of a traffic lane.
button | • Has all of the above been completed correctly and to a high standard? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Construction photos
holdpoint | WITNESS POINT
checkpoint | 2.3 - Placement of Material
label | Ref docs:
label | • VR Clause 304.06
label | • IFC Drawings
label | Acceptance criteria:
label | • Place and compact layers so that the surface finish is smooth and uniform.
label | • The width of each side of the pavement shall not be less than the specified offset width or more than 50 mm outside the specified offset width when measured at right angles from the centre line or design line.
label | • No point > 8 mm below a 3 m straight edge in any direction
label | • No point >10 mm below a 6 m straight edge in any direction
button | • Has all of the above been completed correctly, to a high standard and approved? | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: I
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Construction photos
checkpoint | 2.4 - Moisture
label | Ref docs: VR Clause 304.08(a)
label | Acceptance criteria:
button | • Has the material maintained at optimum moisture content (>85%), with additional water being added if required during compaction? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: I
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Test report
checkpoint | 2.5 - Testing – Stability (Proof Roll)
label | Ref docs: VR Clause 304.08(b)
label | Acceptance criteria:
label | • Area shall withstand test rolling without visible deformation or springing.
button | • Has all of the above been completed correctly, to a high standard and approved by relevant authority? | Yes,No,N/A
label | • If ‘no’ please see below
label | • If ‘yes’ please proceed to 2.7
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Proof roll report
holdpoint | HOLD POINT
checkpoint | 2.6 - Identification of soft wet or unstable material
label | Ref docs: VR Clause 304.08
label | Acceptance criteria:
textbox | • What quantity of soft, wet or unstable material is present? (m2) | m2
textbox | • What quantity of soft, wet or unstable material is present? (m3) | m3
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Survey report
checkpoint | 2.7 - Treatment of unsuitable material (Testing of material to be agreed on site)
label | Ref docs: VR Clause 304.08
label | Acceptance criteria:
button | • Has rectification process been submitted to VicRoads for Review? | Yes,No,N/A
textbox | • What was the rectification process used?
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Proof roll report
holdpoint | HOLD POINT
checkpoint | 2.8 - Protection of compacted layer
label | Ref docs: VR Clause 304.09
label | Acceptance criteria:
label | • Surface of each compacted layer in good order/condition & free from contamination until the subsequent pavement work is to commence.
button | • Has all of the above been completed? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: I
label | Symal Infrastructure - Resp: SE
section | 3.0 Testing
checkpoint | 3.1 - Testing – Compaction
label | Ref docs:
label | • VR Clause 304.08(b)
label | • 304.10
label | • 304.11
label | • Table 304.111
label | Acceptance criteria:
label | • Characteristic Density Ratio % (six tests per lot): Not less than 98.0% Modified (Scale A)
label | • Characteristic Density Ratio % (six tests per lot): Not less than 97.0% Modified (Scale B)
label | • For layer directly beneath bituminous surface, not less than 100.0 for scale A and 98.0 for scale B
button | • Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No,N/A
label | Freq: As required by section 3.2
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: R
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • NATA Test Report
checkpoint | 3.2 - Testing – Reduced Frequency
label | Ref docs:
label | • VR Clause 304.11
label | • Table 304.111
label | Acceptance criteria:
label | • Test every lot for acceptance until three consecutive lot of like material and/or work have passed the requirements.
label | • For Subbase, one Characteristic Density Ration % (six tests) will be completed for every second lot.
label | • Testing will be completed at the minimum frequency until such time as a lot fails to achieve the specified requirements. After a failed result, all subsequent lots will be tested until three consecutive lots of like material and work have achieved the specified standard, at which time the frequency of testing may revert to the minimum frequency
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: R
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
textbox | • If using reduced frequency, provide lot number of previous lot tested:
section | 4.0 Completion
checkpoint | 4.1 - Survey as built
label | Ref docs:
label | • VR Clause 304.06
label | • Table 304.061
label | • Table 304.062
label | Acceptance criteria:
label | • Surface after completion shall be smooth and uniform, free of segmented areas and conforming to grade, thickness and cross-section shown on the drawings.
label | • Surface level checked for compliance with 304.06:
label | ○ Mean +6 mm to -10 mm with a max std deviation of 10 mm (Scale A)
label | ○ Min 80 measurements per lot (Scale A)
label | ○ Mean +8 mm to -16 mm with a max std deviation of 15 mm (Scale B)
label | ○ Min 40 measurements per lot (Scale B)
button | • Has all of the above been proven to meet and/or exceed requirements set out in contract? | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Survey Conformance Certificate
section | 5.0 Work Lot Close Out
checkpoint | 5.1 - Test Reports
label | Ref docs: VR Clause 304
label | Acceptance criteria:
label | • All Test reports received and Reviewed as per Requirements for Testing and Acceptance of Surface Level Measurement, Compaction and Post-compaction Gradings and PIs (Clauses 304.06, 304.08, 304.10 and 304.11)
button | • Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • NATA Endorsed Test Reports | Yes,No,N/A
checkpoint | 5.2 - Product Non-Conformance
label | Ref docs: CMP
label | Acceptance criteria:
label | • All Product Non-Conformance(s) recorded and closed (if applicable)
button | • Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • NCR reports | Yes,No,N/A
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot
checklist | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | [5 empty] | SYM-ITP-003 - Asphalt Placement 1 (Rev A)
section | 1.0 Pre-start activities
checkpoint | 1.1 - Determine lot size
label | Acceptance criteria:
textbox | • What is the lot size? |  |  | m2
label | • Maximum Lot Size = per days production
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Lot map
checkpoint | 1.2 - Asphalt Mix Designs Approval and Compliance
label | Ref docs: VR Clause 407.05 to 407.10
label | Acceptance criteria:
button | • Is the asphalt mix design considered “General” and does it conform with VicRoads Section 407? Has mix design been approved by CYP D&C JV? | Yes,No,N/A
label | Freq: Each possession
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Mix Design Approval
textbox | • Aconex Reference No
holdpoint | HOLD POINT
checkpoint | 1.3 - Conformance of previous layer
label | Acceptance criteria:
button | • Has the previous layer passed acceptance criteria? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
textbox | • Lot reference no:
holdpoint | HOLD POINT
checkpoint | 1.4 - Temperature conditions
label | Ref docs: VR Clause 407.13
label | Acceptance criteria:
button | • For intermediate and base courses surface to be above 5 degrees Celsius. For wearing course installation, surface to be greater then 10 degrees Celsius. Has the above criteria been met? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
holdpoint | HOLD POINT
checkpoint | 1.5 - Existing pit levels
label | Ref docs: VR Clause 407.14
label | Acceptance criteria:
button | • Have the existing pits been raised/lowered to meet the surface level of Asphalt? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
holdpoint | HOLD POINT
section | 2.0 Hot Mix Asphalt Installation
checkpoint | 2.1 - Commencement of Placing
label | Ref docs: VR Clause 407.18
label | Acceptance criteria:
label | • The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until approval to proceed is obtained from CYP D&C JV.
button | • Approval to proceed? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
holdpoint | HOLD POINT
checkpoint | 2.2 - Construction - Jointing
label | Ref docs: VR Clause 407.17
label | Acceptance criteria:
label | • All transverse joints shall be offset from layer to layer by at least 2 m.
label | • Longitudinal joints in the wearing course shall coincide with the location of intended traffic lane lines.
label | • Longitudinal joints in intermediate and base courses shall be offset from layer to layer by not less than 150 mm and shall be within 300 mm of the traffic lane line or the centre of traffic lane.
label | • Where new pavement abuts an existing full depth asphalt pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150 mm.
button | • Has all of the above been completed? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: I
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: I
checkpoint | 2.3 - Matching Existing Pavement Surface at Junctions
label | Ref docs: VR Clause 407.17 (d)
label | Acceptance criteria:
label | • At junctions where the new asphalt mat is required to match the level of existing pavement surface at the limits of work, chases shall be cut into the existing pavement by cold planing as specified in Section 402.
button | • Does new Asphalt Layer match the existing pavement surface with chases cut? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: I
label | Symal Infrastructure - Resp: SE
checkpoint | 2.4 - Paving and Compaction of Asphalt
label | Ref docs:
label | • VR Clause 407.20
label | • IFC Drawings
label | Acceptance criteria:
label | • Asphalt shall be spread in layers at the compacted thicknesses shown on the drawings or specified.
label | • Asphalt shall be uniformly compacted Compaction shall not commence until the asphalt has cooled sufficiently to support the rollers without undue displacement.
button | • Has all of the above been completed? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: I
label | Symal Infrastructure - Resp: SE
section | 3.0 Completion and Compliance
checkpoint | 3.1 - Compaction Testing – Six Tests
label | Ref docs: VR Clause Table 407.221
label | Acceptance criteria:
label | • Thickness < 50 mm: 94.0% Characteristic Density Ratio
label | • Thickness > 50mm: 96.0% Characteristic Density Ratio
button | • Has testing been completed and report received? Do results match requirements? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • NATA Test Report: Compaction Tests
checkpoint | 3.2 - Finished Surface Levels
label | Ref docs:
label | • VR Clause 407.23
label | • Table 407.231
label | • Table 407.232
label | Acceptance criteria:
label | • The mean surface level and the variation in surface level for the base, intermediate and wearing courses within each lot shall meet the requirements (mean +/- 5mm, standard deviation 8mm)
label | • Rectification of surface levels shall not commence until approval to proceed is obtained from the Superintendent.
button | • Is finished surface level acceptable and survey conformance report received? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Conformance Report (Finished surface level and thickness)
holdpoint | HOLD POINT
checkpoint | 3.3 - Finish Surface/Shape
label | Ref docs:
label | • VR Clause 407.23 (a)
label | • IFC Drawings
label | Acceptance criteria:
label | • Surface finish - Uniform in appearance, free of dragged areas, cracks, open textured patches, and roller marks.
label | • Kerb & Channel - Flush or not more than 5mm above lip of channel
label | • Shape – For intermediate and base course layers, the distance below the straight edge shall not exceed 6 mm and 10 mm, respectively.
label | • Alignment - Where asphalt pavement is not placed against a concrete edging, the edge of asphalt layers shall not be more than 50 mm inside nor more than 100 mm outside.
label | • Width - Where asphalt pavement is not placed against a concrete edging, the width of asphalt layers shall not be less than the design or specified width of layer by more than 50 mm or greater than the design or specified width by more than 100 mm.
button | • Have the above requirements been met and surface is acceptable? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Site photos
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot
checklist | SYM-ITP-004 - Underscreed Concrete Pavement (Rev A) | [5 empty] | SYM-ITP-004 - Underscreed Concrete Pavement (Rev A)
section | 1.0 Preliminaries
checkpoint | 1.1 - Concrete mix design approval
label | Ref docs:
label | • VR703.01
label | • VR703.05
label | • AS 1379
label | Acceptance criteria:
button | • Concrete mix design approved by the Superintendent and a registered mix and Material properties meet project specifications | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | CYP D&C JV - Key: H
holdpoint | HOLD POINT
checkpoint | 1.2 - Concrete Grade
label | Ref docs: Project Specs
label | Acceptance criteria:
textbox | • Concrete Strength |  |  | MPA
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | CYP D&C JV - Key: H
holdpoint | HOLD POINT
checkpoint | 1.3 - Conformity with Drawings
label | Ref docs: VR Clause 701.10
label | Acceptance criteria:
button | • Are the drawings, complete & current? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach Recent IFC Drawings
holdpoint | HOLD POINT
checkpoint | 1.4 - Setting Out
label | Ref docs:
label | • VR703.17
label | • VR703.15
label | Acceptance criteria:
button | • Is the work area clearly pegged out for line and level? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SS
label | CYP D&C JV - Key: H
holdpoint | HOLD POINT
checkpoint | 1.5 - Bedding Preparation
label | Ref docs:
label | • VR703.20/703.21
label | • VR204.13
label | • VR304.08
label | Acceptance criteria:
label | • Is edging constructed over Pavement layer?
button | • Where edgings are constructed over pavement layers, bedding shall be provided between the pavement layer and the underside of the edging, or the edging thickened to match the pavement layer. | Yes,No,N/A
button | • Is bedding for footpaths and surfaces compacted to 100mm thickness unless noted otherwise. | Yes,No,N/A
button | • Is bedding for SUPs, bedding compacted to 150mm thick unless noted otherwise. | Yes,No,N/A
button | • Bedding shall be moist but shall have no free water on the surface before concrete is placed | Yes,No,N/A
button | • Is bedding material used for cast in place concrete paving works compacted size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively. | Yes,No,N/A
button | • Is bedding material for shared use paths compacted size 20 mm Class 3 crushed rock or Class 3 crushed concrete in accordance with Section 812 or 820 respectively, and Section 304. | Yes,No,N/A
button | • Are pavement lots tested for compliance with the specified compaction scale for moisture content no less than 85% | Yes,No,N/A
button | • Is fill material used below bedding tested to Table 204.131 Compaction Requirements | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 1.5 - Provision for Permanent Signs
label | Ref docs: VR703
label | Acceptance criteria:
button | • Have sign post sockets been supplied & placed for erection of permanent signs in the areas to be paved as per VR703.22. | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 1.6 - Relevant Permits Required
label | Acceptance criteria:
button | • Relevant permits have been signed and approved. | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
checkpoint | 1.7 - Excavation
label | Ref docs: IFC Drawings
label | Acceptance criteria:
textbox | • Excavation to a total depth of |  |  | mm
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
checkpoint | 1.8 - Sub-Base Course
label | Ref docs: IFC Drawings
label | Acceptance criteria:
textbox | • mm layer of __mm
textbox | • Class __ crushed rock or crushed concrete placed?
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
section | 2.0 Under screed/Concrete Pavement
checkpoint | 2.1 - Formwork
label | Ref docs: VR703.12
label | Acceptance criteria:
button | • Formwork has been installed correctly and sufficiently braced. | Yes,No,N/A
button | • Formwork set out has been done as per latest design drawings and specifications | Yes,No,N/A
button | • Were Construction joints/Expansion Joints/Isolation Joints /or any type of joint as specified in the drawings Installed | Yes,No,N/A
button | • Installations of Cast-Ins/ HD bolts/ Chemical Anchors/Block out Verified/Sockets | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
holdpoint | HOLD POINT
checkpoint | 2.2 - Steel Reinforcement
label | Ref docs:
label | • VR703.13
label | • AS/NZS 4671
label | • AS/ZNS 4680
label | • AS3600
label | • VR703.16
label | Acceptance criteria:
button | • Mesh installed with 40mm top and sides cover and 50 mm Bottom Cover | Yes,No,N/A
button | • Tolerance - As per specifications and Australian Standard | Yes,No,N/A
button | • Steel is free of excess corrosion, loose millings, oil or other contaminants | Yes,No,N/A
button | • Required Connection Details - U Bars/ Z Bars/Cogs/Starter bars Verified | Yes,No,N/A
button | • Correct concrete cover and chairs on sides, bottom and top Verified | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SS
checkpoint | 2.3 - Pre-Pour Inspection
label | Ref docs: IFC Drawings/QMP
label | Acceptance criteria:
button | • Has steel reinforcement been placed correctly with adequate cover? | Yes,No,N/A
button | • Have tie bars and joints been installed at the correct intervals? | Yes,No,N/A
button | • Pour area is free of loose debris, oils, water | Yes,No,N/A
button | • Have any services/penetrations/blockout located within the Pavements been installed, surveyed and pinned down | Yes,No,N/A
button | • Concrete Testing Lab Representative will be available during concrete pour | Yes,No,N/A
button | • Sufficient vibrators are available during concrete pour | Yes,No,N/A
button | • CYP D&C JV informed of concrete pour date and start time | Yes,No,N/A
label | Freq: Prior to start of Concrete Placement
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SS
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach subcontractor ITPs
holdpoint | HOLD POINT
checkpoint | 2.4 - Placing, compacting and finishing concrete
label | Ref docs:
label | • VR610.10/610.13
label | • VR610.18
label | • VR703.08
label | Acceptance criteria:
button | • Is concrete temperature as per VR703. and not mixed when the air temperature is lower than 5°C or greater than 35°C. | Yes,No,N/A
button | • Is discharge Time 60 minutes unless mix design is approved by Proof Engineer for 90 minutes. | Yes,No,N/A
button | • Is concrete thoroughly compacted and works carried out as per Australian Standard & Project Drawings/ Specifications | Yes,No,N/A
button | • Are concrete samples taken in accordance with 610.16(b). | Yes,No,N/A
button | • Is specified slump tolerance within 610.16(c). | Yes,No,N/A
button | • Is concrete mixed for not less than a period of three (3) minutes prior to discharge. | Yes,No,N/A
button | • Is the maximum time lag between truck loads on site shall not exceeding 25 minutes if a continuous pour | Yes,No,N/A
button | • A minimum of one of vibrator used at all times while the concreting is in operation | Yes,No,N/A
button | • Were forms/cast in items monitored during the pour. | Yes,No,N/A
button | • Concrete Dockets Received | Yes,No,N/A
textbox | • Concrete quantity |  |  | M3
textbox | • Pour date
button | • Concrete Fall achieved as per latest IFC drawings | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • Concrete pour record attached | Yes,No
button | • Concrete test results attached. | Yes,No
holdpoint | HOLD POINT
section | 3.0 Post Pour/ Finishing
checkpoint | 4.6 - Post Pour
label | Ref docs: VR703.25
label | Acceptance criteria:
button | • Did concrete achieve the required finish as per specifications | Yes,No,N/A
button | • Are hidden concrete surfaces of concrete paving have a Class 4 surface finish in accordance with AS 3610. | Yes,No,N/A
button | • Curing agent applies as per project specifications | Yes,No,N/A
button | • Concrete reached design strength to strip formwork. (Attach test results) | Yes,No,N/A
button | • Any identified defects after stripping rectified | Yes,No,N/A
button | • Were expansion joints placed at intervals less than 10m. | Yes,No,N/A
button | • As Built Survey completed and report attached. | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • Concrete test results attached. | Yes,No
checkpoint | 4.10 - Backfilling
label | Ref docs: VR703.29
label | Acceptance criteria:
button | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour? | Yes,No,N/A
button | • Were the positions of any existing conduits passing under edgings marked by a chase in the edging immediately above the conduit together with a suitable identification mark. | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE/PE
section | 5.0 Completion
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot
checklist | SYM-ITP-005 - Insitu Kerb and Channel (Rev A) | [5 empty] | SYM-ITP-005 - Insitu Kerb and Channel (Rev A)
section | 1.0 Pre-start activities
checkpoint | 1.1 - Determine lot size
label | Ref docs: Lot map
label | Acceptance criteria:
label | • One lot per days production. To be marked up on lot map.
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Lot map
holdpoint | WITNESS POINT
checkpoint | 1.2 - Concrete mix design approvals
label | Ref docs:
label | • VR Clause 703.05 (b)
label | • 703.11
label | Acceptance criteria:
label | • Concrete used in kerb extrusion machines shall have a minimum cementitious material content in the finished concrete as follows:
label | ○ A minimum of 320 kg of cementitious material for traffic routes
label | ○ A minimum of 280kg of cementitious material for local streets
button | • Concrete mix designs approved by CYP D&C JV? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Delivery Dockets: Concrete
label | • CYP Material Approval
holdpoint | HOLD POINT
checkpoint | 1.3 - Survey set out
label | Ref docs:
label | • VR Clause 703.17
label | • IFC Drawings
label | Acceptance criteria:
label | • All works shall be set out in accordance with the drawings and as specified.
label | • The Superintendent will review and confirm the set out. The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
holdpoint | HOLD POINT
section | 2.0 Construction
checkpoint | 2.1 - Machine extrusion
label | Ref docs: VR Clause 703.23
label | Acceptance criteria:
label | • Concrete shall be fed to the machine at a uniform rate. Surfaces shall be free from surface pitting larger than 5 mm diameter.
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Site photos
checkpoint | 2.2 - Profile transitions and matching existing sections
label | Ref docs:
label | • VR Clause 703.24
label | • SD2102
label | Acceptance criteria:
label | • Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre. Transitions between different profiles shall be made in accordance with the drawings.
button | • Are the profile transitions acceptable? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
checkpoint | 2.3 - Surface Finish
label | Ref docs: VR Clause 703.25
label | Acceptance criteria:
label | • All edgings shall be rendered and have a steel trowel finish. Visible concrete surfaces to have class 3 finish. Hidden surfaces may have a class 4 finish.
button | • Is the surface finish acceptable? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: I
label | Symal Infrastructure - Resp: SE
checkpoint | 2.4 - Joints
label | Ref docs: VR Clause 703.26
label | Acceptance criteria:
label | • Transverse joints shall be constructed at regular intervals not exceeding 2.5 m. The resultant slot in the edging shall be tooled to a depth of 20 mm to produce a neat groove not less than 5 mm wide on the exposed surfaces.
label | • Expansion joints shall be placed at junctions with bridges and shall be 15 mm wide and filled with cork or bituminous impregnated particle board strip extending for the full width and full depth of the edging.
button | • Are joints installed and comply with all specifications? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
checkpoint | 2.5 - Curing & Protection of Concrete
label | Ref docs:
label | • VR Clause 703.10
label | • 703.27
label | Acceptance criteria:
label | • Freshly finished exposed concrete surfaces shall be protected from rain or damage from other sources, until hard set has occurred.
label | • All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
button | • Are finished curbs protected and free from damage? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
checkpoint | 2.6 - Repair of damaged kerb and channel
label | Ref docs: VR Clause 703.30
label | Acceptance criteria:
label | • For damaged kerb and channel and edgings, a length of at least 1 m shall be removed and the replacement section shall be:
label | (a) constructed on compacted bedding;
label | (b) dowelled into the adjoining sections with 12 mm diameter hot dip galvanised dowels embedded at least 100 mm each side of the joint; and
label | (c) shaped and finished with curved trowels to match the profile and surface finish of adjoining sections
button | • Is all damage to curbs repaired in line with specifications? | Yes,No,N/A
label | Freq: Each lot (if required)
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: I
label | Symal Infrastructure - Resp: SE
section | 3.0 Completion
checkpoint | 3.1 - As Built Survey
label | Ref docs: VR Clause 703.15
label | Acceptance criteria:
label | • Concrete paving including footpaths, edgings, other surfaces and shared use paths shall be shaped to match existing fixtures, e.g. pit covers, edgings and vehicle crossings, within 5 mm.
label | • Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of 0 to +10 mm. Except on curves or in shaped areas, the deviation of the finished work from a 3 m straightedge shall not exceed 5 mm at any point.
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: R
checkpoint | 3.2 - Product Non-Conformance
label | Ref docs: QMP
label | Acceptance criteria:
label | • All Product Non-Conformance(s) recorded and closed (if applicable)
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
textbox | • NCR No:
label | • NCR reports
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot
checklist | SYM-ITP-006 - STORMWATER (Rev A) | [5 empty] | SYM-ITP-006 - STORMWATER (Rev A)
section | 1.0 Pre-start activities
checkpoint | 1.1 - Conformity with Drawings
label | Ref docs: VR Clause 701.10
label | Acceptance criteria:
button | • Are the drawings, complete & current? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | CYP D&C JV - Key: H
label | CYP D&C JV - Sign/Date: PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach Recent IFC Drawings
holdpoint | HOLD POINT
checkpoint | 1.2 - Define Work Lot
label | Ref docs:
label | • VR Clause 173.02
label | • 701.20
label | • 701.10
label | • IFC Drawings
label | Acceptance criteria:
label | • Lot shall be defined from pit to pit (or endwall, where applicable).
button | • Do survey boundaries clearly define the Underground Drainage Construction works? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | CYP D&C JV - Key: H
label | CYP D&C JV - Sign/Date: PE
holdpoint | HOLD POINT
checkpoint | 1.3 - Acceptance of Box Culverts
label | Ref docs:
label | • VR Clause 619.22
label | • IFC Drawings
label | Acceptance criteria:
button | • Is the Box Culvert free of defects and to drawing dimensions? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | CYP D&C JV - Key: H
label | CYP D&C JV - Sign/Date: PE
holdpoint | HOLD POINT
checkpoint | 1.4 - Acceptance of Precast Reinforced Concrete/HDPE Pipes
label | Ref docs:
label | • VR Clause 701.05
label | • 701.05(e)
label | • 701.31(a)
label | • IFC Drawing
label | Acceptance criteria:
button | • Is the Pipes free of defects and to drawing dimensions? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | CYP D&C JV - Key: H
label | CYP D&C JV - Sign/Date: PE
holdpoint | HOLD POINT
checkpoint | 1.5 - Acceptance of Precast Covers, Grates, Lids and Pits
label | Ref docs:
label | VR Clause 705.04
label | (a)(ii)
label | 705.04
label | (d)
label | 705.07
label | • IFC Drawings
label | Acceptance criteria:
button | • Have proposed precast Covers, Grates, Lids and Pits been approved for use? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | CYP D&C JV - Key: H
label | CYP D&C JV - Sign/Date: PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • Shop Cards | Yes,No
holdpoint | HOLD POINT
checkpoint | 1.6 - Bedding and Backfill Materials
label | Ref docs:
label | • VR Clause 701.09(e)
label | • Table 701.091
label | • Table 701.092
label | Acceptance criteria:
button | • Is material free from perishable matter and lumps? | Yes,No,N/A
button | • Does the material comply with Table 701.091 & Table 701.092 below? Has the material been approved for use? | Yes,No,N/A
label | --------------------------------------------------------------------------------------------------------------
label | Table 701.091
label | Material ¦¦ Sieve - AS (mm) 75.0, 37.5, 19.0, 2.36, 0.075 :: Percentage Passing (by mass)
label | --------------------------------------------------------------------------------------------------------------
label | Bedding ¦¦ 19.0 :: 100 / 0.075 :: 5-40
label | Selected Backfill ¦¦ 37.5 :: 100 / 0.075 :: 5-40
label | Ordinary Backfill ¦¦ 75.0 :: 100 / 2.36 :: 40-100
label | --------------------------------------------------------------------------------------------------------------
label | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
label | --------------------------------------------------------------------------------------------------------------
label | Table 701.092
label | Test ¦¦ Test Value
label | --------------------------------------------------------------------------------------------------------------
label | Plasticity Index (Max.) ¦¦ 20
label | --------------------------------------------------------------------------------------------------------------
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
label | CYP D&C JV - Key: H
label | CYP D&C JV - Sign/Date: PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • Bedding and Backfill Material Conformance | Yes,No
holdpoint | HOLD POINT
checkpoint | 1.7 - Pipe/Box Culver/PIT Size & Class
label | Acceptance criteria:
textbox | • SIZE
textbox | • CLASS
textbox | • DIA = 150 / 225 / 300 / 375 / 450 / 525 / 1050
textbox | • PIT REF
textbox | • PIT REF
textbox | • PIT REF
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
checkpoint | 1.8 - Stage/Zone
label | Ref docs: Site Layout
label | Acceptance criteria:
label | • 1A / 1B/ 1C/ 1D / 1E / 1F / 1G / 2A / 2B / 2C / 2D / 2E / 2F / 2G / 3A / 3B / 3C / 4A / 4B / 4C / 5A / 5B / 5D / 6A / 6B
textbox | • STAGE
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
section | 2.0 Excavation
checkpoint | 2.1 - Excavation of Trench Pipes/Culverts
label | Ref docs:
label | • VR Clause 701.15
label | • Table 701.151
label | • 701.08
label | Acceptance criteria:
button | • Is the trench clearance width between 300mm to 600mm? | Yes,No,N/A
label | --------------------------------------------------------------------------------------------------------------
label | Table 701.151
label | Pipe Type ¦¦ Nominal Pipe Diameter or Width (mm) ¦¦ Horizontal Clearance to Wall of Trench :: Min. (mm) / Max. (mm)
label | --------------------------------------------------------------------------------------------------------------
label | Corrugated Metal Culvert ¦¦ All ¦¦ 300 mm / 1,000 mm
label | Other ¦¦ All ¦¦ 300 mm / 600 mm
label | --------------------------------------------------------------------------------------------------------------
button | • Is the excavation at a sufficient depth for pipe/box culvert bedding? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: S
label | CYP D&C JV - Sign/Date: SE
checkpoint | 2.2 - Excavation for Pits
label | Ref docs: VR Clause 705.05
label | Acceptance criteria:
button | • Is the pit excavation not less than 400mm from external pit wall to side of excavation? | Yes,No,N/A
button | • Is the excavation at a sufficient depth for pit bedding? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: S
label | CYP D&C JV - Sign/Date: SE
section | 3.0 Bedding
checkpoint | 3.1 - Bedding - Pipes
label | Ref docs: VR Clause 701.16
label | Acceptance criteria:
button | • Is the Pipe Diameter less than 1500mm? If so, has 100mm of bedding been placed? | Yes,No,N/A
button | • Is the Pipe Diameter greater than 1500mm? If so, has 200mm of bedding been placed? | Yes,No,N/A
label | (D = Pipe Diameter/Culvert Width).
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: S
label | CYP D&C JV - Sign/Date: SE
checkpoint | 3.2 - Bedding - Pits
label | Ref docs:
label | • VR Clause 705.05
label | • Table 701.091 & 701.092
label | Acceptance criteria:
button | • Has bedding been placed and compacted to a thickness not less than 80mm on clay foundation? | Yes,No,N/A
button | • Has bedding been placed and compacted to a thickness not less than 150mm on a rock foundation? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: S
label | CYP D&C JV - Sign/Date: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • Bedding and Backfill Material Conformance | Yes,No
checkpoint | 3.3 - Bedding Material - Compaction
label | Ref docs: VR Clause 701.20
label | Acceptance criteria:
button | • Has bedding been compacted to refusal? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: S
label | CYP D&C JV - Sign/Date: SE
section | 4.0 Installation of Pipes/Pits/Culverts
checkpoint | 4.1 - Laying of Pipes
label | Ref docs:
label | • VR Clause 701.17 (a)
label | • 701.17 (e)
label | Acceptance criteria:
button | • Are pipes being laid from downstream end? | Yes,No,N/A
button | • Are socket ends of pipes being placed facing upstream and fully entered? | Yes,No,N/A
button | • Is the pipe in full contact with the bedding for the full length of each section? | Yes,No,N/A
label | • The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: I
label | Symal Infrastructure - Resp: PE
label | CYP D&C JV - Key: S
label | CYP D&C JV - Sign/Date: SE
checkpoint | 4.2 - Installation of Pits
label | Ref docs:
label | • VR Clause 705.07
label | • 705.08
label | • 705.09
label | • 705.11
label | Acceptance criteria:
button | • Have pre-cast pits been installed at the correct location and to the dimensions shown on the drawings? | Yes,No,N/A
button | • Have subsurface drainage connections been cored at appropriate dimensions? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • Test results for fibres and fibre content (if applicable) (Compliance Certificate provided by Supplier) | Yes,No
checkpoint | 4.3 - Step Iron Fitting
label | Ref docs: VR Clause 705.12
label | Acceptance criteria:
button | • Have pits greater than 1.0 meter been fitted with step irons? | Yes,No,N/A
label | • Step irons shall not obstruct openings or be fitted to a wall which has openings.
button | • Have step Irons shall be installed in accordance with the manufacturer’s instructions and are an approved proprietary type? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • Material Conformance Certificates | Yes,No
checkpoint | 4.4 - Shaping the floor and Surface Finish
label | Ref docs:
label | • VR Clause 705.13
label | • 705.14
label | Acceptance criteria:
button | • Has the drainage pit floors been smoothly shaped from the inlets to the outlet for a height of one third of the diameter of the outlet pipe with cementitious mortar? | Yes,No,N/A
label | • Surfaces shall be finished uniform in appearance with a Class 2 surface finish in accordance with the requirements of Section 610.
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
checkpoint | 4.5 - Jointing - Pits
label | Ref docs:
label | • VR Clause 705.14
label | • 705.16
label | • 610.32
label | Acceptance criteria:
button | • Has the joints between drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
checkpoint | 4.6 - Jointing – Pipes
label | Ref docs: VR Clause 701.18
label | Acceptance criteria:
button | • Are rubber rings to be used on rubber ring joint pipes clean and free of debris? | Yes,No,N/A
button | • Have all interlocking joint reinforced concrete pipes been jointed or wrapped with 200mm wide external joint rubber band? Has the rubber band been placed between the spigot and socket? | Yes,No,N/A
button | • Have pipes with lifting holes been placed with lifting holes uppermost? Have lifting holes been plugged after pipe installation? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
checkpoint | 4.7 - Fitting of Covers
label | Ref docs: VR Clause 705.17
label | Acceptance criteria:
label | • Pit Downstream
textbox | ○ Pit Number
textbox | ○ Lid Class
textbox | ○ Lid Type
label | • Pit Upstream
textbox | ○ Pit Number
textbox | ○ Lid Class
textbox | ○ Lid Type
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • Survey Conformance Report | Yes,No
section | 5.0 Installation of Box Culverts
checkpoint | 5.1 - Laying Box Culverts
label | Ref docs: VR Clause 701.17 (a) (c) (d)
label | Acceptance criteria:
button | • Have consecutive sections of box culverts been firmly butted together? | Yes,No,N/A
button | • Does the mortar have a minimum 28 day compressive strength of not less than 40MPa? Is it at least Type C Class? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • Technical Data Sheet | Yes,No
section | 6.0 Backfilling
checkpoint | 6.1 - Backfill – Pipes/Culverts
label | Ref docs: VR Clause 701.19
label | Acceptance criteria:
button | • Has the haunch zone been extended from top of bedding layer to 1/3 pipe diameter? Haunch zone material to be same as bedding layer. Haunch zone to be compacted to refusal in max 150mm layer. | Yes,No,N/A
button | • Is the pipe to be backfilled in under an area to be paved? If so, has excavation below design subgrade level been backfilled with select backfill material? And within the pavement layer backfilled with appropriate pavement material? | Yes,No,N/A
button | • Is the pipe to be backfilled in under an area to be paved? If so, has excavation below design subgrade level been backfilled with select backfill material? And within the pavement layer backfilled with appropriate pavement material? | Yes,No,N/A
button | • Is the pipe to be backfilled in under an area not to be paved? If so, has the trench been backfilled with select backfill material to a level 0.3m above the top of the culvert? Ordinary backfill may be used above that level. | Yes,No,N/A
button | • Has the backfill material been backfilled in max 150mm layers? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | NATA Test Report: Compaction | Yes,No
checkpoint | 6.2 - Backfill - Pits
label | Ref docs: VR Clause 705.18
label | Acceptance criteria:
button | • Has the pit been backfilled in layers not exceeding 300mm? Pit backfill to be compacted to refusal using hand held equipment. | Yes,No
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
section | 7.0 Completion
checkpoint | 7.1 - As-built Survey
label | Ref docs:
label | • VR Clause 705.19
label | • 610.47
label | • 610.46
label | Acceptance criteria:
button | • Has the pipe been laid with adequate fall and invert levels within ±10mm of design? | Yes,No,N/A
button | • Is the invert level of pipes at pipes ±50mm of design? | Yes,No,N/A
button | • Is the line of the pit cover been installed ±10mm of the design kerb line? | Yes,No,N/A
button | • Is the pit cover level ±10 mm of the design level for that point? | Yes,No,N/A
button | • Is the offset of entry pits within ±20 mm of kerbs/barriers? | Yes,No,N/A
button | • Is the offset of entry pits within ±20 mm of kerbs/barries? | Yes,No,N/A
button | • Is the plan location of pits other than offsets to kerb lines or barriers ±100 mm? | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R / H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • Survey Conformance Certificate | Yes,No
holdpoint | HOLD POINT
checkpoint | 7.2 - Compaction and moisture content of backfill & bedding material
label | Ref docs:
label | • 701.20a
label | • 701.20b
label | Acceptance criteria:
button | • Has a total of 3 compaction tests taken place, per lot, inclusive of pit compaction, achieving 97% compaction? | Yes,No,N/A
label | Freq: At 20% of all lots
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R / H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach Compaction Reports
holdpoint | HOLD POINT
checkpoint | 7.3 - CCTV Inspection
label | Ref docs: 701.30
label | Acceptance criteria:
button | • Have all storm water lines been inspected by CCTV and found to be free of defects prior to placement of pavement? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
label | CYP D&C JV - Key: H
label | CYP D&C JV - Sign/Date: PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • CCTV Inspection Report | Yes,No
holdpoint | HOLD POINT
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot
checklist | SYM-ITP-007 - Subsurface Drainage (Rev A) | [5 empty] | SYM-ITP-007 - Subsurface Drainage (Rev A)
section | 1.0 General Details
checkpoint | 1.1 - Set Out
label | Ref docs: Civil drawings
label | Acceptance criteria:
button | • Is the work area clearly pegged out for line and level? | Yes,No,N/A
textbox | Subsurface drainage Reference
textbox | Size of Lot |  |  | M
label | Days production or pit to pit
textbox | Zone
textbox | Stage
label | Freq: Prior to the Start of Activity
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint | 1.2 - Procedure for method of compaction and placement of no fines concrete filter material.
label | Ref docs:
label | • Construction Document (Drainage)
label | • VR702.05
label | Acceptance criteria:
button | • Has the method of compaction shall be in accordance with the Contractor’s quality procedures been submitted for review by the Superintendent and approved? | Yes,No,N/A
button | • Has no fines concrete been used as a filter material? | Yes,No,N/A
button | • Has no fines concrete been placed and compacted within 1 hour of mixing? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • As per approved Construction Document
checkpoint | 1.3 - Conformity with Drawings
label | Ref docs:
label | • VR702.03
label | • IFC Drawings
label | Acceptance criteria:
button | • Are the drawings, complete & current? | Yes,No,N/A
button | • Is the subsurface drainage pipe or the geocomposite invert level not exceeding 25 mm from the specified level and not more than 50 mm from the specified line. With changes of grade not at a rate exceeding 10 mm in any 3 m length. | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach completed Permit
holdpoint | HOLD POINT
checkpoint | 1.4 - Excavation Permit & Penetration Permit
label | Ref docs:
label | • SMP
label | • VR 602.03
label | Acceptance criteria:
button | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services. | Yes,No,N/A
button | • Relevant permits have been signed and approved. | Yes,No,N/A
button | • Extents and levels correct to relevant drawings | Yes,No,N/A
button | • 50mm Blinding to be placed as required to allow working surface and protect excavation. | Yes,No,N/A
button | • Has the trench been excavated to allow 300mm between top of capping and top of subsoil pipe? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
holdpoint | HOLD POINT
section | 2.0 Subsurface drainage materials and installation
checkpoint | 2.1 - Pipes
label | Ref docs:
label | • VR 702.04
label | • VR 702.03
label | • VR 702.09
label | Acceptance criteria:
button | • Has the Pipe Class and size been confirmed as per latest IFC drawings drawings and project Specs? | Yes,No,N/A
button | • Has the slotted pipe been placed centrally in the trench? | Yes,No,N/A
button | • Have plastic pipes been kept away from sunlight and undamaged during delivery and installation? | Yes,No,N/A
button | • Is the subsurface drainage pipe invert level not exceeding 25 mm from the specified level and not more than 50 mm from the specified line. With changes of grade not at a rate exceeding 10 mm in any 3 m length. | Yes,No,N/A
button | • Is the pipe grade not flatter than 1m in 250m? | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach Compliance Certificates.
checkpoint | 2.2 - Geotextiles
label | Ref docs:
label | • VR 702.06
label | • Table 702.061
label | • VR 702.09
label | Acceptance criteria:
button | • Has the outer covering of the subsurface drain been covered in a geotextile surround if specified? | Yes,No,N/A
button | • Has the geotextile been placed without punctures or tears? | Yes,No,N/A
button | • In expansive clays does the geotextile material extend to directly below the kerb line? | Yes,No,N/A
button | • is the Geotextile material supplied and installed as per latest IFC drawings and project specifications? | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | Manufactures Compliance Certificates | Yes,No,N/A
checkpoint | 2.3 - Filter material
label | Ref docs:
label | • VR 702.05
label | • VR 702.13
label | • Table 702.051
label | • Table 702.131
label | • VR 702.09
label | • (g)
label | Acceptance criteria:
button | • Has material been placed in <300mm layers and compacted with minimal disturbance to pipe, geotextile and trench walls? | Yes,No,N/A
button | • Has no fines concrete ratios and specifications applied as per Table 702.051 and VR702.05(e) | Yes,No,N/A
button | • Has crushed rock/concrete ratios and specifications applied as per Table 702.052 and VR702.05(d) | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint | 2.4 - Access points
label | Ref docs: VR 702.10
label | Acceptance criteria:
button | • Have access points installed at intervals of between 100m and 150 m? | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint | 2.5 - Flushing
label | Ref docs: VR 702.10
label | Acceptance criteria:
button | • Has the pipe been flushed with water to remove any debris or blockages in the pipe and it’s working correctly with a smooth flow? | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot
checklist | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | [5 empty] | SYM-ITP-008 - Insitu Concrete Elements (Rev A)
section | 1.0 General Details
checkpoint | 1.1 - Material classification and source
label | Ref docs:
label | • 503.04
label | • VR 610.07
label | • AS 1379
label | Acceptance criteria:
button | • Is Mix design approved prior to placemen and material properties meet project specification, AS 3600, AS 1379. | Yes,No,N/A
textbox | Concrete Strength |  |  | MPA
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 1.2 - Set Out
label | Ref docs: Civil drawings
label | Acceptance criteria:
button | • Is the work area clearly pegged out for line and level? | Yes,No,N/A
textbox | • Wall/Footing Reference
textbox | • Zone
textbox | • Stage
textbox | • Element Description
label | Freq: Prior to the Start of Activity
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach Drawings
checkpoint | 1.3 - Conformity with Drawings
label | Ref docs: VR Clause 701.10
label | Acceptance criteria:
button | • Are the drawings, complete & current? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach Recent IFC Drawings
holdpoint | HOLD POINT
checkpoint | 1.4 - Excavation Permit & Penetration Permit
label | Ref docs:
label | • SMP
label | • VR 602.03
label | Acceptance criteria:
button | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services. | Yes,No,N/A
button | • Relevant permits have been signed and approved. | Yes,No,N/A
button | • Extents and levels correct to relevant drawings | Yes,No,N/A
button | • 50mm Blinding to be placed as required to allow working surface and protect excavation. | Yes,No,N/A
textbox | Excavation to a total depth of |  |  | mm
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach completed Permit
holdpoint | HOLD POINT
section | 2.0 Insitu concrete Element
checkpoint | 2.1 - Ground Preparation
label | Ref docs:
label | • IFC Drawings
label | • VR 610
label | Acceptance criteria:
button | • Is the fill and base of the foundation compacted to achieve at least 98% and achieving Geotechnical strength as per the design requirements. | Yes,No,N/A
button | • Has the surface shall be thoroughly moistened with water and excess surface water removed prior to placing concrete. | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 2.2 - Formwork
label | Ref docs:
label | • Civil drawings.
label | • Project Specs
label | • VR 614.04
label | • VR 613.04
label | • Table 614.041
label | Acceptance criteria:
button | • Formwork has been installed correctly and sufficiently braced. | Yes,No,N/A
button | • Formwork set out has been done as per latest design drawings and specifications | Yes,No,N/A
button | • Were Construction joints/Expansion Joints/Isolation Joints /or any type of joint as specified in the drawings Installed | Yes,No,N/A
button | • Any Backfill/ Underlay Material as per drawings & specifications | Yes,No,N/A
button | • Was Installations of Cast-Ins/ HD bolts/ Chemical Anchors/Block out Verified | Yes,No,N/A
button | • Is the concrete member of height greater than 2m and a formwork design obtained with a certificate of compliance from a Proof Engineer forwarded to the Superintendent for approval? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach formwork design and approvals
checkpoint | 2.3 - Reinforcement
label | Ref docs:
label | • AS3600
label | • VR611
label | • VR610
label | Acceptance criteria:
button | • Tolerance - As per specifications and Australian Standard and minimum cover for steel reinforcement is 40mm. | Yes,No,N/A
button | • Steel is free of excess corrosion, loose millings, oil or other contaminants | Yes,No,N/A
button | • Required Connection details - U Bars/ Z Bars/Cogs Verified/Starter bars | Yes,No,N/A
button | • Correct concrete cover and chairs on sides, bottom and top Verified | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint | 2.4 - Pre-pour Inspections
label | Ref docs:
label | • Civil drawings.
label | • Project Specs
label | Acceptance criteria:
label | • Has steel reinforcement been placed correctly with adequate cover? | Yes,No,N/A
button | • Have tie bars and expansion joints been installed at the correct intervals? | Yes,No,N/A
button | • Pour area is free of loose debris, oils, water | Yes,No,N/A
button | • Have any services located within the slab been installed, surveyed and pinned down | Yes,No,N/A
button | • Concrete Testing Lab Representative will be available during concrete pour | Yes,No,N/A
button | • CYP D&C JV informed of concrete pour date and start time | Yes,No,N/A
label | Freq: Prior to start of each Concrete Pour
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SS
label | CYP D&C JV - Key: H
holdpoint | HOLD POINT
checkpoint | 2.5 - Concrete Placement
label | Ref docs:
label | • VR503.07
label | • VR503.05
label | Acceptance criteria:
button | • Has concrete been transported, handled and placed to prevent segregation, loss or leakage of materials and air temp within 5 to 35 degrees C | Yes,No,N/A
button | • Has Concrete been tamped/vibrated to increase density and prevent voids, honeycombing or surface defects. | Yes,No,N/A
button | • Has a minimum of one of vibrator used at all times while the concreting is in operation | Yes,No,N/A
button | • Ensure monitoring forms/cast in items during the pour | Yes,No,N/A
button | • Concrete Work(s) completed to specification/drawings & Area left clean/tidy | Yes,No,N/A
button | • Concrete Dockets Received, Attach last Docket | Yes,No,N/A
textbox | Pour date
textbox | Total pour Concrete quantity |  |  | M3
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Delivery Doc
label | • Conc pour record
checkpoint | 2.5 - Post Pour
label | Ref docs:
label | • Civil drawings.
label | • Project Specs
label | • VR 610
label | Acceptance criteria:
button | • Was Curing agent applies as per project specifications | Yes,No,N/A
button | • Concrete reached design strength to strip formwork | Yes,No,N/A
button | • Any identified defects after striping rectified | Yes,No,N/A
button | • Attach Subcontractor’s QA | Yes,No,N/A
button | • Does Backfill material comply with Vicroad specs, Project specs and drawings? | Yes,No,N/A
button | • Were as Built completed? Attach report if applicable | Yes,No,N/A
button | • Concrete reached design strength to strip formwork. (Attach test results) | Yes,No,N/A
button | • Were expansion joints placed at intervals less than 10m. | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach concrete Test Report
label | • Attach As built report
checkpoint | 2.6 - Backfilling
label | Ref docs: VR703.29
label | Acceptance criteria:
button | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour? | Yes,No,N/A
button | • Were the positions of any existing conduits passing under edgings marked by a chase in the edging immediately above the conduit together with a suitable identification mark. | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE/PE
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot
checkpoint-no-status | Table 610.161
label | Volume Cast in One Continuous Operation (cubic metre) ¦¦ Minimum Number of Samples
label | --------------------------------------------------------------------------------------------------------------
label | 0 to 10 ¦¦ 1
label | 10 to 25 ¦¦ 2
label | 25 to 50 ¦¦ 3
label | 50 to 100 ¦¦ 4
checkpoint-no-status | Table 610.241
label | Exposure Classification ¦¦ Maximum Acceptable Crack Widths (mm)
label | --------------------------------------------------------------------------------------------------------------
label | A ¦¦ 0.20
label | B1 ¦¦ 0.20
label | B2 ¦¦ 0.15
label | C, U ¦¦ 0.10
checkpoint-no-status | Table 610.162
label | Specified slump, mm ¦¦ Tolerance, mm
label | --------------------------------------------------------------------------------------------------------------
label | < 60 ¦¦ ± 10
label | ≥ 60 ≤ 80 ¦¦ ± 15
label | > 80 ≤ 110 ¦¦ ± 20
label | > 110 ≤ 150 ¦¦ ± 30
label | > 150 ¦¦ ± 40
checkpoint-no-status | Table 614.041
label | Concrete members ¦¦ Formwork documentation ¦¦ Certification of formwork design ¦¦ Proof Engineering of formwork design ¦¦ Certification of erected formwork
label | --------------------------------------------------------------------------------------------------------------
label | (a) Abutments, pilecaps, footings, solid piers, pier columns and walls, with heights less than or equal to 2.0 metres ¦¦ N/A ¦¦ N/A ¦¦ N/A ¦¦ Contractor’s Engineer (Attachment C, as per clause 614.08)
label | (b) Abutments, pilecaps, footings, solid piers, pier columns and walls, with heights greater than 2.0 metres ¦¦ Design drawings and specifications ¦¦ Design Engineer ¦¦ Proof Engineer (Attachment A, as per this clause) ¦¦ Contractor’s Engineer and Design Engineer (Attachment B, as per clause 614.08)
label | (c) All other concrete members ¦¦ Design drawings and specifications ¦¦ Design Engineer ¦¦ Proof Engineer (Attachment A, as per this clause) ¦¦ Contractor’s Engineer and Design Engineer (Attachment B, as per clause 614.08)
label | (d) Any member for which self-compacting concrete is proposed ¦¦ Design drawings and specifications ¦¦ Design Engineer ¦¦ Proof Engineer (Attachment A, as per this clause) ¦¦ Contractor’s Engineer and Design Engineer (Attachment B, as per clause 614.08)
checkpoint-no-status | Table 610.472 Cast In Situ Concrete
label | Item ¦¦ Tolerance (mm unless shown otherwise)
label | --------------------------------------------------------------------------------------------------------------
label | (i) Footings
label | ○ Plane dimensions
label | – Formed footings and pile caps ¦¦ -15 to +50
label | – Unformed footings (when approved by the Superintendent) ¦¦ 0 to +150
label | ○ Thickness
label | – < 300 mm ¦¦ -5 to +25
label | – > 300 mm ¦¦ -10 to +50
label | ○ Top of footing or pile cap reduced level ¦¦ -25 to +25
label | ○ Departure from the plan position in any direction ¦¦ 50
label | --------------------------------------------------------------------------------------------------------------
label | (ii) Cylinders
label | ○ Variation from the vertical ¦¦ 25 mm in 3 m
label | ○ Departure from the plan position in any direction ¦¦ 75
label | --------------------------------------------------------------------------------------------------------------
label | (iii) Variation in Cross Section of Columns, Piers, Pier and Abutment Crossheads, Slabs, Walls, Beams and Similar Parts (excluding deck slabs and end posts)
label | ○ < 3 m ¦¦ -5 to +15
label | ○ > 3 m ¦¦ -10 to +25
label | --------------------------------------------------------------------------------------------------------------
label | (iv) Variation of Cross Section of End Posts ¦¦ -5 to +5
label | --------------------------------------------------------------------------------------------------------------
label | (v) Deck
label | ○ Thickness of Deck Slabs (excluding allowance for correction of camber or hog) ¦¦ 0 to +10
label | ○ Deck surface reduced level ¦¦ -10 to +10
label | --------------------------------------------------------------------------------------------------------------
label | (vi) Deck Joints
label | ○ Width of slot ¦¦ -3 to +3
label | --------------------------------------------------------------------------------------------------------------
label | (vii) Variation from Vertical or Specified Batter of Columns, Piers, Walls, Handrail Posts and Arrises
label | ○ Unexposed concrete ¦¦ 10 mm in 2.5 m (1/250)
label | ○ Exposed concrete ¦¦ 5 mm in 2.5 m (1/500)
label | --------------------------------------------------------------------------------------------------------------
label | (viii) Variation from Grades indicated on Drawings for Railings, Kerbs and Arrises ¦¦ 2.5 mm in 2.5 m (1/1000)
label | --------------------------------------------------------------------------------------------------------------
label | (ix) Reduced Level of Tops of Pier and Abutment Crossheads and Piers
label | ○ With pedestals ¦¦ -10 to +10
label | ○ Without pedestals ¦¦ -5 to +5
label | ○ Difference in Level across width of crosshead ¦¦ 5
label | --------------------------------------------------------------------------------------------------------------
label | (x) Bearing Pedestals
label | ○ Reduced level ¦¦ -2.5 to +2.5
label | ○ Variation from grade across the width of individual pedestals shall not exceed ¦¦ 1 in 200
label | ○ Deviation from flat surface ¦¦ +1.0 to -1.0
label | --------------------------------------------------------------------------------------------------------------
label | (xi) Departure from Plan Position at any level
label | ○ Columns, Piers, Walls, Pier and Abutment Crossheads, Beams, Slabs, Kerbs, Railing and other similar parts ¦¦ 25
label | ○ Relative displacement of adjoining members shall not exceed ¦¦ 10
label | --------------------------------------------------------------------------------------------------------------
label | (xii) Departure from Alignment
label | ○ Rows of columns, faces of piers or walls ¦¦ 10
label | ○ Handrails, Faces of hand rail posts, Kerbs ¦¦ 5
label | --------------------------------------------------------------------------------------------------------------
label | (xiii) Maximum Allowance for Irregularities in Exposed Concrete Surfaces
label | ○ Sections less than 1 m in dimension when measured with a straightedge across the dimension of the section ¦¦ 2.5
label | ○ Sections greater than 1 m in dimension when measured with a straightedge across the dimension of the section, except that when sections are greater than 2.5 m in dimension, a 2.5 m straightedge shall be used ¦¦ 5
label | --------------------------------------------------------------------------------------------------------------
label | (xiv) Irregularities in Railings ¦¦ 2.5 mm in 2.5 m
label | --------------------------------------------------------------------------------------------------------------
label | (xv) Slab Surface Finish ¦¦ 5 mm in 2.5 m
checkpoint-no-status | Table 610.473 Pre-tensioned Concrete
label | Item ¦¦ Tolerance (mm unless shown otherwise)
label | --------------------------------------------------------------------------------------------------------------
label | (i) Cross Section
label | ○ Dimension
label | – < 2 m ¦¦ -3 to +3
label | – > 2 m ¦¦ -6 to +6
label | ○ Out of square
label | – > 2 m ¦¦ 0.5 in 250, or Desirable 3, Maximum 5
label | --------------------------------------------------------------------------------------------------------------
label | (ii) Strand and Reinforcement
label | ○ Placing of reinforcement ¦¦ 5
label | ○ Placing of prestressing strand ¦¦ 3
label | ○ Concrete cover ¦¦ 0 to +5
label | --------------------------------------------------------------------------------------------------------------
label | (iii) Squareness of Ends
label | ○ Dimension
label | Deviation from a plane perpendicular to the longitudal axis of a member, or from the specified end plane:
label | – < 500 mm ¦¦ 3 mm
label | – > 500 mm ¦¦ 6 mm per metre (10 mm maximum)
label | --------------------------------------------------------------------------------------------------------------
label | (iv) Length
label | ○ Diagonal length for precast unit ¦¦ 5
label | ○ Overall length or length centre to centre of bearings (for beams and slabs) ¦¦ 0.06% x specified length (max 20)
label | ○ Centre to centre spacing of holes for transverse rods or both ¦¦ 5
label | --------------------------------------------------------------------------------------------------------------
label | (v) Profile in a Vertical Plane (Hog)
label | The deviation in hog of any unit from the mean hog of all units shall not vary by more than 0.07% of the length of the units. The absolute value for hog for any unit shall not be less than zero. Hog measurements shall be made at transfer of prestress.
label | --------------------------------------------------------------------------------------------------------------
label | (vi) Profile in a Horizontal Plane (Bow)
label | The deviation of a unit from the required profile shall not exceed 0.06% of the length of the unit or a maximum of 15 mm.
label | --------------------------------------------------------------------------------------------------------------
label | (vii) Twist
label | The angular rotation of any cross section relative to an end cross section shall not exceed 1 in 200
label | --------------------------------------------------------------------------------------------------------------
label | (viii) Sole Plates
label | The plane of the sole plate or bearing surface shall not vary from that shown on the drawings by more than 1 in 200 in any direction.
label | --------------------------------------------------------------------------------------------------------------
label | (ix) Deviation
label | ○ The distance of any point from a flat plane held against that surface ¦¦ 3 mm in 2 m
checklist | SYM-ITP-009 - TACTILES (Rev A) | [5 empty] | SYM-ITP-009 - TACTILES (Rev A)
section | 1.0 Preliminaries
checkpoint | 1.1 - Conformity with Drawings
label | Ref docs: TAS-A-AUD-6007-0426 – LANDSCAPE (IFC)
label | Acceptance criteria:
button | • Are the drawings, complete & current? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
holdpoint | HOLD POINT
section | 2.0 Pre-Construction Activities
checkpoint | 2.1 - Survey Set-Out
label | Ref docs: TAS-A-AUD-6007-0426 – LANDSCAPE (IFC)
label | Acceptance criteria:
button | • Have tactiles/pavers been set-out as per current drawings? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 2.2 - Installation Considerations
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00
label | Acceptance criteria:
button | • Is the concrete slab free of any deposits or rubbish, projections/voids? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint-no-status | Does the area include stone TGSI’s?
label | If yes, proceed to Section 3.0
checkpoint-no-status | Does the area include regular tactiles?
label | If yes, proceed to Section 4.0
checkpoint-no-status | Does the area include both types of tactiles?
label | If yes, fill out both Section 3.0 & Section 4.0
section | 3.0 Stone TGSI's (pavers)
checkpoint | 3.1 - Bedding Mortar
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0821 (Mortar)
label | Acceptance criteria:
button | • Has mortar been placed using type/method described in specification? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 3.2 - Directional / Horizontal
label | Ref docs: TAS-A-AUD-6007-0426 – LANDSCAPE (IFC)
label | Acceptance criteria:
button | • Does the section require directional or horizontal TGSI’s, or both? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 3.3 - Laying Pavers
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0774 (Paving – 3.3)
label | Acceptance criteria:
button | • Have pavers been laid as described in specification, considering specified tolerances? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 3.4 - Sealed Joints
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0774 (Paving – 3.9)
label | Acceptance criteria:
button | • Have joints been sealed as described in specification? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
section | 4.0 Regular Tactiles
checkpoint | 4.1 - Tactile Installation
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00
label | Acceptance criteria:
button | • Have tactiles been installed in accordance with manufacturer specifications? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot
checklist | SYM-ITP-011 - LANDSCAPING (Rev A) | [5 empty] | SYM-ITP-011 - LANDSCAPING (Rev A)
section | 1.0 Preliminaries
checkpoint | 1.1 - Conformity with Drawings
label | Ref docs: TAS-A-AUD-6007-0426 - LANDSCAPE
label | Acceptance criteria:
button | • Are the drawings, complete & current? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
holdpoint | HOLD POINT
checkpoint | 1.2 - Sample Submission & Approval
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0171
label | Acceptance criteria:
button | • Have all relevant samples been provided to CYP and approved? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Test results to be provided at least 5 working days prior to bulk deliveries
holdpoint | HOLD POINT
section | 2.0 Pre-Construction Activities
checkpoint | 2.1 - Plant Set-Out
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0752
label | Acceptance criteria:
button | • Have all plants been set out in garden beds prior to planting? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
section | 3.0 Construction Activities
checkpoint | 3.1 - Cultivation of sub-grade
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0751
label | Acceptance criteria:
button | • Has cultivation been undertaken as specified? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 3.2 - Installation of imported topsoil / subsoil / structural soil
label | Ref docs:
label | • TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 - Section 0751
label | • TAS-A-AUD-6007-0426 - LANDSCAPE
label | Acceptance criteria:
button | • Has topsoil been placed in the manner specified, alongside to the depth specified in detail on drawing set? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 3.3 - Installation of imported organic / inorganic mulch
label | Ref docs:
label | • TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0753
label | • TAS-A-AUD-6007-0426 - LANDSCAPE
label | Acceptance criteria:
button | • Has mulch been placed in the manner specified, alongside to the depth specified in detail on drawing set? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 3.4 - Installation of edging
label | Ref docs:
label | • TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0779
label | • TAS-A-AUD-6007-0426 - LANDSCAPE
label | Acceptance criteria:
button | • Has edging been placed in the manner specified, referencing both design standards, drawing details and manufacturers recommendations (where relevant)? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE/PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • All City of Melbourne standard / engineering drawings for relevant edging types can be found in Appendix A3: Authority Design Standards
checkpoint | 3.5 - Installation of plants
label | Ref docs:
label | • TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0753
label | • TAS-A-AUD-6007-0426 - LANDSCAPE
label | Acceptance criteria:
button | • Have all plants been placed / installed in the manner specified? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 3.6 - Installation of turf
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 - Section 0758
label | Acceptance criteria:
button | • Has turf been installed as per method described in section 3.17 ‘turfing’? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot
checklist | SYM-ITP-012 - Stratavaults (Rev A) | [5 empty] | SYM-ITP-012 - Stratavaults (Rev A)
section | 1.0 General Details
checkpoint | 1.1 - Site Preparation and Excavation Sequence
label | Ref docs: Civil Drawings
label | Acceptance criteria:
button | • Prepare the excavation for the Stratavaults | Yes,No,N/A
button | • Are all pipes extended for the startavault install | Yes,No,N/A
label | Freq: Prior to the Start of Activity
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach manufacturer Installation manual
holdpoint | HOLD POINT
checkpoint | 1.2 - Set Out
label | Ref docs: Civil drawings
label | Acceptance criteria:
button | • Is the work area clearly pegged out for line and level? | Yes,No,N/A
textbox | SV Reference
textbox | Zone
textbox | Stage
label | Freq: Prior to the Start of Activity
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint | 1.3 - Excavation Permit & Penetration Permit
label | Ref docs: SMP VR 602.03
label | Acceptance criteria:
label | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services.
label | • Relevant permits have been signed and approved.
label | • Extents and levels correct to relevant drawings
label | Freq: Prior to the Start of Activity
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
holdpoint | HOLD POINT
section | 2.0 Stratavault Installation
checkpoint | 2.1 - Stratavault Installation
label | Ref docs: Civil Drawings
label | Acceptance criteria:
button | • Are all stratavaults installed as per manufacturer specifications | Yes,No,N/A
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach ITP drawings
checkpoint | 2.2 - Soil Testing
label | Ref docs: Civil Drawings
label | Acceptance criteria:
button | • Soil testing and sampling completed as per manufacturer specification | Yes,No,N/A
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach test report
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot
checklist | SYM-ITP-013 - Retaining walls and wall footings (Rev A) | [5 empty] | SYM-ITP-013 - Retaining walls and wall footings (Rev A)
section | 1.0 General Details
checkpoint | 1.1 - Material classification and source
label | Ref docs:
label | • 503.04
label | • VR 610.07
label | • AS 1379
label | Acceptance criteria:
button | • Is Mix design approved prior to placemen and material properties meet project specification, AS 3600, AS 1379. | Yes,No,N/A
textbox | Concrete Strength |  |  | MPA
label | Freq: Prior to the Start of Activity
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 1.2 - Set Out
label | Ref docs: Civil drawings
label | Acceptance criteria:
button | • Is the work area clearly pegged out for line and level? | Yes,No,N/A
textbox | Wall/Footing Reference
textbox | Zone
textbox | Stage
label | Freq: Prior to the Start of Activity
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint | 1.3 - Conformity with Drawings
label | Ref docs: Aconex Documents Register
label | Acceptance criteria:
button | • Are the drawings, complete & current? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach Recent IFC Drawings
holdpoint | HOLD POINT
checkpoint | 1.4 - Excavation Permit & Penetration Permit
label | Ref docs: SMP VR 602.03
label | Acceptance criteria:
button | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services. | Yes,No,N/A
button | • Relevant permits have been signed and approved. | Yes,No,N/A
button | • Extents and levels correct to relevant drawings | Yes,No,N/A
button | • 50mm Blinding to be placed as required to allow working surface and protect excavation. | Yes,No,N/A
textbox | Excavation to a total depth of |  |  | mm
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach completed Permit
holdpoint | HOLD POINT
section | 2.0 Wall Footings
checkpoint | 2.1 - Formwork
label | Ref docs:
label | • Civil drawings.
label | • Project Specs
label | • VR 614.04
label | • VR 613.04
label | • Table 614.041
label | Acceptance criteria:
label | • Formwork has been installed correctly and sufficiently braced. | Yes,No,N/A
label | • Formwork set out has been done as per latest design drawings and specifications | Yes,No,N/A
label | • Were Construction joints/Expansion Joints/Isolation Joints Installed | Yes,No,N/A
label | • Any Backfill/ Underlay Material as per drawings & specifications | Yes,No,N/A
label | • Was Installations of Cast-Ins/ HD bolts/ Chemical Anchors/Block out Verified | Yes,No,N/A
label | • Is the concrete member of height greater than 2m and a formwork design obtained with a certificate of compliance from a Proof Engineer forwarded to the Superintendent for approval? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach formwork design and approvals
checkpoint | 2.2 - Reinforcement
label | Ref docs:
label | • AS3600
label | • VR611
label | • VR610
label | Acceptance criteria:
button | • Tolerance - As per specifications and Australian Standard and minimum cover for steel reinforcement is 40mm. | Yes,No,N/A
button | • Steel is free of excess corrosion, loose millings, oil or other contaminants | Yes,No,N/A
button | • Required Connection details - U Bars/ Z Bars/Cogs Verified/Starter bars | Yes,No,N/A
button | • Correct concrete cover and chairs on sides, bottom and top Verified | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint | 2.3 - Pre-pour Inspections
label | Ref docs:
label | • Civil drawings.
label | • Project Specs
label | Acceptance criteria:
button | • Has steel reinforcement been placed correctly with adequate cover? | Yes,No,N/A
button | • Have tie bars and expansion joints been installed at the correct intervals? | Yes,No,N/A
button | • Pour area is free of loose debris, oils, water | Yes,No,N/A
button | • Have any services located within the slab been installed, surveyed and pinned down | Yes,No,N/A
button | • Concrete Testing Lab Representative will be available during concrete pour | Yes,No,N/A
button | • CYP D&C JV informed of concrete pour date and start time | Yes,No,N/A
label | Freq: Prior to start of each Concrete Pour
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SS
label | CYP D&C JV - Key: H
holdpoint | HOLD POINT
checkpoint | 2.4 - Concrete Placement
label | Ref docs:
label | • VR503.07
label | • VR503.05
label | Acceptance criteria:
button | • Has concrete been transported, handled and placed to prevent segregation, loss or leakage of materials. | Yes,No,N/A
button | • Has Concrete been tamped/vibrated to increase density and prevent voids, honeycombing or surface defects. | Yes,No,N/A
button | • Has a minimum of one of vibrator used at all times while the concreting is in operation | Yes,No,N/A
button | • Ensure monitoring forms/cast in items during the pour | Yes,No,N/A
button | • Concrete Work(s) completed to specification/drawings & Area left clean/tidy | Yes,No,N/A
button | • Concrete Dockets Received, Attach last Docket | Yes,No,N/A
textbox | Pour date
textbox | Total pour Concrete quantity |  |  | M3
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Delivery Doc
label | • Conc pour record
checkpoint | 2.5 - Post Pour
label | Acceptance criteria:
button | • Was Curing agent applies as per project specifications | Yes,No,N/A
button | • Concrete reached design strength to strip formwork | Yes,No,N/A
button | • Any identified defects after striping rectified | Yes,No,N/A
button | • Attach Subcontractor’s QA | Yes,No,N/A
button | • Does Backfill material compl;y with Vicroad specs, Project specs and drawings? | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Concrete Strength Report
checkpoint | 2.6 - Backfilling
label | Ref docs: VR703.29
label | Acceptance criteria:
label | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour? | Yes,No,N/A
label | • Were the positions of any existing conduits passing under edgings marked by a chase in the edging immediately above the conduit together with a suitable identification mark. | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE/PE
section | 3.0 Retaining Walls
checkpoint | 3.1 - Formwork
label | Ref docs:
label | • Civil drawings.
label | • Project Specs
label | Acceptance criteria:
label | • Formwork has been installed correctly and sufficiently braced. | Yes,No,N/A
button | • Formwork set out has been done as per latest design drawings and specifications | Yes,No,N/A
button | • Were Construction joints/Expansion Joints/Isolation Joints /or any type of joint as specified in the drawings Installed | Yes,No,N/A
button | • Any Backfill/ Underlay Material as per drawings & specifications | Yes,No,N/A
button | • Was Installations of Cast-Ins/ HD bolts/ Chemical Anchors/Block out Verified | Yes,No,N/A
button | • Is the concrete member of height greater than 2m and a formwork design obtained with a certificate of compliance from a Proof Engineer forwarded to the Superintendent for approval? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint | 3.2 - Reinforcement
label | Ref docs:
label | • AS3600
label | • VR611
label | Acceptance criteria:
button | • Tolerance - As per specifications and Australian Standard and minimum cover for steel reinforcement is 40mm. | Yes,No,N/A
button | • Steel is free of excess corrosion, loose millings, oil or other contaminants | Yes,No,N/A
button | • Required Connection details - U Bars/ Z Bars/Cogs Verified/Starter bars | Yes,No,N/A
button | • Correct concrete cover and chairs on sides, bottom and top Verified | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint | 3.3 - Pre-pour Inspections
label | Ref docs:
label | • Civil drawings.
label | • Project Specs
label | Acceptance criteria:
button | • Has steel reinforcement been placed correctly with adequate cover? | Yes,No,N/A
button | • Have tie bars and expansion joints been installed at the correct intervals? | Yes,No,N/A
button | • Pour area is free of loose debris, oils, water | Yes,No,N/A
button | • Have any services located within the slab been installed, surveyed and pinned down | Yes,No,N/A
button | • Concrete Testing Lab Representative will be available during concrete pour | Yes,No,N/A
button | • CYP D&C JV informed of concrete pour date and start time | Yes,No,N/A
label | Freq: Prior to start of each Concrete Pour
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SS
label | CYP D&C JV - Key: H
holdpoint | HOLD POINT
checkpoint | 3.4 - Concrete Placement
label | Ref docs:
label | • VR503.07
label | • VR503.05
label | Acceptance criteria:
button | • Has concrete been transported, handled and placed to prevent segregation, loss or leakage of materials. | Yes,No,N/A
button | • Has Concrete been tamped/vibrated to increase density and prevent voids, honeycombing or surface defects. | Yes,No,N/A
button | • Has a minimum of one of vibrator used at all times while the concreting is in operation | Yes,No,N/A
button | • Ensure monitoring forms/cast in items during the pour | Yes,No,N/A
button | • Concrete Work(s) completed to specification/drawings & Area left clean/tidy | Yes,No,N/A
button | • Concrete Dockets Received, Attach last Docket | Yes,No,N/A
textbox | Pour date
textbox | Total pour Concrete quantity |  |  | M3
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Delivery Doc
label | • Conc pour record
checkpoint | 3.5 - Post Pour
label | Ref docs:
label | • Civil drawings.
label | • Project Specs
label | Acceptance criteria:
button | • Was Curing agent applies as per project specifications | Yes,No,N/A
button | • Concrete reached design strength to strip formwork | Yes,No,N/A
button | • Any identified defects after striping rectified | Yes,No,N/A
button | • Attach Subcontractor’s QA | Yes,No,N/A
button | • Does Backfill material compl;y with Vicroad specs, Project specs and drawings? | Yes,No,N/A
button | • Were as Built completed? Attach report if applicable | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Concrete Test Report
checkpoint | 3.6 - Backfilling
label | Ref docs: VR703.29
label | Acceptance criteria:
label | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour? | Yes,No,N/A
label | • Were the positions of any existing conduits passing under edgings marked by a chase in the edging immediately above the conduit together with a suitable identification mark. | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE/PE
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot
checklist | SYM-ITP-016 - Gross Pollutant Trap& Diversion Structure PV-GPT-2 (RevA) | [5 empty] | SYM-ITP-016 - Gross Pollutant Trap& Diversion Structure PV-GPT-2 (RevA)
section | 1.0 General Details
checkpoint | 1.1 - Site Preparation and Excavation Sequence
label | Ref docs:
label | • SPEL
label | • Vortceptor Installation Manual
label | Acceptance criteria:
button | • Prepare the excavation for the Vortceptor separation chamber first. | Yes,No,N/A
button | • Did the excavation for the Diversion Chamber (the rectangular precast concrete chamber) follow afterwards the Vortceptor. | Yes,No,N/A
button | • Was the inlet pipe run would installed, within one or two pipe lengths prior to the diversion chamber. | Yes,No,N/A
label | Freq: Prior to the Start of Activity
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach manufacturer Installation manual
holdpoint | HOLD POINT
checkpoint | 1.2 - Set Out
label | Ref docs: Civil drawings
label | Acceptance criteria:
button | • Is the work area clearly pegged out for line and level? | Yes,No,N/A
textbox | Zone
textbox | Stage
label | Freq: Prior to the Start of Activity
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint | 1.3 - Excavation Permit & Penetration Permit
label | Ref docs:
label | • SMP
label | • VR 602.03
label | Acceptance criteria:
button | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services. | Yes,No,N/A
button | • Relevant permits have been signed and approved. | Yes,No,N/A
button | • Extents and levels correct to relevant drawings | Yes,No,N/A
button | • 50mm Blinding to be placed as required to allow working surface and protect excavation. | Yes,No,N/A
textbox | Excavation for Vortceptor to a total depth of |  |  | mm
textbox | Excavation for Diversion Chamber to a total depth of |  |  | mm
label | Freq: Prior to the Start of Activity
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
holdpoint | HOLD POINT
section | 2.0 Vortceptor Installation
checkpoint | 2.1 - Vortceptor Installation
label | Ref docs:
label | • SPEL
label | • Vortceptor Installation Manual
label | Acceptance criteria:
label | • Were measurements checked on the Vortceptor prior to installation, and confirmd as per approved IFC | Yes,No,N/A
button | • The Vortceptor excavation should be no greater than required, this would be 1000mm oversized or to suit shield sizing. This is with due regard to the amount of backfill to be used under and around the tank. | Yes,No,N/A
button | • Were 150mm thick, compacted base of either a concrete blinding or compacted crushed rock layer installed. | Yes,No,N/A
button | • Was the Vortceptor lowered into the excavation with no rocks or sharp objects falling into the hole and no damage to the tank | Yes,No,N/A
button | • Were the levels of the Vortceptor adjusted to suit pipeworks and diversion chamber inlet void? | Yes,No,N/A
button | • Fill the tank with water up to the invert of the inlet | Yes,No,N/A
button | • Encase & backfill the outside of Vortceptor as per project backfilling specs | Yes,No,N/A
button | • Is the take located in an area subject to high water table or trapped underground water? | Yes,No,N/A
button | • If yes, the tank must be completely encased in unreinforced concrete, up to the specified height above the Vortceptor base, and at the minimum specified width beyond the perimeter of the Vortceptor base. Refer to SPEL Stormwater for recommended concrete dimensions and volumes to withstand buoyancy forces. | Yes,No,N/A
label | Freq: Prior to the Start of Activity
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach IFC drawings
checkpoint | 2.2 - Diversion Chamberb Installation
label | Ref docs:
label | • SPEL
label | • Vortceptor Installation Manual
label | Acceptance criteria:
button | • Were measurements checked on the Diversion Chamber prior to installation, and confirmd as per approved IFC | Yes,No,N/A
button | • Has the diversion chamber excavation pit been prepared as per Construction drawings | Yes,No,N/A
button | • Is sufficient room left to install inlet pipe and pipe is angled to be fed into the diversion chamber? | Yes,No,N/A
button | • Was the Diversion Chamber adjusted to a correct level so the rectangular opening matches the Vortceptor with the inlet and outlet block outs are to match the drainage line. | Yes,No,N/A
button | • Use the template provided with the Vortceptor to drill the bolt holes into the diversion chamber rectangular void. | Yes,No,N/A
button | • Use Sikaflex or silicone to seal the Vortceptor to the Diversion Chamber, use 8.5mm 4 cutter SDS bit to drill the bolt holes. | Yes,No,N/A
button | • Use M8 x 100mm Galvanised screw bolts to fix the Vortceptor to the Diversion Chamber. | Yes,No,N/A
label | Freq: Prior to the Start of Activity
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint | 2.3 - Associated Drainage & Finishing Works.
label | Ref docs:
label | • SPEL
label | • Vortceptor Installation Manual
label | Acceptance criteria:
button | • Were upstream and downstream drainage pipework Installed? | Yes,No,N/A
button | • Connect the pipework to the Diversion Chamber, concrete bandage the inlet and outlet pipes to the Diversion Chamber. | Yes,No,N/A
button | • Internally render the inlet and outlet pipework | Yes,No,N/A
button | • Use low slump concrete to mass infill and bench the base of the diversion chamber and weir. This is to direct the flow and remove any dead zones in the diversion chamber. | Yes,No,N/A
label | Freq: Prior to the Start of Activity
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint | 2.4 - Cover Slab Installation
label | Ref docs:
label | • SPEL
label | • Vortceptor Installation Manual
label | Acceptance criteria:
button | • Use a Sikaflex bead around the rebate on the top of the Diversion Chamber to ensure a satisfactory seal between cover slab (Lid) and chamber. | Yes,No,N/A
button | • Lift and install cover slab, ensure manhole void / cover is on Vortceptor side of the chamber. | Yes,No,N/A
button | • Use Sikaflex and screw bolts to secure fibreglass manhole riser to cover slab | Yes,No,N/A
button | • Tie in the manhole covers as per lid manufacturers installation guidelines, to achieve Finished Surface level. | Yes,No,N/A
label | Freq: Prior to the Start of Activity
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot
checklist | SYM-ITP-017 - Traffic Signals (Rev A) | [5 empty] | SYM-ITP-017 - Traffic Signals (Rev A)
section | 1.0 Preliminaries
checkpoint | 1.1 - Determine lot size
label | Ref docs: Lot map
label | Acceptance criteria:
button | • Has the lot been defined and marked up on lot map? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Lot map
holdpoint | WITNESS POINT
checkpoint | 1.2 - Survey set-out
label | Acceptance criteria:
button | • Has the work area been set out as per IFC drawings? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
holdpoint | WITNESS POINT
section | 2.0 Traffic Signals Installation
checkpoint | 2.1 - Signalised Construction
label | Ref docs: IFC Drawings
label | Acceptance criteria:
button | • Has signalised crossing been constructed in accordance with the IFC Drawings? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Subcontractor ITP's
holdpoint | WITNESS POINT
checkpoint | 2.2 - Testing and Commissioning
label | Ref docs: IFC Drawings
label | Acceptance criteria:
button | • Has Signalised crossing passed all commissioning and testing? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Subcontractor ITP's
holdpoint | WITNESS POINT
checkpoint | 2.3 - VicRoads Approval
label | Acceptance criteria:
label | • DOT inspection & approval provided? | Yes,No,N/A
textbox | Date:
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Subcontractor ITP's
holdpoint | HOLD POINT
section | 4.0 Conformance check
checkpoint | 4.1 - Test Reports & As-builts
label | Ref docs: Subcontractor ITP
label | Acceptance criteria:
button | • All Test reports and as builts received and reviewed. | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Test reports
label | • As-builts
holdpoint | WITNESS POINT
checkpoint | 4.2 - Product non-conformance
label | Acceptance criteria:
button | • All Product Non-Conformance(s) recorded and closed (if applicable) | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Completed NCR form
holdpoint | WITNESS POINT
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot
checklist | SYM-ITP-018 - Public Lighting (Rev A) | [5 empty] | SYM-ITP-018 - Public Lighting (Rev A)
section | 1.0 Preliminaries
checkpoint | 1.1 - Determine lot size
label | Ref docs: Lot map
label | Acceptance criteria:
button | • Has the lot been defined and marked up on lot map? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Lot map
holdpoint | WITNESS POINT
checkpoint | 1.2 - Survey set-out
label | Acceptance criteria:
button | • Has the work area been set out as per IFC drawings? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
holdpoint | WITNESS POINT
section | 2.0 Traffic Signals Installation
checkpoint | 2.1 - Public lighting construction
label | Ref docs: IFC Drawings VR 731
label | Acceptance criteria:
button | • Has the public lighting been constructed in accordance with the IFC Drawings? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Subcontractor ITP's
holdpoint | WITNESS POINT
checkpoint | 2.2 - Testing and Commissioning
label | Ref docs: IFC Drawings VR 731
label | Acceptance criteria:
button | • Has the public lighting passed all commissioning and testing? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Subcontractor ITP's
holdpoint | WITNESS POINT
checkpoint | 2.3 - Powercor Approval
label | Acceptance criteria:
button | • Powercor inspection & approval provided? | Yes,No,N/A
textbox | Date
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Subcontractor ITP's
holdpoint | HOLD POINT
section | 4.0 Conformance check
checkpoint | 4.1 - Test Reports & As-builts
label | Ref docs: Subcontractor ITP
label | Acceptance criteria:
button | • All Test reports and as builts received and reviewed. | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Test reports
label | • As-builts
holdpoint | WITNESS POINT
checkpoint | 4.2 - Product non-conformance
label | Acceptance criteria:
button | • All Product Non-Conformance(s) recorded and closed (if applicable) | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Completed NCR form
holdpoint | WITNESS POINT
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot
checklist | SYM-ITP-019 - CLADDING (Rev A) | [5 empty] | SYM-ITP-019 - CLADDING (Rev A)
section | 1.0 Preliminaries
checkpoint | 1.1 - Conformity with Drawings
label | Ref docs: TAS-A-AUD-6007-0426 – LANDSCAPE (IFC)
label | Acceptance criteria:
button | • Are the drawings, complete & current? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
holdpoint | HOLD POINT
section | 2.0 Pre-Construction Activities
checkpoint | 2.1 - Survey Set-Out
label | Ref docs: TAS-A-AUD-6007-0426 – LANDSCAPE (IFC) & TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0433 Stone Cladding
label | Acceptance criteria:
button | • Has the structure been surveyed, including any fixing inserts, before commencement? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 2.2 - Installation Considerations
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0433 (Stone Cladding 3.4)
label | Acceptance criteria:
button | • Is the structure clear of dirt and blemishes? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
section | 3.0 Construction
checkpoint | 3.1 - Fixings
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0433 (Stone Cladding – 3.5)
label | Acceptance criteria:
button | • Have stone cladding fixings been provided as required, sufficient to support, restrain and resist the structural design loads on each cladding panel, as specified? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 3.2 - Adhesives
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0433 (Stone Cladding – 3.5)
label | Acceptance criteria:
button | • Have adhesives been applied where required, as specified? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 3.3 - Installation of cladding
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0433 (Stone Cladding – 3.7)
label | Acceptance criteria:
button | • Has cladding been installed as described in specification, considering given tolerances? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot
checklist | SYM-ITP-020 - PAVING (Rev A) | [5 empty] | SYM-ITP-020 - PAVING (Rev A)
section | 1.0 Preliminaries
checkpoint | 1.1 - Conformity with Drawings
label | Ref docs: TAS-A-AUD-6007-0426 – LANDSCAPE (IFC)
label | Acceptance criteria:
button | • Are the drawings, complete & current? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
holdpoint | HOLD POINT
section | 2.0 Pre-Construction Activities
checkpoint | 2.1 - Survey Set-Out
label | Ref docs: TAS-A-AUD-6007-0426 – LANDSCAPE (IFC)
label | Acceptance criteria:
button | • Have pavers been set-out as per current drawings? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 2.2 - Installation Considerations
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00
label | Acceptance criteria:
button | • Is the concrete slab free of any deposits or rubbish, projections/voids? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
section | 3.0 Construction
checkpoint | 3.1 - Bedding Mortar
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0821 (Mortar)
label | Acceptance criteria:
button | • Has mortar been placed using type/method described in specification? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 3.2 - Cutting Pavers
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0774 (Paving – 3.4)
label | Acceptance criteria:
button | • Where required, have been pavers been cut as described in specification? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 3.3 - Laying Pavers
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0774 (Paving – 3.3)
label | Acceptance criteria:
button | • Have pavers been laid as described in specification, considering specified tolerances? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 3.4 - Sealed Joints
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0774 (Paving – 3.9)
label | Acceptance criteria:
button | • Have joints been sealed as described in specification? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot
checklist | SYM-ITP-021 - Precast Concrete Elements (Rev A) | [5 empty] | SYM-ITP-021 - Precast Concrete Elements (Rev A)
section | 1.0 Preliminaries, Pre-delivery
checkpoint | 1.1 - Suppliers QA
label | Ref docs: VR620 Project Specs
label | Acceptance criteria:
button | • Has the pre-pour check been completed? | Yes,No,N/A
button | • Has the ITP been completed supplied? | Yes,No,N/A
button | • Have the concrete test certificates been supplied? | Yes,No,N/A
button | • Has the certificate of compliance been supplied? | Yes,No,N/A
label | Freq: Upon delivery of Element
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Pre Pour Check
label | • Precast element Supplier ITP
label | • Concrete Test Certificates
label | • Certificate of compliance
checkpoint | 1.2 - Transporting
label | Ref docs: Vicroads 620.08
label | Acceptance criteria:
button | • Has the concrete reached its 28-day compressive strength Prior to Transport and not transported before 7 days after casting? | Yes,No,N/A
button | • Any defects (Cracks, chips, honeycomb etc) identified. | Yes,No,N/A
label | Freq: Upon delivery of Element
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 1.3 - Element Detail
label | Acceptance criteria:
textbox | Precast element/s Reference/Type/s
textbox | Zone
textbox | Stage
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach Pictures
section | 2.0 Installation of Precast Element
checkpoint | 2.1 - Excavation Permit & Penetration Permit & Bedding
label | Ref docs:
label | • SMP
label | • VR 602.03
label | Acceptance criteria:
button | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services. | Yes,No,N/A
button | • Relevant permits have been signed and approved. | Yes,No,N/A
button | • Extents and levels correct to relevant drawings | Yes,No,N/A
button | • 50mm Blinding to be placed as required to allow working surface and protect excavation. | Yes,No,N/A
textbox | Excavation to a total depth of |  |  | mm
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
holdpoint | HOLD POINT
checkpoint | 2.2 - Installation of precast Element and Backfilling
label | Ref docs:
label | • SMP
label | • IFC Drawings
label | Acceptance criteria:
button | • Has survey set out points identified and existing condition of location checked to ensure suitability of install. | Yes,No,N/A
button | • Has the Precast element been constructed in accordance with the IFC drawings? | Yes,No,N/A
button | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour? | Yes,No,N/A
label | Freq: All stages of Install
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SS
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot
checklist | SYM-ITP-024 - Handrails & Balustrades (Rev A) | [5 empty] | SYM-ITP-024 - Handrails & Balustrades (Rev A)
section | 1.0 Handrails & Balustrades
checkpoint | 1.1 - Set Out
label | Ref docs: Civil drawings
label | Acceptance criteria:
button | • Is the work area clearly pegged out for line and level? | Yes,No,N/A
textbox | • Handrail/Balustrade Reference
textbox | • Zone
textbox | • Stage
label | Freq: Prior to the Start of Activity
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint | 1.2 - Conformity with Drawings
label | Ref docs: Civil Drawings
label | Acceptance criteria:
button | • Are the drawings, complete & current? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach Recent IFC Drawings
label | • Attach Shop Drawings
holdpoint | HOLD POINT
checkpoint | 1.3 - Permit &
label | Ref docs: SMP
label | Acceptance criteria:
button | • Relevant permits have been signed and approved. | Yes,No,N/A
button | • Extents and levels correct to relevant drawings | Yes,No,N/A
button | • Are handrails and Balustrades compliant with DDA standards. | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach completed Permit
holdpoint | HOLD POINT
checkpoint | 1.4 - Material compliance
label | Ref docs: QMP
label | Acceptance criteria:
button | • Are handrails and Balustrades compliant with DDA standards. | Yes,No,N/A
checkpoint | 1.5 - Subcontractor ITP
label | Ref docs: QMP
label | Acceptance criteria:
button | • Have the subcontractor ITP’s been completed and attached | Yes,No,N/A
button | • Have handrail and Balustrades been installed as per approved shop drawings? | Yes,No,N/A
button | • All edges smoothed and final finish provided as per project specs? | Yes,No,N/A
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach subcontractor ITP
checkpoint | 1.6 - As Built
label | Acceptance criteria:
button | Were survey as-builts completed | Yes,No,N/A
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach survey Report
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot
checklist-flat | SYM-Proof Roll Record | [5 empty] | SYM-Proof Roll Record
checkpoint-no-status | PROOF ROLL SIGN-OFF
label | Project: Parkville Urban Realm Works
textbox | Lot ID:
textbox | Stage/ Zone:
textbox | Material Type:
textbox | Plant/ Vehicle:
textbox | Date:
textbox | Road Name:
label | Location: Refer Lot map
textbox | Layer Name:
textbox | No. Passes:
checkpoint-no-status | Symal Sign-off
textbox | Date:
textbox | Name:
holdpoint | Symal Sign-off
checkpoint-no-status | CYP D&C JV Sign-off
textbox | Date:
textbox | Name:
holdpoint | CYP D&C JV Sign-off
checkpoint-no-status | Comments:
button | ACCEPTANCE: | Pass,Fail - re-work as required,Pass on condition of: