## ITP007 - Unbound Pavements
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-ITP-001-Subgrade (Rev A) | [5 empty] | SYM-ITP-001-Subgrade (Rev A)
section | 1.0 Preliminaries
checkpoint | 1.1 - Determine lot size
label | Ref docs: Lot map
label | Acceptance criteria:
textbox | • What is the lot size? |  |  | m2
label | • Maximum lot size = 1 days production or 4000m2
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Lot map
holdpoint | WITNESS POINT
checkpoint | 1.2 - Survey set-out
label | Ref docs: VR Clause 204.03 (a)
label | Acceptance criteria:
button | • Has the work area been set out for line and level? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
holdpoint | HOLD POINT
checkpoint | 1.3 - Excavation material classification
label | Ref docs:
label | • VR Clause
label | • 204.06 (c)
label | • 204.04 (b)
label | Acceptance criteria:
button | • Has the material being excavated been inspected with category agreed upon by Superintendent? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Imported material test report
label | • CYP Material Approval
holdpoint | HOLD POINT
checkpoint | 1.4 - Fill material classification
label | Ref docs:
label | • VR Clause 204.06 (c)
label | • 204.04 (b)
label | • IFC Drawings
label | Acceptance criteria:
button | • Has the material to be used been approved by CYP D&C JV? | Yes,No,N/A
label | Freq: Per material
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Imported material test report
label | • CYP Material Approval
holdpoint | HOLD POINT
checkpoint | 1.5 - Water management
label | Ref docs: VR Clause 204.06 (b)
label | Acceptance criteria:
button | • Where necessary, have batters been rounded and catch drains constructed to allow for potential surface runoff during the course of excavation? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: PE
checkpoint | 1.6 - Stage/ Zone
label | Ref docs: Site Layout
label | Acceptance criteria:
label | • 1A / 1B/ 1C/ 1D / 1E / 1F / 1G / 2A / 2B / 2C / 2D / 2E / 2F / 2G / 3A / 3B / 3C / 4A / 4B / 4C / 5A / 5B / 5D / 6A / 6B
textbox | Stage
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Lot map
checkpoint-no-status | Is the area in cut / fill / both?
label | If in cut proceed to step 2.0 and strike out section 3.0.
label | If in fill please strike out section 2.0 and proceed to section 3.0
label | If in both proceed to step 2.0 as well as section 3.0
section | 2.0 Bulk earthworks - cut
checkpoint | 2.1 - Subgrade preparation
label | Ref docs: VR Clause 204.06
label | Acceptance criteria:
button | • Has the cut surface been trimmed to an even surface free from lose material? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Site photos
holdpoint | WITNESS POINT
checkpoint | 2.2 - Groundwater/ seepage (if applicable)
label | Ref docs: VR Clause 204.06 (h)
label | Acceptance criteria:
label | • If groundwater or seepage is encountered, notify the Superintendent and create a course of proposed action.
label | • Submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
button | • Approval to proceed? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Dewatering permit (if applicable)
holdpoint | WITNESS POINT
checkpoint | 2.3 - Treatment of Cut
label | Ref docs:
label | • VR Clause
label | • 204.06 (e)(ii)
label | • 204.10 (b)
label | • 204.12
label | Acceptance criteria:
label | • The in-situ material shall be ripped to a minimum depth of 150 mm, loosened and broken down to a maximum particle size of 50 mm. Any rocks or boulders larger than 50 mm shall be removed and any resulting depression shall be backfilled with approved material and such backfilling together with the loosened material shall be reworked and compacted as specified to the Cut Floor Level in preparation for test rolling.
button | • Has all of the above been completed? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
holdpoint | WITNESS POINT
checkpoint | 2.4 - Compaction
label | Ref docs:
label | • VR Clause
label | • 204.13
label | • 204.13 (b)
label | • 204.15
label | • 173.04
label | Acceptance criteria:
label | • Compaction Scale B, CBR and Swell Testing per lot (3 tests per lot).
button | • Has the subgrade been adequately compacted achieving a mean value density ratio of 98% Standard? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Test reports
holdpoint | HOLD POINT
checkpoint | 2.5 - Test Rolling of prepared subgrade
label | Ref docs: VR Clause 173.03
label | Acceptance criteria:
button | • Does the layer withstand test rolling without visible deformation or springing? | Yes,No,N/A
label | • If ‘no’ please see below.
label | • If ‘yes’ please proceed
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Proof roll report
holdpoint | HOLD POINT
checkpoint | 2.6 - Identification of soft wet or unstable material
label | Ref docs: VR Clause 204.07
label | Acceptance criteria:
textbox | • What quantity of soft, wet or unstable material is present? |  |  | m3
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Survey report of area
checkpoint | 2.7 - Treatment of unsuitable material
label | Ref docs: VR Clause 204.07(d)
label | Acceptance criteria:
button | • Has rectification process been submitted to the Superintendent for review? | Yes,No,N/A
textbox | • What was the rectification process used?
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Rectification process
holdpoint | HOLD POINT
checkpoint | 2.8 - Maintenance of Cut Floor Level
label | Ref docs:
label | • VR Clause
label | • 204.15
label | • 204.03
label | Acceptance criteria:
label | • Visual inspection to confirm that surface is a smooth, hard, tightly bound surface, free from depressions capable of holding water.
label | • Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of optimum moisture content prior to the placement of any pavement layer.
button | • Has all of the above been completed? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Site photos
holdpoint | WITNESS POINT
section | 3.0 Bulk earthworks - fill
checkpoint | 3.1 - Stripped surface - test rolling (If applicable)
label | Ref docs:
label | • VR Clause
label | • 173.03
label | • 204.10
label | Acceptance criteria:
button | • Does the stripped surface to be filled withstand test rolling without visible deformation or springing? | Yes,No,N/A
label | • If ‘no’ please see below.
label | • If ‘yes’ please proceed to item 3.2
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Material report
label | • Proof roll report
holdpoint | HOLD POINT
checkpoint | 3.2 - Identification of soft wet or unstable material
label | Ref docs: VR Clause 204.07
label | Acceptance criteria:
textbox | • What quantity of soft, wet or unstable material is present? |  |  | m3
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Survey report of area
checkpoint | 3.3 - Treatment of unsuitable material
label | Ref docs: VR Clause 204.07(d)
label | Acceptance criteria:
button | • Has rectification process been submitted to the Superintendent for review? | Yes,No,N/A
textbox | • What was the rectification process used?
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Rectification process
holdpoint | HOLD POINT
checkpoint | 3.4 - Preparation of surface
label | Ref docs: VR Clause 204.13(B)
label | Acceptance criteria:
button | • Has adequate water been added to the stripped surface to ensure adhesion to the next layer? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
checkpoint | 3.5 - Fill Placement
label | Ref docs: VR Clause 204.10
label | Acceptance criteria:
button | • Has fill been placed in maximum 200mm compacted layer thickness? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • As built report
checkpoint | 3.6 - Moisture
label | Ref docs: VR Clause 204.13(B)
label | Acceptance criteria:
button | • Has the material maintained at optimum moisture content (>80%), with additional water being added if required during compaction? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Test reports
holdpoint | WITNESS POINT
checkpoint | 3.7 - Compaction
label | Ref docs: VR Clause 204.13
label | Acceptance criteria:
label | • Compaction Scale B (6 tests per lot)
button | • Has the layer been adequately compacted achieving a mean value density ratio of 98% Standard? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Test reports
holdpoint | WITNESS POINT
checkpoint | 3.8 - Material properties testing
label | Ref docs:
label | • VR Clause
label | • 204.04
label | • Table 204.041
label | • 204.14
label | Acceptance criteria:
label | • Has the material properties testing (CBR / Swell / Grading / PI / LL / Permeability) been undertaken for the first lot of material placement and satisfies the VicRoads requirements as per Table 204.041?
button | • If the first lot of each fill satisfies the specified post compaction requirements, every second lot of like material and work will be tested | Yes,No,N/A
label | Freq: Per material
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Test reports
holdpoint | HOLD POINT
checkpoint | 3.9 - Fill layer – test rolling
label | Ref docs:
label | • VR Clause
label | • 173.03
label | • 204.10
label | Acceptance criteria:
button | • Does the layer withstand test rolling without visible deformation or springing? | Yes,No,N/A
label | • If ‘no’ please see below
label | • If ‘yes’ please proceed to fill construction
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Proof roll report
holdpoint | HOLD POINT
checkpoint | 3.10 - Identification of soft wet or unstable material
label | Ref docs: VR Clause 204.07
label | Acceptance criteria:
textbox | • What quantity of soft, wet or unstable material is present? |  |  | m3
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Survey report of area
checkpoint | 3.11 - Treatment of unsuitable material
label | Ref docs: VR Clause 204.07(d)
label | Acceptance criteria:
button | • Has rectification process been submitted to the Superintendent for review? | Yes,No,N/A
textbox | • What was the rectification process used?
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Rectification process
holdpoint | HOLD POINT
section | 4.0 Conformance check
checkpoint | 4.1 - Width and alignment
label | Ref docs:
label | • VR Clause
label | • 204.03
label | • IFC drawings
label | Acceptance criteria:
button | • Has the pavement been constructed at the correct width and alignment as detailed in the construction drawings? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • As built report
holdpoint | WITNESS POINT
checkpoint | 4.2 - Subgrade level and shape
label | Ref docs:
label | • VR Clause
label | • 204.03
label | • IFC drawings
label | Acceptance criteria:
label | • Has the prepared subgrade been surveyed in accordance with and verifying specified requirements?
button | • Mean Range: +5mm to -25mm Standard Deviation: Maximum 15mm | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • As built report
holdpoint | WITNESS POINT
checkpoint | 4.3 - Test Reports
label | Ref docs: VR Clause 204.14
label | Acceptance criteria:
button | • All Test reports received and reviewed. | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • NATA Endorsed Test Reports
holdpoint | WITNESS POINT
checkpoint | 4.4 - Product non-conformance
label | Acceptance criteria:
button | • All Product Non-Conformance(s) recorded and closed (if applicable) | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Completed NCR form
holdpoint | WITNESS POINT
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot