## ITP007 - Unbound Pavements
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-ITP-002 - Flexible Pavements (Rev A) | [5 empty] | SYM-ITP-002 - Flexible Pavements (Rev A)
section | 1.0 Preliminaries
checkpoint | 1.1 - Survey Set-out
label | Ref docs: IFC Drawings
label | Acceptance criteria:
button | • Has the work area been set out for line and level? | Yes,No,N/A
label | Freq: Prior to start of Works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
holdpoint | HOLD POINT
checkpoint | 1.2 - Conformance of Previous layer
label | Ref docs: VR Clause 304.04
label | Acceptance criteria:
label | • Has the previous layer passed acceptance criteria?
button | • Approval to proceed? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Survey Conformance Certificate
label | • ITP & Test Reports
holdpoint | HOLD POINT
checkpoint | 1.3 - Material classification and source
label | Ref docs:
label | • VR Clause 304.03
label | • 811
label | • 812
label | • IFC Drawings
label | Acceptance criteria:
button | • Is the correct material being used? | Class 2,Class 3,CTCR
button | • Has the material to be used been approved for use (Material certificates to be provided)? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • CYP D&C JV Materials Approval
holdpoint | HOLD POINT
checkpoint | 1.4 - Determine lot size
label | Ref docs: VR Clause 304.111
label | Acceptance criteria:
textbox | • What is the lot size? |  |  | m2
label | • Maximum lot size = 1 days production or 4000m2
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Lot map
holdpoint | HOLD POINT
section | 2.0 Pavement Construction
checkpoint | 2.1 - Layer classification
label | Ref docs:
label | • VR Clause 304
label | • IFC Drawings
label | Acceptance criteria:
button | • Is the pavement intended to be Lower Subbase or Upper Subbase? | Lower subbase,Subbase,Base
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
checkpoint | 2.2 - Construction - Jointing
label | Ref docs: VR Clause 304.07
label | Acceptance criteria:
label | • Transverse - Offset by not less than 2 m to any underlying pavement layers.
label | • Longitudinal - Offset by not less than 150 mm to any underlying pavement layers. Located within 300 mm of the traffic lane lines or within 300 mm of the centre of a traffic lane.
button | • Has all of the above been completed correctly and to a high standard? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Construction photos
holdpoint | WITNESS POINT
checkpoint | 2.3 - Placement of Material
label | Ref docs:
label | • VR Clause 304.06
label | • IFC Drawings
label | Acceptance criteria:
label | • Place and compact layers so that the surface finish is smooth and uniform.
label | • The width of each side of the pavement shall not be less than the specified offset width or more than 50 mm outside the specified offset width when measured at right angles from the centre line or design line.
label | • No point > 8 mm below a 3 m straight edge in any direction
label | • No point >10 mm below a 6 m straight edge in any direction
button | • Has all of the above been completed correctly, to a high standard and approved? | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: I
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Construction photos
checkpoint | 2.4 - Moisture
label | Ref docs: VR Clause 304.08(a)
label | Acceptance criteria:
button | • Has the material maintained at optimum moisture content (>85%), with additional water being added if required during compaction? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: I
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Test report
checkpoint | 2.5 - Testing – Stability (Proof Roll)
label | Ref docs: VR Clause 304.08(b)
label | Acceptance criteria:
label | • Area shall withstand test rolling without visible deformation or springing.
button | • Has all of the above been completed correctly, to a high standard and approved by relevant authority? | Yes,No,N/A
label | • If ‘no’ please see below
label | • If ‘yes’ please proceed to 2.7
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Proof roll report
holdpoint | HOLD POINT
checkpoint | 2.6 - Identification of soft wet or unstable material
label | Ref docs: VR Clause 304.08
label | Acceptance criteria:
textbox | • What quantity of soft, wet or unstable material is present? (m2) | m2
textbox | • What quantity of soft, wet or unstable material is present? (m3) | m3
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Survey report
checkpoint | 2.7 - Treatment of unsuitable material (Testing of material to be agreed on site)
label | Ref docs: VR Clause 304.08
label | Acceptance criteria:
button | • Has rectification process been submitted to VicRoads for Review? | Yes,No,N/A
textbox | • What was the rectification process used?
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Proof roll report
holdpoint | HOLD POINT
checkpoint | 2.8 - Protection of compacted layer
label | Ref docs: VR Clause 304.09
label | Acceptance criteria:
label | • Surface of each compacted layer in good order/condition & free from contamination until the subsequent pavement work is to commence.
button | • Has all of the above been completed? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: I
label | Symal Infrastructure - Resp: SE
section | 3.0 Testing
checkpoint | 3.1 - Testing – Compaction
label | Ref docs:
label | • VR Clause 304.08(b)
label | • 304.10
label | • 304.11
label | • Table 304.111
label | Acceptance criteria:
label | • Characteristic Density Ratio % (six tests per lot): Not less than 98.0% Modified (Scale A)
label | • Characteristic Density Ratio % (six tests per lot): Not less than 97.0% Modified (Scale B)
label | • For layer directly beneath bituminous surface, not less than 100.0 for scale A and 98.0 for scale B
button | • Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No,N/A
label | Freq: As required by section 3.2
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: R
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • NATA Test Report
checkpoint | 3.2 - Testing – Reduced Frequency
label | Ref docs:
label | • VR Clause 304.11
label | • Table 304.111
label | Acceptance criteria:
label | • Test every lot for acceptance until three consecutive lot of like material and/or work have passed the requirements.
label | • For Subbase, one Characteristic Density Ration % (six tests) will be completed for every second lot.
label | • Testing will be completed at the minimum frequency until such time as a lot fails to achieve the specified requirements. After a failed result, all subsequent lots will be tested until three consecutive lots of like material and work have achieved the specified standard, at which time the frequency of testing may revert to the minimum frequency
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: R
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
textbox | • If using reduced frequency, provide lot number of previous lot tested:
section | 4.0 Completion
checkpoint | 4.1 - Survey as built
label | Ref docs:
label | • VR Clause 304.06
label | • Table 304.061
label | • Table 304.062
label | Acceptance criteria:
label | • Surface after completion shall be smooth and uniform, free of segmented areas and conforming to grade, thickness and cross-section shown on the drawings.
label | • Surface level checked for compliance with 304.06:
label | ○ Mean +6 mm to -10 mm with a max std deviation of 10 mm (Scale A)
label | ○ Min 80 measurements per lot (Scale A)
label | ○ Mean +8 mm to -16 mm with a max std deviation of 15 mm (Scale B)
label | ○ Min 40 measurements per lot (Scale B)
button | • Has all of the above been proven to meet and/or exceed requirements set out in contract? | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Survey Conformance Certificate
section | 5.0 Work Lot Close Out
checkpoint | 5.1 - Test Reports
label | Ref docs: VR Clause 304
label | Acceptance criteria:
label | • All Test reports received and Reviewed as per Requirements for Testing and Acceptance of Surface Level Measurement, Compaction and Post-compaction Gradings and PIs (Clauses 304.06, 304.08, 304.10 and 304.11)
button | • Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • NATA Endorsed Test Reports | Yes,No,N/A
checkpoint | 5.2 - Product Non-Conformance
label | Ref docs: CMP
label | Acceptance criteria:
label | • All Product Non-Conformance(s) recorded and closed (if applicable)
button | • Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • NCR reports | Yes,No,N/A
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot