## ITP007 - Unbound Pavements
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | [5 empty] | SYM-ITP-003 - Asphalt Placement 1 (Rev A)
section | 1.0 Pre-start activities
checkpoint | 1.1 - Determine lot size
label | Acceptance criteria:
textbox | • What is the lot size? |  |  | m2
label | • Maximum Lot Size = per days production
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Lot map
checkpoint | 1.2 - Asphalt Mix Designs Approval and Compliance
label | Ref docs: VR Clause 407.05 to 407.10
label | Acceptance criteria:
button | • Is the asphalt mix design considered “General” and does it conform with VicRoads Section 407? Has mix design been approved by CYP D&C JV? | Yes,No,N/A
label | Freq: Each possession
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Mix Design Approval
textbox | • Aconex Reference No
holdpoint | HOLD POINT
checkpoint | 1.3 - Conformance of previous layer
label | Acceptance criteria:
button | • Has the previous layer passed acceptance criteria? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
textbox | • Lot reference no:
holdpoint | HOLD POINT
checkpoint | 1.4 - Temperature conditions
label | Ref docs: VR Clause 407.13
label | Acceptance criteria:
button | • For intermediate and base courses surface to be above 5 degrees Celsius. For wearing course installation, surface to be greater then 10 degrees Celsius. Has the above criteria been met? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
holdpoint | HOLD POINT
checkpoint | 1.5 - Existing pit levels
label | Ref docs: VR Clause 407.14
label | Acceptance criteria:
button | • Have the existing pits been raised/lowered to meet the surface level of Asphalt? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
holdpoint | HOLD POINT
section | 2.0 Hot Mix Asphalt Installation
checkpoint | 2.1 - Commencement of Placing
label | Ref docs: VR Clause 407.18
label | Acceptance criteria:
label | • The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until approval to proceed is obtained from CYP D&C JV.
button | • Approval to proceed? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
holdpoint | HOLD POINT
checkpoint | 2.2 - Construction - Jointing
label | Ref docs: VR Clause 407.17
label | Acceptance criteria:
label | • All transverse joints shall be offset from layer to layer by at least 2 m.
label | • Longitudinal joints in the wearing course shall coincide with the location of intended traffic lane lines.
label | • Longitudinal joints in intermediate and base courses shall be offset from layer to layer by not less than 150 mm and shall be within 300 mm of the traffic lane line or the centre of traffic lane.
label | • Where new pavement abuts an existing full depth asphalt pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150 mm.
button | • Has all of the above been completed? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: I
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: I
checkpoint | 2.3 - Matching Existing Pavement Surface at Junctions
label | Ref docs: VR Clause 407.17 (d)
label | Acceptance criteria:
label | • At junctions where the new asphalt mat is required to match the level of existing pavement surface at the limits of work, chases shall be cut into the existing pavement by cold planing as specified in Section 402.
button | • Does new Asphalt Layer match the existing pavement surface with chases cut? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: I
label | Symal Infrastructure - Resp: SE
checkpoint | 2.4 - Paving and Compaction of Asphalt
label | Ref docs:
label | • VR Clause 407.20
label | • IFC Drawings
label | Acceptance criteria:
label | • Asphalt shall be spread in layers at the compacted thicknesses shown on the drawings or specified.
label | • Asphalt shall be uniformly compacted Compaction shall not commence until the asphalt has cooled sufficiently to support the rollers without undue displacement.
button | • Has all of the above been completed? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: I
label | Symal Infrastructure - Resp: SE
section | 3.0 Completion and Compliance
checkpoint | 3.1 - Compaction Testing – Six Tests
label | Ref docs: VR Clause Table 407.221
label | Acceptance criteria:
label | • Thickness < 50 mm: 94.0% Characteristic Density Ratio
label | • Thickness > 50mm: 96.0% Characteristic Density Ratio
button | • Has testing been completed and report received? Do results match requirements? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • NATA Test Report: Compaction Tests
checkpoint | 3.2 - Finished Surface Levels
label | Ref docs:
label | • VR Clause 407.23
label | • Table 407.231
label | • Table 407.232
label | Acceptance criteria:
label | • The mean surface level and the variation in surface level for the base, intermediate and wearing courses within each lot shall meet the requirements (mean +/- 5mm, standard deviation 8mm)
label | • Rectification of surface levels shall not commence until approval to proceed is obtained from the Superintendent.
button | • Is finished surface level acceptable and survey conformance report received? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Conformance Report (Finished surface level and thickness)
holdpoint | HOLD POINT
checkpoint | 3.3 - Finish Surface/Shape
label | Ref docs:
label | • VR Clause 407.23 (a)
label | • IFC Drawings
label | Acceptance criteria:
label | • Surface finish - Uniform in appearance, free of dragged areas, cracks, open textured patches, and roller marks.
label | • Kerb & Channel - Flush or not more than 5mm above lip of channel
label | • Shape – For intermediate and base course layers, the distance below the straight edge shall not exceed 6 mm and 10 mm, respectively.
label | • Alignment - Where asphalt pavement is not placed against a concrete edging, the edge of asphalt layers shall not be more than 50 mm inside nor more than 100 mm outside.
label | • Width - Where asphalt pavement is not placed against a concrete edging, the width of asphalt layers shall not be less than the design or specified width of layer by more than 50 mm or greater than the design or specified width by more than 100 mm.
button | • Have the above requirements been met and surface is acceptable? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Site photos
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot