## ITP007 - Unbound Pavements
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-ITP-004 - Underscreed Concrete Pavement (Rev A) | [5 empty] | SYM-ITP-004 - Underscreed Concrete Pavement (Rev A)
section | 1.0 Preliminaries
checkpoint | 1.1 - Concrete mix design approval
label | Ref docs:
label | • VR703.01
label | • VR703.05
label | • AS 1379
label | Acceptance criteria:
button | • Concrete mix design approved by the Superintendent and a registered mix and Material properties meet project specifications | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | CYP D&C JV - Key: H
holdpoint | HOLD POINT
checkpoint | 1.2 - Concrete Grade
label | Ref docs: Project Specs
label | Acceptance criteria:
textbox | • Concrete Strength |  |  | MPA
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | CYP D&C JV - Key: H
holdpoint | HOLD POINT
checkpoint | 1.3 - Conformity with Drawings
label | Ref docs: VR Clause 701.10
label | Acceptance criteria:
button | • Are the drawings, complete & current? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach Recent IFC Drawings
holdpoint | HOLD POINT
checkpoint | 1.4 - Setting Out
label | Ref docs:
label | • VR703.17
label | • VR703.15
label | Acceptance criteria:
button | • Is the work area clearly pegged out for line and level? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SS
label | CYP D&C JV - Key: H
holdpoint | HOLD POINT
checkpoint | 1.5 - Bedding Preparation
label | Ref docs:
label | • VR703.20/703.21
label | • VR204.13
label | • VR304.08
label | Acceptance criteria:
label | • Is edging constructed over Pavement layer?
button | • Where edgings are constructed over pavement layers, bedding shall be provided between the pavement layer and the underside of the edging, or the edging thickened to match the pavement layer. | Yes,No,N/A
button | • Is bedding for footpaths and surfaces compacted to 100mm thickness unless noted otherwise. | Yes,No,N/A
button | • Is bedding for SUPs, bedding compacted to 150mm thick unless noted otherwise. | Yes,No,N/A
button | • Bedding shall be moist but shall have no free water on the surface before concrete is placed | Yes,No,N/A
button | • Is bedding material used for cast in place concrete paving works compacted size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively. | Yes,No,N/A
button | • Is bedding material for shared use paths compacted size 20 mm Class 3 crushed rock or Class 3 crushed concrete in accordance with Section 812 or 820 respectively, and Section 304. | Yes,No,N/A
button | • Are pavement lots tested for compliance with the specified compaction scale for moisture content no less than 85% | Yes,No,N/A
button | • Is fill material used below bedding tested to Table 204.131 Compaction Requirements | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 1.5 - Provision for Permanent Signs
label | Ref docs: VR703
label | Acceptance criteria:
button | • Have sign post sockets been supplied & placed for erection of permanent signs in the areas to be paved as per VR703.22. | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 1.6 - Relevant Permits Required
label | Acceptance criteria:
button | • Relevant permits have been signed and approved. | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
checkpoint | 1.7 - Excavation
label | Ref docs: IFC Drawings
label | Acceptance criteria:
textbox | • Excavation to a total depth of |  |  | mm
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
checkpoint | 1.8 - Sub-Base Course
label | Ref docs: IFC Drawings
label | Acceptance criteria:
textbox | • mm layer of __mm
textbox | • Class __ crushed rock or crushed concrete placed?
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
section | 2.0 Under screed/Concrete Pavement
checkpoint | 2.1 - Formwork
label | Ref docs: VR703.12
label | Acceptance criteria:
button | • Formwork has been installed correctly and sufficiently braced. | Yes,No,N/A
button | • Formwork set out has been done as per latest design drawings and specifications | Yes,No,N/A
button | • Were Construction joints/Expansion Joints/Isolation Joints /or any type of joint as specified in the drawings Installed | Yes,No,N/A
button | • Installations of Cast-Ins/ HD bolts/ Chemical Anchors/Block out Verified/Sockets | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
holdpoint | HOLD POINT
checkpoint | 2.2 - Steel Reinforcement
label | Ref docs:
label | • VR703.13
label | • AS/NZS 4671
label | • AS/ZNS 4680
label | • AS3600
label | • VR703.16
label | Acceptance criteria:
button | • Mesh installed with 40mm top and sides cover and 50 mm Bottom Cover | Yes,No,N/A
button | • Tolerance - As per specifications and Australian Standard | Yes,No,N/A
button | • Steel is free of excess corrosion, loose millings, oil or other contaminants | Yes,No,N/A
button | • Required Connection Details - U Bars/ Z Bars/Cogs/Starter bars Verified | Yes,No,N/A
button | • Correct concrete cover and chairs on sides, bottom and top Verified | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SS
checkpoint | 2.3 - Pre-Pour Inspection
label | Ref docs: IFC Drawings/QMP
label | Acceptance criteria:
button | • Has steel reinforcement been placed correctly with adequate cover? | Yes,No,N/A
button | • Have tie bars and joints been installed at the correct intervals? | Yes,No,N/A
button | • Pour area is free of loose debris, oils, water | Yes,No,N/A
button | • Have any services/penetrations/blockout located within the Pavements been installed, surveyed and pinned down | Yes,No,N/A
button | • Concrete Testing Lab Representative will be available during concrete pour | Yes,No,N/A
button | • Sufficient vibrators are available during concrete pour | Yes,No,N/A
button | • CYP D&C JV informed of concrete pour date and start time | Yes,No,N/A
label | Freq: Prior to start of Concrete Placement
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SS
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach subcontractor ITPs
holdpoint | HOLD POINT
checkpoint | 2.4 - Placing, compacting and finishing concrete
label | Ref docs:
label | • VR610.10/610.13
label | • VR610.18
label | • VR703.08
label | Acceptance criteria:
button | • Is concrete temperature as per VR703. and not mixed when the air temperature is lower than 5°C or greater than 35°C. | Yes,No,N/A
button | • Is discharge Time 60 minutes unless mix design is approved by Proof Engineer for 90 minutes. | Yes,No,N/A
button | • Is concrete thoroughly compacted and works carried out as per Australian Standard & Project Drawings/ Specifications | Yes,No,N/A
button | • Are concrete samples taken in accordance with 610.16(b). | Yes,No,N/A
button | • Is specified slump tolerance within 610.16(c). | Yes,No,N/A
button | • Is concrete mixed for not less than a period of three (3) minutes prior to discharge. | Yes,No,N/A
button | • Is the maximum time lag between truck loads on site shall not exceeding 25 minutes if a continuous pour | Yes,No,N/A
button | • A minimum of one of vibrator used at all times while the concreting is in operation | Yes,No,N/A
button | • Were forms/cast in items monitored during the pour. | Yes,No,N/A
button | • Concrete Dockets Received | Yes,No,N/A
textbox | • Concrete quantity |  |  | M3
textbox | • Pour date
button | • Concrete Fall achieved as per latest IFC drawings | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • Concrete pour record attached | Yes,No
button | • Concrete test results attached. | Yes,No
holdpoint | HOLD POINT
section | 3.0 Post Pour/ Finishing
checkpoint | 4.6 - Post Pour
label | Ref docs: VR703.25
label | Acceptance criteria:
button | • Did concrete achieve the required finish as per specifications | Yes,No,N/A
button | • Are hidden concrete surfaces of concrete paving have a Class 4 surface finish in accordance with AS 3610. | Yes,No,N/A
button | • Curing agent applies as per project specifications | Yes,No,N/A
button | • Concrete reached design strength to strip formwork. (Attach test results) | Yes,No,N/A
button | • Any identified defects after stripping rectified | Yes,No,N/A
button | • Were expansion joints placed at intervals less than 10m. | Yes,No,N/A
button | • As Built Survey completed and report attached. | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • Concrete test results attached. | Yes,No
checkpoint | 4.10 - Backfilling
label | Ref docs: VR703.29
label | Acceptance criteria:
button | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour? | Yes,No,N/A
button | • Were the positions of any existing conduits passing under edgings marked by a chase in the edging immediately above the conduit together with a suitable identification mark. | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE/PE
section | 5.0 Completion
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot