## ITP007 - Unbound Pavements
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-ITP-005 - Insitu Kerb and Channel (Rev A) | [5 empty] | SYM-ITP-005 - Insitu Kerb and Channel (Rev A)
section | 1.0 Pre-start activities
checkpoint | 1.1 - Determine lot size
label | Ref docs: Lot map
label | Acceptance criteria:
label | • One lot per days production. To be marked up on lot map.
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Lot map
holdpoint | WITNESS POINT
checkpoint | 1.2 - Concrete mix design approvals
label | Ref docs:
label | • VR Clause 703.05 (b)
label | • 703.11
label | Acceptance criteria:
label | • Concrete used in kerb extrusion machines shall have a minimum cementitious material content in the finished concrete as follows:
label | ○ A minimum of 320 kg of cementitious material for traffic routes
label | ○ A minimum of 280kg of cementitious material for local streets
button | • Concrete mix designs approved by CYP D&C JV? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Delivery Dockets: Concrete
label | • CYP Material Approval
holdpoint | HOLD POINT
checkpoint | 1.3 - Survey set out
label | Ref docs:
label | • VR Clause 703.17
label | • IFC Drawings
label | Acceptance criteria:
label | • All works shall be set out in accordance with the drawings and as specified.
label | • The Superintendent will review and confirm the set out. The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
holdpoint | HOLD POINT
section | 2.0 Construction
checkpoint | 2.1 - Machine extrusion
label | Ref docs: VR Clause 703.23
label | Acceptance criteria:
label | • Concrete shall be fed to the machine at a uniform rate. Surfaces shall be free from surface pitting larger than 5 mm diameter.
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Site photos
checkpoint | 2.2 - Profile transitions and matching existing sections
label | Ref docs:
label | • VR Clause 703.24
label | • SD2102
label | Acceptance criteria:
label | • Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre. Transitions between different profiles shall be made in accordance with the drawings.
button | • Are the profile transitions acceptable? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
checkpoint | 2.3 - Surface Finish
label | Ref docs: VR Clause 703.25
label | Acceptance criteria:
label | • All edgings shall be rendered and have a steel trowel finish. Visible concrete surfaces to have class 3 finish. Hidden surfaces may have a class 4 finish.
button | • Is the surface finish acceptable? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: I
label | Symal Infrastructure - Resp: SE
checkpoint | 2.4 - Joints
label | Ref docs: VR Clause 703.26
label | Acceptance criteria:
label | • Transverse joints shall be constructed at regular intervals not exceeding 2.5 m. The resultant slot in the edging shall be tooled to a depth of 20 mm to produce a neat groove not less than 5 mm wide on the exposed surfaces.
label | • Expansion joints shall be placed at junctions with bridges and shall be 15 mm wide and filled with cork or bituminous impregnated particle board strip extending for the full width and full depth of the edging.
button | • Are joints installed and comply with all specifications? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
checkpoint | 2.5 - Curing & Protection of Concrete
label | Ref docs:
label | • VR Clause 703.10
label | • 703.27
label | Acceptance criteria:
label | • Freshly finished exposed concrete surfaces shall be protected from rain or damage from other sources, until hard set has occurred.
label | • All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
button | • Are finished curbs protected and free from damage? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
checkpoint | 2.6 - Repair of damaged kerb and channel
label | Ref docs: VR Clause 703.30
label | Acceptance criteria:
label | • For damaged kerb and channel and edgings, a length of at least 1 m shall be removed and the replacement section shall be:
label | (a) constructed on compacted bedding;
label | (b) dowelled into the adjoining sections with 12 mm diameter hot dip galvanised dowels embedded at least 100 mm each side of the joint; and
label | (c) shaped and finished with curved trowels to match the profile and surface finish of adjoining sections
button | • Is all damage to curbs repaired in line with specifications? | Yes,No,N/A
label | Freq: Each lot (if required)
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: I
label | Symal Infrastructure - Resp: SE
section | 3.0 Completion
checkpoint | 3.1 - As Built Survey
label | Ref docs: VR Clause 703.15
label | Acceptance criteria:
label | • Concrete paving including footpaths, edgings, other surfaces and shared use paths shall be shaped to match existing fixtures, e.g. pit covers, edgings and vehicle crossings, within 5 mm.
label | • Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of 0 to +10 mm. Except on curves or in shaped areas, the deviation of the finished work from a 3 m straightedge shall not exceed 5 mm at any point.
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: R
checkpoint | 3.2 - Product Non-Conformance
label | Ref docs: QMP
label | Acceptance criteria:
label | • All Product Non-Conformance(s) recorded and closed (if applicable)
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
textbox | • NCR No:
label | • NCR reports
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot