## ITP007 - Unbound Pavements
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-ITP-006 - STORMWATER (Rev A) | [5 empty] | SYM-ITP-006 - STORMWATER (Rev A)
section | 1.0 Pre-start activities
checkpoint | 1.1 - Conformity with Drawings
label | Ref docs: VR Clause 701.10
label | Acceptance criteria:
button | • Are the drawings, complete & current? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | CYP D&C JV - Key: H
label | CYP D&C JV - Sign/Date: PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach Recent IFC Drawings
holdpoint | HOLD POINT
checkpoint | 1.2 - Define Work Lot
label | Ref docs:
label | • VR Clause 173.02
label | • 701.20
label | • 701.10
label | • IFC Drawings
label | Acceptance criteria:
label | • Lot shall be defined from pit to pit (or endwall, where applicable).
button | • Do survey boundaries clearly define the Underground Drainage Construction works? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | CYP D&C JV - Key: H
label | CYP D&C JV - Sign/Date: PE
holdpoint | HOLD POINT
checkpoint | 1.3 - Acceptance of Box Culverts
label | Ref docs:
label | • VR Clause 619.22
label | • IFC Drawings
label | Acceptance criteria:
button | • Is the Box Culvert free of defects and to drawing dimensions? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | CYP D&C JV - Key: H
label | CYP D&C JV - Sign/Date: PE
holdpoint | HOLD POINT
checkpoint | 1.4 - Acceptance of Precast Reinforced Concrete/HDPE Pipes
label | Ref docs:
label | • VR Clause 701.05
label | • 701.05(e)
label | • 701.31(a)
label | • IFC Drawing
label | Acceptance criteria:
button | • Is the Pipes free of defects and to drawing dimensions? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | CYP D&C JV - Key: H
label | CYP D&C JV - Sign/Date: PE
holdpoint | HOLD POINT
checkpoint | 1.5 - Acceptance of Precast Covers, Grates, Lids and Pits
label | Ref docs:
label | VR Clause 705.04
label | (a)(ii)
label | 705.04
label | (d)
label | 705.07
label | • IFC Drawings
label | Acceptance criteria:
button | • Have proposed precast Covers, Grates, Lids and Pits been approved for use? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | CYP D&C JV - Key: H
label | CYP D&C JV - Sign/Date: PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • Shop Cards | Yes,No
holdpoint | HOLD POINT
checkpoint | 1.6 - Bedding and Backfill Materials
label | Ref docs:
label | • VR Clause 701.09(e)
label | • Table 701.091
label | • Table 701.092
label | Acceptance criteria:
button | • Is material free from perishable matter and lumps? | Yes,No,N/A
button | • Does the material comply with Table 701.091 & Table 701.092 below? Has the material been approved for use? | Yes,No,N/A
label | --------------------------------------------------------------------------------------------------------------
label | Table 701.091
label | Material ¦¦ Sieve - AS (mm) 75.0, 37.5, 19.0, 2.36, 0.075 :: Percentage Passing (by mass)
label | --------------------------------------------------------------------------------------------------------------
label | Bedding ¦¦ 19.0 :: 100 / 0.075 :: 5-40
label | Selected Backfill ¦¦ 37.5 :: 100 / 0.075 :: 5-40
label | Ordinary Backfill ¦¦ 75.0 :: 100 / 2.36 :: 40-100
label | --------------------------------------------------------------------------------------------------------------
label | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
label | --------------------------------------------------------------------------------------------------------------
label | Table 701.092
label | Test ¦¦ Test Value
label | --------------------------------------------------------------------------------------------------------------
label | Plasticity Index (Max.) ¦¦ 20
label | --------------------------------------------------------------------------------------------------------------
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
label | CYP D&C JV - Key: H
label | CYP D&C JV - Sign/Date: PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • Bedding and Backfill Material Conformance | Yes,No
holdpoint | HOLD POINT
checkpoint | 1.7 - Pipe/Box Culver/PIT Size & Class
label | Acceptance criteria:
textbox | • SIZE
textbox | • CLASS
textbox | • DIA = 150 / 225 / 300 / 375 / 450 / 525 / 1050
textbox | • PIT REF
textbox | • PIT REF
textbox | • PIT REF
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
checkpoint | 1.8 - Stage/Zone
label | Ref docs: Site Layout
label | Acceptance criteria:
label | • 1A / 1B/ 1C/ 1D / 1E / 1F / 1G / 2A / 2B / 2C / 2D / 2E / 2F / 2G / 3A / 3B / 3C / 4A / 4B / 4C / 5A / 5B / 5D / 6A / 6B
textbox | • STAGE
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
section | 2.0 Excavation
checkpoint | 2.1 - Excavation of Trench Pipes/Culverts
label | Ref docs:
label | • VR Clause 701.15
label | • Table 701.151
label | • 701.08
label | Acceptance criteria:
button | • Is the trench clearance width between 300mm to 600mm? | Yes,No,N/A
label | --------------------------------------------------------------------------------------------------------------
label | Table 701.151
label | Pipe Type ¦¦ Nominal Pipe Diameter or Width (mm) ¦¦ Horizontal Clearance to Wall of Trench :: Min. (mm) / Max. (mm)
label | --------------------------------------------------------------------------------------------------------------
label | Corrugated Metal Culvert ¦¦ All ¦¦ 300 mm / 1,000 mm
label | Other ¦¦ All ¦¦ 300 mm / 600 mm
label | --------------------------------------------------------------------------------------------------------------
button | • Is the excavation at a sufficient depth for pipe/box culvert bedding? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: S
label | CYP D&C JV - Sign/Date: SE
checkpoint | 2.2 - Excavation for Pits
label | Ref docs: VR Clause 705.05
label | Acceptance criteria:
button | • Is the pit excavation not less than 400mm from external pit wall to side of excavation? | Yes,No,N/A
button | • Is the excavation at a sufficient depth for pit bedding? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: S
label | CYP D&C JV - Sign/Date: SE
section | 3.0 Bedding
checkpoint | 3.1 - Bedding - Pipes
label | Ref docs: VR Clause 701.16
label | Acceptance criteria:
button | • Is the Pipe Diameter less than 1500mm? If so, has 100mm of bedding been placed? | Yes,No,N/A
button | • Is the Pipe Diameter greater than 1500mm? If so, has 200mm of bedding been placed? | Yes,No,N/A
label | (D = Pipe Diameter/Culvert Width).
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: S
label | CYP D&C JV - Sign/Date: SE
checkpoint | 3.2 - Bedding - Pits
label | Ref docs:
label | • VR Clause 705.05
label | • Table 701.091 & 701.092
label | Acceptance criteria:
button | • Has bedding been placed and compacted to a thickness not less than 80mm on clay foundation? | Yes,No,N/A
button | • Has bedding been placed and compacted to a thickness not less than 150mm on a rock foundation? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: S
label | CYP D&C JV - Sign/Date: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • Bedding and Backfill Material Conformance | Yes,No
checkpoint | 3.3 - Bedding Material - Compaction
label | Ref docs: VR Clause 701.20
label | Acceptance criteria:
button | • Has bedding been compacted to refusal? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: S
label | CYP D&C JV - Sign/Date: SE
section | 4.0 Installation of Pipes/Pits/Culverts
checkpoint | 4.1 - Laying of Pipes
label | Ref docs:
label | • VR Clause 701.17 (a)
label | • 701.17 (e)
label | Acceptance criteria:
button | • Are pipes being laid from downstream end? | Yes,No,N/A
button | • Are socket ends of pipes being placed facing upstream and fully entered? | Yes,No,N/A
button | • Is the pipe in full contact with the bedding for the full length of each section? | Yes,No,N/A
label | • The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: I
label | Symal Infrastructure - Resp: PE
label | CYP D&C JV - Key: S
label | CYP D&C JV - Sign/Date: SE
checkpoint | 4.2 - Installation of Pits
label | Ref docs:
label | • VR Clause 705.07
label | • 705.08
label | • 705.09
label | • 705.11
label | Acceptance criteria:
button | • Have pre-cast pits been installed at the correct location and to the dimensions shown on the drawings? | Yes,No,N/A
button | • Have subsurface drainage connections been cored at appropriate dimensions? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • Test results for fibres and fibre content (if applicable) (Compliance Certificate provided by Supplier) | Yes,No
checkpoint | 4.3 - Step Iron Fitting
label | Ref docs: VR Clause 705.12
label | Acceptance criteria:
button | • Have pits greater than 1.0 meter been fitted with step irons? | Yes,No,N/A
label | • Step irons shall not obstruct openings or be fitted to a wall which has openings.
button | • Have step Irons shall be installed in accordance with the manufacturer’s instructions and are an approved proprietary type? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • Material Conformance Certificates | Yes,No
checkpoint | 4.4 - Shaping the floor and Surface Finish
label | Ref docs:
label | • VR Clause 705.13
label | • 705.14
label | Acceptance criteria:
button | • Has the drainage pit floors been smoothly shaped from the inlets to the outlet for a height of one third of the diameter of the outlet pipe with cementitious mortar? | Yes,No,N/A
label | • Surfaces shall be finished uniform in appearance with a Class 2 surface finish in accordance with the requirements of Section 610.
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
checkpoint | 4.5 - Jointing - Pits
label | Ref docs:
label | • VR Clause 705.14
label | • 705.16
label | • 610.32
label | Acceptance criteria:
button | • Has the joints between drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
checkpoint | 4.6 - Jointing – Pipes
label | Ref docs: VR Clause 701.18
label | Acceptance criteria:
button | • Are rubber rings to be used on rubber ring joint pipes clean and free of debris? | Yes,No,N/A
button | • Have all interlocking joint reinforced concrete pipes been jointed or wrapped with 200mm wide external joint rubber band? Has the rubber band been placed between the spigot and socket? | Yes,No,N/A
button | • Have pipes with lifting holes been placed with lifting holes uppermost? Have lifting holes been plugged after pipe installation? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
checkpoint | 4.7 - Fitting of Covers
label | Ref docs: VR Clause 705.17
label | Acceptance criteria:
label | • Pit Downstream
textbox | ○ Pit Number
textbox | ○ Lid Class
textbox | ○ Lid Type
label | • Pit Upstream
textbox | ○ Pit Number
textbox | ○ Lid Class
textbox | ○ Lid Type
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • Survey Conformance Report | Yes,No
section | 5.0 Installation of Box Culverts
checkpoint | 5.1 - Laying Box Culverts
label | Ref docs: VR Clause 701.17 (a) (c) (d)
label | Acceptance criteria:
button | • Have consecutive sections of box culverts been firmly butted together? | Yes,No,N/A
button | • Does the mortar have a minimum 28 day compressive strength of not less than 40MPa? Is it at least Type C Class? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • Technical Data Sheet | Yes,No
section | 6.0 Backfilling
checkpoint | 6.1 - Backfill – Pipes/Culverts
label | Ref docs: VR Clause 701.19
label | Acceptance criteria:
button | • Has the haunch zone been extended from top of bedding layer to 1/3 pipe diameter? Haunch zone material to be same as bedding layer. Haunch zone to be compacted to refusal in max 150mm layer. | Yes,No,N/A
button | • Is the pipe to be backfilled in under an area to be paved? If so, has excavation below design subgrade level been backfilled with select backfill material? And within the pavement layer backfilled with appropriate pavement material? | Yes,No,N/A
button | • Is the pipe to be backfilled in under an area to be paved? If so, has excavation below design subgrade level been backfilled with select backfill material? And within the pavement layer backfilled with appropriate pavement material? | Yes,No,N/A
button | • Is the pipe to be backfilled in under an area not to be paved? If so, has the trench been backfilled with select backfill material to a level 0.3m above the top of the culvert? Ordinary backfill may be used above that level. | Yes,No,N/A
button | • Has the backfill material been backfilled in max 150mm layers? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | NATA Test Report: Compaction | Yes,No
checkpoint | 6.2 - Backfill - Pits
label | Ref docs: VR Clause 705.18
label | Acceptance criteria:
button | • Has the pit been backfilled in layers not exceeding 300mm? Pit backfill to be compacted to refusal using hand held equipment. | Yes,No
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE
section | 7.0 Completion
checkpoint | 7.1 - As-built Survey
label | Ref docs:
label | • VR Clause 705.19
label | • 610.47
label | • 610.46
label | Acceptance criteria:
button | • Has the pipe been laid with adequate fall and invert levels within ±10mm of design? | Yes,No,N/A
button | • Is the invert level of pipes at pipes ±50mm of design? | Yes,No,N/A
button | • Is the line of the pit cover been installed ±10mm of the design kerb line? | Yes,No,N/A
button | • Is the pit cover level ±10 mm of the design level for that point? | Yes,No,N/A
button | • Is the offset of entry pits within ±20 mm of kerbs/barriers? | Yes,No,N/A
button | • Is the offset of entry pits within ±20 mm of kerbs/barries? | Yes,No,N/A
button | • Is the plan location of pits other than offsets to kerb lines or barriers ±100 mm? | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R / H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • Survey Conformance Certificate | Yes,No
holdpoint | HOLD POINT
checkpoint | 7.2 - Compaction and moisture content of backfill & bedding material
label | Ref docs:
label | • 701.20a
label | • 701.20b
label | Acceptance criteria:
button | • Has a total of 3 compaction tests taken place, per lot, inclusive of pit compaction, achieving 97% compaction? | Yes,No,N/A
label | Freq: At 20% of all lots
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R / H
label | Symal Infrastructure - Resp: SE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach Compaction Reports
holdpoint | HOLD POINT
checkpoint | 7.3 - CCTV Inspection
label | Ref docs: 701.30
label | Acceptance criteria:
button | • Have all storm water lines been inspected by CCTV and found to be free of defects prior to placement of pavement? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
label | CYP D&C JV - Key: H
label | CYP D&C JV - Sign/Date: PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | • CCTV Inspection Report | Yes,No
holdpoint | HOLD POINT
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot