## ITP007 - Unbound Pavements
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-ITP-007 - Subsurface Drainage (Rev A) | [5 empty] | SYM-ITP-007 - Subsurface Drainage (Rev A)
section | 1.0 General Details
checkpoint | 1.1 - Set Out
label | Ref docs: Civil drawings
label | Acceptance criteria:
button | • Is the work area clearly pegged out for line and level? | Yes,No,N/A
textbox | Subsurface drainage Reference
textbox | Size of Lot |  |  | M
label | Days production or pit to pit
textbox | Zone
textbox | Stage
label | Freq: Prior to the Start of Activity
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint | 1.2 - Procedure for method of compaction and placement of no fines concrete filter material.
label | Ref docs:
label | • Construction Document (Drainage)
label | • VR702.05
label | Acceptance criteria:
button | • Has the method of compaction shall be in accordance with the Contractor’s quality procedures been submitted for review by the Superintendent and approved? | Yes,No,N/A
button | • Has no fines concrete been used as a filter material? | Yes,No,N/A
button | • Has no fines concrete been placed and compacted within 1 hour of mixing? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • As per approved Construction Document
checkpoint | 1.3 - Conformity with Drawings
label | Ref docs:
label | • VR702.03
label | • IFC Drawings
label | Acceptance criteria:
button | • Are the drawings, complete & current? | Yes,No,N/A
button | • Is the subsurface drainage pipe or the geocomposite invert level not exceeding 25 mm from the specified level and not more than 50 mm from the specified line. With changes of grade not at a rate exceeding 10 mm in any 3 m length. | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach completed Permit
holdpoint | HOLD POINT
checkpoint | 1.4 - Excavation Permit & Penetration Permit
label | Ref docs:
label | • SMP
label | • VR 602.03
label | Acceptance criteria:
button | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services. | Yes,No,N/A
button | • Relevant permits have been signed and approved. | Yes,No,N/A
button | • Extents and levels correct to relevant drawings | Yes,No,N/A
button | • 50mm Blinding to be placed as required to allow working surface and protect excavation. | Yes,No,N/A
button | • Has the trench been excavated to allow 300mm between top of capping and top of subsoil pipe? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
holdpoint | HOLD POINT
section | 2.0 Subsurface drainage materials and installation
checkpoint | 2.1 - Pipes
label | Ref docs:
label | • VR 702.04
label | • VR 702.03
label | • VR 702.09
label | Acceptance criteria:
button | • Has the Pipe Class and size been confirmed as per latest IFC drawings drawings and project Specs? | Yes,No,N/A
button | • Has the slotted pipe been placed centrally in the trench? | Yes,No,N/A
button | • Have plastic pipes been kept away from sunlight and undamaged during delivery and installation? | Yes,No,N/A
button | • Is the subsurface drainage pipe invert level not exceeding 25 mm from the specified level and not more than 50 mm from the specified line. With changes of grade not at a rate exceeding 10 mm in any 3 m length. | Yes,No,N/A
button | • Is the pipe grade not flatter than 1m in 250m? | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach Compliance Certificates.
checkpoint | 2.2 - Geotextiles
label | Ref docs:
label | • VR 702.06
label | • Table 702.061
label | • VR 702.09
label | Acceptance criteria:
button | • Has the outer covering of the subsurface drain been covered in a geotextile surround if specified? | Yes,No,N/A
button | • Has the geotextile been placed without punctures or tears? | Yes,No,N/A
button | • In expansive clays does the geotextile material extend to directly below the kerb line? | Yes,No,N/A
button | • is the Geotextile material supplied and installed as per latest IFC drawings and project specifications? | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
button | Manufactures Compliance Certificates | Yes,No,N/A
checkpoint | 2.3 - Filter material
label | Ref docs:
label | • VR 702.05
label | • VR 702.13
label | • Table 702.051
label | • Table 702.131
label | • VR 702.09
label | • (g)
label | Acceptance criteria:
button | • Has material been placed in <300mm layers and compacted with minimal disturbance to pipe, geotextile and trench walls? | Yes,No,N/A
button | • Has no fines concrete ratios and specifications applied as per Table 702.051 and VR702.05(e) | Yes,No,N/A
button | • Has crushed rock/concrete ratios and specifications applied as per Table 702.052 and VR702.05(d) | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint | 2.4 - Access points
label | Ref docs: VR 702.10
label | Acceptance criteria:
button | • Have access points installed at intervals of between 100m and 150 m? | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint | 2.5 - Flushing
label | Ref docs: VR 702.10
label | Acceptance criteria:
button | • Has the pipe been flushed with water to remove any debris or blockages in the pipe and it’s working correctly with a smooth flow? | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot