## ITP007 - Unbound Pavements
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | [5 empty] | SYM-ITP-008 - Insitu Concrete Elements (Rev A)
section | 1.0 General Details
checkpoint | 1.1 - Material classification and source
label | Ref docs:
label | • 503.04
label | • VR 610.07
label | • AS 1379
label | Acceptance criteria:
button | • Is Mix design approved prior to placemen and material properties meet project specification, AS 3600, AS 1379. | Yes,No,N/A
textbox | Concrete Strength |  |  | MPA
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 1.2 - Set Out
label | Ref docs: Civil drawings
label | Acceptance criteria:
button | • Is the work area clearly pegged out for line and level? | Yes,No,N/A
textbox | • Wall/Footing Reference
textbox | • Zone
textbox | • Stage
textbox | • Element Description
label | Freq: Prior to the Start of Activity
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach Drawings
checkpoint | 1.3 - Conformity with Drawings
label | Ref docs: VR Clause 701.10
label | Acceptance criteria:
button | • Are the drawings, complete & current? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach Recent IFC Drawings
holdpoint | HOLD POINT
checkpoint | 1.4 - Excavation Permit & Penetration Permit
label | Ref docs:
label | • SMP
label | • VR 602.03
label | Acceptance criteria:
button | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services. | Yes,No,N/A
button | • Relevant permits have been signed and approved. | Yes,No,N/A
button | • Extents and levels correct to relevant drawings | Yes,No,N/A
button | • 50mm Blinding to be placed as required to allow working surface and protect excavation. | Yes,No,N/A
textbox | Excavation to a total depth of |  |  | mm
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach completed Permit
holdpoint | HOLD POINT
section | 2.0 Insitu concrete Element
checkpoint | 2.1 - Ground Preparation
label | Ref docs:
label | • IFC Drawings
label | • VR 610
label | Acceptance criteria:
button | • Is the fill and base of the foundation compacted to achieve at least 98% and achieving Geotechnical strength as per the design requirements. | Yes,No,N/A
button | • Has the surface shall be thoroughly moistened with water and excess surface water removed prior to placing concrete. | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 2.2 - Formwork
label | Ref docs:
label | • Civil drawings.
label | • Project Specs
label | • VR 614.04
label | • VR 613.04
label | • Table 614.041
label | Acceptance criteria:
button | • Formwork has been installed correctly and sufficiently braced. | Yes,No,N/A
button | • Formwork set out has been done as per latest design drawings and specifications | Yes,No,N/A
button | • Were Construction joints/Expansion Joints/Isolation Joints /or any type of joint as specified in the drawings Installed | Yes,No,N/A
button | • Any Backfill/ Underlay Material as per drawings & specifications | Yes,No,N/A
button | • Was Installations of Cast-Ins/ HD bolts/ Chemical Anchors/Block out Verified | Yes,No,N/A
button | • Is the concrete member of height greater than 2m and a formwork design obtained with a certificate of compliance from a Proof Engineer forwarded to the Superintendent for approval? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach formwork design and approvals
checkpoint | 2.3 - Reinforcement
label | Ref docs:
label | • AS3600
label | • VR611
label | • VR610
label | Acceptance criteria:
button | • Tolerance - As per specifications and Australian Standard and minimum cover for steel reinforcement is 40mm. | Yes,No,N/A
button | • Steel is free of excess corrosion, loose millings, oil or other contaminants | Yes,No,N/A
button | • Required Connection details - U Bars/ Z Bars/Cogs Verified/Starter bars | Yes,No,N/A
button | • Correct concrete cover and chairs on sides, bottom and top Verified | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint | 2.4 - Pre-pour Inspections
label | Ref docs:
label | • Civil drawings.
label | • Project Specs
label | Acceptance criteria:
label | • Has steel reinforcement been placed correctly with adequate cover? | Yes,No,N/A
button | • Have tie bars and expansion joints been installed at the correct intervals? | Yes,No,N/A
button | • Pour area is free of loose debris, oils, water | Yes,No,N/A
button | • Have any services located within the slab been installed, surveyed and pinned down | Yes,No,N/A
button | • Concrete Testing Lab Representative will be available during concrete pour | Yes,No,N/A
button | • CYP D&C JV informed of concrete pour date and start time | Yes,No,N/A
label | Freq: Prior to start of each Concrete Pour
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SS
label | CYP D&C JV - Key: H
holdpoint | HOLD POINT
checkpoint | 2.5 - Concrete Placement
label | Ref docs:
label | • VR503.07
label | • VR503.05
label | Acceptance criteria:
button | • Has concrete been transported, handled and placed to prevent segregation, loss or leakage of materials and air temp within 5 to 35 degrees C | Yes,No,N/A
button | • Has Concrete been tamped/vibrated to increase density and prevent voids, honeycombing or surface defects. | Yes,No,N/A
button | • Has a minimum of one of vibrator used at all times while the concreting is in operation | Yes,No,N/A
button | • Ensure monitoring forms/cast in items during the pour | Yes,No,N/A
button | • Concrete Work(s) completed to specification/drawings & Area left clean/tidy | Yes,No,N/A
button | • Concrete Dockets Received, Attach last Docket | Yes,No,N/A
textbox | Pour date
textbox | Total pour Concrete quantity |  |  | M3
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Delivery Doc
label | • Conc pour record
checkpoint | 2.5 - Post Pour
label | Ref docs:
label | • Civil drawings.
label | • Project Specs
label | • VR 610
label | Acceptance criteria:
button | • Was Curing agent applies as per project specifications | Yes,No,N/A
button | • Concrete reached design strength to strip formwork | Yes,No,N/A
button | • Any identified defects after striping rectified | Yes,No,N/A
button | • Attach Subcontractor’s QA | Yes,No,N/A
button | • Does Backfill material comply with Vicroad specs, Project specs and drawings? | Yes,No,N/A
button | • Were as Built completed? Attach report if applicable | Yes,No,N/A
button | • Concrete reached design strength to strip formwork. (Attach test results) | Yes,No,N/A
button | • Were expansion joints placed at intervals less than 10m. | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach concrete Test Report
label | • Attach As built report
checkpoint | 2.6 - Backfilling
label | Ref docs: VR703.29
label | Acceptance criteria:
button | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour? | Yes,No,N/A
button | • Were the positions of any existing conduits passing under edgings marked by a chase in the edging immediately above the conduit together with a suitable identification mark. | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE/PE
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot
checkpoint-no-status | Table 610.161
label | Volume Cast in One Continuous Operation (cubic metre) ¦¦ Minimum Number of Samples
label | --------------------------------------------------------------------------------------------------------------
label | 0 to 10 ¦¦ 1
label | 10 to 25 ¦¦ 2
label | 25 to 50 ¦¦ 3
label | 50 to 100 ¦¦ 4
checkpoint-no-status | Table 610.241
label | Exposure Classification ¦¦ Maximum Acceptable Crack Widths (mm)
label | --------------------------------------------------------------------------------------------------------------
label | A ¦¦ 0.20
label | B1 ¦¦ 0.20
label | B2 ¦¦ 0.15
label | C, U ¦¦ 0.10
checkpoint-no-status | Table 610.162
label | Specified slump, mm ¦¦ Tolerance, mm
label | --------------------------------------------------------------------------------------------------------------
label | < 60 ¦¦ ± 10
label | ≥ 60 ≤ 80 ¦¦ ± 15
label | > 80 ≤ 110 ¦¦ ± 20
label | > 110 ≤ 150 ¦¦ ± 30
label | > 150 ¦¦ ± 40
checkpoint-no-status | Table 614.041
label | Concrete members ¦¦ Formwork documentation ¦¦ Certification of formwork design ¦¦ Proof Engineering of formwork design ¦¦ Certification of erected formwork
label | --------------------------------------------------------------------------------------------------------------
label | (a) Abutments, pilecaps, footings, solid piers, pier columns and walls, with heights less than or equal to 2.0 metres ¦¦ N/A ¦¦ N/A ¦¦ N/A ¦¦ Contractor’s Engineer (Attachment C, as per clause 614.08)
label | (b) Abutments, pilecaps, footings, solid piers, pier columns and walls, with heights greater than 2.0 metres ¦¦ Design drawings and specifications ¦¦ Design Engineer ¦¦ Proof Engineer (Attachment A, as per this clause) ¦¦ Contractor’s Engineer and Design Engineer (Attachment B, as per clause 614.08)
label | (c) All other concrete members ¦¦ Design drawings and specifications ¦¦ Design Engineer ¦¦ Proof Engineer (Attachment A, as per this clause) ¦¦ Contractor’s Engineer and Design Engineer (Attachment B, as per clause 614.08)
label | (d) Any member for which self-compacting concrete is proposed ¦¦ Design drawings and specifications ¦¦ Design Engineer ¦¦ Proof Engineer (Attachment A, as per this clause) ¦¦ Contractor’s Engineer and Design Engineer (Attachment B, as per clause 614.08)
checkpoint-no-status | Table 610.472 Cast In Situ Concrete
label | Item ¦¦ Tolerance (mm unless shown otherwise)
label | --------------------------------------------------------------------------------------------------------------
label | (i) Footings
label | ○ Plane dimensions
label | – Formed footings and pile caps ¦¦ -15 to +50
label | – Unformed footings (when approved by the Superintendent) ¦¦ 0 to +150
label | ○ Thickness
label | – < 300 mm ¦¦ -5 to +25
label | – > 300 mm ¦¦ -10 to +50
label | ○ Top of footing or pile cap reduced level ¦¦ -25 to +25
label | ○ Departure from the plan position in any direction ¦¦ 50
label | --------------------------------------------------------------------------------------------------------------
label | (ii) Cylinders
label | ○ Variation from the vertical ¦¦ 25 mm in 3 m
label | ○ Departure from the plan position in any direction ¦¦ 75
label | --------------------------------------------------------------------------------------------------------------
label | (iii) Variation in Cross Section of Columns, Piers, Pier and Abutment Crossheads, Slabs, Walls, Beams and Similar Parts (excluding deck slabs and end posts)
label | ○ < 3 m ¦¦ -5 to +15
label | ○ > 3 m ¦¦ -10 to +25
label | --------------------------------------------------------------------------------------------------------------
label | (iv) Variation of Cross Section of End Posts ¦¦ -5 to +5
label | --------------------------------------------------------------------------------------------------------------
label | (v) Deck
label | ○ Thickness of Deck Slabs (excluding allowance for correction of camber or hog) ¦¦ 0 to +10
label | ○ Deck surface reduced level ¦¦ -10 to +10
label | --------------------------------------------------------------------------------------------------------------
label | (vi) Deck Joints
label | ○ Width of slot ¦¦ -3 to +3
label | --------------------------------------------------------------------------------------------------------------
label | (vii) Variation from Vertical or Specified Batter of Columns, Piers, Walls, Handrail Posts and Arrises
label | ○ Unexposed concrete ¦¦ 10 mm in 2.5 m (1/250)
label | ○ Exposed concrete ¦¦ 5 mm in 2.5 m (1/500)
label | --------------------------------------------------------------------------------------------------------------
label | (viii) Variation from Grades indicated on Drawings for Railings, Kerbs and Arrises ¦¦ 2.5 mm in 2.5 m (1/1000)
label | --------------------------------------------------------------------------------------------------------------
label | (ix) Reduced Level of Tops of Pier and Abutment Crossheads and Piers
label | ○ With pedestals ¦¦ -10 to +10
label | ○ Without pedestals ¦¦ -5 to +5
label | ○ Difference in Level across width of crosshead ¦¦ 5
label | --------------------------------------------------------------------------------------------------------------
label | (x) Bearing Pedestals
label | ○ Reduced level ¦¦ -2.5 to +2.5
label | ○ Variation from grade across the width of individual pedestals shall not exceed ¦¦ 1 in 200
label | ○ Deviation from flat surface ¦¦ +1.0 to -1.0
label | --------------------------------------------------------------------------------------------------------------
label | (xi) Departure from Plan Position at any level
label | ○ Columns, Piers, Walls, Pier and Abutment Crossheads, Beams, Slabs, Kerbs, Railing and other similar parts ¦¦ 25
label | ○ Relative displacement of adjoining members shall not exceed ¦¦ 10
label | --------------------------------------------------------------------------------------------------------------
label | (xii) Departure from Alignment
label | ○ Rows of columns, faces of piers or walls ¦¦ 10
label | ○ Handrails, Faces of hand rail posts, Kerbs ¦¦ 5
label | --------------------------------------------------------------------------------------------------------------
label | (xiii) Maximum Allowance for Irregularities in Exposed Concrete Surfaces
label | ○ Sections less than 1 m in dimension when measured with a straightedge across the dimension of the section ¦¦ 2.5
label | ○ Sections greater than 1 m in dimension when measured with a straightedge across the dimension of the section, except that when sections are greater than 2.5 m in dimension, a 2.5 m straightedge shall be used ¦¦ 5
label | --------------------------------------------------------------------------------------------------------------
label | (xiv) Irregularities in Railings ¦¦ 2.5 mm in 2.5 m
label | --------------------------------------------------------------------------------------------------------------
label | (xv) Slab Surface Finish ¦¦ 5 mm in 2.5 m
checkpoint-no-status | Table 610.473 Pre-tensioned Concrete
label | Item ¦¦ Tolerance (mm unless shown otherwise)
label | --------------------------------------------------------------------------------------------------------------
label | (i) Cross Section
label | ○ Dimension
label | – < 2 m ¦¦ -3 to +3
label | – > 2 m ¦¦ -6 to +6
label | ○ Out of square
label | – > 2 m ¦¦ 0.5 in 250, or Desirable 3, Maximum 5
label | --------------------------------------------------------------------------------------------------------------
label | (ii) Strand and Reinforcement
label | ○ Placing of reinforcement ¦¦ 5
label | ○ Placing of prestressing strand ¦¦ 3
label | ○ Concrete cover ¦¦ 0 to +5
label | --------------------------------------------------------------------------------------------------------------
label | (iii) Squareness of Ends
label | ○ Dimension
label | Deviation from a plane perpendicular to the longitudal axis of a member, or from the specified end plane:
label | – < 500 mm ¦¦ 3 mm
label | – > 500 mm ¦¦ 6 mm per metre (10 mm maximum)
label | --------------------------------------------------------------------------------------------------------------
label | (iv) Length
label | ○ Diagonal length for precast unit ¦¦ 5
label | ○ Overall length or length centre to centre of bearings (for beams and slabs) ¦¦ 0.06% x specified length (max 20)
label | ○ Centre to centre spacing of holes for transverse rods or both ¦¦ 5
label | --------------------------------------------------------------------------------------------------------------
label | (v) Profile in a Vertical Plane (Hog)
label | The deviation in hog of any unit from the mean hog of all units shall not vary by more than 0.07% of the length of the units. The absolute value for hog for any unit shall not be less than zero. Hog measurements shall be made at transfer of prestress.
label | --------------------------------------------------------------------------------------------------------------
label | (vi) Profile in a Horizontal Plane (Bow)
label | The deviation of a unit from the required profile shall not exceed 0.06% of the length of the unit or a maximum of 15 mm.
label | --------------------------------------------------------------------------------------------------------------
label | (vii) Twist
label | The angular rotation of any cross section relative to an end cross section shall not exceed 1 in 200
label | --------------------------------------------------------------------------------------------------------------
label | (viii) Sole Plates
label | The plane of the sole plate or bearing surface shall not vary from that shown on the drawings by more than 1 in 200 in any direction.
label | --------------------------------------------------------------------------------------------------------------
label | (ix) Deviation
label | ○ The distance of any point from a flat plane held against that surface ¦¦ 3 mm in 2 m