## ITP007 - Unbound Pavements
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-ITP-009 - TACTILES (Rev A) | [5 empty] | SYM-ITP-009 - TACTILES (Rev A)
section | 1.0 Preliminaries
checkpoint | 1.1 - Conformity with Drawings
label | Ref docs: TAS-A-AUD-6007-0426 – LANDSCAPE (IFC)
label | Acceptance criteria:
button | • Are the drawings, complete & current? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
holdpoint | HOLD POINT
section | 2.0 Pre-Construction Activities
checkpoint | 2.1 - Survey Set-Out
label | Ref docs: TAS-A-AUD-6007-0426 – LANDSCAPE (IFC)
label | Acceptance criteria:
button | • Have tactiles/pavers been set-out as per current drawings? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 2.2 - Installation Considerations
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00
label | Acceptance criteria:
button | • Is the concrete slab free of any deposits or rubbish, projections/voids? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint-no-status | Does the area include stone TGSI’s?
label | If yes, proceed to Section 3.0
checkpoint-no-status | Does the area include regular tactiles?
label | If yes, proceed to Section 4.0
checkpoint-no-status | Does the area include both types of tactiles?
label | If yes, fill out both Section 3.0 & Section 4.0
section | 3.0 Stone TGSI's (pavers)
checkpoint | 3.1 - Bedding Mortar
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0821 (Mortar)
label | Acceptance criteria:
button | • Has mortar been placed using type/method described in specification? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 3.2 - Directional / Horizontal
label | Ref docs: TAS-A-AUD-6007-0426 – LANDSCAPE (IFC)
label | Acceptance criteria:
button | • Does the section require directional or horizontal TGSI’s, or both? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 3.3 - Laying Pavers
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0774 (Paving – 3.3)
label | Acceptance criteria:
button | • Have pavers been laid as described in specification, considering specified tolerances? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 3.4 - Sealed Joints
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0774 (Paving – 3.9)
label | Acceptance criteria:
button | • Have joints been sealed as described in specification? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
section | 4.0 Regular Tactiles
checkpoint | 4.1 - Tactile Installation
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00
label | Acceptance criteria:
button | • Have tactiles been installed in accordance with manufacturer specifications? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot